PMI PMP CERTIFICATION WORKSHOP
Special Topics
Project Management Institute, South Africa Chapter 2015

---
Elmar has held a variety of positions throughout his career, including: Programme / Project Director, Manager of Project Managers, Projects Portfolio Manager, Programme Manager, Project Manager, Systems Developer, Consultant, Systems Architect, Developer and Computer Operator. He is also a Fellow, former Board Member (2006/2012) and past President of Project Management South Africa (PMSA); and a Fellow and former President of the Institute of Information Technology Professionals South Africa (IITPSA – formerly the CSSA).
He is first and foremost a practitioner specialising in Portfolio Management, Programme Management, Project Management, Organisational Change Management, Project Governance, Project Offices and all facets of Information Technology. He has developed and presented training courses in all aspects of project management and systems development since 1984, and has been a popular speaker at local and international conferences. As part of advancing the profession he has been involved in ISO / SABS and other standards development activities since the 1980's.
Elmar extensive industry experience which includes: Engineering, Government, Banking, Higher Education, Manufacturing, Distribution, Insurance, NGO and general business. I proudly advance the principles of batho pele (people first) as a mentor (preferred style) and coach.
Elmar Roberg
+27 82 651 5138
roberg@iafrica.com

---
Various examples
Based on the
PMBOK Guide (5th Edition)
Project Management Institute, South Africa Chapter 2015

---
Agenda

---
Pert estimating

---
Crashing
1. For each activity on critical path, work out crash duration saving
     and at what cost
2. Calc cost per unit
3. Start with lowest cost/unit, accept time saving
4. Have I made up the necessary saving?
     If NO, repeat 3, until achieve goal
5. If critical path has changed, then must repeat this exercise
6. Finally consider: is the reduction in time worth the increased cost?
     (i.e. is the penalty still more than the cost?)

---
Activity on Node (AoN)
ES = Earliest Start Time
D = Duration
EF = Earliest Finish Time
ID = Activity (task) Identifier
LS = Latest Start Time
F = Free Float
LF = Latest Finish Time

---
Basic statistics

---
Net Present Value (NPV)

---
text
text

---
Questions?