## XRef
				Use					Initiating		Planning					Executing					Monitoring & Controlling					Closure
		ID	Use: M: Mandatory; / D: Discretionary; C: Conditional / I: Input; C = Create: U = Update; / L = In/Upd; V = Verify / Validate / Document Name	PMBOK®?	PjMP	Project doc’s	Good Practice	L1: Ad Hoc	L2: Enh	L3: Small	L4+: Full	xref	Dev PjCh	Id Stakeholders	Dev Pj Mgt Plan	Plan Scope Mgt	Collect Rqmts	Define Scope	Create WBS	Plan Schedule Mgt	Define Activities	Sequence Activ	Est Activ Rsrc	Est Activ Dur	Develop Schedule	Plan Cost Management	Estimate Costs	Det Budget	Plan Quality	Plan HR Management	Plan Communication Mgt	Plan Risk Mgt	ID Risks	Perf Qual Risk An	Perf Quan Risk An	Plan Risk Resp	Plan Procurem's	Plan Stakeholder Mgt	Dir& Mng Pj Exec	Manage Proj Knowledge	Manage Quality	Acquire Resources	Dev Pj Team	Mng Pj Team	Manage Communications	Implem Risk Responses	Conduct Procur's	Manage Stakeh’ Engagemt	Mon&Ctl Pj Work	Perf Integ ChgCtl	Validate Scope	Control Scope	Control Schedule	Control Costs	Control Quality	Control Resources	Monitor Comms	Mon&Ctl Risks	Control Procuement's	Control Stakeh’ Engagemt	Close Pj or Phase	Close Procur's
				4.1	13.1	4.2	5.1	5.2	5.3	5.4	6.1	6.2	6.3	9.2	6.4	6.5	7.1	7.2	7.3	8.1	9.1	10.1	11.1	11.2	11.3	11.4	11.5	12.1	13.2	4.3	4.4	8.2	9.3	9.4	9.5	10.2	11.6	12.2	13.3	4.5	4.6	5.5	5.6	6.6	7.4	8.3	9.6	10.3	11.7	12.3	13.4	4.6	12.6		50			Template	Example	Example
				0
			- Benefits Management Plan	Y					I					I
		BUCA	- Business Case	Y			D				M	P000	I					I			2		S010
		DLVA	Accepted Deliverables	Y					P068					C					I			2		S001
		ACTA	Activity Attributes	Y		x	D				D	P023					C	I	I	I	I					5		S002
P		ACE	Activity Cost Estimates	Y			M			C	M	P028					I				C	I					I				I					5		S003
P		ADE	Activity Duration Estimates	Y			M			D	M	P030					C	I					I					3		S004
P		ACTL	Activity List	Y		x	D		D	D	M	P022					C	I	I	I	I					U					6		S005
P		ARR	Activity Resource Requirements	Y			D	D	D	D	M	P026					C	I	I					I					I					5		S006
P		ACP	Administrative Closure Procedure				M	M	M	M	M	P084					0		S084
		AGRM	Agreements	Y			C	C	C	C	C	P004	I				I					I					C		I					I		I			7		S007
		CHA	Approved Change Request	Y					P055					C					I				I					3		S008
			Assumptions Log	Y		x					C					U					I					I
		BOE	Basis of Estimates	Y		x					P037					C	I					I	I					I			5		S009
P		FC	Budget Forecasts					D	M	P073					0		S073
			Business documents	Y					I				I					I
		CL	Change Log	Y		x					P062					I					I		U					I			4		S011
			Change Management Plan	Y	x					I
P		CR	Change Request	Y			M	C	C	C	C	P051					C		C		C			C			C	C	C	I	C	C	C	C	C		C	C	C					16		S012
			Closed Procurements					P071					0		S013
		CLREP	Closure Report				C	C	C	C	C	P085					0		S085
P		UMP	Communications Management Plan	Y	x					D	M	P045					C					I			I					3		S014
			Configuration Management Plan	Y	x					I
P		CONT	Contract					C	C	P078					0		S078
P		CCP	Contract Closure Procedure					C	C	P086					0		S086
P		COND	Contract documents					C	C	P079					0		S079
P		COMP	Contract Management Plan					C	C	P087					0		S087
P		CSOW	Contract Statements of Work					C	C	P088					0		S088
P		CAR	Corrective Action					C	C	P089					0		S089
P		CBL	Cost Baseline	Y	x		M	C	C	D	M	P040					C					I					2		S015
			Cost Estimates	Y		x
			Cost Forecasts	Y		x					P065					L					C					2		S016
P		CMP	Cost Management Plan	Y	x					M	P036					C	I	I					I		I					5		S017
		CSA	Customer Acceptance				C	C	C	C	C	P090					0		S090
P		DR	Defect Repair					C	C	C	C	P091					0		S091
		DELR	Deliverable Record				C	C	C	C	C	P092					0		S092
		DLV	Deliverables	Y			M	M	M	M	M	P053					C	I					I					I			4		S018
			Development Approach	Y	x					I
			Duration Estimates	Y		x
		EEF	Enterprise Environmental Factors	Y			M	M	M	M	M	P002	I	I	I	I	I	I	I	I	I	I	I	I	I		I	I	I	I	I	I	I		I	I	I	I		I	U	U	I				I	I					32		S019
P		EC	Evaluation Criteria					C	C	P075					0		S075
P		FDLV	Final product, service, or result	Y			M	M	M	M	M	P072					C			1		S093
			Final Report	Y					C
		PLNHR	Human Resource Mgt Plan	Y					P038					I			C			I					I		I					5		S020
		IL	Issue Log	Y		x					P058					I				U	L					I			I	I			6		S021
			Lessons Learned Register	Y		x					L	L					L					L
P		MOBD	Make-or-buy Decisions	Y					C	C	P049					C					I					2		S022
P		MSL	Milestone List	Y		x	D	D		D	M	P021					C	I					I					I					I			5		S023
		MSS	Milestone Summary				C	C	C	C	C	P093					0		S094
P		OPA	Organisational Process Assets	Y			D			C	D	P003	I	I	I	I	I	I	I	I	I	I	I	I	I		I	I	L	L	U	I		L	L		I	L	I	I		I	L	L	L		L	U	U	U	L			44		S024
		PLNX	Outputs from Other Processes	Y			D	D	D	D	M	P009			I					1		S025
			Performance Measurement Baseline	Y	x
P		PFREP	Performance Reports	Y			M			D	M	P063					0		S026
			Physical Resource Assignments			x
P		PAR	Preventive Action					C	C	P094					0		S095
P		PIP	Process Improvement Plan	Y					C	P041					C					I					2		S027
		CONA	Procurement Contract Award					P076					0		S076
P		AQDP	Procurement Document Package					C	C	P095					0		S096
		PRCD	Procurement Documentation					P077					I			1		S077
P		AQD	Procurement Documents	Y			C	C	C	C	C	P007		I					I				C					I					I					5		S028
P		AQMP	Procurement Management Plan	Y	x					C	C	P048					C					I					2		S029
		SOWP	Procurement Statement of Work	Y					P050					C					I					2		S030
N		AREG	Project Asset Register					C	M	P096					0		S097
			Project Calendars	Y		x					P035					C					I					2		S031
P		PJCH	Project Charter	Y			M	M	M	M	M	P005	C	I	I	I	I	I		I					I					I					I			10		S032
			Project Communications	Y		x					P059					I					C					I				I			4		S033
N		DLOG	Project Daily Log					D	D	D	D	P097					0		S098
N		DREG	Project Document Register					D	M	P098					0		S099
		PJDC	Project Documents	Y			M	M	M	M	M	P016					I	U	U			U	U	U	U		U	U	U		U		I	U	U	U	U	U	L	I	L			U			L	U	L	L	L	L	U	U	L		U	U	U	L	L			35		S034
P		PFR	Project Funding Requirements	Y				D	D		D	P039					C					U					I					3		S035
N		ISREG	Project Issues Register					M	M	M	M	P099					0		S100
			Project Life cycle description	Y	x					I
		PL	Project Log					P100					0		S101
P		PJMP	Project Management Plan	Y			M			D	M	P008			C	I	I	I		I					U	I			I	I	I	I				U	I	I	L	L	U	U	I	U	U		U	U	L	L	I	L	L	L	L		L	L	L	L	I			35		S036
		PN	Project Notebook					P101					0		S102
P		POC	Project Organisation Charts					M	P080					0		S080
P		SCHED	Project Schedule	Y		x	M			D	M	P031					C		I	I					I		I					I					6		S037
P		PSND	Project Schedule Network Diagram	Y		x				D	D	P024					C			I					2		S038
P		PJSS	Project Scope Statement	Y		x	M			M	M	P015					C	I			I		I	I					5		S039
P		PPJSS	Project Scope statement (Preliminary)					M	P102					0		S103
P		PHRA	Project Team Assignments	Y		x	M			D	M	P034					I					I		C	I	I					5		S040
		SHREG	Project Stakeholder Register				M	M	M	M	M	P103					0		S104
		PSOW	Project Statement of Work	Y			D			D	M	P001					0		S041
N		PJSUM	Project Summary					C	C	C	C	P104					0		S105
P		SL	Qualified Sellers List					C	C	P105					0		S106
P		QBL	Quality Baseline				M	M	M	M	M	P106					0		S107
P		QCL	Quality Checklists	Y					D	C	P042					C					I					2		S042
P		QCM	Quality control measurements	Y		x	M			D	M	P056					I					C					I			3		S043
P		QMP	Quality Management Plan	Y	x					M	P043				I					C				I					I					4		S044
P		QMET	Quality Metrics	Y		x	D			D	M	P044					C					I					I					3		S045
			Quality Reports	Y		x					I					I
		RQD	Requirements Documentation	Y		x	M	M	M	M	M	P014					C					I					I		U					I			5		S046
		RQMP	Requirements Management Plan	Y	x		C				D	P010				C					1		S047
		RQTM	Requirements Traceability Matrix	Y		x	D				M	P013					C					I					I					3		S048
P		RSHI	Resolved Stakeholder Issues				M	C	C	C	C	P082					0		S082
P		RA	Resource Availability				D			D	M	P107					0		S108
P		RBS	Resource Breakdown Structure	Y		x	D			D	D	P025					C	I	I					I					4		S049
		CALR	Resource Calendars	Y		x					P027					I	I	I			I					C	I				C					7		S050
			Resource Management Plan		x
			Resource Requirements	Y		x
		RA	Risk Attributes					P108					0		S109
P		RMP	Risk Management Plan	Y	x					M	P046					C	I	I	I	I					5		S051
P		RREG	Risk Register	Y		x	M	M	M	M	M	P029					I	I	I		I	I	I				C	I	I	I	I		L					L					I			I			15		S052
P		RCA	Risk-related Contractual Decisions					D	D	P081					0		S081
			Risk Report	Y		x					I					I	I					I
P		RR	Roles & Responsibilities				M	D	D	D	M	P109					0		S110
P		TBL	Schedule Baseline	Y	x		M	M	M	M	M	P033					C					I					2		S053
P		TMD	Schedule Data	Y		x					D	P032					C					I					2		S054
			Schedule Forecasts	Y		x					P066					L				C					2		S055
P		TMP	Schedule Management Plan	Y	x					M	P020					C	I	I	I	I	I					I		I					8		S056
P		SBL	Scope Baseline	Y	x		M	M	M	M	M	P019					C		I					I	I					I	I					I					7		S057
P		SMP	Scope Management Plan	Y	x		D				M	P011				C					1		S058
P		SEL	Selected sellers	Y					C	C	P060					C					1		S059
P		PROP	Seller Proposal	Y					C	C	P061					I					1		S060
		SSC	Source Selection Criteria	Y					P047					C			I					I					3		S061
P		HRMP	Staffing Management Plan					D	M	P110					0		S111
		SHS	Stakeholder Engagement Plan	Y	x		D				M	P012					C					I					2		S062
		SHREG	Stakeholder Register	Y		x	D	D	D	D	M	P006		C					I		I	I	I				I	I	U	I					9		S063
		SOW	Statement of Work					C	C	C	C	P111					0		S112
			Team Charter	Y		x
P		TPA	Team Performance Assessment	Y					D	M	P057					C	I					2		S064
		TMA	Teaming Agreements					P083					0		S083
			Test & Evaluation Documents	Y		x
		CHGV	Validated Changes	Y					P064					C					1		S065
		DLVV	Validated Deliverables	Y					P070					C					1		S066
			Verified Deliverables	Y					P069					I					1		S067
P		WBS	WBS	Y			M	M	M	M	M	P017					0		S068
		WBSD	WBS Dictionary	Y			C	C	C	C	M	P018					0		S069
		WO	Work Order				C	D	D	D	D	P112					0		S113
P		WPI	Work Performance Data	Y			M	M	M	M	M	P052					C					I	I	I	I	I		I	I	I	I				10		S070
			Work Performance Information	Y					P067					I		C	C	C	C	C		C	C	C	C				10		S071
		WPM	Work Performance Measurements					P074					0		S074
			Work Performance Reports	Y					P054					I	I				C	I					I	I	I				7		S072
				0

			No of PMBOK Inputs & Outputs:	89	18	33					8	5	5	9	9	6	5	5	7	9	11	12	19	5	10	12	11	5	6	6	14	6	7	4	16	6	19	10	8	6	5	10	7	0	13	8	18	16	7	6	10	8	13	0	8	8	10	7	24	0	0	439

		Use:
		I	I: Input					6	4	4	7	7	4	3	4	4	7	8	10	13	4	7	9	6	4	4	5	13	5	6	2	9	4	7	7	4	3	3	5	3	0	7	3	9	12	3	2	4	2	5	0	3	3	5	3	19	0	0
		C	C: Created					2	1	1	2	2	1	1	1	3	1	2	1	4	1	2	2	4	1	1	1	1	0	0	0	6	1	3	0	1	2	1	1	1	0	4	1	2	1	3	2	3	3	5	0	2	2	2	1	2	0	0
		U	U: Updated					0	0	0	0	0	1	1	0	0	1	1	1	2	0	1	1	1	0	1	0	0	1	1	2	1	1	4	0	2	1	1	3	2	0	1	3	0	1	0	0	1	1	0	0	1	2	2	1	0	0	0
		L	L: Input / Outpit					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	5	3	1	0	0	1	1	0	1	1	7	2	1	2	2	2	3	0	2	1	1	2	3	0	0
		V	V: Verified / Validated					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Notes (practical application / wisdom – not PMBOK):
			M: Mandatory: must be done, even if is an "empty" artefact (with explanation why).
			C: Conditional: must be done if the condition exists.					I	5	4	4	4	5	4	5	4	4	7	8	10	13	4	7	9	6	4	4	5	13	5	6	2	9	4	4		5	3	3	6	4		8	4	7	5	5	5	6	4	8		5	4	6	4	3
			D: Discretionary: should be done if there is a need.					O	1	1	1	2	2	2	2	1	3	2	3	2	6	1	3	3	5	1	2	1	1	1	1	2	7	2	5		4	3	2	5	4		6	5	4	4	4	5	6	6	8		5	5	5	5	2
			Blank: may be done if there is a need, PM's judgement					TT	2	3	2	2	11	4	2	3	3	3	5	6	8	3	10	5	8	5	5	3	7	6	3	4	4	3	3		3	5	7	4	5		7	3	4	3	2	1	7	6	4		3	6	7	3	3

			Tools & Techniques					10	3	11	4	8	5	2	3	3	3	5	6	8	3	10	5	8	5	5	3	7	6	3	4	4	3	3	9	3	5	7	4	5		7	3	4	10	2	1	7	6	4		3	6	7	3	3	0	0	239
			***BOL***					T000
			- DA Alternatives Analysis					TT024				x					x					x					3		T004
			- DA Cost-benefit Analysis					TT045					x					x					2		T025
			- DA Document Analysis					TT007					0		T035
			- DG Brainstorming					x		x
			- DG Checklists					x
			- DG Focus Groups					TT009	x		x					2		T041
			- DG Interviews					TT012	x		x					2		T054
			- DM Autocratic Decision Making					x
			- DM Multi-criteria Decision Analysis					TT079					x					x					2		T061
			- DM Voting					x
			- ITS Active Listening					x
			- ITS Conflict Management					TT090	x		x					x					3		T021
			- ITS Facilitation					TT008	x		x					x					3		T039
			- ITS Leadership					x
			- ITS Meeting Management					x		x
			- ITS Networking					x
			- ITS Political Awareness					x
			Acquisition					TT078					x					1		T001
			Additional Quality Management Tools					TT044					x					1		T002
			Advertising					TT095					x					1		T003
			Alternatives Generation					TT016					0		T005
			Analogous Estimating					TT028					x			x					2		T006
			Analytical Techniques					TT019					X					X					x					x					x		x					x			7		T007
			Approved Change Request Review					TT108					x					1		T008
			Assumptions Analysis					TT056					x					1		T009
			Benchmarking					TT005					x					1		T010
			Bidder Conferences					TT096					x					1		T011
			Bottom-up Estimating					TT025					x				x					2		T012
			Change Control Tools					TT101					x					1		T013
			Checklist Analysis					TT057					x					1		T014
			Claims Administration					TT113					x					1		T015
			Colocation					TT083					x					1		T016
			Communication Methods					TT052					x					x			x					3		T017
			Communication Models					TT053					x					x					2		T018
			Communication Rqmts Analysis					TT054					x					1		T019
			Communication Technology					TT055					x					x					2		T020
			Context Diagrams					TT006					x					1		T022
			Contingent Response Strategies					TT069					x					1		T023
			Contract Change Control System					TT114					x					1		T024
			Cost Aggregation					TT041					x					1		T026
			Cost of Quality					TT039					x		x					2		T027
			Critical Chain Method					TT032					x					1		T028
			Critical Path Method					TT033					x					1		T029
			Data Analysis					x	x	x					x		x
			Data Gather & Represent Techn					TT067					x					1		T030
			Data Gathering					x		x		x
			Data Representation					x
			Decision Making					x	x					x	x
			Decomposition					TT018					x		X					2		T031
			Dependency Determination					TT021					x					1		T032
			Design of Experiments					TT046					x					1		T033
			Diagramming Techniques					TT058					x					1		T034
			Documentation Reviews					TT059					x					1		T036
			Earned Value Management					TT105					x					1		T037
			Expert Judgement					TT001	x	x	x	x	x	x	x	X	X		x	x		x	x	x		x		x	x	x	x	x	x	x	x	x					x		x	x					x			x	x			30		T038
			Facilitation Techniques					TT002					0		T040
			Forecasting					TT106					x					1		T042
			Funding Limit Reconciliation					TT042					x					1		T043
			Ground Rules					TT084					x					1		T044
			Group Creativity Techniques					TT010					0		T045
			Group Decision-making Techniques					TT011					x			x					2		T046
			Historical Relationships					TT043					x					1		T047
			Independent Estimates					TT097					x					1		T048
			Information Gathering Techniques					TT060					x					1		T049
			Information Management					x
			Information Management Systems					TT093					x					x			x				3		T050
			Inspection					TT102					x				x					2		T051
			Inspections & Audits					TT115					x					1		T052
			Interpersonal & Team Skills					TT085	x		x		x	x					x			x	x				x					8		T053
			Knowledge Management					x
			Lead & Lags					TT022					x			x					x					3		T055
			Make-or-Buy Analysis					TT072					x					1		T056
			Management Skills					TT100					x					1		T057
			Market Research					TT073					x					1		T058
			Meetings					TT003	x	x	x	x				X					X			x	x	x	x					x	x	x					x	x					x	x		x	x			19		T059
			Modeling Techniques					TT034					x					x					2		T060
			Negotiation					TT080					x					1		T062
			Networking					TT049					x					1		T063
			- ITS Observation & Conversation					TT091					x					1		T064
			Observations					TT013					0		T065
			Org Charts & Position Descriptions					TT050					x					1		T066
			Organisational Theory					TT051					x					1		T067
			Parametric Estimating					TT029					x			x					2		T068
			Payment Systems					TT116					x					1		T069
			Performance Reporting					TT094					x					x					2		T070
			Performance Reviews					TT104					x	x					2		T071
			Personnel Assessment Tools					TT086					x					1		T072
			Pre-assignment					TT081					x					1		T073
			Precedence Diagramming Method					TT023					x					1		T074
			Probability & Impact Matrix					TT062					x					1		T075
			Process Analysis					TT075					x					1		T076
			Procurement Audits					TT119					0		T077
			Procurement Negotiations					TT098					x					1		T078
			Procurement Performance Reviews					TT117					x					1		T079
			Product Analysis					TT017					x					1		T080
			Project Management Info System					TT074					x					x					2		T081
			Project Management Software					TT026					x				x					x	x					4		T082
			Project Performance Appraisals					TT092					x					1		T083
			Proposal Evaluation Techniques					TT099					x					1		T084
			Prototypes					TT014					x					1		T085
			Published Estimating Data					TT027					x					1		T086
			Quality Audits					TT076					x					1		T087
			Quality Mgt & Control Tools					TT077					x					1		T088
			Quantitative Risk An&Model Techn					TT068					x					1		T089
			- DG Questionnaires & Surveys					TT015					0		T090
			Recognition & Rewards					TT087					x					1		T091
			Records Mgt System					TT118					x					1		T092
			Reserve Analysis					TT030					x			x	x					x				x					5		T093
			Resource Optimisation Techniques					TT035					x					x					2		T094
			Risk Audits					TT109					x					1		T095
			Risk Categorisation					TT063					x					1		T096
			Risk Data Qual Assessment					TT064					x					1		T097
			Risk Prob & Impact Analysis					TT065					x					1		T098
			Risk Reassessment					TT110					x					1		T099
			Risk Urgency Assessment					TT066					x					1		T100
			Rolling Wave Planning					TT020					X					1		T101
			Schedule Compression					TT036					x					x					2		T102
			Schedule Network Analysis					TT037					x					1		T103
			Scheduling Tool					TT038					x					x					2		T104
			Seven Basic Quality Tools					TT047					x					x					2		T105
			Stakeholder Analysis					TT004		x					1		T106
			Statistical Sampling					TT048					x					x					2		T107
			Strategies for Opportunities					TT070					x					1		T108
			Strategies for Threats					TT071					x					1		T109
			SWOT Analysis					TT061					x					1		T110
			Team-building Activities					TT088					x					1		T111
			Technical Performance Measurement					TT111					x					1		T112
			Three-point Estimating					TT031					x			x					2		T113
			To-complete Performance Index					TT107					x					1		T114
			Training					TT089					x					1		T115
			Variance & Trend Analysis					TT112					x					1		T116
			Variance Analysis					TT103					0		T117
			Vendor Bid Analysis					TT040					x					1		T118
			Virtual Teams					TT082					x					1		T119
			***EOL***