BE-Oldest Ice Core (BE-OIC)
- afternoon session -
11 M€
Step 1

---
Agenda of the Frankfurt meeting
Time	Item	Who (chair/speak)
13:00	Status of the submission / Primary objectives / Tasks/sub-tasks => Deliverables (Gantt chart) / Toward step 2 of the proposal => today’s goals	Barbante
13:10	Budget issues/discussion / National contributions / EU-Contribution (drilling/science/logistic)	Barbante/all
14:00	Consortia definition and Chair/discussion	Barbante/all
14:30	WP description/discussion / General description of the WP structure (10’) / WP5 – Ice core science (implementation plan) (10’) / WP4 – Non-core science (5’) / WP3 – Drilling (implementation plan) (10’) / WP2 – Logistic (implementation plan) (10’) / WP6 – International & cross-disciplinary exchange (incl. MoUs, Letters of support) (5’)	Barbante / Dahl-Jensen/Landais* / Parrenin/Eisen / Wilhelms/ Dahl-Jensen / Frezzotti/Bretel / Fischer/van de Wal**
15:30	Implementation of the proposal – step 2/ / /discussion / Writing Team / Timeline / Task assignment / Next meeting	Barbante/all
17:00	Any other business	all
*	with comments by HF and MH (CSA leads of WP Science)
**	with comments by EW (CSA leads of WP Science)

---
Status of the submission
Today’s goals
Agree on the budget (National/EU contributions)
Agree on Consortia definition and chair
Agree on WPs content/leadership
Agree on the implementation plan for Step 2 submission
Draft the Gantt chart with Tasks, Deliverables, Milestones
Deliverables are tangible or intangible objects produced as a result of the project that is intended to be delivered to a stakeholder (either internal or external).  A deliverable could be a report, a document, a server upgrade or any other building block of an overall project.
Milestones are scheduled events signifying the completion of a deliverable or set of related deliverables. There is no work associated with a milestone; it is a flag in the work plan to signify some other work has completed.
A deliverable differs from a project milestone in that a milestone is a measurement of progress toward an output whereas the deliverable is the result of the process. For a typical project, a milestone might be the completion of a product design while the deliverable might be the technical diagram of the product.

---
Beyond EPICA Adventure
Beyond EPICA Adventure
Our dreams
3yrs
5yrs
5yrs
Starting date mid 2019
CSA
Phase 1
Phase 2
19
28
18
24
21
20
23
22
29
25
27
26
17
CSA
Phase 1
3yrs
6 (+) yrs
FP9 ?
The reality, … as it is today
[Speaker Notes: Toward Phase 1 – drilling and Phase 2 analysis]

---
Status of the submission
Where are we ?
LC-CLA-17-2020: Polar climate: understanding the polar processes in a global context
Action should:
Aim at developing innovative approaches to assess the key physical and chemical processes in the ocean and atmosphere and the key ocean-atmosphere-ice interactions in order to improve predictions of future polar and global climate.
Research and Innovation Action (RIA)

---
Status of the submission
Where are we ?
}
a)	13 (6-8 M€)
b)	12 (6-8 M€)
c)	1 (± 10 }M€)
LC-CLA-08-2018: 35 proposals:
60 M€

---
Status of the submission
Primary objectives
Retrieving a continuous ice core to bedrock in Antarctica, which covers the climate history of the Mid Pleistocene Transition and beyond.
Logging, screening and cutting of ice core samples in the field
Establishing a first robust age scale for the BE-OI core
Deriving first high-resolution climate records over the time interval older than 700 kyr
Recovery of basal ice

---
Status of the submission
Tasks/sub-tasks => Deliverables (Gantt chart)

---
Budget issues/discussion
National contributions
Nation	In kind (k€)	Cash (k€)	TOT (k€)
Belgium
Denmark
France
Germany
Italy
Nederland
Norway
Sweden
Switzerland
UK
Only costs related to:
Logistics in DC/DF
Transport of traverse/camp vehicles and their use at LDC
Geophysics at LDC, incl. RAID
Rapid access drills Subglacior, Radix
Basler time at Dome F region
Twin Otter time at Concordia, DF
Drilling equipment
Drilling personnel
Cash contributions

---
Budget issues/discussion
National contributions
1500 k€
400 k€
TOT 9-11 M€
National
Contributions
France, Italy,
Switzerland
Denmark,
Germany, UK
Belgium, Nederland,
Norway, Sweden

---
Consortia definition/Chair
Directly on core/borehole, related to core, only indirectly …
cross-cut., major role, co-lead
1. Water isotopes	DE, FR, UK, IT, DK
2. Gases (greenhouse, isotopes, noble gases, …)	CH, DK, NL, FR
3. Impurities (chemistry, dust, isotopes, aerosols)	CH, DE, SW, IT, FR, UK,
4. Physical properties (electric, microstructure)	DE, FR, NO, UK
5. Basal properties (conventional, bio, …)	BE, DK, DE
6. Logging	FR, DE, DK
1. Signal preservation (air-snow interaction, diffusion, …)	NL, DE, IT, FR,
2. Dating (strat.+absolute+isot.+gas+electric+…)	FR, SW, IT, DK
1. Ice dynamics (local, regional)	BE, FR, UK, IT, DE
2. Geophysics (local, regional, other sites)	UK, NO, DE, DK, IT, FR,
3. Geology (sediment/rock core)	DK, IT
New methods	DK, CH, IT, FR, UK
Coordination project „BE-OI Drilling Phase“: IT (UVEN, Barbante +39 333 43 73 372)
Coordination Science: CH (UBERN, Fischer)
BE, CH, DE, DK, FR, NL, NO, SW, UK – 2 consortium leaders
Montabaur

---
Consortia definition/Chair
[Speaker Notes: We have to find a combination of balance between nations (and their respective contributions), gender, competencies and continuity with CSA]

---
WPs description/Chair
WP1 - Management and Coordination (Barbante)
WP2 - Logistics (Frezzotti, Chappellaz)
WP3 - Drilling (Wilhelms, Popp, Alemany)
WP4 - Ice Core Science (Dahl-Jensen, Landais, Fischer)
WP5 – Non Ice Core Science (Parrenin, Eisen)
WP6 - International & Cross-disciplinary Exchange (Wolff, van de Wal)
WP7 - Data policy, Dissemination, Outreach (Barbante)
Steering Committee (National representatives,
EXCOM (Coordinator, WP Science, WP logistics, WP drilling, field leader)
*policy on data sharing before publication, time(dead)line for measurements, publication policy (e.g. approval by SC),

---
Status of the submission
Tasks/sub-tasks => Deliverables (Gantt chart)

---
Implementation of the proposal - Step 2
	yr 1 / 2019-20	yr 2 / 2020-21	yr 3 / 2021-22	yr 4 / 2022-23	yr 5 / 2023-24	Yr 6 / 2024-25	Sub-Total
Logistic LDC	2	4	2	2	2	4	16
Driller LDC		4	7	7	7	5	30
Researcher LDC	3	1	3	3	3	2	15
Researcher / Concordia			2	2	2		6
Tot Pax	5	9	14	14	14	11	67
Transport by traverse IN	Fuel 10 m3 / Transport from Hb to DdU of the heavy drilling system, drill fluid, camp facility, core boxes	Casing tube, camp facility (10 tons) , fuel (20 m3), drilling system (10 tons), Drilling fluid (10 tons) Core box 10 m3,	Fuel 40 m3, drill fluid 20 m3	Fuel 20 m3, drill fluid 20 m3	Fuel 20 m3,
Start in July 2019
Purchase material
Transport material to Concordia
Ice core stored at Concordia
Transport ice sample to EU laboratories
Return and clean camp
Drilling
Borehole logging
Set-up drill camp
Transport material to DdU
CRESIS, pRES-GPS site refinement
Core processing at Concordia
D R A F T 1st March 2018

---
Implementation of the proposal - Step 2
Structure of the proposal - Step 2
Excellence
1.1 Objectives
1.2 Relation to the WP
1.3 Concept and methodology
1.4 Ambition
Impact
2.1 Expected Impact
2.2 Measures to maximise impact
a) Dissemination and exploitation of results
b) Communication activities
Implementation
3.1 Work plan — Work packages, deliverables
3.2 Management structure, milestones and procedures
3.3 Consortium as a whole
3.4 Resources to be committed
Step 1
Step 2

---
Implementation of the proposal - Step 2
What is needed
- Administrative data of participating organisations (deadline 30 April 2018)
- Budget for the proposal (100%)

---
Implementation of the proposal - Step 2
Work Package
description

---
Implementation of the proposal - Step 2
Work Package
description

---
Implementation of the proposal - Step 2
List of Milestones
Risk for implementation

---
Implementation of the proposal - Step 2
Section 4: Members of the consortium
4.1. Participants (applicants)
4.2. Third parties involved in the project (including use of third party resources)
Section 5: Ethics and Security
Environmental Impact Assesment (ENEA)

---
Implementation of the proposal - Step 2
Writing Team
Same as Step 1 (Barbante, Landais, Wolff, Stenni, Fischer, Wilhelm, Eisen, Frezzotti) + WP Chairs (discussion)
Task assignment
WP Chair must interact with Consortia for the implementation of the WPs
Template not yet available
Google Doc as working tool

---
Implementation of the proposal - Step 2
Timeline
Jun 30
Second draft
May31
First draft
Mar 31: Partner Description (nat. rep.)
Today
Sep 4th
March
April
May
June
July
August
May 31
Letters of
support
Apr 10
Science, Drilling, Logistic plans (WP chairs) – agreement on the budget
Aug 25
Submission
Jul 15
Final (draft) proposal
May 10
WPs Description, incl. D&M (WP chairs)
Meetings

---
Potential community/consortia papers
Community papers
Climatic paper
Mid Pleistocene Tarnsition /CO2
Consortia papers