## Sum
Sum	EC Dept of Education : PSU

					Organisation:	EC Dept of Education				Project Description:					Project Objective/ Purpose:
					Unit:	Infrastructure
					Programme ID:
					Pgm Name:
					Project ID:	P01
					Project Name:	PSU
					Sponsor:	Tsepo Pefole
					Business Owner:	Tsepo Pefole
					Supplier SPoC:	Tsholofelo Diale
					Project Manager:	Martin Bundred
					Req End Date:	31May18
					Req Start Date:	12Feb18

## Inf
Inf	EC Dept of Education : PSU

						DataVersion:	v00.01.00
						EffDate:	21/11/2008

						Sheet Type
						AC	Activity	Act
						BN	Benefit	Ben
						Art	Artefacts	Art
						DC	Decision	Dec
						IS	Issue	Iss
						ME	Meeting	Meet
						MS	Milestone	MS
						MT	Meeting Type	METp
						RK	Risk	Rsk
						RQ	Requirement	Rq
						SH	Stakeholder	SH
						SU	Summary Sheet	Sum
						TD	To Do	ToDo
						TL	Tool	Tool
						AS	Assets	Asset
						LC	Location	Loc
						Help	Field names, etc	Help
						IN	Codes tables, etc	Inf

						Last Rep date:	39740
						Proj St	12/02/18
						Proj end	41973
						Days in project	-836
						Days till report date	-2431
						Days left	1595

						Sunday
						Monday
						Tuesday
						Wednesday
						Thursday
						Friday
						Saturday

						Stakeholders
						5	Inform					5	6	7
						6	Inform, Confirm					1	5	6	7
						7	Consult, Monitor opinion					2	10	12	14
						10	Inform, Monitor					3	15	18	21
						12	Consult, Monitor, Inform
						14	Consult, Actively monitor
						15	Inform, Follow up
						18	Consult, Actively monitor
						21	Negotiate, Get agreement, Actively monitor

						Deliv Type
						Doc: document
						Frm: form
						Rep: report
						Pgm: program code unit
						TstP: test plan
						UsrG: user guide
						TrnM: training material

						Size
						T: tiny		0.1
						VS: very small		0.25
						S: small		0.5
						A: average		1
						L: large		4
						VL: very large		8
						X: exteremely large		16

						Complexity
						VS: very simple		0.25
						S: simple		0.5
						A: average		1
						C: complex		4
						VC: very complex		8
						X: extremely complex		16

						Meeting Type
						PL	Planning
						PR	Progress
						IN	Information
						CPC	Customer Prioitisation Committee
						SC	Steering Committee
						PB	Project Board
						CCB	Change Control Board
						CAB	Change Advisory Board
						BR	Briefing
						RVW	Review

						Asset Type
						CFA	Customer Furnished Asset
						SFA	Supplier Furnished Asset
						NPA	New Project Asset

						Completion status allocation
						1	Signed Off (100%)		1
						2	Started (25%)		0.25
						5	WiP (50%)		0.5
						7	Complete (75%)		0.75
						Y			0

						Schedule Granularity
						d	Days
						m	Months
						w	Weeks
						y	Years

						Non-Work Days
						01/01/2013	Tue, 1Jan13
						02/01/2013	Wed, 2Jan13
						21/03/2013	Thu, 21Mar13
						29/03/2013	Fri, 29Mar13
						01/04/2013	Mon, 1Apr13
						27/04/2013	Sat, 27Apr13
						01/05/2013	Wed, 1May13
						16/06/2013	Sun, 16Jun13
						17/06/2013	Mon, 17Jun13
						09/08/2013	Fri, 9Aug13
						24/09/2013	Tue, 24Sep13
						16/12/2013	Mon, 16Dec13
						25/12/2013	Wed, 25Dec13
						26/12/2013	Thu, 26Dec13
						17/06/2013	Mon, 17Jun13
						09/08/2013	Fri, 9Aug13
						24/09/2013	Tue, 24Sep13
						16/12/2013	Mon, 16Dec13
						25/12/2013	Wed, 25Dec13
						26/12/2013	Thu, 26Dec13
						01/01/2014	Wed, 1Jan14	New Years Day
						21/03/2014	Fri, 21Mar14	Human Rights Day
						18/04/2014	Fri, 18Apr14	Good Friday
						21/04/2014	Mon, 21Apr14	Family Day
						27/04/2014	Sun, 27Apr14	Freedom Day
						28/04/2014	Mon, 28Apr14
						01/05/2014	Thu, 1May14	Workers Day
						07/05/2014	Wed, 7May14	Election
						16/06/2014	Mon, 16Jun14	Youth Day
						09/08/2014	Sat, 9Aug14	Women's Day
						24/09/2014	Wed, 24Sep14	Heritage Day
						16/12/2014	Tue, 16Dec14	Day of Reconciliation
						25/12/2014	Thu, 25Dec14	Christmas
						26/12/2014	Fri, 26Dec14	Day of Goodwill
						01/01/2015	Thu, 1Jan15	New Years Day
						xEND

## Rsk
Rsk	EC Dept of Education : PSU
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44
						Cat					Init		Date
					RskNo	Typ	RskID	Lst#	Risk Name	Src	Grp	Lvl	S	T	E	E	P	L	E	Class	Type	Imp	Prob	Sev	Urg	RaiseBy	AllocTo	Raise	Alloc	Plan	Close	Age	Rank	Mitig	ActTp	Apprch	SH	X-Ref	DocRef	Risk Description	Evidence	Consequence	Status	Response Planning	Notes
					RI0000					1Jan08	4Jan08	16Jan08	17Feb08	47d
					RI0001	T		1	[insufficient capacity (numbers and competence levels)] <inability to complete projects within promised time and cost>					H	H			Elinor					IA			The capacity to deliver projects in the IPIP plan with the required resources - the Implementing Agents resource capacity as regards Programme, Project andSupply Chain Management. This is due both the ability to train or capacitate this function. The Implementing Agencies have the highest impact in terms of the overall success of the Programme. A strategy and plan should therefore be devised to appropriately capacitate the Programme, Project, and Supply Chain Managers.				Build a capacitation program (Actively Manage)			The RISK that [insufficient capacity (numbers and competence levels)] will result in the inability to complete projects within promised time and cost
					RI0002	T		2	[high attrition rate of required professionals] <major cause of capacity issues>					H	H			Elinor					IA			The high attrition rates in some of the Implementing Agencies the DoE Infrastructure Management should investigate the reasons for the high attrition rates of Built Experts, Project Managers, and required professionals in those relevant implementing agents. If possible, an intervention should take place to ensure that this trend is reversed and resources are bolstered through a management intervention				Explore reason for attrition structure an intervention according to requirement -(Actively Managed)			The RISK that [high attrition rate of required professionals will result in the major cause of capacity issues
					RI0003	T		3	[poor cash flow management] <late payments makes it difficult to maintain credit worthiness and places PSP’s and contractors at risk of insolvency>					H	H			Elinor					IA			Poorly managed cashflow management has been an issue as ineffective cashflow management from Implementation Agents leads to untimely payment of PSP (Professional Service Providers) who may either not complete deliverables or become non-compliant in providing EFMS inputs. / It is imperative that cashflow estimates are improved in-order to better budget.				Its important that this is done as soon as possible. Upload Cashflow based on estimated project date and project type. (Actively Managed)			The RISK that [poor cash flow management will result in the late payments makes it difficult to maintain credit worthiness and places PSP’s and contractors at risk of insolvency
					RI0004	T		4	[lack of effective prioritisation model] <funds not being allocated to the highest priority projects>					H	H			Elinor					DoE Director: Physical Resources Planning & Property Management			For the DoE to have to complete realistic planning it must have a view of the amount of outstanding commitments and projects which have run over time into the 2019/2020 year and what monies remain to embark on the projects which are allocated to this period. It is imperative the DoE use a prioritization model to prioritize those projects deemed most important by the Stakeholders which are impacted most by these projects.				its important that this is done as soon as possible. Establish Priority model based on factors such as Condition of schooll, the ASIDI Program is a priority the objective of ASIDI is to eradicate the Basic Safety Norms backlog The poorest of the poor are a priority in terms of their Stakeholder base as communities which require upliftment. (Actively Managed)			The RISK that [lack of effective prioritisation model will result in the funds not being allocated to the highest priority projects
					RI0005	T		5	[competence levels of academic staff] <poor acceptance by community and consequent damage to infrastructure>					H	M			Elinor					DoE Director: Physical Resources Planning & Property Management			Provide high caliber Principles and Teachers which the Education Districts, Chief , Community (Parens and Children ) will acept.Provide high caliber Principles and Teachers which the Education Districts, Chief , Community (Parens and Children ) will acept.				Ensure that Principles and Teachers have the correct qualification, track record and attitude. Poor performing Principles and Teachers should be perormance Manged out of the School system. Grow the Talent Pool of Principles and Teachers. (Actively Managed)			The RISK that [competence levels of academic staff will result in the poor acceptance by community and consequent damage to infrastructure
					RI0006	T		6	[the lack of responsive, integrated and sustainable service delivery plan per district] <scholar non-performance and community resentment>					H	M			Elinor					DoE Director: Physical Resources Planning & Property Management			Responsive, integrated, and sustainable service delivery. UAMP – Integrated plan per district.				Ensure that the municipal plans for schools infrastructure, water, electricity, roads support the population and distribution trends e.g. moving from urban to city and coastal predict a 5-UAMP year change. (Actively Managed)			The RISK that [the lack of responsive, integrated and sustainable service delivery plan per district will result in the scholar non-performance and community resentment
					RI0007	T		7	[poor reporting and evaluation] <poor adherence to commitments made and rolled over from month to month>					H	H			ERM					IA			At the ERM promises are made to correct issues. They then simply get rolled over from meeting to meeting. The minutes are poorly written, which means that person who have not attended the meetings are not informed adequately				Devise a mechanism of effective consequences for non-adherence to commitments. Identify / employ a professional writer (minute taker), or train at least three people in the ECDOE who could act as minute takers at important meetings.			The RISK that [poor reporting and evaluation will result in the poor adherence to commitments made and rolled over from month to month
					RI0008			8	[projects are not included on EFMS] <the needs will not be attended to>					H	H			Dale					IA			41 projects might not be DoE projects based on the IA programme details, all the other projects are clearly on the system as DoE programme Projects.					The RISK that [projects are not included on EFMS will result in the the needs will not be attended to
					RI0009	T		9	[improper updating of EFMS] <cash flow projections and other critical status information will not be available to ECDOE, and consequent payment delays>					H	H			Elmar					IA			It seems that IA representatives doe not understand how EFMS works, and do not capture data timeously or correctly. The incorrect data can be the root cause for many failures that occur in the adminsitration of the projects.				IA to identify EFMS updaters and provide evidence that they are competent to use the system. Consider having an certification process with PDU’s (Prfoessional Development Units) which certified EFMS users must report on on an annual basis (points awarded for accuracy and timeous capture of data)			The RISK that [improper updating of EFMS will result in the cash flow projections and other critical status information will not be available to ECDOE, and consequent payment delays
					RI0010	T		10	[projects are not closed out when they should be] <unauthorised and over-expenditure>					H	H			Dale					IA			Milestone and gate dates not captured on time or al all. / What also needs to be checked is if any of the findings from last year’s audit refer to the DoE disaster programme, in this case then the AG will definitely be investigating exactly these older emergencies as they would be listed in the finding form last year. Maybe Mr Mtyhuda and James Botha can assist to clarify if it would be safe to minimally update these older projects or not, and I would assume that the Irregular Expenditure Disclosures would also have to be checked for specific projects out of the batch that will have to have more inputs, all the Irregular Expenditure disclosures will need a full data base to address the Findings.				Consider using ECDOE officials to update the data.			The RISK that [projects are not closed out when they should be will result in the unauthorised and over-expenditure
					RI0011	C02	C02	C02	C02	C02	C02	C02	C09	C10	C11	C12	C13	C14	C15	C16	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02	C02
						C03

## HighRep
HighRep	EC Dept of Education : PSU
		RiskNo	Lst#	Risk Name	Imp	Prob	RaiseBy	SH	Risk Description	Response Planning

		RI0001	1	The RISK that [insufficient capacity (numbers and competence levels)] will result in the inability to complete projects within promised time and cost	H	H	Elinor	IA	The capacity to deliver projects in the IPIP plan with the required resources - the Implementing Agents resource capacity as regards Programme, Project andSupply Chain Management. This is due both the ability to train or capacitate this function. The Implementing Agencies have the highest impact in terms of the overall success of the Programme. A strategy and plan should therefore be devised to appropriately capacitate the Programme, Project, and Supply Chain Managers.	Build a capacitation program (Actively Manage)
		RI0002	2	The RISK that [high attrition rate of required professionals will result in the major cause of capacity issues	H	H	Elinor	IA	The high attrition rates in some of the Implementing Agencies the DoE Infrastructure Management should investigate the reasons for the high attrition rates of Built Experts, Project Managers, and required professionals in those relevant implementing agents. If possible, an intervention should take place to ensure that this trend is reversed and resources are bolstered through a management intervention	Explore reason for attrition structure an intervention according to requirement -(Actively Managed)