## Slide 1
Cross Project Preparation Approach
Mar
Apr
May
Jun
12
13
14
15
16
17
18
19
20
21
22
23
24
4.6.18
TM BU
Prep. test data incl. testing
TM BU/IT
Consolidate test scenarios for UAT
Checking stock in AFS & EWM
TM IT
TM Logistics
27.4.18
TM BU
Check and create registerd customers (CRM)
Test data request
Check planned release topics
TM IT
TM Logistics
Check coupons for all countries
TM BU
Prep. test data incl. testing
(Sub) PL BU
Create promotion price SAP
TM IT
Planning and coordination of test resources
7.5.18 - 25.5.18
T-Test
Start UAT
4.6.18
4.6.18 - 14.6.18
UAT-Test
Go-Live
18.6.18
Preparation SOM
Preparation SOM
TM IT
Responsible
TM BU/IT
6.4.18
Check & create registered customers (CRM)
TM BU
Definition of test scenarios
Check coupons for all countries
TM BU
10.4.18
Create promotion price SAP
TM IT
Check stock in AFS & EWM
TM BU
Realization TM IT
Start T-Test
7.5.18
Review test documents
TM BU/IT
6.4.18
PL BU / IT
Test Manager BU/IT
Elaboration of possible synergies / risks
TM IT
TM BU / IT
20.4.18
TM BU
DRAFT