## Sheet1
s000	No	Description	Date		Responsible					s000
s001		Creation of Collection EFT file			Bomaid			<Date>			s001
s002		Final Payment			Bomaid			<Date>			s002
s003		Creation of Payment EFT file			Bomaid			<Date>			s003
s004	1	Provide Latest CHF to Mediscor	Fri, 13Dec19	16:00	Bomaid			29 Nov 19 @ 16:00			s004	29Nov19	16:00		Fri, 13Dec19
s005		Provide Latest CHF to MSO	Fri, 13Dec19	16:00	Bomaid			29 Nov 19 @ 16:00			s005	29Nov19	16:00	0	Fri, 13Dec19
s006	2	Stop Ez-Cap system change/update access	Fri, 13Dec19	17:00	Bomaid			29 Nov 19 @ 17:00			s006	29Nov19	17:00	0	Fri, 13Dec19
s007		Allow view access only on Ez-Cap	Fri, 13Dec19	17:00	Bomaid			29 Nov 19 @ 17:00			s007	29Nov19	17:00	0	Fri, 13Dec19
s008		Stop Ez-Cap to Sage Interface	Fri, 13Dec19	17:00	Sage			29 Nov 19 @ 17:00			s008	29Nov19	17:00	0	Fri, 13Dec19
s009		Stop Sage access for Collections	Fri, 13Dec19	17:00	Sage			29 Nov 19 @ 17:00			s009	29Nov19	17:00	0	Fri, 13Dec19
s010		Sage corrections from Ex-Cap Interface	Fri, 13Dec19	18:00	Sage			29 Nov 19 @ 18:00			s010	29Nov19	18:00	0	Fri, 13Dec19
s011	3	Galnet start data Extracts	Fri, 13Dec19	17:15	Galnet			29 Nov 19 @ 17:15			s011	29Nov19	17:15	0	Fri, 13Dec19
s012		Sage start data Extracts	Fri, 13Dec19	17:15	Sage			29 Nov 19 @ 17:15			s012	29Nov19	17:15	0	Fri, 13Dec19
s013	4	FTP data			Galnet			On completion			s013
s014		Membership	Fri, 13Dec19	18:30	Galnet			29 Nov 19 @ 18:30			s014	29Nov19	18:30	0	Fri, 13Dec19
s015		Authorizations	Fri, 13Dec19	20:30	Galnet			29 Nov 19 @ 20:30			s015	29Nov19	20:30	0	Fri, 13Dec19
s016		AR data	Sat, 14Dec19	17:00	Sage			30 Nov 19 @ 17:00			s016	30Nov19	17:00	1	Sat, 14Dec19
s017		Claims	Sat, 14Dec19	17:00	Galnet			30 Nov 19 @ 17:00			s017	30Nov19	17:00	1	Sat, 14Dec19
s018		Latest dump of all data by	Sat, 14Dec19	20:00				30 Nov 19 @ 20:00			s018	30Nov19	20:00	1	Sat, 14Dec19
s019	5	MIP data loaded					s019
s020		Membership	Sun, 15Dec19	12:00	MIP			01 Dec 19 @ 12:00			s020	1Dec19	12:00	2	Sun, 15Dec19
s021		Authorizations	Sun, 15Dec19	12:00	MIP			01 Dec 19 @ 12:00			s021	1Dec19	12:00	2	Sun, 15Dec19
s022		AR data	Sun, 15Dec19	20:00	MIP			01 Dec 19 @ 20:00			s022	1Dec19	20:00	2	Sun, 15Dec19
s023		Claims	Sun, 15Dec19	20:00	MIP			01 Dec 19 @ 20:00			s023	1Dec19	20:00	2	Sun, 15Dec19
s024		Calculate limits	Mon, 16Dec19	20:00	MIP			02 Dec 19 @ 20:00			s024	2Dec19	20:00	3	Mon, 16Dec19
s025	6	Reports Bomaid					s025
s026		Membership balances	Sat, 14Dec19	12:00	Bomaid			30 Nov 19 @ 12:00			s026	30Nov19	12:00	1	Sat, 14Dec19
s027		Age analysis Member	Sat, 14Dec19	12:00	Bomaid			30 Nov 19 @ 12:00			s027	30Nov19	12:00	1	Sat, 14Dec19
s028		Age analysis Provider	Sat, 14Dec19	12:00	Bomaid			30 Nov 19 @ 12:00			s028	30Nov19	12:00	1	Sat, 14Dec19
s029		Claims totals per payment run	Sat, 14Dec19	12:00	Bomaid			30 Nov 19 @ 12:00			s029	30Nov19	12:00	1	Sat, 14Dec19
s030	6	Reports MIP					s030
s031		Membership balances	Sun, 15Dec19	14:00	MIP			01 Dec 19 @ 14:00			s031	1Dec19	14:00	2	Sun, 15Dec19
s032		Age analysis Member	Sun, 15Dec19	14:00	MIP			01 Dec 19 @ 14:00			s032	1Dec19	14:00	2	Sun, 15Dec19
s033		Age analysis Provider	Sun, 15Dec19	14:00	MIP			01 Dec 19 @ 14:00			s033	1Dec19	14:00	2	Sun, 15Dec19
s034		Claims totals per payment run	Tue, 17Dec19	10:00	MIP			03 Dec 19 @ 10:00			s034	3Dec19	10:00	4	Tue, 17Dec19
s035	7	Audit					s035
s036		Start Check and compare	Sun, 15Dec19	15:00	Bomaid/MIP			01 Dec 19 @ 15:00			s036	1Dec19	15:00	2	Sun, 15Dec19
s037	8	Sign Off					s037
s038		Membership	Sun, 15Dec19	18:00	Bomaid/MIP			01 Dec 19 @ 18:00			s038	1Dec19	18:00	2	Sun, 15Dec19
s039		Authorizations	Sun, 15Dec19	18:00	Bomaid/MIP			01 Dec 19 @ 18:00			s039	1Dec19	18:00	2	Sun, 15Dec19
s040		AR data	Sun, 15Dec19	18:00	Bomaid/MIP			01 Dec 19 @ 18:00			s040	1Dec19	18:00	2	Sun, 15Dec19
s041		Claims	Tue, 17Dec19	12:00	Bomaid/MIP			03 Dec 19 @ 12:00			s041	3Dec19	12:00	4	Tue, 17Dec19
s042	9	GO LIVE					s042
s043		Membership					s043
s044		New Membership Start	Mon, 16Dec19	08:00	Bomaid/MIP			02 Dec 19 @ 08:00			s044	2Dec19	08:00	3	Mon, 16Dec19
s045		Call Centre					s045
s046		Clients services Start	Mon, 16Dec19	08:00	Bomaid/MIP			02 Dec 19 @ 08:00			s046	2Dec19	08:00	3	Mon, 16Dec19
s047		Authorisations					s047
s048		MSO (Stand-in)			MSO			Never Stopped			s048
s049		Bomaid	Mon, 16Dec19	08:00	Bomaid/MIP			02 Dec 19 @ 08:00			s049	2Dec19	08:00	3	Mon, 16Dec19
s050		Claims					s050
s051		Scan paper claims	Mon, 16Dec19	08:00	Bomaid			02 Dec 19 @ 08:00			s051	2Dec19	08:00	3	Mon, 16Dec19
s052		Process paper claims	Wed, 18Dec19	08:00	Bomaid			04 Dec 19 @ 08:00			s052	4Dec19	08:00	5	Wed, 18Dec19
s053		Import and process EDI claims	Wed, 18Dec19	08:00	Bomaid			04 Dec 19 @ 08:00			s053	4Dec19	08:00	5	Wed, 18Dec19
s054		Benefit changes for 2020			MIP			Start in November			s054
s055		Benefit files to Mediscor	Tue, 14Jan20	17:00	MIP			31 Dec 19 @ 17:00			s055	31Dec19	17:00	32	Tue, 14Jan20
s056