# Introduction
Just what is a risk, and what is an issue?
Issues arise continually on projects and are second nature to projects. One can put in place mechanisms to reduce their incidence, but one will never remove them completely. They arise as a consequence of human frailty, faulty equipment, software, tools, techniques, inappropriate standards (or the inappropriate application of the appropriate standards) and as many other reasons as one can think of. They can even be positive.
Issues can be classified in the following groups:
Those that involve an as-yet undefined impact on the project, such as
- General concerns (something bothers us, but we are not sure if we should be worried. These may turn out to be unfounded, translate into risks, and/ or change requests. )
- Risks (situations that could have a direct negative impact on the success of the project)
- Future risks (matters that may not affect the project directly, but may impact on the successful use of the output of the project, or a follow-on project)
- Opportunities (something that we could do that may involve some risk, or unplanned expenditure but that could give an advantage to the project)
- Flash of inspiration (similar to an opportunity, but may be at a total tangent to everything that is “official” in the project and thus requires rethinking, negotiation and has an impact on foundational instruments such as the charter, contract, base lined project plan, and so on)
Those that involve work to be done that has not been defined in base lined plans, such as
Issues that have to do with the end product that is to be delivered to the customer, such as
- Defect repair (where a result does not conform in some way or other to an original requirement as specified by the user or owner)
- Change requests (where the original requirement by the user or owner was incorrectly defined or described, not defined at all, or has changed)
In addition, there are issues that may have nothing to do with requirements, but are necessary to be done within the project, such as
- Corrective Action Requests (CAR) (they initiate changes to processes, procedures, standards, guidelines, policies, etc.)
- To do items (things that we know need to be done)
- Parking lot items (things we may have to do, but will review and decide on at a later time)
A final type of issue that should be formally logged and managed is decisions. These typically result in a flow of activity. Often, the original event that gave rise to the activity or activities could be lost.