## 01 to 09
DATE	REF.	DESCRIPTION	LOCATION	LEVEL	INST.	LEN.	WID.	HEI.	NO.	QTY.	MEN	HOURS	LIFTS	VALUATION	UNIT	NO.	QTY	RATE	TOTAL	COMMENTS
03/01/13 TO 04/01/13	01	COMPLETE THE ERECTION OF AN INDEPENDENT SCAFFOLD WITHIN THE BASEMENT 2 TANK ROOM, ADJACENT TO THE LARGE SPRINKLER TANKS, IN ORDER TO ALLOW ACCESS AT CEILING LEVEL FOR THE INSTALLATION OF THE HIGH LEVEL PIPEWORK. / SCAFFOLD COMPLETE WITH ONE FULLY BOARDED LIFT, ALONG WITH 3 INNER BOARDS TO THE TOP BOARDED LIFT, LADDER AND LADDER GATE. / IN ADDITION 4 MEN X A FULL DAY ON 03/01/13, GETTING ALL MATERIALS FROM GROUND FLOOR LEVEL, DOWN THROUGH THE STAIR CORE AND IN TO THE PLANT ROOM, WITH THE SCAFFOLD ERECTED IN AND THROUGH THE PIPEWORK AND PLANT.	LOCATION A	INST1	INST 1 EXAMPLE	25.00	1.30	5.00	1.00	1.00	0.00	0.00	1.00	TEST A	M2	1.00	1.00	£1.00	£1.00
						25.00	1.00	0.00	1.00	1.00	0.00	0.00	1.00	TEST E	M	1.00	1.00	£1.00	£1.00
						0.00	0.00	0.00	2.00	1.00	0.00	0.00	0.00	TEST E	NO.	1.00	1.00	£1.00	£1.00
						0.00	0.00	0.00	1.00	1.00	4.00	8.50	0.00	TEST B	HR.	1.00	1.00	£1.00	£1.00
														TEST C	HR.	1.00	1.00	£1.00	£1.00
04/01/13	02	ERECT A LADDER ACCESS SCAFFOLD, WITHIN THE RISER CUPBOARD, WITH 3 FULLY BOARDED LIFTS, IN AND THROUGH THE DUCTING, FOR REMOVAL OF THE EXISTING DUCTING AT BASEMENT 2 TO BASEMENT 1 LEVEL. / IN ADDITION 3 MEN X 4 HOURS EACH GETTING ALL MATERIALS DOWN FROM GROUND FLOOR LEVEL, INTO BASEMENT 2 AND ACROSS INTO THE RISER CUPBOARD.	LOCATION B LOCATION BLOCATION BLOCATION B	BASEMENT 2	INST 2 EXAMPLE	3.00	2.60	6.00	1.00	1.00	0.00	0.00	3.00	TEST F					£0.00
						0.00	0.00	0.00	3.00	1.00	0.00	0.00	0.00	TEST F					£0.00
						0.00	0.00	0.00	1.00	1.00	3.00	4.00	0.00	TEST B	HR.	1.00	1.00	£1.00	£1.00
														TEST C	HR.	1.00	1.00	£1.00	£1.00
09/01/13	03	ERECT A SERIES OF DOUBLE HANDRAILS AT GROUND FLOOR LEVEL, TO THE STEPHEN STREET ELEVATION CANOPY AREA, TO ALLOW THE GROUND FLOOR SLAB TO BE BROKEN OUT, FOR ACCESS WITH MATERIALS FOR VARIOUS TRADES DOWN INTO THE BASEMENT 1 AREA.	LOCATION C	GROUND FLOOR LEVEL	INST 3 EXAMPLE	11.00	0.00	1.00	1.00	1.00	0.00	0.00	0.00	TEST G					£0.00
14/01/13	04	ERECT AN INDEPENDENT SCAFFOLD AT BASEMENT 2 LEVEL, WITH 2 FULLY BOARDED LIFTS, LADDER AND LADDER GATES, ALONG THE SIDE OF THE SOUTH WALL, TO THE PLANT ROOM, IN ORDER TO ALLOW THE BRICKWALL, TO BE REMOVED, UP TO THE UNDERSIDE OF THE BASEMENT 1 SLAB. / IN ADDITION 3 MEN X 5 HOURS EACH GETTING ALL MATERIALS DOWN FROM GROUND FLOOR LEVEL , ALONG THE CORRIDORS AND INTO THE PLANT ROOM, FOR THE ERECTION OF THE SCAFFOLD.	LOCATION D	BASEMENT 2 LEVEL	INST 5 EXAMPLE	10.00	1.50	5.00	1.00	1.00	0.00	0.00	1.00	TEST H	M2	1.00	1.00	£1.00	£1.00
														TEST I	M	1.00	1.00	£1.00	£1.00
						0.00	0.00	0.00	1.00	1.00	0.00	0.00	0.00	TEST J	NO.	1.00	1.00	£1.00	£1.00
						0.00	0.00	0.00	1.00	1.00	3.00	5.00	0.00	TEST B	HR.	1.00	1.00	£1.00	£1.00
														TEST C	HR.	1.00	1.00	£1.00	£1.00
09/01/13 TO 18/01/13	06	ERECT A FULLY BOARDED UNDERSLUNG LAYDOWN TO THE UNDERSIDE OF THE STEELS, AT BASEMENT 2 LEVEL, IN AND ACROSS THE MAIN DOOR WAY / ENTRANCE TO THE PLANT ROOM, ADJACENT TO THE GAS METER ROOM AREA, FOR THE DEMOLITION OF THE BRICKWORK AT HIGH LEVEL.	LOCATION E	BASEMENT 2 LEVEL	INST 4 EXAMPLE	2.00	1.00	0.00	1.00	1.00	0.00	0.00	1.00	TEST K	M2	1.00	1.00	£1.00	£1.00
																		TOTAL	£13.00