## Sheet1
Project name	MoJ Shared Services	Defence Core Network Services	Transforming the Customer Experience	Defence Information Infrastructure	London Programme for IT	G-Cloud Programme (covers Data Centre Consolidation and Application Store)	ICT Relet Project (formerly entitled ICT Desktop Refresh)	Universal Credit Programme	One Click	SOCA Information Systems and Operating Technology (ISOT) Programme	Shared Services Futures Project	Immigration Case Work (ICW)	DVLA ICT Contract Procurement	Real Time Information (RTI)	NME Programme for IT	N3 Extension	National Cyber Security Programme	Prism and Firecrest Re-procurement Programme	Echo	Electronic Exchange of Social Security Information (EESSI) Programme	Electronic Prescription Service (EPS) Release 2	NHSmail service refresh	Summary Care Record (SCR)	Southern Programme for IT	Falcon - 02 (Increments A & C amalgamated at 1/4/11)	Central Payment System	Public Services Network Programme	End Crypto Units (ECU)					Project OSCAR	Integrated Delivery Programme	National Offender Management Information Systems (NOMIS) Programme	Quantum Re-compete Project		Electronic Monitoring	Future IT Sourcing Programme (FITS)	SOCA Catalyst	Extend and Blend	Immigration and Asylum Biometric System (IABS)		IMPACT	New Passport Programme	Next Generation Outsourced Visa Services Contract		Emergency Services Mobile Communications Programme (ESMCP)	Communications Capabilities Development programme	Police ICT Company Programme		SIG Disclosure & Barring Service Programme (formerly Convergence Programme)	Schengen Information Systems (SIS) II Programme	eBorders	BIS Shared Services	Core Systems Replacement		IMS3
Department	Ministry of Justice	Ministry of Defence	Home Office	Ministry of Defence	Dept. of Health	Cabinet Office	Dept. of Local Gov.	Dept. Work & Pensions	HM Revenue & Customs	Home Office	Dept. for Transport	Home Office	Dept. for Transport	HM Revenue & Customs	Dept. of Health	Dept. of Health	Cabinet Office	Foreign Office	Foreign Office	HM Revenue & Customs	Dept. of Health	Dept. of Health	Dept. of Health	Dept. of Health	Ministry of Defence	Dept. Work & Pensions	Cabinet Office	Ministry of Defence					HM Treasury	Ministry of Justice	Ministry of Justice	Ministry of Justice		Ministry of Justice	Ministry of Justice	Home Office	Home Office	Home Office		Home Office	Home Office	Home Office		Home Office	Home Office	Home Office		Home Office	Home Office	Home Office	Business & Skills	Business & Skills		Dept. of Health
Red-Amber-Green	Red	Red	Red	Amber/Red	Amber/Red	Amber/Red	Amber/Red	Amber/Red	Amber/Red	Amber/Red	Amber/Red	Amber	Amber	Amber	Amber	Amber	Amber	Amber/Green	Amber/Green	Amber/Green	Amber/Green	Amber/Green	Amber/Green	Green	Green	Green					Amber	Amber/Green	Amber	Amber		Amber	Amber	Amber/Green	Green	Amber/Green		Amber	Green	Amber/Green			Amber	Amber		Amber	Amber	Amber	Amber	Amber		Green
Description / aims	The MoJ Shared Services Programme will deliver a transformation in the approach to the provision of back office services in MoJ. The Programme will establish a single professional MoJ Shared Services Organisation, supported by a best fit Enterprise Resource Platform (ERP) and associated technology stack, providing HR, Payroll, Finance, and Requisition to Pay transactional services initially to in scope MoJ Departments and ALBs with potential for further expansion to encompass Other Government Departments (OGDs). Through rationalising the existing disparate back office teams and systems into the single MoJ Shared Services Organisation the programme will deliver cost reductions and service improvements in back office services across MoJ that support Coalition efficiency & savings targets and the aims of the wider MoJ’s Transforming Justice agenda.	DCNS is the programme responsible for replacing Defence’s major information and communications systems, including computers, telephones, and video-conferencing, and the networks that they use, both in the UK and deployed overseas, either permanently or on specific operations. The scope of the DCNS approach is initially focussed on replacing what is currently provided by Defence Electronic Commerce Service (DECS), Defence Fixed Telecommunications Service, Defence Information Infrastructure (DII), Defence High Frequency Communication Services and SkyNet contracts. However, it is intended to expand the approach incrementally to cover all Information Services and Systems (ISS) projects and programmes. Under DCNS, ISS is developing a new acquisition programme approach that is based upon the following key principles: (a) The adoption of a Services Portfolio approach; / (b) A Target Supply Chain Model; / (c) The creation of a Target Operating Model; / (d) Construction of an ISS Delivery Programme	The Application & Enrolment Contract let to Computer Science Corporation in April 2009 (and reset in October 2010) includes the provision of Information Technology Outsourcing Services and a transformation programme to deliver: i) More robust, integrated, secure and cost effective technical infrastructure to support IPS business operations, including networks and telephony. / (ii) A Customer Application Management System (AMS) to replace PASS and a new Online Application Channel for passport applicants in the UK and overseas.	Description: DII is the largest Defence IT programme of its type in the world, with an ultimate global footprint in the Fixed (UK mainland and overseas permanent sites), Mobile ('on the road' and homeworking), and Deployed and Maritime (supporting Operations, Exercises and routine working) environments. DII operates across all security domains. Aims: DII's approved aim is to deliver to Defence a secure and coherent information infrastructure at best value for money and to approved cost; this capability was approved partly on the basis that it will replace the MOD's costly and outdated legacy systems and deliver significant operational and efficiency benefits.	LPfIT has overall responsibility for upgrading NHS information technology to make it possible for hospitals, community services and mental health trusts to implement Electronic Patient Record as per the LSP contract with BT. This will enable the NHS to provide better, safer care for patients wherever and whenever they need it.	Implementing the Government Cloud, CloudStore (formerly the Applications Store) and rationalising the number of data centres (programme now known as Hosting Services Consolidation) in order to deliver financial savings. / Achieved by the delivery of the following action identified in the Government ICT Strategy published in March 2011: / * Create a online Applications Store by April 2012 / * Reduce the cost of data centres across the Government estate leading to a 35% reduction in costs over 5 years. Produce a plan by October 2011 / * Publish a Cloud Computing Strategy by October 2011	DCLG must replace current ICT services by February 2014 when the current supplier service contract ends. There is an opportunity to break the current contract in August 2013 something DCLG are hoping to do inn order to reduce costs as quickly as possible. The existing IT estate is up to 7 years old and requires updating. The service will include circa 2,500 desktops across 20 offices and 50 business applications.	Universal Credit provides a new single system of means-tested support for working-age people who are in or out of work. / It aims to reduce the number of work-less households: by reducing the financial and administrative barriers to work that exist in the current system of benefits and tax credits; and replacing the complex system of income-related benefits (Housing Benefit, Income Support, income-related Employment and Support Allowance, income-related Jobseeker’s Allowance, Working Tax Credit and Child Tax Credit) with a single payment.	One Click brings many tax services (Corporation Tax, Income Tax Self Assessment, Value Added Tax, and Pay As You Earn) that businesses need together in one place, online. Focuses on key events in a business' lifecycle, with information for pre-start ups, a single place to register for business taxes, and a self-serve facility to view and update details online.	The SOCA ISOT Programme is replacing multiple existing ICT contracts with one contract which will enable the necessary step-change in SOCA’s capacity and capability to make a difference in the world of serious organised crime and its harmful impact on the public, by contracting for and modernising to an effective, efficient, managed ICT delivery capability.	The Shared Services Futures (SSF) project was established to develop, evaluate and deliver a new approach to the future sourcing of back office shared services functions by the Department for Transport (including its Executive Agencies). / The DfT Board confirmed in April 2010 that running shared services is not “core business” for the DfT and subsequently the SSF Project was set up. Phase 1 of the project (August-November 2010) considered the potential for transfer to another Government Department or the private sector – as well as a base case of continued in-house provision. / After Phase 1 the Project Board recommend to the DfT Board progressing divestment as a preferred option for the Shared Service centre subject to market testing. The DfT Board decided on the 9th December 2010 that its preferred option would be to sell Shared Services to a private sector provider. In taking this decision, the Board has committed to buying Shared Services from the new owner for up to 10 years and plan to require the new owner to retain a significant presence in Swansea. / The Project is undertaking a competitive dialogue to deliver its chosen provider. Following a procurement process, 3 preferred bidders were chosen in late 2011 and Competitive Dialogue started in February 2012. This process is due complete in October 2012 and contract award is targeted for December 2012. / The SSF project is also a key deliverable for the Next Generation Shared Services Programme (NGSS) which is managed by the Cabinet Office. This Programme is focused on the centralisation of transactional functions for Finance, HR, Payroll and Procurement into 2 Independent Shared Service Centres (ISSC). / SSF will therefore be ISSC 1 and it is currently planned that the centre will include a low cost type ERP option, with smaller government departments joining this centre through using a call off arrangement. / The key objectives are to identify and deliver an approach to the future provision of back office shared services to the Department which offer increased value for money by: / a) delivering the required services and maintaining acceptable minimum quality levels (“delivers acceptable service”); / b) standardising processes and outcomes sought from shared services wherever realistically possible, affordable and cost effective including through minimising and prioritising change requests (“standardised approach”); / c) reducing significantly the management time and attention devoted to, and the need for future up front capital investment in, shared services provision (“reduces demands on DfT”); / d) achieving material and continued overall cost savings within the current (2011/12-2014/15) and subsequent spending periods (“achieves cost efficiency”); / e) minimising the risk to ongoing service delivery (“offers acceptable risk”); and which is also / f) Consistent with wider Government initiatives and so supported by the Efficiency and Reform Group (“consistent with wider objectives”).	The ICW Programme is a business-led change programme with the objective of supporting the Home Office and the former UK Border Agency in achieving their strategic objectives, through the delivery of a world-class case working capability.	The contract for Driver and Vehicle Licensing Agency's (DVLA) ICT service provision must be replaced by September 2015, when the current contract extension with IBM/Fujitsu runs out. This programme will: / Seek to reduce the overall cost of delivery of ICT within DVLA / Move away from a single monolithic contract to a supply chain made up of smaller, shorter contracts which avoid lock in to any supplier. We will do this by: / a) contributing and aligning to a cross-Government approach / b) undertaking preparatory work to specify the form, scope, nature and structure of provision required for the future / c) work closely with others across DfT on contracts, data centre consolidation and virtualisation of databases / d) planning and scoping the subsequent DVLA procurement activities needed / e) delivering the future internal management arrangements needed to manage contract and service delivery (both up to and post 2015).	Real Time Information is the next stage of improving Pay As You Earn through the use of real time information. / It will deliver a series of projects to implement measures designed to improve the efficiency and effectiveness of the Pay As You Earn system. / This will underpin the introduction by the Department for Work and Pensions of the Universal Credit regime.	NMEPfIT Programme: Increased patient safety and quality of healthcare and also greater clinical effectiveness and administration efficiency	N3 is the National Network for the NHS. It is a Wide Area Network (WAN) deployed as a Virtual Private Network (VPN) and is one of the largest in Europe. It provides reliable, supporting IT infrastructure, world class Internet Protocol (IP) networking services and sufficient, secure connectivity and broadband capacity to meet current and future NHS IT needs. It provides connectivity to all NHS organisations in England, as well as non- NHS sites providing NHS care, ensuring a reliable service at every site where NHS services are delivered or managed. Via N3 Voice Services it makes best value IP telephony services available to all NHS organisations including GP’s. N3 Managed Video Conferencing services are also available supporting the full range of devices from large VC dedicated rooms to desktop webcams which affords the opportunity for significant cost saving and productivity benefits for subscribed users via the suite of collaboration tools. N3 is a fully managed IP network with over 46,000 connections (consisting of over 15,000 physical, 11,500 aggregator and 19,500 VPN Token connections) which is contracted to be available 24hrs, 7days a week for 365 days per year.	The National Cyber Security Programme (NCSP) was put in place as a consequence of the Strategic Defence and Security Review (SDSR), with a budget of £650 million over 4 years. Its aim is to deliver a transformative programme to give the UK a strategic advantage in cyber security and resilience. The programme is managed by the Office of Cyber Security and Information Assurance (OCSIA) in the Cabinet Office.	To renew the contracts for the following business critical ICT services: / • Prism : FCO's Oracle based enterprise resource and financial planning (ERP) contract with Cap-Gemini. / • Firecrest: FCO's Microsoft based desktop infrastructure and management contract with Hewlett Packard. / and procure a new ICT Management service / • SMI : FCO's new Service Management Integration contract	Echo is a new global network for voice and data services currently delivered through the FCO Telecommunications Network (FTN) to FCO Overseas Posts. It will also replace the Managed Telephony Service (MTS) delivered to FCO sites across the UK. The Echo Programme will make a substantial contribution to delivering the FCO’s ICT Strategy and, in turn, support Diplomatic Excellence which is the FCO’s reform and modernisation programme.	The Electronic Exchange of Social Security Information Programme aims to introduce a means of communicating electronically with other European Union Member States in respect of the Social Security affairs of migrant workers	The Electronic Transmission of Prescriptions (ETP) Programme is delivering the Electronic Prescription Service (EPS) which is a national service that has its origins in a number of government policy initiatives from 1998. However, work on building this new service that will operate in all GP practices and pharmacies in England, began in December 2003. / With 1.6 million paper prescriptions generated every working day in England and a predicted annual rise of 5 per cent, the EPS provides an alternative means of generating and processing the growing number of prescriptions / The NHS Electronic Prescription Service (EPS) enables prescribers, such as GPs and practice nurses, to send prescriptions electronically to a dispenser (such as a community pharmacy or dispensing appliance contractor) of the patient’s choice. Dispensing contractors can subsequently send electronic reimbursement endorsement claims to the NHS Prescription Service. The main aims of the ETP programme are: / o To enable the electronic transmission of prescription data in England between: / - Prescribers (GP, nurses, supplementary) / - Dispensing contractors (community pharmacy, dispensing doctors and dispensing appliance contractors) / - The NHS Care Record Service / - Reimbursement Agencies (e.g. the Business Services Authority’s NHS Prescription Services) / o To facilitate the efficient, convenient and accurate dispensing of medication to patients. The scope of the programme covers all primary care prescribing and dispensing (excluding Schedule 2 and 3 controlled drugs) and supply of medicines, drugs, appliances and chemical reagents by authorised dispensing contractors. Secondary care prescriptions issued for dispensing in the community are also within scope / o To enable the NHS Prescription Service to re-engineer their processes to increase capacity and reduce the unit cost of processing prescriptions.	NHSmail provides a secure email service for the NHS. Relay provides a message routing service linking NHS organisations and the NHS with the internet. To decommission over 9,000 locally provided email services - this will continue until at least 2013 (contract term).	Delivery of the SCR which supports urgent and emergency care settings, providing information to authorised health care professionals to support care where no information is currently held about a patient, for example in out-of-hours settings, emergency departments, treating temporary residents and emergency admissions to secondary care.	SPFIT Programme: Ensuring patients detailed clinical information is available at the point of care.	Falcon provides a tactical formation level secure communications system for the UK and will provide this for the Allied Rapid Reaction Corps (ARRC). Falcon will enable High Readiness Force (Land) (HRF(L)) units to be deployed rapidly to areas of crisis, allowing the UK to remain a pivotal member of the ARRC. It has delivered a major upgrade to the RAF's ability to handle complex network-enabled operations on deployed operating bases.	The implementation of the Central Payment System (CPS) will provide DWP with a fully integrated payment and accounting solution which will handle in excess of £130bn of annual expenditure. It will bring with it significant improvements in the level of customer service, deliver the flexibility needed to support future methods of payment and provide opportunities to identify instances of fraud and official error. It will also introduce higher levels of resilience to our business, reduce our dependency on old systems and deliver a flexible platform to meet future business needs.	The Public Services Network is creating a single network for government IT, ensuring information can be securely and easily accessed by service providers wherever they are, ridding us of the cost and inefficiency of multiple, incompatible networks.”	ECU is a minimised set of the most urgently required cryptographic equipment necessary to ensure that MOD’s Safety and Security requirements are satisfied and that highly protectively marked information continues to be protected to levels that meet Government policy. The project is an incremental programme to introduce a smaller family of new technology crypto devices to replace those which will be unsupportable over the coming years. Capability gaps to be filled by a mixture of industry specified Commercial Off The Shelf (COTS) products and MOD developed items for smaller volume requirements.					OSCAR replaces the COINS financial reporting system which supports fiscal management and spending control within HMT, produces Parliamentary Estimates and Public Expenditure Statistics.	The programme will introduce: / • A new case management system for civil certificated work / • Electronic ways of working with providers / • New integrated cash collection and debt management systems / • A new general ledger and chart of accounts for the Legal aid fund / which in turn will increase efficiency, improve control and bring LSC systems in line with those in Government.	The NOMIS Programme is giving prison and probation staff new and improved access to the information they need to manage offenders efficiently and effectively throughout the system - protecting the public and reducing re-offending. / NOMIS is five IT-enabled business change projects: / Probation Case Management System (PCMS) - Replacing a variety of different systems with one centralised system for probation; / Offender Assessment System Replacement (OASys-R) - Improved, shared system for offender assessment across both prisons and probation; / Delivered / Prison-NOMIS - An improved, centralised prisons case management system now fully rolled out; / Data Share System (DSS) - Enabling probation staff to access the core Prison-NOMIS information they need for effective offender management; and / Inmate Information System (IIS) update - Improving functionality	Services under the current Quantum contract that is due to expire in July 2012 will continue to be provided under a new replacement Quantum contract (or combination of new contracts). The new Quantum contract will sustain the Quantum service until the forthcoming Future IT Sourcing (FITS) contracts are in place and are ready for applicable services to be transitioned. The new Quantum contract can be terminated by service ‘tower’ and by month, to be replaced by FITS contracts for service towers, unless the contractor can demonstrate superior value for money during the remaining contract term.		deliver a service bringing the affordable requirements of stakeholders into scope in order to improve the service and provide best value for money. / • consider alternative approaches to the use of monitoring including its place in the outcomes of the Green Paper, sentencing review framework and changing sentencing policy and in offender management. / • support the development of a co-operative and constructive partnership approach to delivery through the engagement of key stakeholders across the criminal justice sector both in the project and following implementation of the contract(s). / • ensure that transition between old and new service is managed effectively and service levels and performance are maintained at the existing levels during this period. / • ensure that the contract pricing structure, performance measurement system, data access and collection procedures and governance are fit for purpose and support delivery reflecting the NOMS regional structure. This includes the critical compliance with revised Government Information Assurance standards. / • run a competition within EU regulation that stimulates the market and increases competition, delivers a smooth transition from old to new service and delivers a contract structure which generates best value for money, defends the Authority’s interests and reflects best commercial practice. / • investigate and exploit new technologies providing appropriate reliability and security whilst reducing costs. / • achieve significant budget reduction against current allocations on a like-for-like basis in line with CSR expectations.	The FITS Programme aims to deliver a £110m pa reduction in MoJ ICT operating costs through the design and implementation of a new ICT Operating Model and sourcing approach. Existing ICT services are being re-competed to drive significant cost reductions in the delivery of these services.	The objective of the SOCA Catalyst Programme is to secure, by 31 March 2012, an integrated physical infrastructure capable of sustaining delivery of our business outcomes, improving operational performance, value for money, recruitment, retention and career development paths.	Extend and Blend is a Home Office programme to move the department to a new restricted IT infrastructure and service arrangements, covering around 25,000 users. The programme aims to cut costs by over a quarter, modernise and join up IT services to staff, introduce greater resilience, mobility and flexibility, and put in place a strategic platform for the future development of the department's IT in line with the Government's ICT Strategy.	IABS is used to record, store and match biometric information from visa applicants, asylum seekers requiring registration cards, individuals applying for biometric residence permits, and all fingerprints taken for immigration purposes.		The programme’s mandate, as set out in the 2005 Bichard progress report, is to deliver an effective, integrated, national, regional and local information sharing and intelligence capability which will improve the ability of the police and partner agencies to proactively use information for intelligence purposes to: / - Prevent crime; / - Bring offenders to justice; / - Safeguard children and vulnerable people; and / - Professionalise the investigation process.	The programme delivered the procurement of a new supplier for a new, more secure passport design, production and integrated centralised personalisation of around 5 million passports a year. Additionally, the Regional Office Printing Equipment project enabled local personalisation of the new passport at IPS regional offices for up to 400,000 premium customers a year.	The project will ensure that International Operations and Visa Group has contracted commercial partners who will undertake key and specified functions as part of the visa process from 1 April 2014 and which enables the Group to meet its obligations to secure the border, provide good customer service in support of the UK Government’s growth agenda and meet our Spending Review obligations.		The main aim of the Emergency Services Mobile Communications Programme (ESMCP) is to deliver mobile voice and data communications services to the emergency services, other public safety organisations and potentially other public sector bodies. The services to be provided under this programme will replace, but are not exclusive to, those delivered under existing contract(s) such as Airwave.	The Communications Capabilities Development programme (CCD programme) brings together work to ensure that, in a changing communications environment, communications data and interception of communications can continue to protect the public and save lives. / Our ongoing programme reflects the vital role communications data plays in investigating and prosecuting serious crimes such as child sex abuse, kidnap, murder and drug related crime, as well as in public protection – such as locating missing persons.	In July 2011, the Home Secretary announced a fundamental reform to the way ICT is managed in the police forces with the establishment of a police-led ICT company. / The reform is aimed at achieving four strategic objectives: / 1. To free chief officers and police staff to focus on fighting crime and making their communities safer / 2. To provide the British police service with more effective and innovative ICT support / 3. To improve value for money from ICT services / 4. To ensure services and products support forces and other customers in their drive for interoperability.		The Disclosure & Barring Service Programme is a change programme established to modernise and improve the disclosure and barring services previously delivered by the Criminal Records Bureau (CRB) and the Independent Safeguarding Authority - and now delivered by the Disclosure and Barring Service (DBS).	The second generation Schengen Information System (SIS II) will routinely provide UK Law Enforcement Agencies with real-time data on wanted and missing persons, as well as lost and stolen objects from across 31 participating states. SIS II will deliver several key strategic benefits on behalf of the Home Office, police forces and the wider criminal justice sector: / Reduced crime – particularly via the ability to screen for wanted criminals via border controls / Greater identity assurance at the border / Improved public and law enforcement officer protection / Improved judicial cooperation across the Schengen Area / Improved Police co-operation across the Schengen Area.	The e-Borders Programme will create an integrated, secure border for the 21st century. The programme contains project portfolios aimed at establishing a modernised, intelligence-led immigration control framework, counter-terrorism support and criminality detection.	A shared service solution for the BIS network will: / - deliver a structural reduction in the cost base; / - provide simpler, transparent and more integrated processes across the BIS family of organisations; and / - secure continuous cost and process improvement through innovation and the application of a professional business focus. / Shared services enables wider business transformation. Greater benefits will be realised as the service matures beyond transactional services to higher value ones. There are opportunities for shared services to support: / - transformation of grants processing – a business-critical function that is a particular feature in BIS and its partners, but managed in many different ways with multiple hand-offs that complicate accounting treatment / - strategic procurement with effective compliance – managing the >£1bn contract expenditure of BIS and partners much more effectively, to deliver savings that could dwarf those from consolidating transactional services / - real benefits from Clear Line of Sight – so that rather than being an initiative about consolidating end-year accounts, it can underpin strategic management of BIS and its partners with timely, accurate, valued and well-aligned financial management information	The objectives of the programme respond to a number of challenges including the reforms introduced in the White Paper "Students at the Heart of the System". Over the next three years the SLC anticipates major increases in student numbers, loan values and volumes. The student experience at present is very poor, due to operational and technology issues including lack of availability of complete case information and the time delay between the issue of evidence by students to the completion of the application process at times of high demand. Due to the limited technology update over the last few years the current system needs replacement. A robust and agile customer-centred student finance system is required. / Summary of Programme objectives / • Introduce a modern, integrated and flexible IT system to enable the safe delivery of HE reform (including changes to borrowers’ repayment terms including variable interest rates). / • Enhance customer service and operational efficiency. / • Support the transformation of SLC’s business through introduction of a unified technology platform and the standardisation of processes. / Expected benefits: / • Improved customer experience: easier access to real time information, additional communication channels and a reduction in incomplete calls, etc; / • Operational efficiencies: increased process automation, reducing avoidable contact and standardisation of workflows; / • Strategic fit: alignment of the programme with Government ICT strategy as well as with the strategic direction taken by SLC. / • Financial benefits to Government: ensuring HE reform-related savings, agreed as part of the Comprehensive Spending Review, are realised; potential for increasing the value of the loan book and an increase in the recovery of student debts; / • ICT efficiencies: introduction of a unified business technology platform, the use of standard technology and the ability to use more agile development approaches		The reprocurement and implementation of the ICT managed service capability for DH and its ALBs. IMS3 is a project, running a procurement against the ASCC framework to provide the next generation of agile ICT services to DH and its ALBS. The project has now awarded the ICT contract and has entered a transition phase with Atos IT Solutions & Services Ltd to implement the new modernised ICT solution for core DH and ALB consumers and to "on-board" new emerging ALBs requiring ICT services in a phased approach.
Department comment > action following traffic light assessment	The programme submitted a revised Full Business Case (FBC) to Cabinet Office in October 12. Following feedback from CO the FBC has been updated and a further submission to CO and HM Treasury will be made in March 13. In revising the FBC the MoJ team has been working with suppliers to assess options to reduce the costs to complete the programme. The programme has completed a restructure and has made new appointments to the leadership team to ensure that individuals with relevant experience and skills are in place to drive the current stage of the programme.	Significant and ongoing engagement took place between the Programme, MOD officials and their Cabinet Office counterparts to clearly articulate the case for extension of DII contracts and the implications of not doing so. Separately, Cabinet Office engaged with Hewlett-Packard (the main supplier within the DII contract) at global level. MOD supported this engagement by driving down the cost of the proposed extension. This culminated in spend approval being given by Cabinet Office Ministers on 30 April 13 which resolved the issues driving the MPA's poor September 2012 Delivery Confidence Assessment. / Following the original MPA PAR assessment of AMBER/RED in July 12 an Action Plan was initiated to address the recommendations of that PAR. To date the vast majority of the proposed actions have been completed satisfactorily. A small number of residual actions were predicated on the appointment of an Industry Strategic Partner to the programme. This appointment was made in March 13 and it is anticipated that the residual actions will be addressed as a matter of urgency by the Strategic Partner in conjunction with the DCNS Programme.	The programme is making progress and is in the latter stages of application software delivery. The contract construct has provided financial protection against delay which will help to deliver the programme within approved envelopes. Issues are specific to the development of the Application Management System; the supplier has performed well in other areas of the broader programme under contract such as managing legacy IT systems.	DII is taking the following action to bring the remaining delivery challenges into line under a robust risk-adjusted plan. Above SECRET: Fixed rollout and the Deployed element has completed user acceptance trialling. Some residual performance issues are being addressed. Dependencies exist with other critical programmes of work to deliver the required capability and to enable the retirement of legacy systems. Deployed Maritime: Progressing well but subject to challenges to meet the Fleet's requirements at sea. Deployed Land: Work continues to address the impact of evolving requirements. Gateways: Testing continues on the initial International Gateway solution to enable information exchange with close allies and the retirement of the legacy gateway in 2013. Collaborative Software: A revised schedule for EDRMS (corporate records management) rollout has been agreed for completion in spring 2014. Web Browser: A pilot completed successfully in October 2012. Work is being completed to ensure MOD-wide applications' compatibility. Enterprise-wide rollout is anticipated to begin in April 2013.	OGC Gateway 5 Review forecast for December 2012.	The Programme has delivered a viable CloudStore supported by an ambitious procurement framework. / It has marketed this across a wide range of ICT vendors and the public sector. The concept has clearly generated an enthusiastic response from suppliers, particularly SMEs, that have not previously had access to government. / In the last couple of months G-Cloud has started to see exponential growth in sales and anecdotal evidence suggests that it has driven considerable levels of savings through transparent pricing. / The Programme still has a significant number of challenges to overcome to reach its stated savings objectives and its aspiration to fundamentally change central government ICT buying behaviours. / In particular, departments have yet to fully change their culture in terms of approach to ICT as old ways of doing things are so deeply engrained. / Key to this is a reshaping of the Programme to focus on the commercial aspects of the CloudStore as a retail proposition, improving the user experience and engaging the buying community more directly in the objectives of the programme. / Crucial to large scale take-up will be working with departments and the Cabinet Office spending controls team to enforce use of the CloudStore across central government. / Scaling G-Cloud has been difficult to achieve to date due to the team’s focus on the start up activities and the lack of appropriate funds and resources.	The contract for the supply of new services was let in December 2012 and robust plans are in place to transition to a new Fujitsu service in the summer of 2013. Five months of the 12 month procurement timetable were spent waiting for spend control approval from Cabinet Office Efficiency and Reform Group and now that these are in place the project is progressing well. The procurement phase has secured savings of circa 40% on a like for like basis.	This rating dates back to September 2012, more than seven months ago. / Since then, significant progress has been made in the delivery of Universal Credit. The Pathfinder was successfully launched and we are on course both to expand the Pathfinder in July 2013 and start the progressive national roll-out of Universal Credit in October.	Most of this programme has been delivered. Delivery of the VAT Registration Transformation and iForms projects has been re-scheduled. / The increased cost associated with the phasing of the delivery of the remaining parts of the Programme have been subjected to rigorous scrutiny by the Programme. The level of investment needed to allow the remaining work to move forward has been subject of considerable challenge from HMRC’s governance processes, Cabinet Office and HM Treasury. Action has been taken since October 2012 to revise the budget.	A Risk Mitigation based re-plan of the Contract is underway following intervention by the SOCA Board. This has led to a revision of programme plans, more realistic delivery timescales and improved joint working arrangements between the supplier and SOCA. The Home Office and the Cabinet Office have provided support and direction so that SOCA's capability to deliver the programme has been strengthened and both of these stakeholders continue to provide additional programme level assurance to the programme leader. Contract scope and financial controls are being adhered to.	As a project we produced a detailed Project Plan that gave us a critical path to project end, specifically taking into account the approvals process in the run up to contract award. This would ensure a more effective approach to planning and delivery.	The programme has successfully delivered an online student application process. Depending on the business requirement, future releases will develop the other tiers on this common model, reusing data wherever applicable. This is a significant step on the route to deliver a Single Case Working Model for the Home Office.	Agency strategy has been re-defined to reflect digital delivery and to give clear context for required structure of contracts moving forward. / Engagement Partner to be procured to address lack of in house capability to develop and deliver the delivery of the required contracts. / Programme governance has been re-designed to facilitate effective decision making.	The pilot has now completed, standing the Programme in good stead for the forthcoming main migration period, and by 5 April 2013 the Programme had over 6 million employments being reported to HMRC in real time. Feedback from employers and intermediaries remains positive. The business case has been revised and although costs have increased, this has been subjected to rigorous scrutiny by the Programme and challenge from the Department’s governance processes, Cabinet Office and HM Treasury.	At Q2 no assurance planned.	OGC Gateway 5 Review undertaken July 2012	In recent months, significant progress has been made on governance and benefits management, which were in their early stages at the time of this assessment by the MPA, and the programme was given a largely positive profile in the recent NAO Landscape Report.				OGC Gateway 5 Review forecast for November 2012	OGC Gateway 0/3 Review undertaken March 2012 / OGC Gateway 5 Review forecast for April 2013, subject to submission of RPA and agreement with MPA.	OGC Gateway 0 Review undertaken February 2012 / OGC Gateway 5 Review forecast for February 2013 / OGC Gateway 5 Review forecast for March 2014	OGC Gateway 5 Review forecast for November 2012	The project had experienced various delays relating to technical issues with the cryptographic technology, which protects the security of the information being transmitted. These issues caused a 15 months delay overall to the project. The forecast in-service date for all the variants of the equipment was December 2012. However, the project went into service in October 2012 ahead of the revised date. As a result the RAG status is now GREEN.	Following re-launch in 2009, the Programme made good progress against milestones. Although there were some changes to plan, the costs remained broadly in line with original estimates and the Programme successfully implemented two major releases, the second of which went live in January 2012. This was followed by an extensive roll out to offices and feeder systems which was completed successfully in August 2012. The Programme Board agreed to formal closure in August and a Lessons Learned Report was produced covering the key learning for DWP. Now well established as a critical component of live operations, CPS is in good shape. It has processed more than one billion customer payments and will form the payment and accounting platform for the new Welfare Reform processes.	This is a mature and successful programme, delivering quantifiable benefit, as recognised by the Major Projects Authority					Confidence in project delivery is generally high. Amber status reflects a necessary deviation from the original delivery schedule. Although identified costs are on an upward trajectory, the project is still expected to deliver within its total budget and in line with the timeframes required by the business.	The implementation of IDP has been replanned due to meeting MoJ ICT standards, and Legal Aid Reform implementation.	Recommendations from MPA (Oct 12) completed. RAG remains Amber. / PCMS: Hertfordshire pilot completed Dec 12, went live early Feb 13. Further 6 Probation Trusts have gone live since. Roll-out to all Trusts on track to complete (Oct 13). Upcoming challenges: completion of PCMS Pilot (Cambs) & Delius Pilot (West Mids). / OASys-R: Pilot with 3 Trusts & 7 Prisons completed Feb 13. MPA Healthcheck conducted Mar 13: highlighted further recommendations to be worked through prior to go live. Target go live remains Easter weekend 2013.	The new NOMS IS Services contract can be terminated by service ‘tower’ and by month, to be replaced by FITS contracts for service towers, unless the contractor can demonstrate superior value for money during the remaining contract term. The delivery part of the new contract is now referred to as the NOMS ICT Services (NIS) Programme and covers the transformation of the current technology to the new infrastructure services.		The Project timeline has been rescheduled to reflect the impacts of changing the Hardware Specification to a single Multi Application Tag and as a result of the number of clarification requests from bidders during the second stage of tender negotiations, however it is still a tight timetable. The Project is in the process of completing the final stage of the tendering process and will then evaluating them to determine which bidders are to progress to the final 'preferred bidder' stage.	The Programme is tracking to plan and effective risk management plans and mitigations are in place. An IAAP is in place and an MPA Gate 0 Review was carried out in January 2013.	The SOCA Catalyst Programme closed following successful delivery as scheduled and business change activity is being undertaken as part of the work to establish the National Crime Agency.	The new systems have now been rolled out to the user community of around 25,000 users. Functionality continues to be enhanced during the final stages of the programme. The programme has successfully cut costs by over 25%.	The programme delivered to schedule and the capability operated effectively as part of the Olympic security arrangements.		The programme has delivered well to date with volumes of data uploaded far exceeding initial estimates.	The capability is now operating as Business As Usual.	The programme has now taken account of the additional requirements for interviewing and an internal review has suggested improvements to planning to facilitate management of the programme's tight timescales.				The rating reflects the successful establishment of the Police ICT Company with the company being incorporated in June 2012. This has provided the basis for the viable operation of the Company going forward.		The programme team is working with the suppliers to develop a robust implementation plan.	The programme has continued to work successfully with diverse stakeholders and to monitor the work being undertaken by the other European states.	The system was upgraded and operated effectively as part of the Olympic security arrangements. Further improvements to the resilience and capabilities of the two core systems are on track for delivery during 2013.	In order to reduce the risks involved with going live the programme has re-phased the go-live for Phase 1 of the programme. On the 1 November 2012 go-live date all services for BIS, Intellectual Property Office and Insolvency Service will transfer to the Shared Services Centre, however they will remain on existing systems, meaning that the major change will be transfer of personnel. All Phase 1 organisations will then move onto the Shared Services systems from 1 April 2013, reducing the number of incidences of change within each organisation and providing increased time to resolve technical issues.	Department actions to improve RAG rating: / - Business engagement will be led by the CEO. / - Procurement strategy will be revised to provide greater flexibility for other options. / - Procurement strategy will be reviewed and approved. Endorsement will be sought from GDS, GPS, HEDA and BIS. / - A risk analyst will be engaged to embed risk management framework. / - Programme structure will be reviewed to ensure alignment with Company strategy and programme objectives. / - The programme will communicate with the market to raise awareness and generate interest. / - The governance and approval process of the programme will be streamlined to facilitate rapid and effective decision making.		Actions in train to continue to deliver to plan
Project Start Date	01/07/2009	01/12/2009	14/05/2007	01/09/2001	18/12/2003	31/10/2011	16/11/2011	17/11/2011	24/03/2010	01/04/2008	10/12/2010	25/06/2007	01/03/2011	05/07/2010	01/04/2004	19/02/2004	01/04/2011	01/01/2011	09/06/2009	02/12/2009	28/11/2003	31/10/2004	01/04/2006	26/01/2004	01/01/1998	01/09/2008	31/08/2011	31/08/2007					24/08/2011	01/07/2009	08/01/2008	18/07/2011		10/05/2011	01/03/2011	01/06/2010	01/10/2009	01/10/2006		01/04/2004	01/03/2008	09/12/2011		01/06/2011		01/09/2011		29/12/2010	01/04/2006	26/10/2011	04/05/2011	01/03/2012		16/05/2011
Project End Date	07/06/2013	01/03/2020	31/03/2012	31/03/2015	19/10/2015	30/06/2015	28/02/2014	31/12/2017	10/04/2013	30/09/2013	31/12/2014	30/07/2013	30/09/2015	31/10/2014	31/07/2016	31/03/2014	01/04/2015	30/11/2013	31/12/2012	31/05/2014	31/03/2014	30/06/2013	31/03/2016	31/10/2015	31/03/2035	21/06/2012	30/01/2015	31/08/2040					07/02/2013	30/10/2013	31/10/2013	30/11/2012		30/09/2013	31/12/2014	30/09/2012	30/04/2012	31/12/2012		31/03/2012	01/11/2012	01/07/2014		31/12/2020		31/08/2012		01/10/2015	31/03/2015	01/08/2014	30/04/2013	19/03/2016		29/03/2013
Department comment on schedule	The programme completed Phase 1 (HR services transformation) to schedule in June 2011. At the commencement of Phase 2 (New ERP design, build and deploy) in 2011 the programme was forecasting an initial deployment in late 2012 and completion of deployment in 2013. The need to review MoJ client department change requests and issues encountered regarding the progress of the application design and infrastructure design for the new ERP system mean that it will not now be possible to complete deployment before 2014. Contracts for existing MoJ ERP systems have been extended to December 2014 in recognition of the delay in the programme deployment dates.	While DCNS has continued to make progress with the EMPORIUM (DECS replacement) Interim Purchase to Payment contract signed on time in Dec 12, the delay in approval for GRAPEVINE 1 (DII extension) was a significant deviation from the planned schedule for that element of the programme. Remedial action to gain approval and bring GRAPEVINE 1 back on track was successful as outlined above in the "Departmental Actions Narrative on RAG" box. Separately, work has been maintained to progress other elements of the DCNS programme through the adoption of a working assumption that the GRAPEVINE 1 Business Case would be approved. This approach has reduced the impact of the delay to that approval that might otherwise have been had on other elements of the programme	At the reporting point the programme was working on a re-phased plan to accommodate operational capacity and now forecasts a revised end date of 01/11/2014.	Current approvals require programme completion at 31 Mar 15.	Programme is on schedule to end as per the current approved business case		On Schedule	The Universal Credit Pathfinder was successfully launched on 29th April in some parts of Greater Manchester & Cheshire. / Ashton-under-Lyne is accepting claims for Universal Credit. / Wigan, Warrington and Oldham are trialling the Claimant Commitment and applying a more intensive approach to work search and ensuring new JSA claimants are signed onto Universal Jobmatch. / We are on course to expand the Pathfinder in July, when Wigan Warrington and Oldham will also take claims for Universal Credit. / This careful and controlled approach will ensure that all aspects of Universal Credit are tested – starting small and refining before we start the progressive national roll out from October 2013. / Our plan is to make sure the full transition to Universal Credit is delivered in a safe and managed way. / In terms of how we manage delivery implementation from the start of progressive roll-out in October to full transition in 2017, there are three key factors we will consider. / First, we will learn valuable lessons from the Pathfinder – that is the whole point of a Pathfinder. We will examine the results forensically, and apply them in rolling out Universal Credit nationally. / Second, David Pitchford has been acting as interim Chief Executive for Universal Credit following the sad death of Philip Langsdale. / As Head of the Cabinet Office’s Major Projects Authority, he has provided valuable insights into the most effective way to deliver a complex IT project of this scale, in line with the Government’s Digital Strategy – including latest thinking on the best enabling technologies and platforms, how best to manage suppliers and deliver value to money. / Third, Howard Shiplee, the man that built the Olympic Park, has now taken over from David Pitchford in overseeing the delivery of Universal Credit. He will be using these ideas in finalising the detail of the long-term delivery plan for UC, together with his own wealth of experience in successful project delivery.			There was some slippage in the Project, but that was predominantly down to lack of resource i.e. we had a very small team operating in many workstreams at one time. However, with the use of the aforementioned project plan, we can ensure committing to the contract award date.	Programme end date was revised at Qtr 4 to 30/11/2015 due to re-scoping.	Contract Let Procurement Programme (CLPP) had deviated from the planned activities as a result of the aggregation of a number of significant events. / • Emergence of key Government Procurement Services (GPS) Frameworks in areas where DVLA had anticipated the requirement to undertake OJEU procurements. / • Impact of Government Digital Services (GDS) intervention on the delivery of the digital agenda and the DVLA ICT Transformation Plan (ITTP). / • Impact of Cabinet Office challenge on value for money from the existing PACT ICT contract and DVLA’s acknowledgement of the requirement for disaggregation of large contracts. / • Delay in approval to recruit specialised resources to assist in the procurement of the TDP. / As a result the programme went into Exception in August 2012 and was re-planned and resource gaps identified. The need for a delivery partner was reviewed as part of that exception process. It was anticipated that 'outcome based' procurements, probably via Cloudstore, would be used to fill the gaps. The Strategic Outline Case was approved by Board Investment Commercial Committee in November 2012.		Programme is on schedule to end as per the current approved business case	Programme is on schedule to end as per the current approved business case		On schedule	The programme rollout to overseas Posts was delayed, largely as a result of Olympics activities taking higher priority and an end date of 31/3/2013 is currently forecast.		Programme is on schedule to end as per the current approved business case	Programme is on schedule to end as per the current approved business case, however given that the current contract ends 30 June 2013, it would be difficult to close down the programme within that timescale should the Extension not be agreed.	Programme is on schedule to end as per the current approved business case	Programme is on schedule to end as per the current approved business case	The Project was on track to enter service against the revised project baseline agreed under Review Note December 2011, however this was achieved 2 months ahead of schedule (October 12).	Final programme closure took place in August 2012 to ensure full and effective handover to DWP Finance teams, responsible for managing "business as usual".	Schedule re-baselined by the Programme Board on 20 Feb 2013 to reflect the strategic refresh of last year. No deviation from planned schedule	After a difficult start, this technically and programmatically challenging project is progressing well and delivering against the revised schedule. Some elements have already been delivered and the first new crypto units are due to complete their technical evaluation in the first half of this year (2013).					Delays to the very complicated WGA elements of the project mean that we are now working towards signing off the final delivery milestone at the end of May 2013	The implementation of IDP has been replanned due to Secure Enclave, and Legal Aid Reform implementation. / IDP have confirmed the implementation timetable for the pilot, which took place in two phases, between October and December 2012. A third phase is planned for May 2013. / National rollout is forecast to conclude by the end of 2013. / There is no risk to overall successful delivery of the programme and associated benefits.	Project on schedule.	'Project on schedule'.		A new project timeline was recently agreed with Ministers. Contract award is expected in the Summer of this year followed by Service Commencement in the Winter.	The Programme is currently tracking to plan.		The programme was re-phased to take account of Olympic requirements, with commercial milestones moved to the end of 2012, and final closure of the programme following in February 2013.	The programme end date was revised to 30/09/2013.		The programme end date has now been revised to 30/04/2013.	The start date reflects the start of the procurement activity which completed with award of contract on 10/06/2009.					The programme successfully transferred services to the Shared Service Centre on 1 November 2012. The first organisations were originally scheduled to move onto a new system from 1 April 2013, however this will now occur between August and October 2013. A decision was made to move the shift to new systems based on the complexity of finalising the design of the new system and ensuring that the appropriate level of accreditation was achieved.	The baseline date of end September 20113 for contract signature remains secure, however, intermediate milestones will come under increasing time pressure. To mitigate the risk of slippage to the September 2013 date and beyond, it is proposed to: / - streamline the governance and approvals process to allow faster and more effective decisions. / - recruit additional resources to support procurement work		DH and its ALBS continue to work together on the installation of an ICT shared service together with the deployment of the shared desktop service. / Whilst currently at 3 months behind schedule appropriate contingency arrangements are in place.
Budget (£m) 2012/13	42.94	18.00	46.72	850.24	163.35	0.58	1.90	386.50	10.01	43.71	0.50	59.97	6.96	28.32	273.05	114.31	155.00		29.96	0.12	8.85	7.90	24.87	102.39	29.02	23.50	1.05					4.71	13.59	8.00	103.73		0.99	22.10	6.74	69.98	24.69		5.93	45.71					127.43	11.86		11.26	2.91		70.11
Forecast (£m) 2012/13	58.94	13.79	50.01	831.40	174.67	0.58	1.90	378.99	26.04	44.54	0.50	59.97	3.46	28.32	405.75	120.34	155.00		32.07	0.12	10.26	22.83	24.17	78.95	29.02	22.32	1.05					4.67	13.59	40.00	103.73		0.99	22.10	6.74	66.23	27.70		5.93	45.27					5.92	14.48		11.41	2.62		55.40
Total budget (£m)	127.09	5,051.05	424.29	7,331.72	627.59	0.58	36.63	12,845.38	113.18	398.60	3.20	374.00	102.06	241.10	5,636.19	371.89	650.00		179.19	5.29	36.38	96.05	51.10	634.06	1,467.04	284.90	24.96					19.56	73.89	444.00	156.97		891.96	138.50	216.70	503.30	367.15		184.84	455.95					709.77	168.17		15.54	131.91		139.38
Department comment on budget slippages in 2012 / 2013	Due to slippage in the programme timelines costs originally forecast for 2011/12 were reprofiled into 2012/13. This was the main reason for the cost variance reported in the Q2 GMPP return. The programme has recently been working on a revised Full Business Case which will be submitted to Cabinet Office and HM Treasury in March 2013. Due to delays in the programme deployment dates costs for the deployment of the new ERP system have risen. The programme has therefore been reviewing alternative lower cost options as part of the business case submission. A pause in development activity has also been implemented whilst the business case options are being assessed.	The forecast figure £13.79m includes elements of the programme that have since been removed, and on current data should read £10M. The variance of 2012/13 forecast costs of £10m against budgeted costs of £18m can be attributed to slippage of planned activities (-£1.1M) and approval delays (-£6.9M).	The original project plan, upon which the £46.70m 2012/13 budget was set, assumed that Application Management System (AMS) service charges would be incurred for a full year in 2012/13. In reality, AMS service charges will not now start until 2013/14. This explains the in year under spend.		Costs relate to the most recent approved CCN4 (2011) for LPfIT. / Work is progressing on a revised case therefore there is a variance this quarter.	To date the G-Cloud Programme has made considerable progress despite limited resources. / The challenge now is to fundamentally change government IT buying behaviours and key to this is reshaping the programme to focus on the commercial aspects of the cloudstore as a retail proposition, improving the user experience and engaging the buying community. / A commercial business case is being drafted to release funds and headcount to reach the ambitious cultural and financial objectives.	Variance within tolerance	At the time of the review, there was a slight variance against budget.	The forecast costs of £26.04m for 2012/13 (shown above) exceed the budgeted costs of £10.01m for 2012/13 (shown above) because the budgeted costs do not include the costs associated with the final tranche of work required to complete the VAT Registration Transformation Project. These costs have been subject to considerable scrutiny as described above and action has been taken since October 2012 to revise the budget figure to reflect the costs associated with the final tranche of work required.	The programme costs are tracking profiles within the agreed variance permitted.		Spend is within budget.	Funding of £6.96m was included in the DVLA Business Plan for FY 2012-13. This was reduced to £3.46m at the Agency's first quarter Executive Board financial review as a result of delays in obtaining approvals and revisions to Programme scope. Q2 budgets reflected the original Strategic Outline Business Case information which was subsequently revised and approved at Board Investment Commercial Committee in November 2012. Figures will be further refined as the Outline Business Case is prepared.		Costs related to the most recent approved SARPA business case (2008/09) for NMEPfIT. / Work is progressing on a revised case therefore there is a variance this quarter.	The variance between the two figures is due mainly to GPNGA movements. The project spend slipped from 11-12 to 12-13 – the original EBC only had £5m for this project – the forecast shown in the GMPP was £20m. Re-evaluation of the spend profile was carried out for the budget request and this accounts for the rest of the delta.			The programme rollout to overseas Posts was delayed, largely as a result of Olympics activities taking higher priority. Operation of the existing Foreign Office Telecoms Network (FTN) therefore had to be extended and the increase in the 12/13 budget reflects the additional costs.		Q1 costs related to the original EPS R2 business case. Following the MPA Gate 4 in May 2011, specific elements of the FBC were reviewed and updated. This led to a variance in the Q2 return. / The main variance relates to a capital spend of £2m for Controlled Drugs functionality to be introduced into EPS, which was rolled over into the 2012/13 forecast from the 2011/12 budget. However, this was not included within 2012/13 budget.	As of Q2, the most recent fully approved Business Case dates from 2004 where the budget for 2012/13 was set at £7.9M. During the same period (Q2>3), a Refresh Business Case was in approval to describe the current services provided by NHSmail. The current 2012/13 forecast therefore reflects this Refresh Case.	Q1 costs related to another business case following review by the MPA specific elements of the FBC were reviewed and updated; therefore, the FBC was not approved in FY 2011/12 as anticipated. As a result a revised FBC, now covering the period 2012/13 to 2015/16 was produced which was approved by HMT on 24 July 2012. / This meant a variance in the quarter return.	Difference on figures between quarters relates to indexation as Q1 price bases were at 11/12 and Q2 price were adjusted to 12/13 prices.	Not required as variance is with +/- 5%.	There was a reduction of 5% against 2012/13 budget allocation, as the risks associated with the activation of the final payment feed were managed successfully and were not realised.					Spend in 2012/2013 has been higher than forecasted, due to the WGA dealys. This overspend is likely to be offset by an underspend in 2011/2012		On 18/9/12 H.M. Treasury approved an Addendum to the NOMIS FBC, resulting in the approved financial envelope to March 2020 for the NOMIS Programme moving from £444 m to £477.3 m. The variance above was anticipated in the annual spending profile for 12/13 in the Addendum submitted to HMT, and was therefore eliminated once the revised funding envelope was approved.					The programme costs are tracking profiles.	The projected variance against budget in 2012/13 reflects the release of contingency and funding not required following a reduction in requirements for technical refresh activity.	The variance reflects additional activities undertaken under the wider programme portfolio.		The programme costs are tracking profiles.	Programme spend has been tracking profile.	N/A		N/A	N/A	N/A		The variance is a result of additional Programme-related costs, which were met from DBS fee income, and a re-profiling of capital expenditure. In addition, an error was rectified relating to the inclusion of all CRB/DBS costs for the 2012/13 financial year.	The variance reflects re-profiling of work from 2011/12 into 2012/13 necessitated by the need to give priority to earlier work in preparation for the Olympics.	N/A		Underspend in this financial year (FY 12-13) due to extension of procurement phase moving Technology and Market advisor costs into next financial year. (FY 13-14)		BAU activity to deploy ICT service running behind schedule. Resulting in milestone payments to supplier not being made as planned. Further the Capex for 12/13 was overallocaed. / The procurement project completed in Jan 2012. Then began the BAU activity of design, build and installation of replacement IT infrastructure and desktop services for DH and its ALBS.
Department comment on budgeted whole life costs	MPA have advised that additional commentary can be added here if we wanted to give a fuller explanation of the figure (for example, if the project is only partly funded by Government). If you want to leave blank, please add 'n/a'	WLC includes sunk costs of £26M (FY10/11 to FY12/13) and FY13/14 10 year costed plan of £5,025M.	The programme is currently forecasting a Whole Life Cost within budget.	It should be noted that this is not the cost of DII singularly and includes other - separately funded - programmes of work on which DII relies	WLC is Gov Spend / There is no Non Gov Spend in this business case	No formal budget has been agreed for the G-Cloud Programme. / Initial business case completed in 2011 suggested a budget of £4.93m.		The budgeted whole life costs will be contained within any Treasury limits and approvals.		Costings of the revised work plan will be assessed in due course.	A large majority of our admin budget was on consultancy spend; we were aware that these costs would increase in the run up to project end but we foresaw no consultancy spend in the next financial year. This would allow us to manage our budget more effectively going forward.	The Whole Life Cost was corrected at Qtr 4 to £385m following identification of a data entry error.	2012-13 Q2 financials reflected those presented in the original CLPP Strategic Outline Case (project and TDP costs) and were based on best estimates at the time over a ten year planning period (to be further refined as Outline Business Case options are evaluated).		WLC is Gov Spend / There is no Non Gov Spend in this business case	WLC is Gov Spend / There is no Non Gov Spend in this business case	The Programme is finalising FY 13/14 plans and is in a good place to prudently spend FY 13/14 and FY 14/15 funds. There will be no more than a 0.01% variance over the SR10 period				WLC is Gov Spend / There is no Non Gov Spend in this business case	WLC is Gov Spend / There is no Non Gov Spend in this business case	WLC is Gov Spend / There is no Non Gov Spend in this business case	WLC is Gov Spend / There is no Non Gov Spend in this business case	The Budgeted WLC up to FY34/35 for the Falcon project includes Phase 1 - Inc Project A & C support costs with minimal remaining Equipment Procurement Programme (EPP) budget. It also includes Phase 2 which covers 2a Coherency (to upgrade remaining fleet to UOR standard), 2b Tech Refresh (including crypto upgrade), 2c Air Portable/early entry (miniaturisation) and Phase 2d Tech Refresh.	Project now complete	The majority of PSN's historic and projected funding comes from GPS levies. / These figures exclude the PSN Cyber programme work packages. / The programme has declared forecast benefits totalling £678.2M up to including financial year 15/16. / Cash benefits do not accrue to the PSN Programme, but to the Departments themselves. / The benefits, realised or focused, are, or will be, reported by Departments in the form of reductions in telecoms spend, therefore the savings will accrue to those Departments.					Total whole life costs currently exceed that originally forecast. Whole life costs include a generous allowance for future upgrades during the life of the project and will only be used if essential. As a result, it is quite possible that the overspend may be reduced before the end of the life of the solution.		In September 2012, H.M. Treasury approved a revised financial envelope of £477.3 million for the NOMIS Programme for WLC to March 2020.			These figures do not take into account the increased project costs as a result of the increased work undertaken to date. The revised financial figures for the project were submitted in the most recent report.		The return on investment will be considered in due course.	Budgeted Whole Life Costs for Extend & Blend include the cost of initial investment and transition to the new services, together with the cost of those services to the end of contract in 2016. These represent a saving of 25% against previous costs. The programme is on track to exceed this figure.	The full benefits of the programme will be assessed in due course.		The return on investment will be considered in due course.	The Whole Life Cost remains on track subject to forecast volumes of usage which are not expected to change.	N/A		N/A	N/A	The company will be delivered within existing, funding allocations and projected costs for establishing the company will be subject to official scrutiny through a full business case.		The Whole Life Costs include the operational costs relating to the DBS from 2013/14 to 2017/18. These costs will be recovered from fees paid by customers and as a result do not represent costs to Government.	The Whole Life Cost has been reduced following a reforecast to reflect cost savings already made and proposed change in scope and approach, which has now been approved.	N/A	The rephasing of the Phase 1 go-live will change the spending profile slightly but will not have any impact on the whole life costs	Total lifecycle costs expected to remain within OBC budget.		Whole life cost is funded by DH and its ALBs as operational running costs