Environment
KMTC
Prod
DR
Production
Int
server
DB
SAN
App
This first diagram just shows all the
system components that will be involved in any of the testing and migration steps:
DR in KMTC
Training in KMTC
Production in Prod
New servers in Prod
DPS
Training
New
Page
6/25/14 01:24:27 PM
SRDF

---
Set up to test Informix Replication
Testing replication from a busy system to an idle system
Informix-based full backup to disk
onbar or ontape in KMTC
DPS replicates the backup to Prod
Full restore from disk to the new DB server
Training
DPS replication
onbar
onbar

---
Test Informix Replication
Activate Informix replication to push changes
Watch for any performance impact on Training
Borrow some test environment app and interface servers if we want to truly test the replicated data.
Some test
environment
Training
Informix Replication

---
Test DB Migration
Clean up LUNs on new DB server so they contain only DB volumes, no filesystems
Create a BCV or clone for each Prod LUN
Import LUNs into new DB server
Borrow some test environment app and interface servers if we want to truly test the replicated data.
Production
Some test
environment
LUN
copy

---
Test Backup
Set up and test BCV backups for DB volumes on new server
Set up and test BCV-to-DPS backups for new server
Backup

---
Test Restore
Test restore request from DPS to BCV's
Import LUNs into new DB server
Borrow some test environment app and interface servers if we want to truly test the restored data.
Some test
environment
LUN
import

---
Live DB Migration: Copy Data
Production
Stop SRDF replication temporarily
Create a BCV or clone for each Prod LUN
Import LUNs into new DB server
LUN
copy
SRDF

---
Live DB Migration: Swap Servers
Production
Change hostnames and maybe IP addresses so new servers take over Production
Stop SRDF replication permanently

---
Live Migration: Set up Informix Replication
Informix-based full backup to disk
onbar or ontape in Prod
DPS replicates the backup to KMTC
Full restore from disk to the DR server
DPS replication
onbar
onbar

---
Live Migration: Informix Replication
Activate Informix replication to push changes
Informix replication