## Release
Project number	3					'file:../../Company Scrum Backlog.ods'#$Resources.G					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AD$7:$AD$606		'file:../Project 3 Scrum Backlog.ods'#$Stories.$AF$7:$AF$606			'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$7:$AI$606	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AP$5:$FC$5	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AL$7:$AL$606
Project name	Base	'file:../../Company Scrum Backlog.ods'#$Projects.$B$9					'file:../../Company Scrum Backlog.ods'#$Resources.D845:D944					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AE$7:$AE$606		'file:../Project 3 Scrum Backlog.ods'#$Stories.$AG$7:$AG$606			'file:../Project 3 Scrum Backlog.ods'#$Stories.$AK$7:$AK$606	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AP$6:$FC$6	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AM$7:$AM$606
Company file link	Company Scrum Backlog.ods					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$7:$AI$606		'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$7:$AI$606			'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$7:$K$606	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AP$7	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$7:$AI$606
Project file link	Project 3 Scrum Backlog.ods			'file:./Release 1 Scrum Backlog.ods'#$Release.$B$18					'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$7:$K$606		'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$7:$K$606				'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$11	'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$7:$K$606
Release number	2			'file:./Release 1 Scrum Backlog.ods'#$Release.$F$25					'file:../../Company Scrum Backlog.ods'#$Resources.E845:E944					12					12			12
Release name	Release 2 – Industrialisation	'file:../Project 3 Scrum Backlog.ods'#$Releases.$B$13					849					'file:../Project 3 Scrum Backlog.ods'#$Releases.$B$4					'file:../Project 3 Scrum Backlog.ods'#$Releases.$B$7			'file:../Project 3 Scrum Backlog.ods'#$Releases.$B$5
Release state	In progress	'file:../Project 3 Scrum Backlog.ods'#$Releases.$C$13					:AMJ					'file:../Project 3 Scrum Backlog.ods'#$Releases.$AD$12					'file:../Project 3 Scrum Backlog.ods'#$Releases.$AR$12			'file:../Project 3 Scrum Backlog.ods'#$Releases.$AT$12
Release beginning date	21/10/15					'file:../../Company Scrum Backlog.ods'#$Resources.G849:AMJ849				'file:../../Company Scrum Backlog.ods'#$Resources.G850:AMJ850		Release					15,0034602076					0			0
Release ending date	18/12/16					'file:../../Company Scrum Backlog.ods'#$Resources.$G$1:$AMJ$1					Sprints/Sprint
Release work days (D)	293	'file:../Project 3 Scrum Backlog.ods'#$Releases.$M$13					Scrum Backlog.ods'#$Sprint.
Release full time equivalent	0,0	'file:../Project 3 Scrum Backlog.ods'#$Releases.$O$13
Release total man days (D)	12	'file:../Project 3 Scrum Backlog.ods'#$Releases.$P$13
Release estimated capacity (pts)	78	'file:../Project 3 Scrum Backlog.ods'#$Releases.$R$13
Release average production capacity (%)	1%	'file:../Project 3 Scrum Backlog.ods'#$Releases.$T$13
Release estimated capacity (H)	2	'file:../Project 3 Scrum Backlog.ods'#$Releases.$U$13
Release total effort (H)	639
Release ideal engineering hours (H / D)	53,3
Release sprints number	30
Sprint number in progress	1
Release estimated progress (%)	15%	'file:../Project 3 Scrum Backlog.ods'#$Releases.$AA$13
Release planned points (pts)	777,5	'file:../Project 3 Scrum Backlog.ods'#$Releases.$AL$13
				Sprint cumulated cancelled / reported points (pts)	Cumulated active points (pts)				Cumulated validated points in release (pts)	Sprint cumulated velocity (pts)					Sprint initial release burn down projection	Sprint real release burn down projection	Sprint average velocity projection	Sprint average focus factor projection	Sprint number + Sprint ending date
Sprint number	Sprint name	Sprint state	Sprint file link	Sprint beginning date	Sprint ending date	Sprint work days (D)	Remaining sprint work days (D)	Sprint full time equivalent	Sprint total man days (D)	Sprint cumulated total man days (D)	Sprint average total man days (D)	Sprint estimated capacity (pts)	Sprint average production capacity (%)	Sprint estimated capacity (H)	Sprint file link	Total effort external link	Sprint total effort (H)	Sprint ideal engineering hours (H / D)	Sprint average ideal engineering hours (H / D)	Global average ideal engineering hours (H / D)	Added points in sprint (pts)	Cumulated added points in release (pts)	Cancelled points in sprint (pts)	0	777,5	Sprint planned points (pts)	Sprint estimated planned points (pts)	Validated points in sprint (pts)	0	0	Sprint velocity (pts)	Sprint average velocity (pts)	Global average velocity (pts)	Sprint focus factor (pts / D)	Sprint average focus factor (pts / D)	Global average focus factor (pts / D)	778	778	778	778	0 - 21/10/15
1	R2.S1	In progress	Sprint 1 Scrum Backlog.ods	mer. 21/10/15	dim. 08/11/15	13	0	0,9	12	12	12	0	23%	42	'file:./Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.B18	639	53,3	53,3	15,0	0	0	0	0	777,5	0	194	13	13	0	0	0	0	0,00	0,00	0,00	752	752	778	778	1 - 08/11/15
2	R2.S2	Waiting	Sprint 2 Scrum Backlog.ods	lun. 09/11/15	dim. 22/11/15	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	777,5	194	0	13	0	0	0	0	0,00	0,00	0,00	701	701	778	778	2 - 22/11/15
3	R2.S4	Waiting	Sprint 3 Scrum Backlog.ods	lun. 23/11/15	dim. 06/12/15	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 3 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 3 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	631	631	778	778	3 - 06/12/15
4	R2.S5	Waiting	Sprint 4 Scrum Backlog.ods	lun. 07/12/15	dim. 20/12/15	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 4 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 4 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	547	547	778	778	4 - 20/12/15
5	R2.S6	Waiting	Sprint 5 Scrum Backlog.ods	lun. 21/12/15	dim. 03/01/16	8	8	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 5 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 5 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	456	456	778	778	5 - 03/01/16
6	R2.S7	Waiting	Sprint 6 Scrum Backlog.ods	lun. 04/01/16	dim. 17/01/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 6 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 6 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	365	365	778	778	6 - 17/01/16
7	R2.S8	Waiting	Sprint 7 Scrum Backlog.ods	lun. 18/01/16	dim. 31/01/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 7 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 7 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	280	280	778	778	7 - 31/01/16
8	R2.S9	Waiting	Sprint 8 Scrum Backlog.ods	lun. 01/02/16	dim. 14/02/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 8 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 8 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	205	205	778	778	8 - 14/02/16
9	R2.S10	Waiting	Sprint 9 Scrum Backlog.ods	lun. 15/02/16	dim. 28/02/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 9 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 9 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	144	144	778	778	9 - 28/02/16
10	R2.S11	Waiting	Sprint 10 Scrum Backlog.ods	lun. 29/02/16	dim. 13/03/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 10 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 10 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	96	96	778	778	10 - 13/03/16
11	R2.S12	Waiting	Sprint 11 Scrum Backlog.ods	lun. 14/03/16	dim. 27/03/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 11 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 11 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	61	61	778	778	11 - 27/03/16
12	R2.S13	Waiting	Sprint 12 Scrum Backlog.ods	lun. 28/03/16	dim. 10/04/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 12 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 12 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	36	36	778	778	12 - 10/04/16
13	R2.S14	Waiting	Sprint 13 Scrum Backlog.ods	lun. 11/04/16	dim. 24/04/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 13 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 13 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	21	21	778	778	13 - 24/04/16
14	R2.S15	Waiting	Sprint 14 Scrum Backlog.ods	lun. 25/04/16	dim. 08/05/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 14 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 14 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	11	11	778	778	14 - 08/05/16
15	R2.S16	Waiting	Sprint 15 Scrum Backlog.ods	lun. 09/05/16	dim. 22/05/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 15 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 15 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	5	5	778	778	15 - 22/05/16
16	R2.S17	Waiting	Sprint 16 Scrum Backlog.ods	lun. 23/05/16	dim. 05/06/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 16 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 16 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	3	3	778	778	16 - 05/06/16
17	R2.S18	Waiting	Sprint 17 Scrum Backlog.ods	lun. 06/06/16	dim. 19/06/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 17 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 17 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	1	1	778	778	17 - 19/06/16
18	R2.S19	Waiting	Sprint 18 Scrum Backlog.ods	lun. 20/06/16	dim. 03/07/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 18 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 18 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	18 - 03/07/16
19	R2.S20	Waiting	Sprint 19 Scrum Backlog.ods	lun. 04/07/16	dim. 17/07/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 19 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 19 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	19 - 17/07/16
20	R2.S21	Waiting	Sprint 20 Scrum Backlog.ods	lun. 18/07/16	dim. 31/07/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 20 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 20 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	20 - 31/07/16
21	R2.S22	Waiting	Sprint 21 Scrum Backlog.ods	lun. 01/08/16	dim. 14/08/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 21 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 21 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	21 - 14/08/16
22	R2.S23	Waiting	Sprint 22 Scrum Backlog.ods	lun. 15/08/16	dim. 28/08/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 22 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 22 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	22 - 28/08/16
23	R2.S24	Waiting	Sprint 23 Scrum Backlog.ods	lun. 29/08/16	dim. 11/09/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 23 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 23 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	23 - 11/09/16
24	R2.S25	Waiting	Sprint 24 Scrum Backlog.ods	lun. 12/09/16	dim. 25/09/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 24 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 24 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	24 - 25/09/16
25	R2.S26	Waiting	Sprint 25 Scrum Backlog.ods	lun. 26/09/16	dim. 09/10/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 25 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 25 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	25 - 09/10/16
26	R2.S27	Waiting	Sprint 26 Scrum Backlog.ods	lun. 10/10/16	dim. 23/10/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 26 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 26 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	26 - 23/10/16
27	R2.S28	Waiting	Sprint 27 Scrum Backlog.ods	lun. 24/10/16	dim. 06/11/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 27 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 27 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	27 - 06/11/16
28	R2.S29	Waiting	Sprint 28 Scrum Backlog.ods	lun. 07/11/16	dim. 20/11/16	9	9	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 28 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 28 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	28 - 20/11/16
29	R2.S30	Waiting	Sprint 29 Scrum Backlog.ods	lun. 21/11/16	dim. 04/12/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 29 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 29 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	29 - 04/12/16
30	R2.S31	Waiting	Sprint 30 Scrum Backlog.ods	lun. 05/12/16	dim. 18/12/16	10	10	0	0	12	12	0	0%	0	'file:./Release 2 Sprints/Sprint 30 Scrum Backlog.ods'#$Sprint.	'file:./Release 2 Sprints/Sprint 30 Scrum Backlog.ods'#$Sprint.B18	0	0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00	0	0	778	778	30 - 18/12/16
31				lun. 19/12/16	dim. 01/01/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	31 - 01/01/17
32				lun. 02/01/17	dim. 15/01/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	32 - 15/01/17
33				lun. 16/01/17	dim. 29/01/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	33 - 29/01/17
34				lun. 30/01/17	dim. 12/02/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	34 - 12/02/17
35				lun. 13/02/17	dim. 26/02/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	35 - 26/02/17
36				lun. 27/02/17	dim. 12/03/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	36 - 12/03/17
37				lun. 13/03/17	dim. 26/03/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	37 - 26/03/17
38				lun. 27/03/17	dim. 09/04/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	38 - 09/04/17
39				lun. 10/04/17	dim. 23/04/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	39 - 23/04/17
40				lun. 24/04/17	dim. 07/05/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	40 - 07/05/17
41				lun. 08/05/17	dim. 21/05/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	41 - 21/05/17
42				lun. 22/05/17	dim. 04/06/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	42 - 04/06/17
43				lun. 05/06/17	dim. 18/06/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	43 - 18/06/17
44				lun. 19/06/17	dim. 02/07/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	44 - 02/07/17
45				lun. 03/07/17	dim. 16/07/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	45 - 16/07/17
46				lun. 17/07/17	dim. 30/07/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	46 - 30/07/17
47				lun. 31/07/17	dim. 13/08/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	47 - 13/08/17
48				lun. 14/08/17	dim. 27/08/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	48 - 27/08/17
49				lun. 28/08/17	dim. 10/09/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	49 - 10/09/17
50				lun. 11/09/17	dim. 24/09/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	50 - 24/09/17
51				lun. 25/09/17	dim. 08/10/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	51 - 08/10/17
52				lun. 09/10/17	dim. 22/10/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	52 - 22/10/17
53				lun. 23/10/17	dim. 05/11/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	53 - 05/11/17
54				lun. 06/11/17	dim. 19/11/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	54 - 19/11/17
55				lun. 20/11/17	dim. 03/12/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	55 - 03/12/17
56				lun. 04/12/17	dim. 17/12/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	56 - 17/12/17
57				lun. 18/12/17	dim. 31/12/17	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	57 - 31/12/17
58				lun. 01/01/18	dim. 14/01/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	58 - 14/01/18
59				lun. 15/01/18	dim. 28/01/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	59 - 28/01/18
60				lun. 29/01/18	dim. 11/02/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	60 - 11/02/18
61				lun. 12/02/18	dim. 25/02/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	61 - 25/02/18
62				lun. 26/02/18	dim. 11/03/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	62 - 11/03/18
63				lun. 12/03/18	dim. 25/03/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	63 - 25/03/18
64				lun. 26/03/18	dim. 08/04/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	64 - 08/04/18
65				lun. 09/04/18	dim. 22/04/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	65 - 22/04/18
66				lun. 23/04/18	dim. 06/05/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	66 - 06/05/18
67				lun. 07/05/18	dim. 20/05/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	67 - 20/05/18
68				lun. 21/05/18	dim. 03/06/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	68 - 03/06/18
69				lun. 04/06/18	dim. 17/06/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	69 - 17/06/18
70				lun. 18/06/18	dim. 01/07/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	70 - 01/07/18
71				lun. 02/07/18	dim. 15/07/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	71 - 15/07/18
72				lun. 16/07/18	dim. 29/07/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	72 - 29/07/18
73				lun. 30/07/18	dim. 12/08/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	73 - 12/08/18
74				lun. 13/08/18	dim. 26/08/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	74 - 26/08/18
75				lun. 27/08/18	dim. 09/09/18	10		0	0	12	12	0	0%	0				0,0	53,3	15,0	0	0	0	0	777,5	0	0	0	13	0	0	0	0	0,00	0,00	0,00			778	778	75 - 09/09/18

## Dashboard
Release burn down
Sprint number
Points (pts)

Release burn up
Sprint number
Points (pts)
Velocity
Sprint number
Velocity (pts)
Release capacity
Sprint number
Man days (D)
Release focus factor
Sprint number
Focus factor (pts / D)
Release ideal engineering hours
Sprint number
Ideal engineering hours (H / D)

## Parameters
Company Scrum Backlog directory link	'file:../../
Company Scrum Backlog file link	'file:../../Company Scrum Backlog.ods'
Project Scrum Backlog directory link	'file:../
Project Scrum Backlog file link	'file:../Project 3 Scrum Backlog.ods'
Release Scrum Backlog directory link	'file:./

Sprint parameters
		Sprint state
	'file:../../Company Scrum Backlog.ods'#$Parameters.$H4	Finished
	'file:../../Company Scrum Backlog.ods'#$Parameters.$H5	In progress
	'file:../../Company Scrum Backlog.ods'#$Parameters.$H6	Waiting
	'file:../../Company Scrum Backlog.ods'#$Parameters.$H7
	'file:../../Company Scrum Backlog.ods'#$Parameters.$H8

Resource parameters

		Public holidays
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B43	01/01/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B44	21/04/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B45	01/05/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B46	08/05/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B47	29/05/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B48	14/07/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B49	15/08/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B50	01/11/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B51	11/11/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B52	25/12/14
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B53	01/01/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B54	06/04/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B55	01/05/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B56	08/05/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B57	14/05/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B58	25/05/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B59	14/07/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B60	15/08/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B61	01/11/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B62	11/11/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B63	25/12/15
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B64	01/01/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B65	28/03/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B66	01/05/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B67	05/05/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B68	08/05/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B69	16/05/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B70	14/07/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B71	15/08/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B72	01/11/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B73	11/11/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B74	25/12/16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B75

Directory parameters

		Directory
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B33	C:

Line index parameters
	Company file				Project file				Release file				Sprint file				Story file
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C107	Project line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$F107	Feature line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I107	Sprint line index	23		'file:../../Company Scrum Backlog.ods'#$Parameters.$L107	Task line index	26		'file:../../Company Scrum Backlog.ods'#$Parameters.$O107	Task line index	24
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C108	Project total man days line index	843		'file:../../Company Scrum Backlog.ods'#$Parameters.$F108	Story line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I108	Sprint lines number	75		'file:../../Company Scrum Backlog.ods'#$Parameters.$L108	Task lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$O108	Task lines number	200
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C109	Ressource line index	2		'file:../../Company Scrum Backlog.ods'#$Parameters.$F109	Release line index	11		'file:../../Company Scrum Backlog.ods'#$Parameters.$I109				'file:../../Company Scrum Backlog.ods'#$Parameters.$L109				'file:../../Company Scrum Backlog.ods'#$Parameters.$O109
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C110	Project lines number	50		'file:../../Company Scrum Backlog.ods'#$Parameters.$F110	Story lines number	600		'file:../../Company Scrum Backlog.ods'#$Parameters.$I110				'file:../../Company Scrum Backlog.ods'#$Parameters.$L110				'file:../../Company Scrum Backlog.ods'#$Parameters.$O110
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C111	Ressource lines number	42		'file:../../Company Scrum Backlog.ods'#$Parameters.$F111	Feature lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I111				'file:../../Company Scrum Backlog.ods'#$Parameters.$L111				'file:../../Company Scrum Backlog.ods'#$Parameters.$O111
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C112		20		'file:../../Company Scrum Backlog.ods'#$Parameters.$F112	Release lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I112				'file:../../Company Scrum Backlog.ods'#$Parameters.$L112				'file:../../Company Scrum Backlog.ods'#$Parameters.$O112

Color parameters
	Margin of error for planned points (% pts)				Margin for ratio (%)				Margin for progress (%)
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I116	Green (>)	100%
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I117	Orange	0%