## Story
Project number	3					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AH$8		1	2
Project name	Base	'file:../../Company Scrum Backlog.ods'#$Projects.$B$9					1		2	30
Company file link	Company Scrum Backlog.ods					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$8		'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$12	'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$13
Project file link	Project 3 Scrum Backlog.ods					2	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.
Story number	2					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AJ$8	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$E$27:$E$226
Story name	Select and toggle off master elements directly via Delete	'file:../Project 3 Scrum Backlog.ods'#$Stories.$E$8					1	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$I$27:$I$226
Feature number	1	'file:../Project 3 Scrum Backlog.ods'#$Stories.$A$8					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AK$8	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$U$27:$U$226
Feature name	Database	'file:../Project 3 Scrum Backlog.ods'#$Stories.$C$8					2	2	2	30	30
Story original macro estimate (pts)	3	'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$8					Release	1	1	2	2
Story original macro estimate (D)	1	'file:../Project 3 Scrum Backlog.ods'#$Stories.$L$8					Sprint	1	2	1	2
Story total original estimate (H)	356					'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226
Story total original estimate (D)	45	'file:../Project 3 Scrum Backlog.ods'#$Stories.$Q$8
Story total original estimate (pts)	156	'file:../Project 3 Scrum Backlog.ods'#$Stories.$R$8
Story average macro original estimate ratio (%)	5192%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$S$8
Story total effort (H)	122
Story total effort estimate (D)	15,3	'file:../Project 3 Scrum Backlog.ods'#$Stories.$V$8
Story total effort estimate (pts)	53	'file:../Project 3 Scrum Backlog.ods'#$Stories.$W$8
Story average total effort ratio (%)	1779%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$X$8
Story total estimated remaining effort (H)	42
Story estimated progress (%)	74%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AC$8
Tasks number	21
Tasks closed	19
				Task ratio (%)
Task number	Task description	Task state	Is cancelled ?	Task type	Task original estimate (H)	Task total effort (H)	Estimated remaining effort (H)	Task estimated progress (%)	70,67%	Beginning sprint N effort	Sprint N+1 effort	Sprint N+2 effort	Sprint N+3 effort	Sprint N+4 effort	Sprint N+5 effort	Sprint N+6 effort	Sprint N+7 effort	Sprint N+8 effort	Sprint N+9 effort	Sprint N+10 effort	Sprint N+11 effort	Sprint N+12 effort	Sprint N+13 effort	Task line number in sprint N ?	Task line number in sprint N+1 ?	Task line number in sprint N+2 ?	Task line number in sprint N+3 ?	Task line number in sprint N+4 ?	Task line number in sprint N+5 ?	Task line number in sprint N+6 ?	Task line number in sprint N+7 ?	Task line number in sprint N+8 ?	Task line number in sprint N+9 ?	Task line number in sprint N+10 ?	Task line number in sprint N+11 ?	Task line number in sprint N+12 ?	Task line number in sprint N+13 ?	Beginning sprint N estimated remaining effort	Sprint N+1 estimated remaining effort	Sprint N+2 estimated remaining effort	Sprint N+3 estimated remaining effort	Sprint N+4 estimated remaining effort	Sprint N+5 estimated remaining effort	Sprint N+6 estimated remaining effort	Sprint N+7 estimated remaining effort	Sprint N+8 estimated remaining effort	Sprint N+9 estimated remaining effort	Sprint N+10 estimated remaining effort	Sprint N+11 estimated remaining effort	Sprint N+12 estimated remaining effort	Sprint N+13 estimated remaining effort
1	Select and toggle off master elements directly via Delete	Finished	No	Development	16	16	0	100%	100%	16					2					0	0	0	0	0	0	0	0	0	0	0	0	0	0
2	Select and toggle off master elements directly via Delete 1	Finished	No	Meeting	8	7	0	100%	88%	2		5					117		115					6	6	0	0	0	0	0	0	0	0	0	0	0	0
3	Select and toggle off master elements directly via Delete 2	Finished	No	Environments	4	2	0	100%	50%	2					118			2					2	2	2	0	0	0	0	0	0	0	0	0	0	0
4	Select and toggle off master elements directly via Delete 3	Finished	No	Peer review	2	8	0	100%	400%	2		6					119		116					0,5	0,5	0	0	0	0	0	0	0	0	0	0	0	0
5	Select and toggle off master elements directly via Delete 4	Finished	No	Support	6	2	0	100%	33%	2					120			3					4	4	4	0	0	0	0	0	0	0	0	0	0	0
6	Select and toggle off master elements directly via Delete 5	Finished	No	Technical design	12	9	0	100%	75%	2		7					121		117					10	10	0	0	0	0	0	0	0	0	0	0	0	0
7	Select and toggle off master elements directly via Delete 6	Finished	No	Environments	24	10	0	100%	42%	2		8					122		118					22	22	0	0	0	0	0	0	0	0	0	0	0	0
8	Select and toggle off master elements directly via Delete 7	Finished	No	Peer review	36	11	0	100%	31%	2		9					123		119					34	34	0	0	0	0	0	0	0	0	0	0	0	0
9	Select and toggle off master elements directly via Delete 8	Finished	No	Development	34	12	0	100%	35%	2		10					124		120					32	32	0	0	0	0	0	0	0	0	0	0	0	0
10	Select and toggle off master elements directly via Delete 9	In progress	No	Meeting	22	2	20	9%	9%	2					125			4					20	20	20	20	20	20	20	20	20	20	20	20	20	20
11	Select and toggle off master elements directly via Delete 10	Finished	No	Environments	10	2	0	100%	20%		2					73		5					10	8	8	0	0	0	0	0	0	0	0	0	0	0
12	Select and toggle off master elements directly via Delete 11	Finished	No	Peer review	14	2	0	100%	14%		2					74					14	0	0	0	0	0	0	0	0	0	0	0	0	0
13	Select and toggle off master elements directly via Delete 12	Finished	No	Support	16	13	0	100%	81%		2	11					75	122					16	14	0	0	0	0	0	0	0	0	0	0	0	0
14	Select and toggle off master elements directly via Delete 13	Finished	No	Technical design	16	2	0	100%	13%		2					76		6					16	14	14	0	0	0	0	0	0	0	0	0	0	0
15	Select and toggle off master elements directly via Delete 14	Finished	No	Environments	2	2	0	100%	100%		2					77					2	0	0	0	0	0	0	0	0	0	0	0	0	0
16	Select and toggle off master elements directly via Delete 15	Finished	No	Peer review	6	14	0	100%	233%		2	12					78	123					6	4	0	0	0	0	0	0	0	0	0	0	0	0
17	Select and toggle off master elements directly via Delete 16	Finished	No	Development	12	2	0	100%	17%		2					79		7					12	10	10	0	0	0	0	0	0	0	0	0	0	0
18	Select and toggle off master elements directly via Delete 17	In progress	No	Development	24	2	22	8%	8%		2					80		8					24	22	22	22	22	22	22	22	22	22	22	22	22	22
19	Select and toggle off master elements directly via Delete 18	Finished	No	Development	36	2	0	100%	6%		2					81		9					36	34	34	0	0	0	0	0	0	0	0	0	0	0
20	Select and toggle off master elements directly via Delete 19	Finished	No	Development	34	2	0	100%	6%		2					82		10					34	32	32	0	0	0	0	0	0	0	0	0	0	0
21	Select and toggle off master elements directly via Delete 20	Finished	No	Development	22	0	0	100%	0%					11					22	22	22	0	0	0	0	0	0	0	0	0	0	0
22			No
23			No
24			No
25			No
26			No
27			No
28			No
29			No
30			No
31			No
32			No
33			No
34			No
35			No
36			No
37			No
38			No
39			No
40			No
41			No
42			No
43			No
44			No
45			No
46			No
47			No
48			No
49			No
50			No
51			No
52			No
53			No
54			No
55			No
56			No
57			No
58			No
59			No
60			No
61			No
62			No
63			No
64			No
65			No
66			No
67			No
68			No
69			No
70			No
71			No
72			No
73			No
74			No
75			No
76			No
77			No
78			No
79			No
80			No
81			No
82			No
83			No
84			No
85			No
86			No
87			No
88			No
89			No
90			No
91			No
92			No
93			No
94			No
95			No
96			No
97			No
98			No
99			No
100			No
101			No
102			No
103			No
104			No
105			No
106			No
107			No
108			No
109			No
110			No
111			No
112			No
113			No
114			No
115			No
116			No
117			No
118			No
119			No
120			No
121			No
122			No
123			No
124			No
125			No
126			No
127			No
128			No
129			No
130			No
131			No
132			No
133			No
134			No
135			No
136			No
137			No
138			No
139			No
140			No
141			No
142			No
143			No
144			No
145			No
146			No
147			No
148			No
149			No
150			No
151			No
152			No
153			No
154			No
155			No
156			No
157			No
158			No
159			No
160			No
161			No
162			No
163			No
164			No
165			No
166			No
167			No
168			No
169			No
170			No
171			No
172			No
173			No
174			No
175			No
176			No
177			No
178			No
179			No
180			No
181			No
182			No
183			No
184			No
185			No
186			No
187			No
188			No
189			No
190			No
191			No
192			No
193			No
194			No
195			No
196			No
197			No
198			No
199			No
200			No

## Dashboard
Task type	Total effort (%)	Total effort (H)
Development	30%	36
Documentation	0%	0
Environments	13%	16
Functional design	0%	0
Functional tests	0%	0
Maintenance	0%	0
Management	0%	0
Meeting	7%	9
Peer review	29%	35
Support	12%	15
Technical design	9%	11
Unit tests	0%	0

	100%	122

Task state	Total task number (%)	Total task number (H)
Cancelled	0%	0
Finished	90%	19
In progress	10%	2
Waiting	0%	0

	100,00%	21
Task type distribution following effort (%) Task state distribution (%)

## Parameters
Company Scrum Backlog directory link	'file:../../
Company Scrum Backlog file link	'file:../../Company Scrum Backlog.ods'
Project Scrum Backlog directory link	'file:../
Project Scrum Backlog file link	'file:../Project 3 Scrum Backlog.ods'
Release Scrum Backlog directory link	'file:../
Release Scrum Backlog file link	'file:../Releases/Release 2 Scrum Backlog.ods'

Sprint parameters
		Task type			Task state			Is Cancelled ?
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D4	Development		'file:../../Company Scrum Backlog.ods'#$Parameters.$F4	Cancelled		'file:../../Company Scrum Backlog.ods'#$Parameters.$J89	Yes
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D5	Documentation		'file:../../Company Scrum Backlog.ods'#$Parameters.$F5	Finished		'file:../../Company Scrum Backlog.ods'#$Parameters.$J90	No
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D6	Environments		'file:../../Company Scrum Backlog.ods'#$Parameters.$F6	In progress		'file:../../Company Scrum Backlog.ods'#$Parameters.$J91
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D7	Functional design		'file:../../Company Scrum Backlog.ods'#$Parameters.$F7	Waiting		'file:../../Company Scrum Backlog.ods'#$Parameters.$J92
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D8	Functional tests		'file:../../Company Scrum Backlog.ods'#$Parameters.$F8
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D9	Maintenance
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D10	Management
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D11	Meeting
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D12	Peer review
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D13	Support
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D14	Technical design
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D15	Unit tests
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D17
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D18

Directory parameters

		Directory
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B33	C:

Line index parameters
	Company file				Project file				Release file				Sprint file				Story file
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C107	Project line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$F107	Feature line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I107	Sprint line index	23		'file:../../Company Scrum Backlog.ods'#$Parameters.$L107	Task line index	26		'file:../../Company Scrum Backlog.ods'#$Parameters.$O107	Task line index	24
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C108	Project total man days line index	843		'file:../../Company Scrum Backlog.ods'#$Parameters.$F108	Story line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I108	Sprint lines number	75		'file:../../Company Scrum Backlog.ods'#$Parameters.$L108	Task lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$O108	Task lines number	200
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C109	Ressource line index	2		'file:../../Company Scrum Backlog.ods'#$Parameters.$F109	Release line index	11		'file:../../Company Scrum Backlog.ods'#$Parameters.$I109				'file:../../Company Scrum Backlog.ods'#$Parameters.$L109				'file:../../Company Scrum Backlog.ods'#$Parameters.$O109
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C110	Project lines number	50		'file:../../Company Scrum Backlog.ods'#$Parameters.$F110	Story lines number	600		'file:../../Company Scrum Backlog.ods'#$Parameters.$I110				'file:../../Company Scrum Backlog.ods'#$Parameters.$L110				'file:../../Company Scrum Backlog.ods'#$Parameters.$O110
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C111	Ressource lines number	42		'file:../../Company Scrum Backlog.ods'#$Parameters.$F111	Feature lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I111				'file:../../Company Scrum Backlog.ods'#$Parameters.$L111				'file:../../Company Scrum Backlog.ods'#$Parameters.$O111
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C112		20		'file:../../Company Scrum Backlog.ods'#$Parameters.$F112	Release lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I112				'file:../../Company Scrum Backlog.ods'#$Parameters.$L112				'file:../../Company Scrum Backlog.ods'#$Parameters.$O112

Color parameters
	Margin of error for planned points (% pts)				Margin for ratio (%)				Margin for progress (%)
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I116	Green (>)	100%
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I117	Orange	0%