## Story
Project number	3					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AH$39		1	2
Project name	Base	'file:../../Company Scrum Backlog.ods'#$Projects.$B$9					1		2	30
Company file link	Company Scrum Backlog.ods					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$39		'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$12	'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$13
Project file link	Project 3 Scrum Backlog.ods					2	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.
Story number	33					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AJ$39	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$E$27:$E$226
Story name	C++ UNO language binding and URE libraries	'file:../Project 3 Scrum Backlog.ods'#$Stories.$E$39					1	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$I$27:$I$226
Feature number	5	'file:../Project 3 Scrum Backlog.ods'#$Stories.$A$39					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AK$39	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$U$27:$U$226
Feature name	SQL engine	'file:../Project 3 Scrum Backlog.ods'#$Stories.$C$39					2	2	2	30	30
Story original macro estimate (pts)	5	'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$39					Release	1	1	2	2
Story original macro estimate (D)	1	'file:../Project 3 Scrum Backlog.ods'#$Stories.$L$39					Sprint	1	2	1	2
Story total original estimate (H)	735					'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226
Story total original estimate (D)	92	'file:../Project 3 Scrum Backlog.ods'#$Stories.$Q$39
Story total original estimate (pts)	322	'file:../Project 3 Scrum Backlog.ods'#$Stories.$R$39
Story average macro original estimate ratio (%)	6431%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$S$39
Story total effort (H)	669
Story total effort estimate (D)	83,6	'file:../Project 3 Scrum Backlog.ods'#$Stories.$V$39
Story total effort estimate (pts)	293	'file:../Project 3 Scrum Backlog.ods'#$Stories.$W$39
Story average total effort ratio (%)	5854%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$X$39
Story total estimated remaining effort (H)	161
Story estimated progress (%)	74%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AC$39
Tasks number	51
Tasks closed	36
				Task ratio (%)
Task number	Task description	Task state	Is cancelled ?	Task type	Task original estimate (H)	Task total effort (H)	Estimated remaining effort (H)	Task estimated progress (%)	293,26%	Beginning sprint N effort	Sprint N+1 effort	Sprint N+2 effort	Sprint N+3 effort	Sprint N+4 effort	Sprint N+5 effort	Sprint N+6 effort	Sprint N+7 effort	Sprint N+8 effort	Sprint N+9 effort	Sprint N+10 effort	Sprint N+11 effort	Sprint N+12 effort	Sprint N+13 effort	Task line number in sprint N ?	Task line number in sprint N+1 ?	Task line number in sprint N+2 ?	Task line number in sprint N+3 ?	Task line number in sprint N+4 ?	Task line number in sprint N+5 ?	Task line number in sprint N+6 ?	Task line number in sprint N+7 ?	Task line number in sprint N+8 ?	Task line number in sprint N+9 ?	Task line number in sprint N+10 ?	Task line number in sprint N+11 ?	Task line number in sprint N+12 ?	Task line number in sprint N+13 ?	Beginning sprint N estimated remaining effort	Sprint N+1 estimated remaining effort	Sprint N+2 estimated remaining effort	Sprint N+3 estimated remaining effort	Sprint N+4 estimated remaining effort	Sprint N+5 estimated remaining effort	Sprint N+6 estimated remaining effort	Sprint N+7 estimated remaining effort	Sprint N+8 estimated remaining effort	Sprint N+9 estimated remaining effort	Sprint N+10 estimated remaining effort	Sprint N+11 estimated remaining effort	Sprint N+12 estimated remaining effort	Sprint N+13 estimated remaining effort
1	C++ UNO language binding and URE libraries	Finished	No	Development	16	40	0	100%	250%	16	16	8					11	11	4					5	5	0	0	0	0	0	0	0	0	0	0	0	0
2	C++ UNO language binding and URE libraries 1	Finished	No	Development	8	31	0	100%	388%	16	8	7					35	40	23					21	15	0	0	0	0	0	0	0	0	0	0	0	0
3	C++ UNO language binding and URE libraries 2	Finished	No	Development	32	43	0	100%	134%	16	27					36	41					2	0	0	0	0	0	0	0	0	0	0	0	0	0
4	C++ UNO language binding and URE libraries 3	Finished	No	Development	44	33	0	100%	75%	25	8					37	42					6	0	0	0	0	0	0	0	0	0	0	0	0	0
5	C++ UNO language binding and URE libraries 4	Finished	No	Unit tests	26	18	0	100%	69%	16	2					38	43					5	0	0	0	0	0	0	0	0	0	0	0	0	0
6	C++ UNO language binding and URE libraries 5	Finished	No	Unit tests	20	14	0	100%	70%	14					39					0	0	0	0	0	0	0	0	0	0	0	0	0	0
7	C++ UNO language binding and URE libraries 6	Finished	No	Unit tests	18	44	0	100%	244%	44					40					0	0	0	0	0	0	0	0	0	0	0	0	0	0
8	C++ UNO language binding and URE libraries 7	Finished	No	Management	18	8	0	100%	44%	8					41					0	0	0	0	0	0	0	0	0	0	0	0	0	0
9	C++ UNO language binding and URE libraries 8	Finished	No	Management	4	27	0	100%	675%	27					42					0	0	0	0	0	0	0	0	0	0	0	0	0	0
10	C++ UNO language binding and URE libraries 9	Finished	No	Management	2	31	0	100%	1550%	8	16	7					43	44	24					24	12	0	0	0	0	0	0	0	0	0	0	0	0
11	C++ UNO language binding and URE libraries 10	Finished	No	Management	3	2	0	100%	67%	2					44					0	0	0	0	0	0	0	0	0	0	0	0	0	0
12	C++ UNO language binding and URE libraries 11	Finished	No	Functional tests	1	39	0	100%	3900%	16	16	7					45	45	25					15	13	0	0	0	0	0	0	0	0	0	0	0	0
13	C++ UNO language binding and URE libraries 12	Finished	No	Functional tests	5	16	0	100%	320%	16					46					0	0	0	0	0	0	0	0	0	0	0	0	0	0
14	C++ UNO language binding and URE libraries 13	Finished	No	Functional tests	8	32	0	100%	400%	24	8					47	46					8	0	0	0	0	0	0	0	0	0	0	0	0	0
15	C++ UNO language binding and URE libraries 14	Finished	No	Development	9	41	0	100%	456%	14	27					48	47					6	0	0	0	0	0	0	0	0	0	0	0	0	0
16	C++ UNO language binding and URE libraries 15	Finished	No	Environments	10	56	0	100%	560%	41	8	7					49	48	26					8	2	0	0	0	0	0	0	0	0	0	0	0	0
17	C++ UNO language binding and URE libraries 16	Finished	No	Meeting	12	51	0	100%	425%	42	2	7					50	49	27					12	3	0	0	0	0	0	0	0	0	0	0	0	0
18	C++ UNO language binding and URE libraries 17	Finished	No	Meeting	12	14	0	100%	117%	7		7					51	50	28					12	12	0	0	0	0	0	0	0	0	0	0	0	0
19	C++ UNO language binding and URE libraries 18	Finished	No	Functional tests	8	8	0	100%	100%	1		7					52	51	29					8	8	0	0	0	0	0	0	0	0	0	0	0	0
20	C++ UNO language binding and URE libraries 19	Finished	No	Environments	5	2	0	100%	40%		2					53	52					5	0	0	0	0	0	0	0	0	0	0	0	0	0
21	C++ UNO language binding and URE libraries 20	Finished	No	Functional tests	45	12	0	100%	27%		5	7					54	53	30					45	1	0	0	0	0	0	0	0	0	0	0	0	0
22	C++ UNO language binding and URE libraries 21	Finished	No	Development	18	0	0	100%	0%					49	114					18	18	18	0	0	0	0	0	0	0	0	0	0	0
23	C++ UNO language binding and URE libraries 22	Finished	No	Peer review	12	10	0	100%	83%			10					50					12	12	0	0	0	0	0	0	0	0	0	0	0	0
24	C++ UNO language binding and URE libraries 23	Finished	No	Maintenance	14	10	0	100%	71%			10					51					14	14	0	0	0	0	0	0	0	0	0	0	0	0
25	C++ UNO language binding and URE libraries 24	Finished	No	Maintenance	15	10	0	100%	67%			10					52					15	15	0	0	0	0	0	0	0	0	0	0	0	0
26	C++ UNO language binding and URE libraries 25	Finished	No	Development	12	0	0	100%	0%					53	115					12	12	12	0	0	0	0	0	0	0	0	0	0	0
27	C++ UNO language binding and URE libraries 26	Waiting	No	Unit tests	16	0	16	0%	0%					85	116					16	16	16	16	16	16	16	16	16	16	16	16	16	16
28	C++ UNO language binding and URE libraries 27	Finished	No	Unit tests	14	0	0	100%	0%					86	117					14	14	14	0	0	0	0	0	0	0	0	0	0	0
29	C++ UNO language binding and URE libraries 28	Finished	No	Unit tests	12	8	0	100%	67%			8					87					12	12	0	0	0	0	0	0	0	0	0	0	0	0
30	C++ UNO language binding and URE libraries 29	Finished	No	Management	10	7	0	100%	70%			7					88					10	10	0	0	0	0	0	0	0	0	0	0	0	0
31	C++ UNO language binding and URE libraries 30	Finished	No	Management	16	0	0	100%	0%					89	118					16	16	16	0	0	0	0	0	0	0	0	0	0	0
32	C++ UNO language binding and URE libraries 31	Finished	No	Management	8	0	0	100%	0%					90	119					8	8	8	0	0	0	0	0	0	0	0	0	0	0
33	C++ UNO language binding and URE libraries 32	Waiting	No	Management	32	0	32	0%	0%					91	120					32	32	32	32	32	32	32	32	32	32	32	32	32	32
34	C++ UNO language binding and URE libraries 33	Finished	No	Functional tests	44	0	0	100%	0%					92	121					44	44	44	0	0	0	0	0	0	0	0	0	0	0
35	C++ UNO language binding and URE libraries 34	Finished	No	Functional tests	26	0	0	100%	0%					93	122					26	26	26	0	0	0	0	0	0	0	0	0	0	0
36	C++ UNO language binding and URE libraries 35	Finished	No	Functional tests	20	20	0	100%	100%			20					94					20	20	0	0	0	0	0	0	0	0	0	0	0	0
37	C++ UNO language binding and URE libraries 36	Waiting	No	Development	18	0	18	0%	0%					95					18	18	18	18	18	18	18	18	18	18	18	18	18	18
38	C++ UNO language binding and URE libraries 37	Waiting	No	Environments	18	0	18	0%	0%					96					18	18	18	18	18	18	18	18	18	18	18	18	18	18
39	C++ UNO language binding and URE libraries 38	Waiting	No	Meeting	4	0	4	0%	0%					97					4	4	4	4	4	4	4	4	4	4	4	4	4	4
40	C++ UNO language binding and URE libraries 39	Finished	No	Meeting	2	2	0	100%	100%			2					98					2	2	0	0	0	0	0	0	0	0	0	0	0	0
41	C++ UNO language binding and URE libraries 40	Waiting	No	Functional tests	3	0	3	0%	0%					99					3	3	3	3	3	3	3	3	3	3	3	3	3	3
42	C++ UNO language binding and URE libraries 41	Waiting	No	Environments	1	0	1	0%	0%					100					1	1	1	1	1	1	1	1	1	1	1	1	1	1
43	C++ UNO language binding and URE libraries 42	Waiting	No	Functional tests	5	0	5	0%	0%					101					5	5	5	5	5	5	5	5	5	5	5	5	5	5
44	C++ UNO language binding and URE libraries 43	Waiting	No	Development	8	0	8	0%	0%					102					8	8	8	8	8	8	8	8	8	8	8	8	8	8
45	C++ UNO language binding and URE libraries 44	Waiting	No	Peer review	9	0	9	0%	0%					103					9	9	9	9	9	9	9	9	9	9	9	9	9	9
46	C++ UNO language binding and URE libraries 45	Waiting	No	Maintenance	10	0	10	0%	0%					104					10	10	10	10	10	10	10	10	10	10	10	10	10	10
47	C++ UNO language binding and URE libraries 46	Waiting	No	Maintenance	12	0	12	0%	0%					105					12	12	12	12	12	12	12	12	12	12	12	12	12	12
48	C++ UNO language binding and URE libraries 47	Waiting	No	Development	12	0	12	0%	0%					106					12	12	12	12	12	12	12	12	12	12	12	12	12	12
49	C++ UNO language binding and URE libraries 48	Waiting	No	Unit tests	8	0	8	0%	0%					107					8	8	8	8	8	8	8	8	8	8	8	8	8	8
50	C++ UNO language binding and URE libraries 49	Waiting	No	Unit tests	5	0	5	0%	0%					108					5	5	5	5	5	5	5	5	5	5	5	5	5	5
51	C++ UNO language binding and URE libraries 50	Finished	No	Unit tests	45	40	0	100%	89%			40					109					45	45	0	0	0	0	0	0	0	0	0	0	0	0
52			No
53			No
54			No
55			No
56			No
57			No
58			No
59			No
60			No
61			No
62			No
63			No
64			No
65			No
66			No
67			No
68			No
69			No
70			No
71			No
72			No
73			No
74			No
75			No
76			No
77			No
78			No
79			No
80			No
81			No
82			No
83			No
84			No
85			No
86			No
87			No
88			No
89			No
90			No
91			No
92			No
93			No
94			No
95			No
96			No
97			No
98			No
99			No
100			No
101			No
102			No
103			No
104			No
105			No
106			No
107			No
108			No
109			No
110			No
111			No
112			No
113			No
114			No
115			No
116			No
117			No
118			No
119			No
120			No
121			No
122			No
123			No
124			No
125			No
126			No
127			No
128			No
129			No
130			No
131			No
132			No
133			No
134			No
135			No
136			No
137			No
138			No
139			No
140			No
141			No
142			No
143			No
144			No
145			No
146			No
147			No
148			No
149			No
150			No
151			No
152			No
153			No
154			No
155			No
156			No
157			No
158			No
159			No
160			No
161			No
162			No
163			No
164			No
165			No
166			No
167			No
168			No
169			No
170			No
171			No
172			No
173			No
174			No
175			No
176			No
177			No
178			No
179			No
180			No
181			No
182			No
183			No
184			No
185			No
186			No
187			No
188			No
189			No
190			No
191			No
192			No
193			No
194			No
195			No
196			No
197			No
198			No
199			No
200			No

## Dashboard
Task type	Total effort (%)	Total effort (H)
Development	28%	188
Documentation	0%	0
Environments	9%	58
Functional design	0%	0
Functional tests	19%	127
Maintenance	3%	20
Management	11%	75
Meeting	10%	67
Peer review	1%	10
Support	0%	0
Technical design	0%	0
Unit tests	19%	124

	100%	669

Task state	Total task number (%)	Total task number (H)
Cancelled	0%	0
Finished	71%	36
In progress	0%	0
Waiting	29%	15

	100,00%	51
Task type distribution following effort (%) Task state distribution (%)

## Parameters
Company Scrum Backlog directory link	'file:../../
Company Scrum Backlog file link	'file:../../Company Scrum Backlog.ods'
Project Scrum Backlog directory link	'file:../
Project Scrum Backlog file link	'file:../Project 3 Scrum Backlog.ods'
Release Scrum Backlog directory link	'file:../
Release Scrum Backlog file link	'file:../Releases/Release 33 Scrum Backlog.ods'

Sprint parameters
		Task type			Task state			Is Cancelled ?
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D4	Development		'file:../../Company Scrum Backlog.ods'#$Parameters.$F4	Cancelled		'file:../../Company Scrum Backlog.ods'#$Parameters.$J89	Yes
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D5	Documentation		'file:../../Company Scrum Backlog.ods'#$Parameters.$F5	Finished		'file:../../Company Scrum Backlog.ods'#$Parameters.$J90	No
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D6	Environments		'file:../../Company Scrum Backlog.ods'#$Parameters.$F6	In progress		'file:../../Company Scrum Backlog.ods'#$Parameters.$J91
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D7	Functional design		'file:../../Company Scrum Backlog.ods'#$Parameters.$F7	Waiting		'file:../../Company Scrum Backlog.ods'#$Parameters.$J92
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D8	Functional tests		'file:../../Company Scrum Backlog.ods'#$Parameters.$F8
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D9	Maintenance
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D10	Management
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D11	Meeting
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D12	Peer review
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D13	Support
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D14	Technical design
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D15	Unit tests
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D17
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D18

Directory parameters

		Directory
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B33	C:

Line index parameters
	Company file				Project file				Release file				Sprint file				Story file
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C107	Project line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$F107	Feature line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I107	Sprint line index	23		'file:../../Company Scrum Backlog.ods'#$Parameters.$L107	Task line index	26		'file:../../Company Scrum Backlog.ods'#$Parameters.$O107	Task line index	24
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C108	Project total man days line index	843		'file:../../Company Scrum Backlog.ods'#$Parameters.$F108	Story line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I108	Sprint lines number	75		'file:../../Company Scrum Backlog.ods'#$Parameters.$L108	Task lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$O108	Task lines number	200
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C109	Ressource line index	2		'file:../../Company Scrum Backlog.ods'#$Parameters.$F109	Release line index	11		'file:../../Company Scrum Backlog.ods'#$Parameters.$I109				'file:../../Company Scrum Backlog.ods'#$Parameters.$L109				'file:../../Company Scrum Backlog.ods'#$Parameters.$O109
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C110	Project lines number	50		'file:../../Company Scrum Backlog.ods'#$Parameters.$F110	Story lines number	600		'file:../../Company Scrum Backlog.ods'#$Parameters.$I110				'file:../../Company Scrum Backlog.ods'#$Parameters.$L110				'file:../../Company Scrum Backlog.ods'#$Parameters.$O110
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C111	Ressource lines number	42		'file:../../Company Scrum Backlog.ods'#$Parameters.$F111	Feature lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I111				'file:../../Company Scrum Backlog.ods'#$Parameters.$L111				'file:../../Company Scrum Backlog.ods'#$Parameters.$O111
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C112		20		'file:../../Company Scrum Backlog.ods'#$Parameters.$F112	Release lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I112				'file:../../Company Scrum Backlog.ods'#$Parameters.$L112				'file:../../Company Scrum Backlog.ods'#$Parameters.$O112

Color parameters
	Margin of error for planned points (% pts)				Margin for ratio (%)				Margin for progress (%)
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I116	Green (>)	100%
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I117	Orange	0%