## Story
Project number	3					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AH$10		1	2
Project name	Base	'file:../../Company Scrum Backlog.ods'#$Projects.$B$9					1		2	30
Company file link	Company Scrum Backlog.ods					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AI$10		'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$12	'file:../Project 3 Scrum Backlog.ods'#$Releases.$G$13
Project file link	Project 3 Scrum Backlog.ods					2	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.
Story number	4					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AJ$10	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$E$27:$E$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$E$27:$E$226
Story name	Page Title field	'file:../Project 3 Scrum Backlog.ods'#$Stories.$E$10					1	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$I$27:$I$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$I$27:$I$226
Feature number	1	'file:../Project 3 Scrum Backlog.ods'#$Stories.$A$10					'file:../Project 3 Scrum Backlog.ods'#$Stories.$AK$10	'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$U$27:$U$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$U$27:$U$226
Feature name	Database	'file:../Project 3 Scrum Backlog.ods'#$Stories.$C$10					2	2	2	30	30
Story original macro estimate (pts)	3	'file:../Project 3 Scrum Backlog.ods'#$Stories.$K$10					Release	1	1	2	2
Story original macro estimate (D)	1	'file:../Project 3 Scrum Backlog.ods'#$Stories.$L$10					Sprint	1	2	1	2
Story total original estimate (H)	5518					'file:../Releases/Release 1 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 1 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 2 Sprints/Sprint 1 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226	'file:../Releases/Release 2 Sprints/Sprint 2 Scrum Backlog.ods'#$Sprint.$AA$27:$BB$226
Story total original estimate (D)	690	'file:../Project 3 Scrum Backlog.ods'#$Stories.$Q$10
Story total original estimate (pts)	2414	'file:../Project 3 Scrum Backlog.ods'#$Stories.$R$10
Story average macro original estimate ratio (%)	80471%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$S$10
Story total effort (H)	85
Story total effort estimate (D)	10,6	'file:../Project 3 Scrum Backlog.ods'#$Stories.$V$10
Story total effort estimate (pts)	37	'file:../Project 3 Scrum Backlog.ods'#$Stories.$W$10
Story average total effort ratio (%)	1240%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$X$10
Story total estimated remaining effort (H)	4704
Story estimated progress (%)	2%	'file:../Project 3 Scrum Backlog.ods'#$Stories.$AC$10
Tasks number	200
Tasks closed	31
				Task ratio (%)
Task number	Task description	Task state	Is cancelled ?	Task type	Task original estimate (H)	Task total effort (H)	Estimated remaining effort (H)	Task estimated progress (%)	19,92%	Beginning sprint N effort	Sprint N+1 effort	Sprint N+2 effort	Sprint N+3 effort	Sprint N+4 effort	Sprint N+5 effort	Sprint N+6 effort	Sprint N+7 effort	Sprint N+8 effort	Sprint N+9 effort	Sprint N+10 effort	Sprint N+11 effort	Sprint N+12 effort	Sprint N+13 effort	Task line number in sprint N ?	Task line number in sprint N+1 ?	Task line number in sprint N+2 ?	Task line number in sprint N+3 ?	Task line number in sprint N+4 ?	Task line number in sprint N+5 ?	Task line number in sprint N+6 ?	Task line number in sprint N+7 ?	Task line number in sprint N+8 ?	Task line number in sprint N+9 ?	Task line number in sprint N+10 ?	Task line number in sprint N+11 ?	Task line number in sprint N+12 ?	Task line number in sprint N+13 ?	Beginning sprint N estimated remaining effort	Sprint N+1 estimated remaining effort	Sprint N+2 estimated remaining effort	Sprint N+3 estimated remaining effort	Sprint N+4 estimated remaining effort	Sprint N+5 estimated remaining effort	Sprint N+6 estimated remaining effort	Sprint N+7 estimated remaining effort	Sprint N+8 estimated remaining effort	Sprint N+9 estimated remaining effort	Sprint N+10 estimated remaining effort	Sprint N+11 estimated remaining effort	Sprint N+12 estimated remaining effort	Sprint N+13 estimated remaining effort
1	Page Title field	Finished	No	Development	8	25	0	100%	313%	25					3					0	0	0	0	0	0	0	0	0	0	0	0	0	0
2	Page Title field 1	Finished	No	Documentation	10	2	0	100%	20%	2					131			14					8	8	8	0	0	0	0	0	0	0	0	0	0	0
3	Page Title field 2	Finished	No	Environments	12	2	0	100%	17%	2					132			15					10	10	10	0	0	0	0	0	0	0	0	0	0	0
4	Page Title field 3	In progress	No	Functional design	14	2	12	14%	14%	2					133			16					12	12	12	12	12	12	12	12	12	12	12	12	12	12
5	Page Title field 4	Finished	No	Functional tests	16	2	0	100%	13%	2					134			17					14	14	14	0	0	0	0	0	0	0	0	0	0	0
6	Page Title field 5	Finished	No	Maintenance	18	2	0	100%	11%	2					135			18					16	16	16	0	0	0	0	0	0	0	0	0	0	0
7	Page Title field 6	Finished	No	Management	20	2	0	100%	10%	2					136			19					18	18	18	0	0	0	0	0	0	0	0	0	0	0
8	Page Title field 7	Cancelled	Yes	Meeting	22	0	0	100%	0%					137					0	0	0	0	0	0	0	0	0	0	0	0	0	0
9	Page Title field 8	In progress	No	Peer review	24	2	22	8%	8%	2					138			20					22	22	22	22	22	22	22	22	22	22	22	22	22	22
10	Page Title field 9	Finished	No	Support	26	4	0	100%	15%	2	2					139	83		21					24	22	22	0	0	0	0	0	0	0	0	0	0	0
11	Page Title field 10	Finished	No	Technical design	28	2	0	100%	7%	2					140			22					26	26	26	0	0	0	0	0	0	0	0	0	0	0
12	Page Title field 11	Finished	No	Unit tests	30	4	0	100%	13%	2	2					141	84		23					28	26	26	0	0	0	0	0	0	0	0	0	0	0
13	Page Title field 12	In progress	No	Development	32	2	30	6%	6%	2					142			24					30	30	30	30	30	30	30	30	30	30	30	30	30	30
14	Page Title field 13	Finished	No	Documentation	34	4	0	100%	12%	2	2					143	85		25					32	30	30	0	0	0	0	0	0	0	0	0	0	0
15	Page Title field 14	Finished	No	Environments	36	2	0	100%	6%	2					144			26					34	34	34	0	0	0	0	0	0	0	0	0	0	0
16	Page Title field 15	Finished	No	Functional design	38	4	0	100%	11%	2	2					145	86					36	0	0	0	0	0	0	0	0	0	0	0	0	0
17	Page Title field 16	Finished	No	Functional tests	40	2	0	100%	5%	2					146			27					38	38	38	0	0	0	0	0	0	0	0	0	0	0
18	Page Title field 17	In progress	No	Maintenance	42	2	40	5%	5%		2					87		28					42	40	40	40	40	40	40	40	40	40	40	40	40	40
19	Page Title field 18	Finished	No	Management	44	0	0	100%	0%					29					44	44	44	0	0	0	0	0	0	0	0	0	0	0
20	Page Title field 19	Finished	No	Meeting	46	2	0	100%	4%		2					88		30					46	44	44	0	0	0	0	0	0	0	0	0	0	0
21	Page Title field 20	Finished	No	Peer review	48	0	0	100%	0%					31					48	48	48	0	0	0	0	0	0	0	0	0	0	0
22	Page Title field 21	In progress	No	Support	50	2	48	4%	4%		2					89		32					50	48	48	48	48	48	48	48	48	48	48	48	48	48
23	Page Title field 22	Finished	No	Technical design	8	0	0	100%	0%					33					8	8	8	0	0	0	0	0	0	0	0	0	0	0
24	Page Title field 23	Finished	No	Unit tests	10	2	0	100%	20%		2					90		34					10	8	8	0	0	0	0	0	0	0	0	0	0	0
25	Page Title field 24	Finished	No	Development	12	0	0	100%	0%					35					12	12	12	0	0	0	0	0	0	0	0	0	0	0
26	Page Title field 25	Finished	No	Documentation	14	2	0	100%	14%		2					91					14	0	0	0	0	0	0	0	0	0	0	0	0	0
27	Page Title field 26	Waiting	No	Environments	16	0	16	0%	0%					36					16	16	16	16	16	16	16	16	16	16	16	16	16	16
28	Page Title field 27	Finished	No	Functional design	18	2	0	100%	11%		2					92		37					18	16	16	0	0	0	0	0	0	0	0	0	0	0
29	Page Title field 28	Finished	No	Functional tests	20	0	0	100%	0%					38					20	20	20	0	0	0	0	0	0	0	0	0	0	0
30	Page Title field 29	Finished	No	Maintenance	22	2	0	100%	9%		2					93		39					22	20	20	0	0	0	0	0	0	0	0	0	0	0
31	Page Title field 30	Waiting	No	Management	24	0	24	0%	0%					40					24	24	24	24	24	24	24	24	24	24	24	24	24	24
32	Page Title field 31	Finished	No	Meeting	26	2	0	100%	8%		2					94		41					26	24	24	0	0	0	0	0	0	0	0	0	0	0
33	Page Title field 32	Finished	No	Peer review	28	0	0	100%	0%					42					28	28	28	0	0	0	0	0	0	0	0	0	0	0
34	Page Title field 33	Finished	No	Support	30	0	0	100%	0%					43					30	30	30	0	0	0	0	0	0	0	0	0	0	0
35	Page Title field 34	Waiting	No	Technical design	32	0	32	0%	0%					44					32	32	32	32	32	32	32	32	32	32	32	32	32	32
36	Page Title field 35	Waiting	No	Unit tests	34	0	34	0%	0%					34	34	34	34	34	34	34	34	34	34	34	34	34	34
37	Page Title field 36	Waiting	No	Development	36	0	36	0%	0%					36	36	36	36	36	36	36	36	36	36	36	36	36	36
38	Page Title field 37	Waiting	No	Documentation	38	0	38	0%	0%					38	38	38	38	38	38	38	38	38	38	38	38	38	38
39	Page Title field 38	Waiting	No	Environments	40	0	40	0%	0%					40	40	40	40	40	40	40	40	40	40	40	40	40	40
40	Page Title field 39	Waiting	No	Functional design	42	0	42	0%	0%					42	42	42	42	42	42	42	42	42	42	42	42	42	42
41	Page Title field 40	Waiting	No	Functional tests	44	0	44	0%	0%					44	44	44	44	44	44	44	44	44	44	44	44	44	44
42	Page Title field 41	Waiting	No	Maintenance	46	0	46	0%	0%					46	46	46	46	46	46	46	46	46	46	46	46	46	46
43	Page Title field 42	Waiting	No	Management	48	0	48	0%	0%					48	48	48	48	48	48	48	48	48	48	48	48	48	48
44	Page Title field 43	Waiting	No	Meeting	50	0	50	0%	0%					50	50	50	50	50	50	50	50	50	50	50	50	50	50
45	Page Title field 44	Waiting	No	Peer review	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
46	Page Title field 45	Waiting	No	Support	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
47	Page Title field 46	Waiting	No	Technical design	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
48	Page Title field 47	Waiting	No	Unit tests	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
49	Page Title field 48	Waiting	No	Development	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
50	Page Title field 49	Waiting	No	Documentation	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
51	Page Title field 50	Waiting	No	Environments	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
52	Page Title field 51	Waiting	No	Functional design	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
53	Page Title field 52	Waiting	No	Functional tests	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
54	Page Title field 53	Cancelled	Yes	Maintenance	26	0	0	100%	0%					0	0	0	0	0	0	0	0	0	0	0	0	0	0
55	Page Title field 54	Waiting	No	Management	28	0	28	0%	0%					28	28	28	28	28	28	28	28	28	28	28	28	28	28
56	Page Title field 55	Waiting	No	Meeting	30	0	30	0%	0%					30	30	30	30	30	30	30	30	30	30	30	30	30	30
57	Page Title field 56	Waiting	No	Peer review	32	0	32	0%	0%					32	32	32	32	32	32	32	32	32	32	32	32	32	32
58	Page Title field 57	Waiting	No	Support	34	0	34	0%	0%					34	34	34	34	34	34	34	34	34	34	34	34	34	34
59	Page Title field 58	Waiting	No	Technical design	36	0	36	0%	0%					36	36	36	36	36	36	36	36	36	36	36	36	36	36
60	Page Title field 59	Waiting	No	Unit tests	38	0	38	0%	0%					38	38	38	38	38	38	38	38	38	38	38	38	38	38
61	Page Title field 60	Waiting	No	Development	40	0	40	0%	0%					40	40	40	40	40	40	40	40	40	40	40	40	40	40
62	Page Title field 61	Waiting	No	Documentation	42	0	42	0%	0%					42	42	42	42	42	42	42	42	42	42	42	42	42	42
63	Page Title field 62	Waiting	No	Environments	44	0	44	0%	0%					44	44	44	44	44	44	44	44	44	44	44	44	44	44
64	Page Title field 63	Waiting	No	Functional design	46	0	46	0%	0%					46	46	46	46	46	46	46	46	46	46	46	46	46	46
65	Page Title field 64	Waiting	No	Functional tests	48	0	48	0%	0%					48	48	48	48	48	48	48	48	48	48	48	48	48	48
66	Page Title field 65	Waiting	No	Maintenance	50	0	50	0%	0%					50	50	50	50	50	50	50	50	50	50	50	50	50	50
67	Page Title field 66	Waiting	No	Management	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
68	Page Title field 67	Waiting	No	Meeting	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
69	Page Title field 68	Waiting	No	Peer review	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
70	Page Title field 69	Waiting	No	Support	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
71	Page Title field 70	Waiting	No	Technical design	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
72	Page Title field 71	Waiting	No	Unit tests	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
73	Page Title field 72	Waiting	No	Development	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
74	Page Title field 73	Waiting	No	Documentation	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
75	Page Title field 74	Waiting	No	Environments	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
76	Page Title field 75	Waiting	No	Functional design	26	0	26	0%	0%					26	26	26	26	26	26	26	26	26	26	26	26	26	26
77	Page Title field 76	Waiting	No	Functional tests	28	0	28	0%	0%					28	28	28	28	28	28	28	28	28	28	28	28	28	28
78	Page Title field 77	Waiting	No	Maintenance	30	0	30	0%	0%					30	30	30	30	30	30	30	30	30	30	30	30	30	30
79	Page Title field 78	Waiting	No	Management	32	0	32	0%	0%					32	32	32	32	32	32	32	32	32	32	32	32	32	32
80	Page Title field 79	Waiting	No	Meeting	34	0	34	0%	0%					124					34	34	34	34	34	34	34	34	34	34	34	34	34	34
81	Page Title field 80	Waiting	No	Peer review	36	0	36	0%	0%					125					36	36	36	36	36	36	36	36	36	36	36	36	36	36
82	Page Title field 81	Waiting	No	Support	38	0	38	0%	0%					126					38	38	38	38	38	38	38	38	38	38	38	38	38	38
83	Page Title field 82	Waiting	No	Technical design	40	0	40	0%	0%					127					40	40	40	40	40	40	40	40	40	40	40	40	40	40
84	Page Title field 83	Waiting	No	Unit tests	42	0	42	0%	0%					128					42	42	42	42	42	42	42	42	42	42	42	42	42	42
85	Page Title field 84	Waiting	No	Development	44	0	44	0%	0%					129					44	44	44	44	44	44	44	44	44	44	44	44	44	44
86	Page Title field 85	Waiting	No	Documentation	46	0	46	0%	0%					130					46	46	46	46	46	46	46	46	46	46	46	46	46	46
87	Page Title field 86	Waiting	No	Environments	48	0	48	0%	0%					131					48	48	48	48	48	48	48	48	48	48	48	48	48	48
88	Page Title field 87	Waiting	No	Functional design	50	0	50	0%	0%					132					50	50	50	50	50	50	50	50	50	50	50	50	50	50
89	Page Title field 88	Waiting	No	Functional tests	8	0	8	0%	0%					133					8	8	8	8	8	8	8	8	8	8	8	8	8	8
90	Page Title field 89	Waiting	No	Maintenance	10	0	10	0%	0%					134					10	10	10	10	10	10	10	10	10	10	10	10	10	10
91	Page Title field 90	In progress	No	Management	12	6	8	43%	50%			6					135					12	12	8	8	8	8	8	8	8	8	8	8	8	8
92	Page Title field 91	Waiting	No	Meeting	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
93	Page Title field 92	Waiting	No	Peer review	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
94	Page Title field 93	Waiting	No	Support	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
95	Page Title field 94	Waiting	No	Technical design	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
96	Page Title field 95	Waiting	No	Unit tests	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
97	Page Title field 96	Waiting	No	Development	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
98	Page Title field 97	Waiting	No	Documentation	26	0	26	0%	0%					26	26	26	26	26	26	26	26	26	26	26	26	26	26
99	Page Title field 98	Waiting	No	Environments	28	0	28	0%	0%					28	28	28	28	28	28	28	28	28	28	28	28	28	28
100	Page Title field 99	Waiting	No	Functional design	30	0	30	0%	0%					30	30	30	30	30	30	30	30	30	30	30	30	30	30
101	Page Title field 100	Waiting	No	Functional tests	32	0	32	0%	0%					32	32	32	32	32	32	32	32	32	32	32	32	32	32
102	Page Title field 101	Waiting	No	Maintenance	34	0	34	0%	0%					34	34	34	34	34	34	34	34	34	34	34	34	34	34
103	Page Title field 102	Waiting	No	Management	36	0	36	0%	0%					36	36	36	36	36	36	36	36	36	36	36	36	36	36
104	Page Title field 103	Cancelled	Yes	Meeting	38	0	0	100%	0%					0	0	0	0	0	0	0	0	0	0	0	0	0	0
105	Page Title field 104	Waiting	No	Peer review	40	0	40	0%	0%					40	40	40	40	40	40	40	40	40	40	40	40	40	40
106	Page Title field 105	Waiting	No	Support	42	0	42	0%	0%					42	42	42	42	42	42	42	42	42	42	42	42	42	42
107	Page Title field 106	Waiting	No	Technical design	44	0	44	0%	0%					44	44	44	44	44	44	44	44	44	44	44	44	44	44
108	Page Title field 107	Waiting	No	Unit tests	46	0	46	0%	0%					46	46	46	46	46	46	46	46	46	46	46	46	46	46
109	Page Title field 108	Waiting	No	Development	48	0	48	0%	0%					48	48	48	48	48	48	48	48	48	48	48	48	48	48
110	Page Title field 109	Waiting	No	Documentation	50	0	50	0%	0%					50	50	50	50	50	50	50	50	50	50	50	50	50	50
111	Page Title field 110	Waiting	No	Environments	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
112	Page Title field 111	Waiting	No	Functional design	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
113	Page Title field 112	Waiting	No	Functional tests	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
114	Page Title field 113	Waiting	No	Maintenance	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
115	Page Title field 114	Waiting	No	Management	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
116	Page Title field 115	Waiting	No	Meeting	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
117	Page Title field 116	Waiting	No	Peer review	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
118	Page Title field 117	Waiting	No	Support	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
119	Page Title field 118	Waiting	No	Technical design	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
120	Page Title field 119	Waiting	No	Unit tests	26	0	26	0%	0%					26	26	26	26	26	26	26	26	26	26	26	26	26	26
121	Page Title field 120	Waiting	No	Development	28	0	28	0%	0%					28	28	28	28	28	28	28	28	28	28	28	28	28	28
122	Page Title field 121	Waiting	No	Documentation	30	0	30	0%	0%					30	30	30	30	30	30	30	30	30	30	30	30	30	30
123	Page Title field 122	Waiting	No	Environments	32	0	32	0%	0%					32	32	32	32	32	32	32	32	32	32	32	32	32	32
124	Page Title field 123	Waiting	No	Functional design	34	0	34	0%	0%					34	34	34	34	34	34	34	34	34	34	34	34	34	34
125	Page Title field 124	Waiting	No	Functional tests	36	0	36	0%	0%					36	36	36	36	36	36	36	36	36	36	36	36	36	36
126	Page Title field 125	Waiting	No	Maintenance	38	0	38	0%	0%					38	38	38	38	38	38	38	38	38	38	38	38	38	38
127	Page Title field 126	Waiting	No	Management	40	0	40	0%	0%					40	40	40	40	40	40	40	40	40	40	40	40	40	40
128	Page Title field 127	Waiting	No	Meeting	42	0	42	0%	0%					42	42	42	42	42	42	42	42	42	42	42	42	42	42
129	Page Title field 128	Waiting	No	Peer review	44	0	44	0%	0%					44	44	44	44	44	44	44	44	44	44	44	44	44	44
130	Page Title field 129	Waiting	No	Support	46	0	46	0%	0%					46	46	46	46	46	46	46	46	46	46	46	46	46	46
131	Page Title field 130	Waiting	No	Technical design	48	0	48	0%	0%					48	48	48	48	48	48	48	48	48	48	48	48	48	48
132	Page Title field 131	Waiting	No	Unit tests	50	0	50	0%	0%					50	50	50	50	50	50	50	50	50	50	50	50	50	50
133	Page Title field 132	Waiting	No	Development	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
134	Page Title field 133	Waiting	No	Documentation	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
135	Page Title field 134	Waiting	No	Environments	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
136	Page Title field 135	Waiting	No	Functional design	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
137	Page Title field 136	Waiting	No	Functional tests	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
138	Page Title field 137	Waiting	No	Maintenance	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
139	Page Title field 138	Waiting	No	Management	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
140	Page Title field 139	Waiting	No	Meeting	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
141	Page Title field 140	Waiting	No	Peer review	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
142	Page Title field 141	Waiting	No	Support	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
143	Page Title field 142	Waiting	No	Technical design	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
144	Page Title field 143	Waiting	No	Unit tests	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
145	Page Title field 144	Waiting	No	Development	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
146	Page Title field 145	Waiting	No	Documentation	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
147	Page Title field 146	Waiting	No	Environments	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
148	Page Title field 147	Waiting	No	Functional design	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
149	Page Title field 148	Cancelled	Yes	Functional tests	22	0	0	100%	0%					0	0	0	0	0	0	0	0	0	0	0	0	0	0
150	Page Title field 149	Waiting	No	Maintenance	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
151	Page Title field 150	Waiting	No	Management	26	0	26	0%	0%					26	26	26	26	26	26	26	26	26	26	26	26	26	26
152	Page Title field 151	Waiting	No	Meeting	28	0	28	0%	0%					28	28	28	28	28	28	28	28	28	28	28	28	28	28
153	Page Title field 152	Waiting	No	Peer review	30	0	30	0%	0%					30	30	30	30	30	30	30	30	30	30	30	30	30	30
154	Page Title field 153	Waiting	No	Support	32	0	32	0%	0%					32	32	32	32	32	32	32	32	32	32	32	32	32	32
155	Page Title field 154	Waiting	No	Technical design	34	0	34	0%	0%					34	34	34	34	34	34	34	34	34	34	34	34	34	34
156	Page Title field 155	Waiting	No	Unit tests	36	0	36	0%	0%					36	36	36	36	36	36	36	36	36	36	36	36	36	36
157	Page Title field 156	Waiting	No	Development	38	0	38	0%	0%					38	38	38	38	38	38	38	38	38	38	38	38	38	38
158	Page Title field 157	Waiting	No	Documentation	40	0	40	0%	0%					40	40	40	40	40	40	40	40	40	40	40	40	40	40
159	Page Title field 158	Waiting	No	Environments	42	0	42	0%	0%					42	42	42	42	42	42	42	42	42	42	42	42	42	42
160	Page Title field 159	Waiting	No	Functional design	44	0	44	0%	0%					44	44	44	44	44	44	44	44	44	44	44	44	44	44
161	Page Title field 160	Waiting	No	Functional tests	46	0	46	0%	0%					46	46	46	46	46	46	46	46	46	46	46	46	46	46
162	Page Title field 161	Waiting	No	Maintenance	48	0	48	0%	0%					48	48	48	48	48	48	48	48	48	48	48	48	48	48
163	Page Title field 162	Waiting	No	Management	50	0	50	0%	0%					50	50	50	50	50	50	50	50	50	50	50	50	50	50
164	Page Title field 163	Waiting	No	Meeting	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
165	Page Title field 164	Waiting	No	Peer review	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
166	Page Title field 165	Waiting	No	Support	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
167	Page Title field 166	Waiting	No	Technical design	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
168	Page Title field 167	Waiting	No	Unit tests	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
169	Page Title field 168	Waiting	No	Development	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
170	Page Title field 169	Waiting	No	Documentation	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
171	Page Title field 170	Waiting	No	Environments	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
172	Page Title field 171	Waiting	No	Functional design	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
173	Page Title field 172	Waiting	No	Functional tests	26	0	26	0%	0%					26	26	26	26	26	26	26	26	26	26	26	26	26	26
174	Page Title field 173	Waiting	No	Maintenance	28	0	28	0%	0%					28	28	28	28	28	28	28	28	28	28	28	28	28	28
175	Page Title field 174	Waiting	No	Management	30	0	30	0%	0%					30	30	30	30	30	30	30	30	30	30	30	30	30	30
176	Page Title field 175	Waiting	No	Meeting	32	0	32	0%	0%					32	32	32	32	32	32	32	32	32	32	32	32	32	32
177	Page Title field 176	Waiting	No	Peer review	34	0	34	0%	0%					34	34	34	34	34	34	34	34	34	34	34	34	34	34
178	Page Title field 177	Waiting	No	Support	36	0	36	0%	0%					36	36	36	36	36	36	36	36	36	36	36	36	36	36
179	Page Title field 178	Waiting	No	Technical design	38	0	38	0%	0%					38	38	38	38	38	38	38	38	38	38	38	38	38	38
180	Page Title field 179	Waiting	No	Unit tests	40	0	40	0%	0%					40	40	40	40	40	40	40	40	40	40	40	40	40	40
181	Page Title field 180	Waiting	No	Development	42	0	42	0%	0%					42	42	42	42	42	42	42	42	42	42	42	42	42	42
182	Page Title field 181	Waiting	No	Documentation	44	0	44	0%	0%					44	44	44	44	44	44	44	44	44	44	44	44	44	44
183	Page Title field 182	Waiting	No	Environments	46	0	46	0%	0%					46	46	46	46	46	46	46	46	46	46	46	46	46	46
184	Page Title field 183	Waiting	No	Functional design	48	0	48	0%	0%					48	48	48	48	48	48	48	48	48	48	48	48	48	48
185	Page Title field 184	Cancelled	Yes	Functional tests	50	0	0	100%	0%					0	0	0	0	0	0	0	0	0	0	0	0	0	0
186	Page Title field 185	Waiting	No	Maintenance	8	0	8	0%	0%					8	8	8	8	8	8	8	8	8	8	8	8	8	8
187	Page Title field 186	Waiting	No	Management	10	0	10	0%	0%					10	10	10	10	10	10	10	10	10	10	10	10	10	10
188	Page Title field 187	Waiting	No	Meeting	12	0	12	0%	0%					12	12	12	12	12	12	12	12	12	12	12	12	12	12
189	Page Title field 188	Waiting	No	Peer review	14	0	14	0%	0%					14	14	14	14	14	14	14	14	14	14	14	14	14	14
190	Page Title field 189	Waiting	No	Support	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
191	Page Title field 190	Waiting	No	Technical design	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
192	Page Title field 191	Waiting	No	Unit tests	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
193	Page Title field 192	Waiting	No	Development	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
194	Page Title field 193	Waiting	No	Documentation	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
195	Page Title field 194	Waiting	No	Environments	16	0	16	0%	0%					16	16	16	16	16	16	16	16	16	16	16	16	16	16
196	Page Title field 195	Waiting	No	Functional design	18	0	18	0%	0%					18	18	18	18	18	18	18	18	18	18	18	18	18	18
197	Page Title field 196	Waiting	No	Functional tests	20	0	20	0%	0%					20	20	20	20	20	20	20	20	20	20	20	20	20	20
198	Page Title field 197	Waiting	No	Maintenance	22	0	22	0%	0%					22	22	22	22	22	22	22	22	22	22	22	22	22	22
199	Page Title field 198	Waiting	No	Meeting	24	0	24	0%	0%					24	24	24	24	24	24	24	24	24	24	24	24	24	24
200	Page Title field 199	Waiting	No	Technical design	26	0	26	0%	0%					26	26	26	26	26	26	26	26	26	26	26	26	26	26

## Dashboard
Task type	Total effort (%)	Total effort (H)
Development	32%	27
Documentation	9%	8
Environments	5%	4
Functional design	9%	8
Functional tests	5%	4
Maintenance	7%	6
Management	9%	8
Meeting	5%	4
Peer review	2%	2
Support	7%	6
Technical design	2%	2
Unit tests	7%	6

	100%	85

Task state	Total task number (%)	Total task number (H)
Cancelled	3%	5
Finished	13%	26
In progress	3%	6
Waiting	82%	163

	100,00%	200
Task type distribution following effort (%) Task state distribution (%)

## Parameters
Company Scrum Backlog directory link	'file:../../
Company Scrum Backlog file link	'file:../../Company Scrum Backlog.ods'
Project Scrum Backlog directory link	'file:../
Project Scrum Backlog file link	'file:../Project 3 Scrum Backlog.ods'
Release Scrum Backlog directory link	'file:../
Release Scrum Backlog file link	'file:../Releases/Release 4 Scrum Backlog.ods'

Sprint parameters
		Task type			Task state			Is Cancelled ?
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D4	Development		'file:../../Company Scrum Backlog.ods'#$Parameters.$F4	Cancelled		'file:../../Company Scrum Backlog.ods'#$Parameters.$J89	Yes
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D5	Documentation		'file:../../Company Scrum Backlog.ods'#$Parameters.$F5	Finished		'file:../../Company Scrum Backlog.ods'#$Parameters.$J90	No
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D6	Environments		'file:../../Company Scrum Backlog.ods'#$Parameters.$F6	In progress		'file:../../Company Scrum Backlog.ods'#$Parameters.$J91
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D7	Functional design		'file:../../Company Scrum Backlog.ods'#$Parameters.$F7	Waiting		'file:../../Company Scrum Backlog.ods'#$Parameters.$J92
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D8	Functional tests		'file:../../Company Scrum Backlog.ods'#$Parameters.$F8
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D9	Maintenance
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D10	Management
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D11	Meeting
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D12	Peer review
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D13	Support
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D14	Technical design
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D15	Unit tests
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D16
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D17
	'file:../../Company Scrum Backlog.ods'#$Parameters.$D18

Directory parameters

		Directory
	'file:../../Company Scrum Backlog.ods'#$Parameters.$B33	C:

Line index parameters
	Company file				Project file				Release file				Sprint file				Story file
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C107	Project line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$F107	Feature line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I107	Sprint line index	23		'file:../../Company Scrum Backlog.ods'#$Parameters.$L107	Task line index	26		'file:../../Company Scrum Backlog.ods'#$Parameters.$O107	Task line index	24
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C108	Project total man days line index	843		'file:../../Company Scrum Backlog.ods'#$Parameters.$F108	Story line index	6		'file:../../Company Scrum Backlog.ods'#$Parameters.$I108	Sprint lines number	75		'file:../../Company Scrum Backlog.ods'#$Parameters.$L108	Task lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$O108	Task lines number	200
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C109	Ressource line index	2		'file:../../Company Scrum Backlog.ods'#$Parameters.$F109	Release line index	11		'file:../../Company Scrum Backlog.ods'#$Parameters.$I109				'file:../../Company Scrum Backlog.ods'#$Parameters.$L109				'file:../../Company Scrum Backlog.ods'#$Parameters.$O109
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C110	Project lines number	50		'file:../../Company Scrum Backlog.ods'#$Parameters.$F110	Story lines number	600		'file:../../Company Scrum Backlog.ods'#$Parameters.$I110				'file:../../Company Scrum Backlog.ods'#$Parameters.$L110				'file:../../Company Scrum Backlog.ods'#$Parameters.$O110
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C111	Ressource lines number	42		'file:../../Company Scrum Backlog.ods'#$Parameters.$F111	Feature lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I111				'file:../../Company Scrum Backlog.ods'#$Parameters.$L111				'file:../../Company Scrum Backlog.ods'#$Parameters.$O111
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C112		20		'file:../../Company Scrum Backlog.ods'#$Parameters.$F112	Release lines number	200		'file:../../Company Scrum Backlog.ods'#$Parameters.$I112				'file:../../Company Scrum Backlog.ods'#$Parameters.$L112				'file:../../Company Scrum Backlog.ods'#$Parameters.$O112

Color parameters
	Margin of error for planned points (% pts)				Margin for ratio (%)				Margin for progress (%)
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F116	Red (>)	100%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I116	Green (>)	100%
	'file:../../Company Scrum Backlog.ods'#$Parameters.$C117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$F117	Yellow	75%		'file:../../Company Scrum Backlog.ods'#$Parameters.$I117	Orange	0%