## W.I.P. Summary
B & L Mechanical, Inc.
Work in Process Summary
April 2, 2015

Work in Process
	Cost Plus	199,681.90
	Firm	181,488.74
	TOTAL	381,170.65

Billing in Excess of Costs
	Firm	24,200.40
	TOTAL	24,200.40

	Shelco, Inc. AR Adjustment	236,060.73
	for November, December, January & February invoices (paid)	356,970.25

	Upcoming Shelco, Inc. Receivables Adjustment	138,308.61
	for March invoice

## Cost Plus W.I.P.
	B & L Mechanical, Inc.
	Cost Plus Jobs W.I.P. Report
	April 2, 2015

Date Last Activity	Job Number	Job Description	Materials	Non-Taxable And Subs	Labor and Burden	Misc Expense	Rental Expense	Open PO's	Actual Cost With Taxes JTD	OH %	Fee %	Total Commitment With Tax-OH-Fee	Total Billed - JTD	Proj. Mgr.	W.I.P
11/30/14	34149	G-3 INSTALL CHI	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
04/01/15	34157C1	MATRIX FILTER S	0.00	337.50	889.48	0.00	907.67	152.70	2,287.35	23	10	3,094.78	0.00	DB	2,888.18	2,134.65	1.23	1.10	2888.18
04/02/15	35023C1	CUT HOLES IN SH	17.03	0.00	999.62	0.00	0.00	0.00	1,016.65	0	9	1,108.15	0.00	DB	1,108.15	1,016.65	1	1.09	1108.15
04/02/15	35032C1	EXTRA PURCHASE	222.68	0.00	527.60	0.00	0.00	2,960.48	3,710.76	23	10	5,020.65	0.00	DB	1,015.13	750.28	1.23	1.10	1015.13
04/02/15	35036	HM1 ELECTRICAL	0.00	0.00	1,894.40	0.00	0.00	0.00	1,894.40	0	9	2,064.90	0.00	DB	2,064.90	1,894.40	1	1.09	2064.9
04/30/15	35042	INSTALL NORFAB	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	0.00	0.00	1.23	1.10	0
04/02/15	3FE4010	GUARDHOUSE PREP	92.09	0.00	2,032.73	0.00	0.00	50.99	2,175.81	0	9	2,371.63	479.60	DB	1,836.45	2,124.82	1	1.09	2316.05
04/01/15	3FM5011	CLEAN OUT RECLA	410.05	3,045.00	1,551.84	0.00	115.97	0.00	5,122.86	0	9	5,583.92	5,688.68	DB	0.00	5,122.86	1	1.09	5583.92
04/02/15	3FM5018S	REPAIR SIDE WAL	11,054.83	0.00	10,966.21	0.00	0.00	0.00	22,021.04	23	10	29,794.47	0.00	DB	29,794.47	22,021.04	1.23	1.10	29794.47
04/02/15	3FM5018	REPAIR SIDE WAL	578.66	3,018.00	21,101.97	0.00	363.88	41.20	25,103.71	0	9	27,363.04	0.00	DB	27,318.14	25,062.51	1	1.09	27318.14
03/31/15	3FM5023	CLEAN & PAINT T	0.00	0.00	474.15	0.00	0.00	10,000.00	10,474.15	0	9	11,416.82	0.00	DB	516.82	474.15	1	1.09	516.82
04/01/15	3FM5025	UNPLUG THE SILO	0.00	0.00	3,936.18	0.00	263.55	0.00	4,199.73	0	9	4,577.71	4,816.32	DB	0.00	4,199.73	1	1.09	4577.71
03/31/15	3FM5028	TEST & CERTIFY	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
04/02/15	3FM5032	REPIPE G2 LLF T	74.94	0.00	6,245.64	0.00	0.00	0.00	6,320.58	23	10	8,551.74	0.00	DB	8,551.74	6,320.58	1.23	1.10	8551.74
04/02/15	3FM5036	REPAIR BOILER #	49.96	0.00	2,061.64	0.00	0.00	1,544.82	3,656.42	0	9	3,985.50	0.00	DB	2,301.64	2,111.60	1	1.09	2301.64
03/31/15	3FM5039	REPLACE LEAKING	0.00	0.00	0.00	0.00	0.00	340.39	340.39	0	9	371.03	0.00	DB	0.00	0.00	1	1.09	0
03/31/15	3FM5040	REMOVE 2-1/2 VA	0.00	0.00	0.00	0.00	0.00	340.99	340.99	0	9	371.68	0.00	DB	0.00	0.00	1	1.09	0
03/31/15	3FM5041	INSTALL EJECTOR	0.00	0.00	0.00	0.00	0.00	1,652.94	1,652.94	0	9	1,801.70	0.00	DB	0.00	0.00	1	1.09	0
03/31/15	3FM5042	REPLACE LEAKING	0.00	0.00	0.00	0.00	0.00	3,085.13	3,085.13	0	9	3,362.79	0.00	DB	0.00	0.00	1	1.09	0
04/30/15	3FM5043	DEMO OLD FLOAT	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
02/28/14	3TM40149	ASSIST W/GRINDE	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
04/30/14	3TM4047V	T & F INSULATIO	0.00	0.00	0.00	0.00	0.00	925.00	925.00	0	9	1,008.25	0.00	DB	0.00	0.00	1	1.09	0
09/30/14	3TM4116V	REPLACE INSULAT	0.00	0.00	0.00	0.00	0.00	18,483.00	18,483.00	0	9	20,146.47	0.00	DB	0.00	0.00	1	1.09	0
12/31/14	3TM4155	CLEAN BAGHOUSE	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
03/31/15	3TM5008S	FURNISH LEXAN T	0.00	0.00	67.21	0.00	0.00	358.84	426.05	0	9	464.39	0.00	DB	73.26	67.21	1	1.09	73.26
03/31/15	3TM5009	REAPIR ALL STEA	0.00	0.00	0.00	0.00	0.00	340.99	340.99	0	9	371.68	0.00	DB	0.00	0.00	1	1.09	0
04/02/15	3TM5010	ASSIT WHSE LOAD	24.72	0.00	374.41	0.00	0.00	10.00	409.13	0	9	445.95	0.00	DB	435.05	399.13	1	1.09	435.05
03/31/15	3TM5011	CLEAN TREATERS	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
03/31/15	3TM5012	TRAM 17J PULL R	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
03/31/15	3TM5013V	17J FILM LINE O	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	0.00	0.00	1	1.09	0
04/02/15	AB5010	SPRAY NOZZLES E	29.90	0.00	1,433.47	107.00	0.00	0.00	1,570.37	23	10	2,124.72	2,124.86	TD	0.00	1,570.37	1.23	1.10	2124.71
04/02/15	AB5012	MUELLER WORK	0.00	0.00	8,881.74	626.00	0.00	0.00	9,507.74	23	10	12,863.97	0.00	TD	12,863.97	9,507.74	1.23	1.10	12863.97
04/02/15	AB5013	REPAIR T FRAMES	14.55	0.00	2,111.78	428.00	0.00	0.00	2,554.33	23	10	3,456.01	3,456.16	TD	0.00	2,554.33	1.23	1.10	3456.01
03/31/15	AB5014	WELD SPRAY NOZZ	0.00	0.00	85.77	0.00	0.00	0.00	85.77	23	10	116.05	0.00	TD	116.05	85.77	1.23	1.10	116.05
04/02/15	AB5015	REMOVE ESP DOOR	0.00	0.00	1,411.34	128.70	0.00	0.00	1,540.04	23	10	2,083.68	2,083.82	TD	0.00	1,540.04	1.23	1.10	2083.67
04/02/15	AB5016	REPAIR STEAM LE	754.19	0.00	1,655.29	122.01	0.00	0.00	2,531.49	23	10	3,425.10	0.00	TD	3,425.11	2,531.49	1.23	1.10	3425.11
04/02/15	AB5018	DRIVE ROLL LAST	12.70	0.00	419.44	0.00	0.00	0.00	432.14	23	10	584.68	0.00	TD	584.69	432.14	1.23	1.10	584.69
03/05/15	BA4003S	FAB SS FLASHING	20.47	0.00	141.41	13.00	0.00	0.00	174.88	23	10	236.61	236.61	SL	0.00	174.88	1.23	1.10	236.61
03/05/15	BA5001S	SUPPLY & DELIVE	177.18	0.00	57.73	12.00	0.00	0.00	246.91	23	10	334.07	344.07	SL	0.00	246.91	1.23	1.10	334.07
12/11/14	BB4032	MISC WORK	0.00	0.00	2,517.69	257.50	112.50	0.00	2,887.69	23	10	3,907.05	0.00	TD	3,907.04	2,887.69	1.23	1.10	3907.04
12/18/14	BB4035	REPLACE & REPAI	5.07	0.00	281.10	30.00	15.00	0.00	331.17	23	10	448.07	0.00	TD	448.07	331.17	1.23	1.10	448.07
03/05/15	BB5004	ANCHOR TABLE FO	4.72	0.00	420.29	88.90	15.00	0.00	528.91	23	10	715.62	0.00	TD	715.62	528.91	1.23	1.10	715.62
03/31/15	BB5005	INSTALL CLIPS &	0.00	0.00	309.05	33.00	15.00	0.00	357.05	23	10	483.09	0.00	TD	483.09	357.05	1.23	1.10	483.09
03/31/15	BB5006	INSTALL HANDRAI	0.00	0.00	309.13	33.00	15.00	0.00	357.13	23	10	483.20	0.00	TD	483.20	357.13	1.23	1.10	483.2
04/02/15	CB5002S	FAB BRACKETS	17.38	0.00	129.56	0.00	0.00	0.00	146.94	23	10	198.81	0.00	SL	198.81	146.94	1.23	1.10	198.81
04/02/15	CB5002	MOVE EXISTING R	67.99	0.00	4,202.98	332.00	157.00	0.00	4,759.97	23	10	6,440.24	0.00	SL	6,440.24	4,759.97	1.23	1.10	6440.24
03/31/15	CI5003	REPAIR STEAM LI	218.76	0.00	864.07	65.00	75.00	0.00	1,222.83	15	10	1,546.88	0.00	SL	1,546.88	1,222.83	1.15	1.10	1546.88
03/04/15	CM5002	REPAIR BOILER	141.80	0.00	479.27	3.00	165.00	0.00	789.07	15	10	998.17	0.00	SL	998.17	789.07	1.15	1.10	998.17
04/30/15	CM5003	REPAIR BOILER	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	SL	0.00	0.00	1.23	1.10	0
01/31/15	CS5001	REPAIR CONDENSE	61.49	0.00	102.04	0.00	145.00	0.00	308.53	23	10	417.44	0.00	SL	417.44	308.53	1.23	1.10	417.44
01/31/15	CS5002	REPAIR R3 REACT	72.57	0.00	393.85	2.00	190.00	0.00	658.42	23	10	890.85	0.00	SL	890.84	658.42	1.23	1.10	890.84
02/28/15	CS5003	REPAIR STEADY B	77.18	0.00	565.39	2.00	165.00	0.00	809.57	23	10	1,095.35	0.00	SL	1,095.35	809.57	1.23	1.10	1095.35
04/02/15	CS5004S	FAB COLD FINGER	259.22	0.00	654.62	0.00	0.00	0.00	913.84	23	10	1,236.42	0.00	SL	1,236.43	913.84	1.23	1.10	1236.43
04/02/15	CS5004	TRIAL PROJECT	742.77	0.00	6,299.41	164.00	725.00	261.00	8,192.18	23	10	11,084.02	0.00	SL	10,730.89	7,931.18	1.23	1.10	10730.89
03/31/15	CS5005	REPAIR HOT OIL	90.85	0.00	712.45	4.00	120.00	0.00	927.30	23	10	1,254.64	0.00	SL	1,254.64	927.30	1.23	1.10	1254.64
04/02/15	CS5006	INSTALL 2" SS L	82.04	0.00	228.76	0.00	75.00	0.00	385.80	23	10	521.98	0.00	SL	521.99	385.80	1.23	1.10	521.99
03/31/15	CS5007	REPAIR COIL ON	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	SL	0.00	0.00	1.23	1.10	0
10/31/14	ET4008S	FAB FLANGE & IN	0.00	0.00	194.10	0.00	0.00	0.00	194.10	23	10	262.61	0.00	SL	262.62	194.10	1.23	1.10	262.62
10/31/14	ET4008	FAB FLANGE & IN	18.39	0.00	0.00	0.00	0.00	0.00	18.39	23	10	24.88	0.00	SL	24.88	18.39	1.23	1.10	24.88
12/11/14	ET4009	INSTALL 1-1/2 N	70.62	0.00	1,127.21	2.00	45.00	0.00	1,244.83	23	10	1,684.25	0.00	SL	1,684.25	1,244.83	1.23	1.10	1684.25
12/11/14	ET4010	NOZZLE FOR R3	180.05	0.00	915.35	2.00	190.00	0.00	1,287.40	23	10	1,741.85	0.00	SL	1,741.85	1,287.40	1.23	1.10	1741.85
12/11/14	ET4011	INSTALL NOZZLE	129.30	0.00	915.40	0.00	190.00	0.00	1,234.70	23	10	1,670.55	0.00	SL	1,670.55	1,234.70	1.23	1.10	1670.55
03/23/15	ET4012	INSTALL PIPING	3,170.02	0.00	41,433.48	444.50	2,535.00	0.00	47,583.00	15	10	60,192.50	56,167.50	SL	4,025.00	47,583.00	1.15	1.10	60192.5
12/31/14	ET4013	INSTALL NOZZLE	101.63	0.00	870.03	4.00	145.00	0.00	1,120.66	23	10	1,516.25	0.00	SL	1,516.25	1,120.66	1.23	1.10	1516.25
04/02/15	ET5001	SUPPLY LABOR CO	43.04	0.00	5,053.30	263.50	285.00	0.00	5,644.84	15	10	7,140.73	1,599.41	SL	5,541.31	5,644.84	1.15	1.10	7140.72
04/02/15	ET5002S	FAB 36" DIA CON	1,045.40	0.00	2,148.49	0.00	45.00	0.00	3,238.89	15	10	4,097.19	0.00	SL	4,097.20	3,238.89	1.15	1.10	4097.2
04/02/15	ET5003	FAB PLATFROM	19.21	0.00	4,031.92	207.00	180.00	0.00	4,438.13	15	10	5,614.24	0.00	SL	5,614.23	4,438.13	1.15	1.10	5614.23
04/01/15	ET5004S	REPAIR R2 REACT	130.00	0.00	32.00	0.00	0.00	0.00	162.00	15	10	204.93	0.00	SL	204.93	162.00	1.15	1.10	204.93
04/02/15	ET5004	REPAIR REACTOR	0.00	0.00	446.20	38.50	60.00	0.00	544.70	15	10	689.05	0.00	SL	689.05	544.70	1.15	1.10	689.05
11/30/12	HK2009S	REMAKE SS LID	72.25	0.00	425.67	0.00	0.00	0.00	497.92	15	10	629.87	0.00	JC	629.87	497.92	1.15	1.10	629.87
01/09/13	HK2009	REMAKE SS LID &	0.00	76.97	525.47	15.00	7.50	0.00	624.94	15	10	790.55	0.00	JC	790.55	624.94	1.15	1.10	790.55
01/31/13	HK3001S	FAB & INSTALL S	13.89	0.00	0.00	0.00	0.00	0.00	13.89	15	10	17.57	0.00	JC	17.57	13.89	1.15	1.10	17.57
02/28/13	HK3001	FAB & INSTALL S	0.00	0.00	0.00	0.00	0.00	0.00	0.00	15	10	0.00	0.00	JC	0.00	0.00	1.15	1.10	0
02/28/15	IM5001S	HYDROTEST AFTER	21.36	0.00	112.78	0.00	0.00	0.00	134.14	23	10	181.49	0.00	SL	181.49	134.14	1.23	1.10	181.49
04/30/15	M5004S	REPAIR FAN	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	SL	0.00	0.00	1.23	1.10	0
04/30/15	MP5001	CUT FLOOR MATES	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	TD	0.00	0.00	1.23	1.10	0
09/30/13	PA3009	INSTALL SUPPORT	348.72	0.00	1,258.06	5.00	285.00	0.00	1,896.78	23	10	2,566.34	0.00	SL	2,566.34	1,896.78	1.23	1.10	2566.34
01/31/14	PA4001S	FAB DRIP PAN	331.21	0.00	824.67	0.00	0.00	0.00	1,155.88	23	10	1,563.90	0.00	SL	1,563.91	1,155.88	1.23	1.10	1563.91
09/30/14	PA4003S	FAB 2 SS PANS	18.63	0.00	64.16	0.00	0.00	0.00	82.79	23	10	112.01	0.00	SL	112.01	82.79	1.23	1.10	112.01
11/30/14	PA4004S	FAB SS TROTH	0.00	0.00	353.37	0.00	0.00	0.00	353.37	15	10	447.02	0.00	SL	447.01	353.37	1.15	1.10	447.01
03/31/15	SC5002	MOVE BEAM TO RE	277.80	0.00	2,611.01	118.00	742.12	0.00	3,748.93	15	10	4,742.40	0.00	TD	4,742.40	3,748.93	1.15	1.10	4742.4
03/31/15	SC5003	REPAIR REACTOR	89.71	0.00	848.29	4.00	165.00	0.00	1,107.00	23	10	1,497.77	0.00	SL	1,497.77	1,107.00	1.23	1.10	1497.77
03/10/15	SM5001	COOLING TOWER M	3,958.21	2,372.00	3,914.49	12.00	360.00	2.00	10,618.70	15	10	13,432.66	0.00	SL	13,430.13	10,616.70	1.15	1.10	13430.13
02/28/15	SM5002	INSULATE CHILL	0.00	1,470.00	0.00	0.00	0.00	0.00	1,470.00	15	10	1,859.55	0.00	SL	1,859.55	1,470.00	1.15	1.10	1859.55
04/02/15	SS5001S	CUT 3" PLATE	0.00	0.00	95.93	0.00	0.00	0.00	95.93	15	10	121.35	0.00	SL	121.35	95.93	1.15	1.10	121.35
02/28/15	SV5004S	FAB ZSK BLADE	29.64	0.00	597.96	0.00	135.00	0.00	762.60	23	10	1,031.80	0.00	SL	1,031.80	762.60	1.23	1.10	1031.8
02/28/15	SV5005S	FAB COVER LOADI	50.14	0.00	210.21	0.00	0.00	0.00	260.35	23	10	352.25	0.00	SL	352.25	260.35	1.23	1.10	352.25
02/28/15	SV5006	REPAIR PACK OUT	0.00	0.00	1,711.36	3.00	90.00	0.00	1,804.36	23	10	2,441.30	0.00	SL	2,441.30	1,804.36	1.23	1.10	2441.3
02/28/15	SV5007	ASSIST W/ TURN	175.90	0.00	1,364.36	15.00	240.00	0.00	1,795.26	23	10	2,428.99	0.00	SL	2,428.99	1,795.26	1.23	1.10	2428.99
02/28/15	SV5008	INSTALL N2 FILT	83.22	0.00	694.39	3.00	120.00	0.00	900.61	23	10	1,218.53	0.00	SL	1,218.53	900.61	1.23	1.10	1218.53
03/31/15	SV5010	REPAIR MILL TAN	35.40	0.00	1,493.30	0.00	45.00	0.00	1,573.70	23	10	2,129.22	0.00	SL	2,129.22	1,573.70	1.23	1.10	2129.22
03/31/15	SV5011	FAB OVEN STAND	68.33	0.00	181.21	0.00	0.00	0.00	249.54	23	10	337.62	0.00	SL	337.63	249.54	1.23	1.10	337.63
03/31/15	SV5012S	PIPE N2 TANK	9.43	0.00	744.79	0.00	0.00	0.00	754.22	23	10	1,020.46	0.00	SL	1,020.46	754.22	1.23	1.10	1020.46
04/01/15	SV5012	PIPE N2 TANK	365.66	0.00	804.77	27.00	330.00	0.00	1,527.43	23	10	2,066.61	0.00	SL	2,066.61	1,527.43	1.23	1.10	2066.61
04/02/15	SV5013	INSTALL UPSTAGE	121.70	0.00	1,103.38	32.50	105.00	12.00	1,374.58	23	10	1,859.80	0.00	SL	1,843.57	1,362.58	1.23	1.10	1843.57
04/01/15	SV5014	INSTALL OVEN VE	211.29	0.00	0.00	0.00	0.00	0.00	211.29	23	10	285.88	0.00	SL	285.88	211.29	1.23	1.10	285.88
03/31/15	SV5015	INSTALL N2 FILT	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	SL	0.00	0.00	1.23	1.10	0
02/05/15	TM4009S	1 STOV CENTER P	15.15	0.00	30.88	0.00	0.00	0.00	46.03	23	10	62.28	62.28	SL	0.00	46.03	1.23	1.10	62.28
02/05/15	TM4010S	BRACKETS PER DR	39.70	0.00	246.30	0.00	0.00	0.00	286.00	15	10	361.79	361.79	SL	0.00	286.00	1.15	1.10	361.79
03/17/14	TT1015	INSTALL AIR PIP	268.54	201.76	975.20	13.00	230.00	0.00	1,688.50	15	10	2,135.96	109.28	SL	2,026.67	1,688.50	1.15	1.10	2135.95
01/31/12	TT2001	RELOCATE AIR LI	33.47	0.00	188.35	21.00	0.00	0.00	242.82	15	10	307.16	0.00	SL	307.17	242.82	1.15	1.10	307.17
03/02/15	TT2014S	FAB LIGHT FIXTU	8.93	50.29	102.06	0.00	45.00	0.00	206.28	15	10	260.94	155.15	SL	105.79	206.28	1.15	1.10	260.94
02/15/12	VT2001	CUT 20" SS PIPE	14.82	0.00	209.77	1.00	45.00	0.00	270.59	15	10	342.30	443.42	SL	0.00	270.59	1.15	1.10	342.3
02/28/15	YC5001S	MODIFY I BEAM	47.39	0.00	32.05	0.00	0.00	0.00	79.44	15	10	100.50	0.00	SL	100.49	79.44	1.15	1.10	100.49
04/02/15	YM5001S	MODIFY EQUIP	48.15	0.00	498.13	0.00	0.00	0.00	546.28	15	10	691.04	0.00	SL	691.04	546.28	1.15	1.10	691.04
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
						0.00	0.00	1	1.00	0
	TOTALS		27,042.09	10,571.52	167,180.56	3,682.11	10,260.19	40,562.47	259,298.94			322,459.91	78,128.95		199,681.90
	Work In Process					199,681.90

## Firm W.I.P.
	B & L Mechanical, Inc.
	Firm Jobs W.I.P. Report
	April 2, 2015
						Job Analysis (Experimental)
Date Last Activity	Job Number	Job Description	Materials	Non-Taxable And Subs	Labor and Burden	Misc Expense	Rental Expense	Open PO's	Actual Cost With Taxes JTD	OH %	Fee %	Total Commitment With Tax-OH-Fee	Total Billed - JTD	Proj. Mgr.	Contract Amount				Total Cost with Tax-OH-Fee (excludes Open PO's)	W.I.P Calc #1	W.I.P. Calc #2	W.I.P.	Indicator	(Potential) Loss [Problem] or Amount Left Unbilled [Uneasy]	WIP Analysis	Estimated Cost
02/18/15	33039	CLIPS	7136.27	394.15	171088.68	12.80	0.00	0.00	178631.90	0	10	196495.09	184545.00	DB	184545.00	178,631.90	1	1.10	196495.09	0.00	N/A	0.00	Problem	11,950.09	OK	166090.5
09/16/14	34057	REPAIR CORES	307.16	0.00	1790.89	0.00	61.46	0.00	2159.51	23	10	2921.82	2580.00	DB	2580.00	2,159.51	1.23	1.10	2921.82	0.00	N/A	0.00	Problem	341.82	OK	1728.6
09/16/14	34062C1	CITY WATER UPGR	1579.47	0.00	7623.88	2.00	273.78	0.00	9479.13	23	10	12825.26	12985.00	DB	12985.00	9,479.13	1.23	1.10	12825.26	-159.74	N/A	-159.74	OK	N/A	OK	8699.95
07/14/14	34062E	CITY WATER UPGR	0.00	0.00	0.00	0.00	4252.30	0.00	4252.30	0	9	4635.01	5000.00	DB	5000.00	4,252.30	1	1.09	4635.01	-364.99	N/A	-364.99	OK	N/A	OK	4550
01/05/15	34062V	CITY WATER UPGR	0.00	7422.20	0.00	0.00	0.00	0.00	7422.20	0	9	8090.20	8730.00	DB	8730.00	7,422.20	1	1.09	8090.2	-639.80	N/A	-639.80	OK	N/A	OK	7944.3
08/26/14	34062	CITY WATER PIPI	23404.94	0.00	31720.19	48.00	1445.26	0.00	56618.39	23	10	76604.68	61815.00	DB	61815.00	56,618.39	1.23	1.10	76604.68	0.00	N/A	0.00	Problem	14,789.68	OK	41416.05
08/14/14	34072S	FAB DUCT WORK &	1491.12	0.00	5193.73	6.00	0.00	0.00	6690.85	23	10	9052.73	9106.00	DB	9106.00	6,690.85	1.23	1.10	9052.72	-53.28	N/A	-53.28	OK	N/A	OK	6101.02
07/14/14	34072V	HM2 SHUT DOWN I	0.00	14647.00	0.00	0.00	0.00	0.00	14647.00	0	9	15965.23	15966.00	DB	15966.00	14,647.00	1	1.09	15965.23	-0.77	N/A	-0.77	OK	N/A	OK	14529.06
09/15/14	34072	TAPE PLANT DIE	3987.18	0.00	43203.01	80.00	524.00	0.00	47794.19	23	10	64665.54	45928.00	DB	45928.00	47,794.19	1.23	1.10	64665.54	0.00	N/A	0.00	Problem	18,737.54	OK	30771.76
03/11/15	34097	G-2 VACUUM PULL	233.32	131.25	3737.62	0.00	76.35	0.00	4178.54	23	10	5653.56	5800.00	DB	5800.00	4,178.54	1.23	1.10	5653.56	-146.44	N/A	-146.44	OK	N/A	OK	3886
01/06/15	34113S	FAB & DELIVER D	4969.84	599.62	13488.44	8.40	45.00	0.00	19111.30	15	10	24175.80	21865.00	DB	36436.00	19,111.30	1.15	1.10	24175.79	2,310.79	N/A	2,310.79	Uneasy	2,310.80	OK	27327
01/22/15	34113	HM1 UPGRADE DEM	233.63	0.00	10596.44	0.00	0.00	0.00	10830.07	23	10	14653.09	15668.00	DB	52225.00	10,830.07	1.23	1.10	14653.08	-1,014.92	N/A	-1,014.92	OK	N/A	OK	34990.75
09/30/14	34116V	FURNISH RIGGER	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	15696.00	0.00	1	1.09	0	0.00	0	0.00	OK	N/A	OK	14283.36
09/30/14	34116	INSTALL HM1 PLA	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	31975.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	21423.25
09/30/14	34117	HM1 UPGRADE DUC	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	59504.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	39867.68
01/15/15	34118S	HM1 DUCT FAB, M	5331.97	599.63	4691.91	0.00	0.00	0.00	10623.51	15	10	13438.74	12600.00	DB	41990.00	10,623.51	1.15	1.10	13438.74	838.74	N/A	838.74	Uneasy	838.74	OK	31492.5
09/30/14	34118V	DEMO INSULATION	0.00	0.00	0.00	0.00	0.00	43200.00	43200.00	0	9	47088.00	0.00	DB	47088.00	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	47,088.00	OK	42850.08
09/30/14	34118	HM1 1ST FLOOR D	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	47725.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	31975.75
10/31/14	34137V	HM1 INSULATE CO	0.00	0.00	0.00	0.00	0.00	3475.00	3475.00	0	10	3822.50	0.00	DB	3980.00	0.00	1	1.10	0	0.00	N/A	0.00	Uneasy	3,822.50	OK	3582
02/05/15	34137	HM1 AIR OPERATE	6278.67	350.00	12457.94	0.00	68.23	0.00	19154.84	23	10	25916.50	13105.00	DB	33380.00	19,154.84	1.23	1.10	25916.5	12,811.50	N/A	12,811.50	Uneasy	12,811.50	OK	22364.6
10/31/14	34138V	DEMO INSULATION	0.00	0.00	0.00	0.00	0.00	1700.00	1700.00	0	9	1853.00	0.00	DB	1875.00	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	1,853.00	OK	1706.25
10/31/14	34138	HM1 CONDENSATE	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	10875.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	7286.25
10/31/14	34141V	INSTALL 1 FREE	0.00	0.00	0.00	0.00	0.00	20996.00	20996.00	0	9	22885.64	0.00	DB	22885.64	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	22,885.64	OK	20825.93
10/31/14	34142V	FRANK CRUMB SAF	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	2455.00	0.00	1	1.09	0	0.00	0	0.00	OK	N/A	OK	2234.05
10/31/14	34142	ASSIST GREENVIL	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	2800.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	1876
03/12/15	34143	INSTALL G-2 NEW	0.00	0.00	4667.00	0.00	0.00	0.00	4667.00	23	10	6314.45	8690.00	DB	8690.00	4,667.00	1.23	1.10	6314.45	-2,375.55	N/A	-2,375.55	OK	N/A	OK	5822.3
01/27/15	34146S	RS8 FAB DUCT SU	448.65	0.00	2907.89	0.00	0.00	0.00	3356.54	23	10	4541.39	4606.06	DB	4606.06	3,356.54	1.23	1.10	4541.4	-64.66	N/A	-64.66	OK	N/A	OK	3086.06
02/18/15	34146	BLDG #9 RS8 DIV	492.91	0.00	17328.06	0.00	3256.64	0.00	21077.61	23	10	28518.01	24960.00	DB	24960.00	21,077.61	1.23	1.10	28518.01	0.00	N/A	0.00	Problem	3,558.01	OK	16723.2
03/19/15	34157	REPLACE G-2 EXT	28.43	892.75	4149.52	0.00	121.30	0.00	5192.00	23	10	7024.78	0.00	DB	10820.00	5,192.00	1.23	1.10	7024.78	7,024.78	N/A	7,024.78	Uneasy	7,024.78	OK	7249.4
03/02/15	34160V	SAFETY CONSULTA	0.00	17887.50	0.00	0.00	0.00	112.50	18000.00	0	9	19620.00	19620.00	DB	19620.00	17,887.50	1	1.09	19497.38	-122.63	N/A	-122.63	OK	N/A	OK	17854.2
03/18/15	34161	INSTALL ROTARY	653.80	0.00	10534.10	0.00	90.97	0.00	11278.87	23	10	15260.31	0.00	DB	17750.00	11,278.87	1.23	1.10	15260.31	15,260.31	N/A	15,260.31	Uneasy	15,260.31	OK	11892.5
01/08/15	34165S	HM2 TREATER FLA	93.15	0.00	521.05	0.00	0.00	0.00	614.20	23	10	831.02	0.00	DB	960.00	614.20	1.23	1.10	831.01	831.01	N/A	831.01	Uneasy	831.02	OK	643.2
02/18/15	34165	INSTALL TREATER	0.00	0.00	540.77	0.00	121.30	0.00	662.07	23	10	895.79	1535.00	DB	1535.00	662.07	1.23	1.10	895.78	-639.22	N/A	-639.22	OK	N/A	OK	1028.45
02/26/15	34169S	G3 DYE PLATFORM	1524.92	0.00	3801.84	0.00	0.00	0.00	5326.76	23	10	7207.10	0.00	DB	11418.00	5,326.76	1.23	1.10	7207.11	7,207.11	N/A	7,207.11	Uneasy	7,207.10	OK	7650.06
12/31/14	34173S	FAB G-3 HOPPER	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	1450.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	971.5
02/23/15	34174	INSTALL WDS EQU	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	1625.00	DB	1625.00	0.00	1.23	1.10	0	-1,625.00	-1088.75	-1,088.75	OK	N/A	OK	1088.75
03/05/15	34178	FAB & INSTALL B	34.35	0.00	669.82	0.00	99.24	0.00	803.41	23	10	1087.01	1110.00	DB	1110.00	803.41	1.23	1.10	1087.01	-22.99	N/A	-22.99	OK	N/A	OK	743.7
02/10/15	35001S	FAB DUCT	1.20	0.00	33.73	0.00	0.00	0.00	34.93	23	10	47.26	2500.00	DB	2500.00	34.93	1.23	1.10	47.26	-2,452.74	N/A	-2,452.74	OK	N/A	OK	1675
03/04/15	35001V	G-3 PHASE 2 CTR	0.00	5201.00	0.00	0.00	0.00	0.00	5201.00	23	10	7036.95	8500.00	DB	8500.00	5,201.00	1.23	1.10	7036.95	-1,463.05	N/A	-1,463.05	OK	N/A	OK	5695
02/19/15	35001	G-3 PHASE 2 CTR	2623.66	0.00	6696.04	14.00	1853.14	0.00	11186.84	23	10	15135.79	14500.00	DB	14500.00	11,186.84	1.23	1.10	15135.79	0.00	N/A	0.00	Problem	635.79	OK	9715
02/26/15	35003	SOLUTION HANDLI	884.19	0.00	1534.55	87.19	0.00	0.00	2505.93	23	10	3390.52	3426.00	DB	3426.00	2,505.93	1.23	1.10	3390.52	-35.48	N/A	-35.48	OK	N/A	OK	2295.42
03/26/15	35004	REBUILD CLIPS	200.74	0.00	24923.01	0.00	0.00	0.00	25123.75	23	10	33992.43	13905.00	DB	26865.00	25,123.75	1.23	1.10	33992.43	12,960.00	N/A	12,960.00	Problem	7,127.43	OK	17999.55
01/31/15	35006	REPLACEMENT OF	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	19050.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	12763.5
03/05/15	35007S	FAB BERRINGER F	13.92	0.00	125.44	0.00	0.00	0.00	139.36	23	10	188.55	500.00	DB	500.00	139.36	1.23	1.10	188.55	-311.45	N/A	-311.45	OK	N/A	OK	335
03/05/15	35007	BERRINGER EXHAU	187.20	0.00	1881.99	0.00	0.00	0.00	2069.19	23	10	2799.61	3980.00	DB	3980.00	2,069.19	1.23	1.10	2799.61	-1,180.39	N/A	-1,180.39	OK	N/A	OK	2666.6
02/04/15	35008M	PURCHASE 1" X 2	1667.94	0.00	0.00	0.00	0.00	0.00	1667.94	0	9	1818.05	1650.00	DB	1650.00	1,667.94	1	1.09	1818.05	0.00	N/A	0.00	Problem	168.05	OK	1501.5
02/03/15	35008S	WATER JET 1" LE	100.00	0.00	126.07	0.00	0.00	0.00	226.07	23	10	305.88	325.00	DB	325.00	226.07	1.23	1.10	305.87	-19.13	N/A	-19.13	OK	N/A	OK	217.75
02/26/15	35009	INSTALL DOOR ON	80.30	0.00	2843.58	0.00	76.35	0.00	3000.23	23	10	4059.31	3916.00	DB	3916.00	3,000.23	1.23	1.10	4059.31	0.00	N/A	0.00	Problem	143.31	OK	2623.72
01/31/15	35010V	INSTALL NEW SPE	0.00	0.00	0.00	0.00	0.00	15319.00	15319.00	0	9	16697.71	0.00	DB	16697.71	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	16,697.71	OK	15194.92
02/12/15	35014	CUT TAPE OFF CO	0.00	0.00	912.36	0.00	0.00	0.00	912.36	23	10	1234.42	0.00	DB	5960.00	912.36	1.23	1.10	1234.42	1,234.42	N/A	1,234.42	Uneasy	1,234.42	OK	3993.2
03/26/15	35015	PURCHASE 13" NO	2084.83	0.00	7125.07	0.00	90.97	0.00	9300.87	0	9	10137.95	0.00	DB	5045.00	9,300.87	1	1.09	10137.95	5,045.00	N/A	5,045.00	Problem	5,092.95	OK	4590.95
02/28/15	35017	TRANE RAIL- RIG	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	890.00	DB	890.00	0.00	1.23	1.10	0	-890.00	-596.3	-596.30	OK	N/A	OK	596.3
03/18/15	35018	INSTALL AIR SHO	28.43	0.00	4422.80	0.00	90.97	0.00	4542.20	23	10	6145.60	0.00	DB	11900.00	4,542.20	1.23	1.10	6145.6	6,145.60	N/A	6,145.60	Uneasy	6,145.60	OK	7973
03/12/15	35019S	ALUM GASKETS	996.60	0.00	1585.68	0.00	0.00	0.00	2582.28	23	10	3493.82	3520.00	DB	3520.00	2,582.28	1.23	1.10	3493.82	-26.18	N/A	-26.18	OK	N/A	OK	2358.4
03/12/15	35021S	FAB VIBRATOR BR	529.83	0.00	1019.51	0.00	0.00	0.00	1549.34	23	10	2096.26	0.00	DB	2150.00	1,549.34	1.23	1.10	2096.26	2,096.26	N/A	2,096.26	Uneasy	2,096.26	OK	1440.5
02/28/15	35021	INSTALL VIBRATO	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	9500.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	6365
03/25/15	35022S	G-3 PLENIUM FAB	245.38	0.00	827.78	0.00	0.00	0.00	1073.16	23	10	1451.99	1455.00	DB	1455.00	1,073.16	1.23	1.10	1451.99	-3.01	N/A	-3.01	OK	N/A	OK	974.85
03/26/15	35023S	FAB & DELIVER H	697.02	0.00	3325.89	0.00	0.00	1.00	4023.91	23	10	5444.35	0.00	DB	6500.00	4,022.91	1.23	1.10	5443	5,443.00	N/A	5,443.00	Uneasy	5,444.35	OK	4355
02/28/15	35023V	INSULATE HVAC D	0.00	0.00	0.00	0.00	0.00	1375.00	1375.00	0	9	1498.75	0.00	DB	1500.00	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	1,498.75	OK	1365
03/25/15	35023	INSTALL HVAC &	0.00	0.00	3219.49	39.00	790.65	0.00	4049.14	23	10	5478.48	0.00	DB	9950.00	4,049.14	1.23	1.10	5478.49	5,478.49	N/A	5,478.49	Uneasy	5,478.48	OK	6666.5
03/31/15	35024	HM1 SHUTDOWN UN	45.77	0.00	2233.21	0.00	90.97	0.00	2369.95	23	10	3206.54	0.00	DB	3220.00	2,369.95	1.23	1.10	3206.54	3,206.54	N/A	3,206.54	Uneasy	3,206.54	OK	2157.4
03/31/15	35025E	RENTAL EQUIPMEN	0.00	0.00	0.00	0.00	0.00	962.95	962.95	0	10	1059.25	0.00	DB	1800.00	0.00	1	1.10	0	0.00	N/A	0.00	Uneasy	1,059.25	OK	1620
03/31/15	35025	INSTALL VACUUM	2995.22	0.00	7975.52	0.00	1400.41	10.00	12381.15	23	10	16751.69	0.00	DB	17900.00	12,371.15	1.23	1.10	16738.17	16,738.17	N/A	16,738.17	Uneasy	16,751.69	OK	11993
03/31/15	35026	REPAIR 12 DAMAG	28.73	0.00	1713.29	0.00	90.97	0.00	1832.99	23	10	2480.04	2580.00	DB	2580.00	1,832.99	1.23	1.10	2480.04	-99.96	N/A	-99.96	OK	N/A	OK	1728.6
03/31/15	35027V	PAINT 3M GUARD	0.00	0.00	0.00	0.00	0.00	1750.00	1750.00	0	9	1907.50	0.00	DB	1907.50	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	1,907.50	OK	1735.83
03/31/15	35028S	FAB G-1 FILTER	6867.69	0.00	1076.52	0.00	0.00	10434.52	18378.73	23	10	24866.42	0.00	DB	39200.00	7,944.21	1.23	1.10	10748.52	10,748.52	N/A	10,748.52	Uneasy	24,866.42	OK	26264
03/31/15	35029S	FAB ALUM KNIFE	87.73	0.00	629.71	0.00	0.00	59.81	777.25	23	10	1051.62	1200.00	DB	1200.00	717.44	1.23	1.10	970.7	-229.30	N/A	-229.30	OK	N/A	OK	804
03/31/15	35030	INSTALL BAFFLES	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	33100.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	22177
03/31/15	35031V	INSTALL SCAFFOL	0.00	0.00	0.00	0.00	0.00	3295.52	3295.52	0	9	3592.12	0.00	DB	3592.12	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	3,592.12	OK	3268.83
03/31/15	35032S	PURCHASE NORFAB	0.00	0.00	0.00	0.00	0.00	182.56	182.56	23	10	247.01	0.00	DB	21750.00	0.00	1.23	1.10	0	0.00	N/A	0.00	Uneasy	247.01	OK	14572.5
03/31/15	35032V	SAFETY OBSERVAT	0.00	300.00	0.00	0.00	0.00	0.00	300.00	0	9	327.00	0.00	DB	327.00	300.00	1	1.09	327	327.00	N/A	327.00	Uneasy	327.00	OK	297.57
03/31/15	35033	PURCHASE BLINDS	0.00	0.00	0.00	0.00	0.00	478.06	478.06	0	9	521.09	0.00	DB	521.09	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	521.09	OK	474.19
03/31/15	35034	REMOVE CITY WAT	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	1580.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	1058.6
03/31/15	35035	INSTALL VACUUM	0.00	0.00	769.81	0.00	0.00	0.00	769.81	23	10	1041.56	0.00	DB	1180.00	769.81	1.23	1.10	1041.55	1,041.55	N/A	1,041.55	Uneasy	1,041.56	OK	790.6
03/31/15	35037	SCRAP WINDERS A	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	1698.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	1137.66
03/31/15	35038	TEST BACK FLOWS	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	1040.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	696.8
03/31/15	35039E	RENT 7 WELDING	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	2715.00	0.00	1	1.09	0	0.00	0	0.00	OK	N/A	OK	2470.65
01/31/14	3FE4005	PATCH HOLES & P	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	DB	1308.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	876.36
01/27/15	3FM4106	REPAIR G-2 FILT	0.00	1675.00	0.00	0.00	0.00	2100.00	3775.00	0	9	4114.75	4114.75	DB	4114.75	1,675.00	1	1.09	1825.75	-2,289.00	N/A	-2,289.00	OK	N/A	OK	3744.42
02/23/15	3FM5008	REPAINT EAST EX	0.00	0.00	0.00	0.00	0.00	1760.00	1760.00	0	9	1918.40	0.00	DB	1907.50	0.00	1	1.09	0	0.00	N/A	0.00	Problem	10.90	OK	1735.83
02/25/15	3FM5013	REPLACE RECLAIM	131.56	0.00	1287.69	0.00	1570.02	0.00	2989.27	23	10	4044.48	5040.00	DB	5040.00	2,989.27	1.23	1.10	4044.48	-995.52	N/A	-995.52	OK	N/A	OK	3376.8
03/12/15	3FM5014	INSTALL G-1 CEN	299.14	0.00	1263.26	0.00	0.00	0.00	1562.40	23	10	2113.93	1920.00	DB	1920.00	1,562.40	1.23	1.10	2113.93	0.00	N/A	0.00	Problem	193.93	OK	1286.4
02/28/15	3FM5015	DEMO G-1 PACKAG	28.43	0.00	1440.70	0.00	83.97	0.00	1553.10	23	10	2101.34	2415.00	DB	2415.00	1,553.10	1.23	1.10	2101.34	-313.66	N/A	-313.66	OK	N/A	OK	1618.05
03/18/15	3FM5017	RENT 3 TON LULL	0.00	0.00	0.00	0.00	2877.23	0.00	2877.23	0	9	3136.18	0.00	DB	3075.00	2,877.23	1	1.09	3136.18	3,075.00	N/A	3,075.00	Problem	61.18	OK	2798.25
02/28/15	3FM5019E	RENT 19' SCISSO	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	10	0.00	0.00	DB	847.44	0.00	1	1.10	0	0.00	0	0.00	OK	N/A	OK	762.7
03/12/15	3FM5019	DEMO CHILLED WA	28.73	0.00	1163.30	0.00	0.00	0.00	1192.03	23	10	1612.82	0.00	DB	6850.00	1,192.03	1.23	1.10	1612.82	1,612.82	N/A	1,612.82	Uneasy	1,612.82	OK	4589.5
02/28/15	3FM5020	STEAM REGULATOR	0.00	0.00	936.50	0.00	0.00	850.00	1786.50	23	10	2417.14	0.00	DB	8812.00	936.50	1.23	1.10	1267.08	1,267.08	N/A	1,267.08	Uneasy	2,417.14	OK	5904.04
03/17/15	3FM5021	G-1 6TH FLOOR K	0.00	750.00	0.00	0.00	0.00	0.00	750.00	23	10	1014.75	750.00	DB	750.00	750.00	1.23	1.10	1014.75	0.00	N/A	0.00	Problem	264.75	OK	502.5
03/31/15	3FM5022	REPAIR ROOF LEA	0.00	2613.32	0.00	0.00	0.00	0.00	2613.32	0	9	2848.52	2848.52	DB	2848.52	2,613.32	1	1.09	2848.52	0.00	N/A	0.00	OK	N/A	OK	2592.15
03/31/15	3FM5024	REPAIR G-1 T-66	0.00	0.00	0.00	0.00	0.00	1125.00	1125.00	0	9	1226.25	0.00	DB	1226.25	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	1,226.25	OK	1115.89
03/31/15	3FM5026	REPAIT THE G-3	25.12	0.00	797.57	0.00	0.00	0.00	822.69	23	10	1113.10	1255.00	DB	1255.00	822.69	1.23	1.10	1113.1	-141.90	N/A	-141.90	OK	N/A	OK	840.85
03/31/15	3FM5027	SUB HYDROCHEM T	0.00	0.00	0.00	0.00	0.00	6825.00	6825.00	0	9	7439.25	0.00	DB	7439.25	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	7,439.25	OK	6769.72
03/31/15	3FM5029	CLEAN & PAINT R	0.00	0.00	0.00	0.00	0.00	14178.69	14178.69	0	9	15454.77	0.00	DB	15454.88	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	15,454.77	OK	14063.94
03/31/15	3FM5031	CO2 BLAST THE G	864.16	3650.00	0.00	0.00	0.00	0.00	4514.16	23	10	6107.66	4920.44	DB	4920.44	4,514.16	1.23	1.10	6107.66	0.00	N/A	0.00	Problem	1,187.22	OK	3296.69
03/31/15	3FM5033	PRSSURE VESSEL	0.00	0.00	0.00	0.00	0.00	6250.00	6250.00	0	9	6812.50	0.00	DB	6812.50	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	6,812.50	OK	6199.38
03/31/15	3FM5034	CODE REPAIRS ON	387.05	0.00	6817.48	0.00	0.00	20.00	7224.53	0	10	7946.98	0.00	DB	9680.00	7,204.53	1	1.10	7924.98	7,924.98	N/A	7,924.98	Uneasy	7,946.98	OK	8712
03/31/15	3FM5035	MISC PAINTING O	0.00	0.00	0.00	0.00	0.00	10600.00	10600.00	0	9	11554.00	0.00	DB	11554.00	0.00	1	1.09	0	0.00	N/A	0.00	Uneasy	11,554.00	OK	10514.14
03/31/15	3FM5037	SCAFFOLDING FOR	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	6019.19	0.00	1	1.09	0	0.00	0	0.00	OK	N/A	OK	5477.46
07/31/14	AB4102	MODIFY THEIS PL	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	TD	1300.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	871
03/25/15	AB5007	BUILD BASE PLAT	1006.97	0.00	468.21	0.00	0.00	0.00	1475.18	23	10	1995.92	2824.00	TD	2824.00	1,475.18	1.23	1.10	1995.92	-828.08	N/A	-828.08	OK	N/A	OK	1892.08
03/31/15	AB5009	R200 STEAM SNUF	0.00	0.00	683.25	0.00	0.00	10.00	693.25	23	10	937.97	0.00	TD	1717.00	683.25	1.23	1.10	924.44	924.44	N/A	924.44	Uneasy	937.97	OK	1150.39
03/31/15	AD5001	INSTALL NATURAL	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	JC	2568.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	1720.56
03/24/15	AE5001V	SAFETY CONSULTA	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	495.00	DB	495.00	0.00	1	1.09	0	-495.00	-450.45	-450.45	OK	N/A	OK	450.45
03/31/15	AE5002V	SAFETY TRAINING	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	408.75	DB	408.75	0.00	1	1.09	0	-408.75	-371.96	-371.96	OK	N/A	OK	371.96
02/25/15	BB5002	FAB & INSTALL S	0.00	0.00	843.11	66.00	30.00	0.00	939.11	23	10	1270.62	1271.00	TD	3447.00	939.11	1.23	1.10	1270.62	-0.38	N/A	-495.00	OK	N/A	OK	2309.49
02/28/15	CA5001V	SAFETY CONSULTA	0.00	450.00	0.00	0.00	0.00	0.00	450.00	0	9	490.50	0.00	DB	490.50	450.00	1	1.09	490.5	490.50	N/A	490.50	Uneasy	490.50	OK	446.36
03/26/15	CB5001	REPAIR BALER DO	439.22	0.00	2872.11	0.00	90.00	0.00	3401.33	23	10	4602.00	0.00	SL	5865.00	3,401.33	1.23	1.10	4602	4,602.00	N/A	-0.38	Uneasy	4,602.00	OK	3929.55
03/31/15	EN5001	CHILLWATER PIPI	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	0.00	JC	5283.00	0.00	1.23	1.10	0	0.00	0	0.00	OK	N/A	OK	3539.61
03/18/15	FQ4005	INSTALL (7) CLE	1062.62	0.00	1931.32	915.60	259.00	0.00	4168.54	23	10	5640.03	5222.98	TD	5222.98	4,168.54	1.23	1.10	5640.03	0.00	N/A	4,602.00	Problem	417.05	OK	3499.4
03/31/15	FQ5001	CLEAN COOLING T	0.00	0.00	0.00	0.00	0.00	25.19	25.19	23	10	34.08	0.00	TD	2867.00	0.00	1.23	1.10	0	0.00	N/A	0.00	Uneasy	34.08	OK	1920.89
03/31/15	HC5001	HVAC REPLACEMEN	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	10	0.00	0.00	JC	297274.00	0.00	1	1.10	0	0.00	0	0.00	OK	N/A	OK	267546.6
01/07/15	HK4003	FABRICATE BOX	637.86	0.00	891.30	45.50	0.00	0.00	1574.66	23	10	2130.51	1942.00	JC	1942.00	1,574.66	1.23	1.10	2130.51	0.00	N/A	0.00	Problem	188.51	OK	1301.14
02/28/15	HR5001V	SAFETY TRAINING	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	0.00	DB	350.00	0.00	1	1.09	0	0.00	0	0.00	OK	N/A	OK	318.5
02/28/15	M5003S	SQ TO ROUND	0.00	0.00	93.73	0.00	45.00	0.00	138.73	23	10	187.70	355.00	SL	355.00	138.73	1.23	1.10	187.7	-167.30	N/A	-167.30	OK	N/A	OK	237.85
02/09/15	NP4014	PRESSURE WASHER	0.00	0.00	0.00	0.00	0.00	0.00	0.00	23	10	0.00	300.00	TD	300.00	0.00	1.23	1.10	0	-300.00	-201	-201.00	OK	N/A	OK	201
01/19/15	SB4001	INSTALL FAN & L	7811.90	1585.00	4282.43	0.00	450.00	0.00	14129.33	23	10	19116.99	18122.00	JC	18122.00	14,129.33	1.23	1.10	19116.98	0.00	N/A	0.00	Problem	994.99	OK	12141.74
03/26/15	SC5001	RELOCATE TWO HE	1605.15	223.17	11049.64	249.00	6233.88	0.00	19360.84	23	10	26195.21	28948.00	TD	28948.00	19,360.84	1.23	1.10	26195.22	-2,752.78	N/A	-300.00	OK	N/A	OK	19395.16
03/04/15	SE5001	INSTALL HOT WAT	247.73	0.00	980.97	2.00	45.00	0.00	1275.70	23	10	1726.02	3226.00	JC	3226.00	1,275.70	1.23	1.10	1726.02	-1,499.98	N/A	-1,499.98	OK	N/A	OK	2161.42
03/19/15	SM5003	INSTALL N2 COPP	9324.49	0.00	7379.72	28.00	1671.01	0.00	18403.22	15	10	23280.07	0.00	SL	27975.00	18,403.22	1.15	1.10	23280.07	23,280.07	N/A	-2,752.78	Uneasy	23,280.07	OK	20981.25
03/26/15	SV5009S	FAB AL6XN PIPIN	37.50	0.00	4171.85	0.00	45.00	0.00	4254.35	23	10	5756.14	0.00	SL	16950.00	4,254.35	1.23	1.10	5756.14	5,756.14	N/A	5,756.14	Uneasy	5,756.14	OK	11356.5
03/26/15	SV5009	INSTALL AL6XN P	10684.18	0.00	896.70	12.00	90.00	41.07	11723.95	23	10	15862.51	0.00	SL	16950.00	11,682.88	1.23	1.10	15806.94	15,806.94	N/A	23,280.07	Uneasy	15,862.51	OK	11356.5
03/31/15	TF5001V	SAFETY TRAINING	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0	9	0.00	245.75	DB	245.75	0.00	1	1.09	0	-245.75	-223.63	-223.63	OK	N/A	OK	223.63
02/18/15	TM4011S	1000 JOINT SEGM	1001.17	0.00	863.18	0.00	0.00	0.00	1864.35	15	10	2358.40	2304.00	SL	2304.00	1,864.35	1.15	1.10	2358.4	0.00	N/A	15,806.94	Problem	54.40	OK	1728
03/31/15	TT5003S	30 SWADGING	0.00	0.00	67.22	0.00	0.00	0.00	67.22	23	10	90.95	150.00	SL	150.00	67.22	1.23	1.10	90.95	-59.05	N/A	-59.05	OK	N/A	OK	100.5
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0
						0.00	1	1.00	0	0.00	0	0.00	OK	N/A	OK	0

	SUBTOTALS		114,219.14	59,371.59	476,895.07	1,615.49	28,410.37	147,136.87	827,648.53			1,016,200.21	629,764.25		1,715,308.82	680,511.66					157,288.34		385,393.72		1,329,093.49
	GRAND TOTALS		114,219.14	59,371.59	476,895.07	1,615.49	28,410.37	147,136.87	827,648.53			1,016,200.21	629,764.25		1,715,308.82	680,511.66					157,288.34				1,329,093.49
	PERCENTAGE		1.00	1.00	1.00	1.00	1.00	1.00	1.00			1.00	1.00		1.00	1.00					1.00				1.00
		Work In Process					181,488.74
		Billing in Excess of Costs					-24,200.40

						Key:
						Problem	means	We've spent (or committed) over the contract amount
						Uneasy	means	We've spent (or committed) more than we have billed.
						OK	means	No worries :)