## Sheet1
Task	Nbr.	Dependency	DL	Est. / time	Est. start	Est. finish	State	Updated / State
COMPLETE CONTRACT	1	5
Complete the sale and get access!	2		*		17-Dec-2014	17-Dec-2014	c
Finalise the building & electrical work to be done.	3		*				c
Finalise the design of new kitchen so Dan can give a cost estimate to Jason.	4		*				c
Finalise Jason Stokes' quote and sign a contract.	5	2,3,4	*		04-Aug-2015	04-Aug-2015	c

PREPARATION #1 - Jason	10	11,12
Seal rodent entry points.	11	1			13-Aug-2015	14-Aug-2015
Remove ducted A/C, overhaul Daikin system.	12	1			14-Aug-2015	14-Aug-2015

PREPARATION #2 - Jason	14	15,16,17,18,19
Disconnect kitchen, etc (plumber, electrician).	15	1			13-Aug-2015	14-Aug-2015
Remove all the floor coverings.	16	1			17-Aug-2015	21-Aug-2015
Remove kitchen	17	1			17-Aug-2015	21-Aug-2015
Remove fuel stove	18	1			17-Aug-2015	21-Aug-2015
Any other demolition	19	1			17-Aug-2015	21-Aug-2015

PREPARATION - RB	20	21,22,23,24,25
Buy exhaust fan, cooktop, oven, dishwasher.	21	1	*		03-Aug-2015
Buy wall lights and/or a pendant light for living room.	22	1	*		03-Aug-2015
Clean the ceiling space	23	10	*		17-Aug-2015
Consult Jason's TV antenna & wiring person.	24	23	*		?
Wash the walls in the living area & hall (at least).	25	14	*		24-Aug-2015	02-Sep-2015

ELECTRICAL	30	31,32
Electrical rough-in	31				26-Aug-2015	26-Aug-2015
Gas rough-in (for possible gas log fire)	32				26-Aug-2015	26-Aug-2015

PAINTING	40	41,42
Patch All Walls & Cornice ETC	41	15,20,30			03-Sep-2015
Paint the interior.	42	41			14-Sep-2015

INSTALL NEW KITCHEN	50				07-Sep-2015

FINISH ELECTRICAL & GAS WORK	60				15-Sep-2015

TIMBER FLOORING	70
Get an initial quote for the timber flooring.	71		*		15-May-2015	15-May-2015	c
Level the slab where necessary (“3mm in 3 metres”).	72		*
Sydney Flooring to inspect the job & confirm quote.	73		*
Install the new timber flooring.	74		*		15-Sep-2015	18-Sep-2015

CARPETING	80
Get a quote for new carpets.			*
Order carpets.			*
Deliver & onstall carpets.			*

OTHER BUILDING WORK	90
Replace the laundry ramp & landing.	91				31-Aug-2015
Install the new bathroom access and sliding door to laundry.	92				27-Aug-2015
Install bathroom skylight shaft	93				27-Aug-2015
Install skylight	94				26-Aug-2015
Repair the crushed downpipe near the garage, fix the roof tiling near its flue and the ducted A/C flue.	95				01-Sep-2015
Fit architraves & skirting	96				08-Sep-2015

	State	Definition					Next state
	P	Pending - waiting on dependency(ies)					R
	R	Ready to begin					W
	W	Work in progress					C
	I	Interrupted					R
	C	Completed					C