## Meeting Details
CHANGE ADVISORY BOARD
CAB Week : 6th May 2015. 02:00 PM CET
Contact Details |  |  | Agenda
Meeting scheduled to be held: |  | 6th May 2015. 02:00 PM CET | 1 | Review & discuss previous meeting action items
Location: |  | Teleconference | 2 | Review changes unclosed
Teleconference Number: |  |  | 3 | Review & discuss emergency & failed changes implemented in the last 7 days
PIN: |  |  | 4 | Closed changes implemented in the last 7 days
Next meeting to be held: |  |  | 5 | Review & discuss proposed changes for implementation
Review Of Previous Meeting Action Items
CR NUMBER | SUBMITTER | COMMENTS |  |  | Status
Comments and Action Items
CR NUMBER | SUBMITTER | COMMENTS |  |  | Status

## Attendance
CHANGE ADVISORY BOARD
CAB Week : 6th May 2015. 02:00 PM CET
Department | Invitees | % Attended | % Missed | 2015-05-06 | 2015-05-13 | 2015-05-20 | 2015-05-27

## Unclosed
CHANGE ADVISORY BOARD
CAB Week : 6th May 2015. 02:00 PM CET
Review of changes not marked as COMPLETED/CLOSED: Including Major/Minor Changes (Defined as changes which have gone 24 hours past the End Date & Time and have a status other than COMPLETED/CLOSED)
Customer Company*+ | Change ID*+ | Scheduled Start Date+ | Scheduled End Date+ | Outage Involved | Outage Start Date/Time | Outage End Date/Time | Timing* | Impact* | Lead Time (in Days) | Business Unit Impacted | Status* | Summary* | Notes | Change Environment | Submit Date | Implementer Support Group Name+ | Change Implementer | Change Manager | Comments
None
Total - 00

## -7 Days Emergency & Failed
CHANGE ADVISORY BOARD
CAB Week : 6th May 2015. 02:00 PM CET
Review & discuss all emergency and failed changes implemented in the last 7 days (Emergency changes are in response to a Severity 1 or 2 incident record that need to be implemented immediately due to a failure or imminent failure of a critical system or infrastructure.) (Failed changes are changes that did not successfully achieved the outcomes documented in the RFC or did not meet the requirements of the Change Management Process.)
Customer Company*+ | Change ID*+ | Scheduled Start Date+ | Scheduled End Date+ | Outage Involved | Outage Start Date/Time | Outage End Date/Time | Timing* | Impact* | Lead Time (in Days) | Business Unit Impacted | Status* | Summary* | Notes | Change Environment | Submit Date | Implementer Support Group Ne+ | Change Implementer | Change Manager | Comments
Emergency Changes
| XX | 2015-04-29 | 2015-04-29 | No | No | No | 18:00:00 to 19:00:00 CEST | No | 1 | XX | Completed Successfully | YYY |  | Production | 2015-04-29 | SS | ZZ | ZZ
| XX | 2015-05-02 | 2015-05-02 | Yes | 02-05-2015/5:30 CEST | 02-05-2015/ 16:30 CEST | 5:30:00 to 16:30:00 CEST | Yes | 1 | XX | Completed Successfully | YYY |  | Production | 2015-04-29 | SS | ZZ | ZZ
| XX | 2015-04-30 | 2015-04-30 | No | No | No | 19:00:00 to 20:00:00 CEST | No | 1 | XX | Completed Successfully | YYY |  | Production | 2015-04-30 | SS | ZZ | ZZ
| XX | 2015-05-05 | 2015-05-05 | No | No | No | 20:15:00 to 21:15:00 CEST | No | 0 | XX | Completed Successfully | YYY |  | Production | 2015-05-06 | SS | ZZ | ZZ
Total - 04
Failed Changes
| CR-UN-290402 | 2015-04-30 | 2015-05-01 | No | No | No | 07:00:00 to 19:30:00 CEST | No | 1 | BD Corp (Luxembourg) | Change Failed | Installation of CA Nimsoft robot agent for Linux Servers monitoring in Test env |  | Test | 2015-04-29 | Unix | Vishal Malik | Shalabh Yadav/Parijit Nath
Total - 01

## - 7 Days Sucessful & Ongoing
CHANGE ADVISORY BOARD
CAB Week : 6th May 2015. 02:00 PM CET
Review of changes implemented in the last 7 days Or currently in their change windows
Customer Company*+ | Change ID*+ | Scheduled Start Date+ | Scheduled End Date+ | Outage Involved | Outage Start Date/Time | Outage End Date/Time | Timing* | Impact* | Lead Time (in Days) | Business Unit Impacted | Status* | Summary* | Notes | Change Environment | Submit Date | Implementer Support Group Name+ | Change Implementer | Change Manager | Comments
Successful Changes
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 19:00:00 to 20:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 20:00:00 to 21:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 18:00:00 to 19:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 18:00:00 to 19:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 21:00:00 to 22:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 22:00:00 to 23:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
XX | YY | 2015-04-29 | 2015-04-29 | No | No | No | 21:00:00 to 22:00:00 CEST | No | 3 | ZZ | Completed Successfully | VV |  | Production | 2015-04-28 | SS | SS | SS
Total - 10
Ongoing Changes
AM | CR-AD-2701-01 | 2015-04-28 | 2015-05-08 | No | No | No | 22:00:00 to 08:00:00 CEST | No | 1 | BD Corp | In Progress | Implementation of prerequisites before migration |  | Production | 2015-04-27 | Benoit Leroux (AD - Telindus company) |  | Shalabh Yadav/ Parijit Nath
Total - 01

## Future Changes
CHANGE ADVISORY BOARD
CAB Week : 6th May 2015. 02:00 PM CET
Review & discuss planned changes for implementation as required: XX (Review in detail, all major changes and other changes as deemed required by the CCB and refine the proposed change schedule in light of change conflicts and timing issues)
Customer Company*+ | Change ID*+ | Scheduled Start Date+ | Scheduled End Date+ | Outage Involved | Outage Start Date/Time | Outage End Date/Time | Timing* | Impact* | Lead Time (in Days) | Business Unit Impacted | Status* | Summary* | Notes | Change Environment | Submit Date | Implementer Support Group Name+ | Change Implementer | Change Manager | Comments
Future Changes:
Major Changes:
None
Minor Changes:
XX | XX | 16-05-2015 | 2015-06-05 | Yes | Please see comments |  | 16-05-2015: 12:00:00 to 05-06-2015 : 7:30:00 CEST | No | 3 | XX | Awaiting Review | XX |  | XX | 2015-05-04 | XX | XX | XX
XX | XX | 2015-05-06 | 2015-05-06 | No | No | No | 06-05-2015 : 16:00:00 to 18:00:00 CEST | No | 3 | XX | Awaiting Review | XX |  | XX | 2015-04-30 | XX | XX | XX
XX | XX | 2015-05-08 | 2015-05-08 | No | No | No | 08-05-2015 : 09:00:00 to 18:00:00 CEST | No | 3 | XX | Awaiting Review | XX |  | XX |  | XX | XX | XX
XX | XX | 2015-05-07 | 2015-05-07 | No | No | No | 07-05-2015 : 19:00:00 to 20:00:00 CEST | No | 3 | XX | Awaiting Review | XX |  | XX |  | XX | XX | XX
XX | XX | 2015-05-06 | 2015-05-06 | No | No | No | 06-05-2015 : 17:00:00 to 18:00:00 CEST | No | 1 | XX | Awaiting Review | XX |  | XX |  | XX | XX | XX
Standard Changes:
None
Late Arrival:
Rejected Changes: Action Required
Note on F10: Downtime Start Date/Time 16-05-2015 12:00 AM Downtime End Date/Time 17-05-2015 11:59 PM Downtime Start Date/Time 23-05-2015 12:00 AM Downtime End Date/Time 24-05-2015 11:59 PM Downtime Start Date/Time 30-05-2015 12:00 AM Downtime End Date/Time 31-05-2015 11:59 PM

## Process Reminders
CHANGE ADVISORY BOARD
Date | Client specific process | Agreed with