TABLE of DELIVERABLES and MILESTONES
WPs	Title and nature of deliverables and milestones	Nature of deliverables	Delivery date	Partner responsible of the deliverable/Milestone
1	Specification of data recording parameters	Internal report	T0 + 2	Ifsttar
	Installation, instrumentation and testing of two PTWs / -trajectory measurement (WPs 2, 4, 5) / -information transmission to the rider (WPs 4, 5) / -trajectory prediction (onboard calculator, WP 4) / Installation, instrumentation and testing of one PTW / Measuring the riding parameters and the rider/PTW interactions (WP 3)	Material and internal report	T0 + 6 / T0 + 15 / T0 + 24 / T0 + 12	UPSud
	Identification of geometric and inertial parameters / (WP 4)	Internal report	T0 + 9	UEVE
	Vehicle trajectory visualization system (WPs 2, 5)	Material, Software and internal report	T0 + 8	Ifsttar
	Simulator instrumentation (WP 5)	Material and internal report	T0 + 28	UPSud
2	off-line “accurate” Trajectory prediction module	Software and internal report	T0+20	Ifsttar
	on-line “accurate” Trajectory prediction module	Software and internal report	T0+24	UEVE
3	Data base of real riding practices	Database and internal report	T0 + 16	Ifsttar
	Development of a PTW rider model	Software and internal report	T0 + 40	Irccyn
4	Warning Curve module	Software and internal report	T0+37	UEVE
5	Design of an “off-line” system for the evaluation of motorcycle paths, which is usable in riding schools	Software and internal report	T0+26	ENPC-Editions
	Design of dynamics models for a low cost simulator, and tests		T0+26	Ifsttar
	Design of dynamics models for high end simulator, and tests		T0+32	Ifsttar
	Development of simulator scenarios for safe bend-taking and evaluation		T0+32	ENPC-Editions
	Design of an “on-line” evaluation device for bend-taking, usable in riding schools and with trainees (ITS)		T0+42	ENPC-Editions
6	Consortium agreement signed by all partners		T0 + 12	Ifsttar
	Progress reports	ANR report	T0 + 6 / T0 + 18
	Web-site of the project		T0 + 12
	Minutes of meetings of the project	ANR report
	Final report	ANR report	T0 + 43
	Users forum		T0 + 26 / T0 + 42