## Release Dates and Revisions
Release dates, corrections and revisions
Document release dates, corrections and revisions are listed below.
Table 1: Release Dates and Revisions
Date | Comments | Author | QA
2009-12-11 | Creation | Baracos

## Introduction
1 | Introduction
1.1 | Project Overview
The City of Calgary Reversible Lane Control System comprises central servers, cameras, PLC, gates, signal heads and signs. Its mission is to safely and effectively control and monitor the operation of traffic lane reversals in the project area.
1.2 | Document Roll within the Project Test Plan
This document provides a guide to the System Integration and Acceptance Test (in Calgary The relationship of this documents among the various elements defined by the Project Test Plan is shown below.
Project Test Plan
|  | Preliminary SW Validation Workshop | Control Panel Factory Acceptance | System Factory Acceptance (also know as System Pre-Integration) | System Integration and Acceptance
1.3 | Purpose
The purpose of the System Integration and Acceptance test-plan element is to verify that entire installed system functions as expected in an integrated manner and fulfis its intended purpose, that is, the safe transition between lane states. After the tests listed herein are successfully completed by ICx personnel and witnessed by City of Calgary personnel, the signed version of this document serves as formal documentation of this final element of the Project Test Plan. The signed copy will be scanned and forwarded to the City of Calgary engineer for record purposes.
1.4 | Definitions
Acronyms and terms used in this document are defined in Table 2.
Table 2: Definitions
|  | Term | Definition
|  | Checklist | A list of items to test, inspect or observe.
|  | Component | A PLC, switch, router, device server, computer or other part of the control system.
|  | Device, or | A camera, gate, signal head or sign used to control and monitor the operation of traffic lane reversals in the project area.
|  | HMI | Human-Machine Interface
|  | PLC | Programmable Logic Controller
|  | SW | Software
|  | Test | A procedure to follow when checking that a product, service, or system meets some particular specification(s).
|  | TMC | Traffic Management Centre
|  | Validation | The process of checking that a product, service, or system fulfills its intended purpose (usually through an engineering review).
|  | Verification | The process of checking that a product, service, or system meets specifications (usually against a checklist).

## Instructions
2 | Instructions
2.1 | System Integration and Acceptance Test
2.1.1 | Features to Be Tested
This set of tests verifies that:
1) | All PLCs, switches, device servers, software (PLC and Cameleon), and associated components function as expected, in an integrated manner (I.e. as a complete system), when installed in Calgary.
2.1.2 | Procedure
1) | Operate all field devices, from the TMC, to each controllable state and verify correct status is displayed by the system..
2) | Operate all field devices, from the Local HMI, to each controllable state and verify correct status is displayed by the system.
3) | Test all configured device alarms.
4) | Verify correct operation of all lane transitions from the TMC.
5) | Run through checklist of any remaining contractual and other requirements not covered in the preceding steps.
6) | Validate transition sequences with CoC engineer, including: - Safe transition between lane states - Fulfilment of intended purpose
7) | Approve Interlock Report - the City of Calgary Engineer shall consider the safety implications of each device interlock. (No actual test procedure is involved.)

## Device & Alarm Status
Test # | System (red if system not in name) | Cabinet | PLC | Name | PLC Terminal | PLC Address | Terminal Block | Pass
1 | BT |  | PLC01 | Communication loss to BT CC01 (PLC01)
4 | BT |  | PLC01 | Communication loss to BT CC04 (Remote I/O PLC01)
5 | BT |  | PLC01 | Communication loss to BT CC05 (Remote I/O PLC01)
7 | BT |  | PLC01 | Failed to change state as commanded BT DSS04
8 | BT |  | PLC01 | Failed to change state as commanded BT DSS05
11 | BT |  | PLC01 | Failed to change state as commanded BT G01
12 | BT |  | PLC01 | Failed to change state as commanded BT G02
18 | BT |  | PLC01 | Intrusion alarm at BT CC01
21 | BT |  | PLC01 | Intrusion alarm at BT CC04
22 | BT |  | PLC01 | Intrusion alarm at BT CC05
23 | BT |  | PLC01 | Intrusion alarm at gate cabinet BT G01
24 | BT |  | PLC01 | Intrusion alarm at gate cabinet BT G02
30 | BT |  | PLC01 | Invalid PLC checksum at BT PLC01
33 | BT |  | PLC01 | PLC fault at BT PLC01
36 | BT |  | PLC01 | Power loss at BT CC01 (PLC01)
39 | BT |  | PLC01 | Power loss at BT CC04 (Remote I/O PLC01)
40 | BT |  | PLC01 | Power loss at BT CC05 (Remote I/O PLC01)
42 | BT |  | PLC01 | Sign fault at BT DSS04
43 | BT |  | PLC01 | Sign fault at BT DSS05
47 | BT |  | PLC01 | Uncommanded change of state at BT DSS04
48 | BT |  | PLC01 | Uncommanded change of state at BT DSS05
51 | BT |  | PLC01 | Uncommanded change of state at BT G01
52 | BT |  | PLC01 | Uncommanded change of state at BT G02
2 | BT |  | PLC02 | Communication loss to BT CC02 (PLC02)
14 | BT |  | PLC02 | Failed to change state as commanded BT G04
15 | BT |  | PLC02 | Failed to change state as commanded BT G05A
16 | BT |  | PLC02 | Failed to change state as commanded BT G05B
17 | BT |  | PLC02 | Failed to change state as commanded BT G05C
19 | BT |  | PLC02 | Intrusion alarm at BT CC02
26 | BT |  | PLC02 | Intrusion alarm at gate cabinet BT G04
27 | BT |  | PLC02 | Intrusion alarm at gate cabinet BT G05A
28 | BT |  | PLC02 | Intrusion alarm at gate cabinet BT G05B
29 | BT |  | PLC02 | Intrusion alarm at gate cabinet BT G05C
31 | BT |  | PLC02 | Invalid PLC checksum at BT PLC02
34 | BT |  | PLC02 | PLC fault at BT PLC02
37 | BT |  | PLC02 | Power loss at BT CC02 (PLC02)
54 | BT |  | PLC02 | Uncommanded change of state at BT G04
55 | BT |  | PLC02 | Uncommanded change of state at BT G05A
56 | BT |  | PLC02 | Uncommanded change of state at BT G05B
57 | BT |  | PLC02 | Uncommanded change of state at BT G05C
3 | BT |  | PLC03 | Communication loss to BT CC03 (PLC03)
6 | BT |  | PLC03 | Failed to change state as commanded BT DSS01
9 | BT |  | PLC03 | Failed to change state as commanded BT DSS06
10 | BT |  | PLC03 | Failed to change state as commanded BT DSS07
13 | BT |  | PLC03 | Failed to change state as commanded BT G03
20 | BT |  | PLC03 | Intrusion alarm at BT CC03
25 | BT |  | PLC03 | Intrusion alarm at gate cabinet BT G03
32 | BT |  | PLC03 | Invalid PLC checksum at BT PLC03
35 | BT |  | PLC03 | PLC fault at BT PLC03
38 | BT |  | PLC03 | Power loss at BT CC03 (PLC03)
41 | BT |  | PLC03 | Sign fault at BT DSS01
44 | BT |  | PLC03 | Sign fault at BT DSS06
45 | BT |  | PLC03 | Sign fault at BT DSS07
46 | BT |  | PLC03 | Uncommanded change of state at BT DSS01
49 | BT |  | PLC03 | Uncommanded change of state at BT DSS06
50 | BT |  | PLC03 | Uncommanded change of state at BT DSS07
53 | BT |  | PLC03 | Uncommanded change of state at BT G03
58 | MD |  | PLC01 | Communication loss to MD CC01 (PLC01)
60 | MD |  | PLC01 | Conflict monitor trip at MD CC01 Sign Bridge 3 | IM1.B04 | %I00020 | CMU
61 | MD |  | PLC01 | Conflict monitor trip at MD CC01 Sign Bridge 4 | IM1.B05 | %I00021 | CMU
62 | MD |  | PLC01 | Conflict monitor trip at MD CC01 Sign Bridge 5 | IM1.B06 | %I00022 | CMU
65 | MD |  | PLC01 | Failed to change state as commanded MD G01A
66 | MD |  | PLC01 | Failed to change state as commanded MD G01B
67 | MD |  | PLC01 | Failed to change state as commanded MD G01C
68 | MD |  | PLC01 | Failed to change state as commanded MD G02A
69 | MD |  | PLC01 | Failed to change state as commanded MD G02B
70 | MD |  | PLC01 | Failed to change state as commanded MD G02C
71 | MD |  | PLC01 | Intrusion alarm at gate cabinet MD G01A
72 | MD |  | PLC01 | Intrusion alarm at gate cabinet MD G01B
73 | MD |  | PLC01 | Intrusion alarm at gate cabinet MD G01C
74 | MD |  | PLC01 | Intrusion alarm at gate cabinet MD G02A
75 | MD |  | PLC01 | Intrusion alarm at gate cabinet MD G02B
76 | MD |  | PLC01 | Intrusion alarm at gate cabinet MD G02C
77 | MD |  | PLC01 | Intrusion alarm at MD CC01
79 | MD |  | PLC01 | Invalid PLC checksum at MD PLC01
81 | MD |  | PLC01 | PLC fault at MD PLC01
83 | MD |  | PLC01 | Power loss at MD CC01 (PLC01)
85 | MD |  | PLC01 | Uncommanded change of state at MD G01A
86 | MD |  | PLC01 | Uncommanded change of state at MD G01B
87 | MD |  | PLC01 | Uncommanded change of state at MD G01C
88 | MD |  | PLC01 | Uncommanded change of state at MD G02A
89 | MD |  | PLC01 | Uncommanded change of state at MD G02B
90 | MD |  | PLC01 | Uncommanded change of state at MD G02C
59 | MD |  | PLC02 | Communication loss to MD CC02 (PLC02)
63 | MD |  | PLC02 | Conflict monitor trip at MD CC02 Sign Bridge 6 | IM1.A2 | %I00002 | CMU
64 | MD |  | PLC02 | Conflict monitor trip at MD CC02 Sign Bridge 7 & 8 | IM1.A3 | %I00003 | CMU
78 | MD |  | PLC02 | Intrusion alarm at MD CC02
80 | MD |  | PLC02 | Invalid PLC checksum at MD PLC02
82 | MD |  | PLC02 | PLC fault at MD PLC02
84 | MD |  | PLC02 | Power loss at MD CC02 (PLC02)

## Device Control
Test # | System | Cabinet | PLC | Name | Operates from TMC | Operates from Local HMI | Other | Pass
1 | BT | CC01 | PLC01 | DSS04-IA
2 | BT | CC01 | PLC01 | DSS04-IB
3 | BT | CC01 | PLC01 | DSS04-IC
4 | BT | CC01 | PLC01 | DSS05-IA
5 | BT | CC01 | PLC01 | DSS05-IB
6 | BT | CC01 | PLC01 | DSS05-IC
7 | BT | CC01 | PLC01 | G01_CLOSE |  |  | LEDs on
8 | BT | CC01 | PLC01 | G01_OPEN
9 | BT | CC01 | PLC01 | G02_CLOSE |  |  | LEDs on
10 | BT | CC01 | PLC01 | G02_OPEN
11 | BT | CC02 | PLC02 | G04_CLOSE |  |  | LEDs on
12 | BT | CC02 | PLC02 | G04_OPEN
13 | BT | CC02 | PLC02 | G05A_CLOSE |  |  | LEDs on
14 | BT | CC02 | PLC02 | G05A_OPEN
15 | BT | CC02 | PLC02 | G05B_CLOSE |  |  | LEDs on
16 | BT | CC02 | PLC02 | G05B_OPEN
17 | BT | CC02 | PLC02 | G05C_CLOSE |  |  | LEDs on
18 | BT | CC02 | PLC02 | G05C_OPEN
19 | BT | CC02 | PLC02 | SB01_01EF_GRN
20 | BT | CC02 | PLC02 | SB01_01EF_RED
21 | BT | CC02 | PLC02 | SB01_02EF_GRN
22 | BT | CC02 | PLC02 | SB02_01EF_GRN
23 | BT | CC02 | PLC02 | SB02_01EF_YLW
24 | BT | CC02 | PLC02 | SB02_02EF_GRN
25 | BT | CC03 | PLC03 | DSS06-IA
26 | BT | CC03 | PLC03 | DSS06-IB
27 | BT | CC03 | PLC03 | DSS06-IC
28 | BT | CC03 | PLC03 | DSS07-IA
29 | BT | CC03 | PLC03 | DSS07-IB
30 | BT | CC03 | PLC03 | DSS07-IC
31 | BT | CC03 | PLC03 | G03_CLOSE |  |  | LEDs on
32 | BT | CC03 | PLC03 | G03_OPEN
33 | BT | CC04 | PLC01 | DSS01-IA
34 | BT | CC04 | PLC01 | DSS01-IB
35 | BT | CC04 | PLC01 | DSS01-IC
36 | BT | CC04 | PLC01 | DSS02_CLOSE (PM)
37 | BT | CC04 | PLC01 | DSS02_OPEN (AM)
38 | BT | CC05 | PLC01 | DSS03_CLOSE (PM)
39 | BT | CC05 | PLC01 | DSS03_OPEN (AM)
40 | MD | CC01 | PLC01 | DSS01_AM
41 | MD | CC01 | PLC01 | DSS01_PM
42 | MD | CC01 | PLC01 | G01A_CLOSE |  |  | LEDs on
43 | MD | CC01 | PLC01 | G01A_OPEN
44 | MD | CC01 | PLC01 | G01B_CLOSE |  |  | LEDs on
45 | MD | CC01 | PLC01 | G01B_OPEN
46 | MD | CC01 | PLC01 | G01C_CLOSE |  |  | LEDs on
47 | MD | CC01 | PLC01 | G01C_OPEN
48 | MD | CC01 | PLC01 | G02A_CLOSE |  |  | LEDs on
49 | MD | CC01 | PLC01 | G02A_OPEN
50 | MD | CC01 | PLC01 | G02B_CLOSE |  |  | LEDs on
51 | MD | CC01 | PLC01 | G02B_OPEN
52 | MD | CC01 | PLC01 | G02C_CLOSE |  |  | LEDs on
53 | MD | CC01 | PLC01 | G02C_OPEN
54 | MD | CC01 | PLC01 | SB01_01WF_GRN
55 | MD | CC01 | PLC01 | SB01_02WF_GRN
56 | MD | CC01 | PLC01 | SB01_02WF_YLW
57 | MD | CC01 | PLC01 | SB02_01WF_GRN
58 | MD | CC01 | PLC01 | SB02_02WF_GRN
59 | MD | CC01 | PLC01 | SB02_02WF_RED
60 | MD | CC01 | PLC01 | SB03_01EF_RED
61 | MD | CC01 | PLC01 | SB03_01WF_GRN
62 | MD | CC01 | PLC01 | SB03_02EF_RED
63 | MD | CC01 | PLC01 | SB03_02EF_YLW
64 | MD | CC01 | PLC01 | SB03_02WF_GRN
65 | MD | CC01 | PLC01 | SB03_02WF_RED
66 | MD | CC01 | PLC01 | SB03_03EF_GRN
67 | MD | CC01 | PLC01 | SB03_03EF_RED
68 | MD | CC01 | PLC01 | SB03_04EF_GRN
69 | MD | CC01 | PLC01 | SB04_01EF_RED
70 | MD | CC01 | PLC01 | SB04_01WF_GRN
71 | MD | CC01 | PLC01 | SB04_02EF_GRN
72 | MD | CC01 | PLC01 | SB04_02EF_RED
73 | MD | CC01 | PLC01 | SB04_02WF_GRN
74 | MD | CC01 | PLC01 | SB04_02WF_RED
75 | MD | CC01 | PLC01 | SB04_03EF_GRN
76 | MD | CC01 | PLC01 | SB04_03EF_YLW
77 | MD | CC01 | PLC01 | SB04_04EF_GRN
78 | MD | CC01 | PLC01 | SB05_01EF_RED
79 | MD | CC01 | PLC01 | SB05_01WF_GRN
80 | MD | CC01 | PLC01 | SB05_02EF_GRN
81 | MD | CC01 | PLC01 | SB05_02EF_RED
82 | MD | CC01 | PLC01 | SB05_02WF_GRN
83 | MD | CC01 | PLC01 | SB05_02WF_RED
84 | MD | CC01 | PLC01 | SB05_03EF_GRN
85 | MD | CC01 | PLC01 | SB05_04EF_GRN
86 | MD | CC02 | PLC02 | SB06_01EF_RED
87 | MD | CC02 | PLC02 | SB06_01WF_GRN
88 | MD | CC02 | PLC02 | SB06_02EF_GRN
89 | MD | CC04 | PLC04 | SB06_02EF_RED
90 | MD | CC06 | PLC06 | SB06_02WF_GRN
91 | MD | CC08 | PLC08 | SB06_02WF_RED
92 | MD | CC10 | PLC10 | SB06_03EF_GRN
93 | MD | CC11 | PLC11 | SB06_03WF_RED
94 | MD | CC12 | PLC12 | SB06_04EF_GRN
95 | MD | CC13 | PLC13 | SB07_01WF_GRN
96 | MD | CC14 | PLC14 | SB07_02WF_GRN
97 | MD | CC16 | PLC16 | SB07_02WF_RED
98 | MD | CC18 | PLC18 | SB07_03WF_RED
99 | MD | CC19 | PLC19 | SB08_01EF_RED
100 | MD | CC20 | PLC20 | SB08_02EF_GRN
101 | MD | CC22 | PLC22 | SB08_02EF_RED
102 | MD | CC02 | PLC02 | SB08_03EF_GRN
103 | MD | CC02 | PLC02 | SB08_04EF_GRN
104 | MD | CC02 | PLC02 | SB09_01WF_GRN
105 | MD | CC02 | PLC02 | SB09_02EF_RED
106 | MD | CC02 | PLC02 | SB09_02WF_GRN
107 | MD | CC02 | PLC02 | SB09_02WF_RED
108 | MD | CC02 | PLC02 | SB09_03EF_GRN
109 | MD | CC02 | PLC02 | SB09_03WF_RED
110 | MD | CC02 | PLC02 | SB09_04EF_GRN
111 | MD | CC02 | PLC02 | SB10_01WF_GRN
112 | MD | CC02 | PLC02 | SB10_02WF_GRN

## Lane Transitions
Test # | System | Transition start state | Transition end state | Addition instructions | Pass
1 | BT | Fifth Avenue Connector Normal Westbound | Fifth Avenue Connector AM Counterflow Eastbound
2 | BT | Fifth Avenue Connector AM Counterflow Eastbound | Fifth Avenue Connector Normal Westbound
3 | BT | Fifth Avenue Connector Normal Westbound | Fifth Avenue Connector Weekend Westbound
4 | BT | Fifth Avenue Connector Weekend Westbound | Fifth Avenue Connector Normal Westbound
5 | MD | Memorial Drive Normal 2EB + 2 WB | Memorial Drive PM Counterflow 1EB + 3 WB
6 | MD | Memorial Drive PM Counterflow 1EB + 3 WB | Memorial Drive Normal 2EB + 2 WB
7 | BT | Unknown state | Fifth Avenue Connector AM Counterflow Eastbound | run this test with driver in test mode
8 | BT | Unknown state | Fifth Avenue Connector Normal Westbound | run this test with driver in test mode
9 | BT | Unknown state | Fifth Avenue Connector Weekend Westbound | run this test with driver in test mode
10 | MD | Unknown state | Memorial Drive PM Counterflow 1EB + 3 WB | run this test with driver in test mode
11 | MD | Unknown state | Memorial Drive Normal 2EB + 2 WB | run this test with driver in test mode

## Interlocks
# | Area | PLC | Command Name | Interlock | Pass
1 | BT | PLC03 | BT_DSS01.AM_MODE | (bt_g02.status ~ bt_g02.opened) Or (bt_g03.status ~ bt_g03.closed) Or (evt_bt_g04g05_closed.value ~ true)
2 | BT | PLC03 | BT_DSS01.PM_MODE
3 | BT | PLC03 | BT_DSS02.AM_MODE | (bt_g02.status ~ bt_g02.opened) Or (bt_g03.status ~ bt_g03.closed) Or (evt_bt_g04g05_closed.value ~ true)
4 | BT | PLC03 | BT_DSS02.PM_MODE
5 | BT | PLC03 | BT_DSS03.AM_MODE | (bt_g02.status ~ bt_g02.opened) Or (bt_g03.status ~ bt_g03.closed) Or (evt_bt_g04g05_closed.value ~ true)
6 | BT | PLC03 | BT_DSS03.PM_MODE
7 | BT | PLC01 | BT_DSS04.AM_MODE | (bt_g01.status ~ bt_g01.opened)
8 | BT | PLC01 | BT_DSS04.PM_MODE
9 | BT | PLC01 | BT_DSS05.AM_MODE | (bt_g02.status ~ bt_g02.opened) Or (bt_g03.status ~ bt_g03.closed) Or (evt_bt_g04g05_closed.value ~ true)
10 | BT | PLC01 | BT_DSS05.PM_MODE
11 | BT | PLC03 | BT_DSS06.AM_MODE
12 | BT | PLC03 | BT_DSS06.PM_MODE | (bt_g02.status ~ bt_g02.closed) Or (bt_g03.status ~ bt_g03.opened)
13 | BT | PLC03 | BT_DSS07.AM_MODE
14 | BT | PLC03 | BT_DSS07.PM_MODE | (bt_g02.status ~ bt_g02.closed) Or (bt_g03.status ~ bt_g03.opened)
15 | BT | PLC01 | BT_G01.Close | (bt_dss04.status ~ bt_dss04.pm_mode)
16 | BT | PLC01 | BT_G01.Open
17 | BT | PLC01 | BT_G02.Close | (bt_dss01.status ~ bt_dss01.pm_mode) Or (bt_dss02.status ~ bt_dss02.pm_mode) Or (bt_dss03.status ~ bt_dss03.pm_mode) Or (bt_dss05.status ~ bt_dss05.pm_mode)
18 | BT | PLC01 | BT_G02.Open | (bt_g03.status ~ bt_g03.closed) Or (evt_bt_g04g05_closed.value ~ true)
19 | BT | PLC03 | BT_G03.Close | (bt_dss06.status ~ bt_dss06.am_mode) Or (bt_dss07.status ~ bt_dss07.am_mode)
20 | BT | PLC03 | BT_G03.Open | (bt_g02.status ~ bt_g02.closed)
21 | BT | PLC02 | BT_G04.Close | (bt_g05a.status ~ bt_g05a.closed) Or (bt_g05b.status ~ bt_g05b.closed) Or (bt_g05c.status ~ bt_g05c.closed) Or (evt_bt_4thave_signals_closed.value ~ true)
22 | BT | PLC02 | BT_G04.Open | (bt_g02.status ~ bt_g02.closed)
23 | BT | PLC02 | BT_G05A.Close | (evt_bt_4thave_signals_closed.value ~ true)
24 | BT | PLC02 | BT_G05A.Open | (bt_g02.status ~ bt_g02.closed) Or (bt_g04.status ~ bt_g04.opened) Or (bt_g05c.status ~ bt_g05c.opened) Or (bt_g05b.status ~ bt_g05b.opened)
25 | BT | PLC02 | BT_G05B.Close | (evt_bt_4thave_signals_closed.value ~ true) Or (bt_g05a.status ~ bt_g05a.closed)
26 | BT | PLC02 | BT_G05B.Open | (bt_g02.status ~ bt_g02.closed) Or (bt_g04.status ~ bt_g04.opened) Or (bt_g05c.status ~ bt_g05c.opened)
27 | BT | PLC02 | BT_G05C.Close | (evt_bt_4thave_signals_closed.value ~ true) Or (bt_g05a.status ~ bt_g05a.closed) Or (bt_g05b.status ~ bt_g05b.closed)
28 | BT | PLC02 | BT_G05C.Open | (bt_g02.status ~ bt_g02.closed) Or (bt_g04.status ~ bt_g04.opened)
29 | BT | PLC02 | BT_SB01_01EF.Green | (bt_g02.status ~ bt_g02.closed) Or (bt_g04.status ~ bt_g04.opened) Or (bt_g05c.status ~ bt_g05c.opened) Or (bt_g05b.status ~ bt_g05b.opened) Or (bt_g05a.status ~ bt_g05a.opened)
30 | BT | PLC02 | BT_SB01_01EF.Red | (bt_sb01_01ef.status ~ bt_sb01_01ef.yellow)
31 | BT | PLC02 | BT_SB01_01EF.Yellow | (bt_sb02_01ef.status ~ bt_sb02_01ef.yellow)
32 | BT | PLC02 | BT_SB02_01EF.Green | (bt_g02.status ~ bt_g02.closed) Or (bt_g04.status ~ bt_g04.opened) Or (bt_g05c.status ~ bt_g05c.opened) Or (bt_g05b.status ~ bt_g05b.opened) Or (bt_g05a.status ~ bt_g05a.opened) Or (bt_sb01_01ef.status ~ bt_sb01_01ef.green)
33 | BT | PLC02 | BT_SB02_01EF.Yellow
34 | MD | PLC01 | MD_DSS01.AM_MODE
35 | MD | PLC01 | MD_DSS01.PM_MODE | (evt_md_ebfastlane_gates_closed.value ~ true) Or (evt_md_ebfastlane_wf_signals_red.value ~ true) Or (md_sb05_02ef.status ~ md_sb05_02ef.green)
36 | MD | PLC01 | MD_G01A.Close | (evt_md_ebfastlane_signals_red.value ~ true)
37 | MD | PLC01 | MD_G01A.Open | (evt_md_ebfastlane_signals_red.value ~ true) Or (md_g01c.status ~ md_g01c.opened) Or (md_g01b.status ~ md_g01b.opened)
38 | MD | PLC01 | MD_G01B.Close | (evt_md_ebfastlane_signals_red.value ~ true) Or (md_g01a.status ~ md_g01a.closed)
39 | MD | PLC01 | MD_G01B.Open | (evt_md_ebfastlane_signals_red.value ~ true) Or (md_g01c.status ~ md_g01c.opened)
40 | MD | PLC01 | MD_G01C.Close | (evt_md_ebfastlane_signals_red.value ~ true) Or (md_g01a.status ~ md_g01a.closed) Or (md_g01b.status ~ md_g01b.closed)
41 | MD | PLC01 | MD_G01C.Open | (evt_md_ebfastlane_signals_red.value ~ true)
42 | MD | PLC01 | MD_G02A.Close | (md_sb04_03ef.status ~ md_sb04_03ef.yellow) Or (md_sb03_03ef.status ~ md_sb03_03ef.red)
43 | MD | PLC01 | MD_G02A.Open | (md_sb03_02ef.status ~ md_sb03_02ef.red) Or (md_sb04_02ef.status ~ md_sb04_02ef.red) Or (md_sb05_02ef.status ~ md_sb05_02ef.red) Or (md_dss01.status ~ md_dss01.am_mode) Or (md_g02c.status ~ md_g02c.opened) Or (md_g02b.status ~ md_g02b.opened)
44 | MD | PLC01 | MD_G02B.Close | (md_sb04_03ef.status ~ md_sb04_03ef.yellow) Or (md_sb03_03ef.status ~ md_sb03_03ef.red) Or (md_g02a.status ~ md_g02a.closed)
45 | MD | PLC01 | MD_G02B.Open | (md_sb03_02ef.status ~ md_sb03_02ef.red) Or (md_sb04_02ef.status ~ md_sb04_02ef.red) Or (md_sb05_02ef.status ~ md_sb05_02ef.red) Or (md_dss01.status ~ md_dss01.am_mode) Or (md_g02c.status ~ md_g02c.opened)
46 | MD | PLC01 | MD_G02C.Close | (md_sb04_03ef.status ~ md_sb04_03ef.yellow) Or (md_sb03_03ef.status ~ md_sb03_03ef.red) Or (md_g02a.status ~ md_g02a.closed) Or (md_g02b.status ~ md_g02b.closed)
47 | MD | PLC01 | MD_G02C.Open | (md_sb03_02ef.status ~ md_sb03_02ef.red) Or (md_sb04_02ef.status ~ md_sb04_02ef.red) Or (md_sb05_02ef.status ~ md_sb05_02ef.red) Or (md_dss01.status ~ md_dss01.am_mode)
48 | MD | PLC01 | MD_SB01_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb02_02wf.status ~ md_sb02_02wf.green)
49 | MD | PLC01 | MD_SB01_02WF.Yellow
50 | MD | PLC01 | MD_SB02_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb03_02wf.status ~ md_sb03_02wf.green)
51 | MD | PLC01 | MD_SB02_02WF.Red | (md_sb02_02wf.status ~ md_sb02_02wf.yellow)
52 | MD | PLC01 | MD_SB02_02WF.Yellow | (md_sb01_02wf.status ~ md_sb01_02wf.yellow)
53 | MD | PLC01 | MD_SB03_02EF.Red | (md_sb03_02ef.status ~ md_sb03_02ef.yellow)
54 | MD | PLC01 | MD_SB03_02EF.Yellow | (evt_md_ebfastlane_gates_closed.value ~ true) Or (evt_md_ebfastlane_wf_signals_red.value ~ true)
55 | MD | PLC01 | MD_SB03_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb04_02wf.status ~ md_sb04_02wf.green)
56 | MD | PLC01 | MD_SB03_02WF.Red | (md_sb03_02wf.status ~ md_sb03_02wf.yellow)
57 | MD | PLC01 | MD_SB03_02WF.Yellow | ((md_sb02_02wf.status ~ md_sb02_02wf.yellow) AND (md_sb02_02wf.status ~ md_sb02_02wf.red))
58 | MD | PLC01 | MD_SB03_03EF.Green | (evt_md_wbfastlane_gates_opened.value ~ true)
59 | MD | PLC01 | MD_SB03_03EF.Red | (md_sb03_03ef.status ~ md_sb03_03ef.yellow)
60 | MD | PLC01 | MD_SB03_03EF.Yellow | (md_sb04_03ef.status ~ md_sb04_03ef.yellow)
61 | MD | PLC01 | MD_SB04_02EF.Green | (evt_md_ebfastlane_gates_closed.value ~ true) Or (evt_md_ebfastlane_wf_signals_red.value ~ true) Or (md_sb03_02ef.status ~ md_sb03_02ef.yellow)
62 | MD | PLC01 | MD_SB04_02EF.Red | (md_sb04_02ef.status ~ md_sb04_02ef.yellow)
63 | MD | PLC01 | MD_SB04_02EF.Yellow | ((md_sb05_02ef.status ~ md_sb05_02ef.yellow) AND (md_sb05_02ef.status ~ md_sb05_02ef.red))
64 | MD | PLC01 | MD_SB04_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb05_02wf.status ~ md_sb05_02wf.green)
65 | MD | PLC01 | MD_SB04_02WF.Red | (md_sb04_02wf.status ~ md_sb04_02wf.yellow)
66 | MD | PLC01 | MD_SB04_02WF.Yellow | ((md_sb03_02wf.status ~ md_sb03_02wf.yellow) AND (md_sb03_02wf.status ~ md_sb03_02wf.red))
67 | MD | PLC01 | MD_SB04_03EF.Green | (evt_md_wbfastlane_gates_opened.value ~ true) Or (md_sb03_03ef.status ~ md_sb03_03ef.green)
68 | MD | PLC01 | MD_SB04_03EF.Yellow
69 | MD | PLC01 | MD_SB05_02EF.Green | (evt_md_ebfastlane_gates_closed.value ~ true) Or (evt_md_ebfastlane_wf_signals_red.value ~ true) Or (md_sb04_02ef.status ~ md_sb04_02ef.green)
70 | MD | PLC01 | MD_SB05_02EF.Red | (md_sb05_02ef.status ~ md_sb05_02ef.yellow)
71 | MD | PLC01 | MD_SB05_02EF.Yellow | ((md_sb06_02ef.status ~ md_sb06_02ef.yellow) AND (md_sb06_02ef.status ~ md_sb06_02ef.red))
72 | MD | PLC01 | MD_SB05_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb06_02wf.status ~ md_sb06_02wf.green)
73 | MD | PLC01 | MD_SB05_02WF.Red | (md_sb05_02wf.status ~ md_sb05_02wf.yellow)
74 | MD | PLC01 | MD_SB05_02WF.Yellow | ((md_sb04_02wf.status ~ md_sb04_02wf.yellow) AND (md_sb04_02wf.status ~ md_sb04_02wf.red))
75 | MD | PLC02 | MD_SB06_02EF.Green | (evt_md_ebfastlane_gates_closed.value ~ true) Or (evt_md_ebfastlane_wf_signals_red.value ~ true) Or (md_sb05_02ef.status ~ md_sb05_02ef.green)
76 | MD | PLC02 | MD_SB06_02EF.Red | (md_sb06_02ef.status ~ md_sb06_02ef.yellow)
77 | MD | PLC02 | MD_SB06_02EF.Yellow | ((md_sb08_02ef.status ~ md_sb08_02ef.yellow) AND (md_sb08_02ef.status ~ md_sb08_02ef.red))
78 | MD | PLC02 | MD_SB06_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb07_02wf.status ~ md_sb07_02wf.green)
79 | MD | PLC02 | MD_SB06_02WF.Red | (md_sb06_02wf.status ~ md_sb06_02wf.yellow)
80 | MD | PLC02 | MD_SB06_02WF.Yellow | ((md_sb05_02wf.status ~ md_sb05_02wf.yellow) AND (md_sb05_02wf.status ~ md_sb05_02wf.red))
81 | MD | PLC02 | MD_SB07_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true) Or (md_sb09_02wf.status ~ md_sb09_02wf.green)
82 | MD | PLC02 | MD_SB07_02WF.Red | (md_sb07_02wf.status ~ md_sb07_02wf.yellow)
83 | MD | PLC02 | MD_SB07_02WF.Yellow | ((md_sb06_02wf.status ~ md_sb06_02wf.yellow) AND (md_sb06_02wf.status ~ md_sb06_02wf.red))
84 | MD | PLC02 | MD_SB08_02EF.Green | (evt_md_ebfastlane_gates_closed.value ~ true) Or (evt_md_ebfastlane_wf_signals_red.value ~ true) Or (md_sb06_02ef.status ~ md_sb06_02ef.green)
85 | MD | PLC02 | MD_SB08_02EF.Red | (md_sb08_02ef.status ~ md_sb08_02ef.yellow)
86 | MD | PLC02 | MD_SB08_02EF.Yellow
87 | MD | PLC02 | MD_SB09_02WF.Green | (evt_md_ebfastlane_gates_opened.value ~ true) Or (evt_md_ebfastlane_ef_signals_red.value ~ true)
88 | MD | PLC02 | MD_SB09_02WF.Red | (md_sb09_02wf.status ~ md_sb09_02wf.yellow)
89 | MD | PLC02 | MD_SB09_02WF.Yellow | ((md_sb07_02wf.status ~ md_sb07_02wf.yellow) AND (md_sb07_02wf.status ~ md_sb07_02wf.red))

## System REQ Checklist
2 | Functional Requirements (REQ) Checklist
REQ | Description
1 | The RLCS provides the capability for a system administrator to configure and maintain the system.
2 | The RLCS provides supervisory control and data acquisition capability from the TMC including: 1) Device status 2) Device control 3) Reversible lane status 4) Reversible lane control 5) Alarm monitoring 6) Archiving and reporting
3 | The RLCS implements strategies to maintain full or degraded operation in the event of partial loss of hardware and/or software functionality including: 1) Redundant head end hardware. 2) Redundant head end software. 3) Local control in case of communications loss 4) Ability to place malfunctioning devices in an offline mode
4 | The RLCS provides prompts at pre-defined times during the day to indicate when a reversal should be initiated. SYSTEM OPERATING TIMES 3M10 4:00 p.m. – 6:00 p.m. 5 Avenue Connector 6:00 a.m. – 9:00 a.m.
5 | The system provides the capability to define interlocks that will prevent the operation of devices if the interlock condition is true. (PBA will submit a proposed interlock table for approval.)
6 | The system provides a mechanism by which an operator with sufficient privilege can override an interlock to operate a device.
7 | Using built-in configuration functionality the Cameleon Server provides the capability for a system administrator to configure and maintain the system.
8 | The Cameleon Server provides the capability to define interlocks that will prevent the operation of devices if the interlock condition is true.
9 | The Cameleon Client displays maps showing the project area.
10 | The Cameleon Client displays real-time information including: 1) Gate status 2) Signal status 3) DSS status 4) VMS status 5) Camera status 6) Live video 7) Overall lane status 8) PLC status 9) Miscellaneous device status (E.g. door switches)
11 | The Cameleon Head End provides the capability to initiate preconfigured lane transitions to change the overall state of the reversible lanes.
12 | The Cameleon Head End provides the capability to manually operate individual devices.
13 | Using built-in alarm management functionality, the head end informs operators of alarm conditions, including: 1) Cabinet intrusion on PLC and DSS cabinets 2) Loss of communication with a PLC 3) Loss of valid device status for DSS, VMS, Gates, and Signals. 4) Loss of communication with Camera 5) Loss of communication between a PLC and its remote I/O 6) Device interlock contradictions
14 | Using the built-in logging and reporting functionality, the Cameleon Client provides the capability for a user to view and export archived data including: 1) System status 2) Device status 3) Alarms 4) Administrative events (E.g. user login activity)
15 | The Cameleon Head End implements strategies to maintain full or degraded operation in the event of partial loss of hardware and/or software functionality including: 1) Dual redundant Cameleon Server hardware and software (including Cameleon ITS Server, Device Drivers and Archive Server applications). 2) Multiple redundant Cameleon Client hardware and software. 3) Ability to place malfunctioning devices in an offline mode.
16 | The Cameleon Head End sends a heartbeat signal to each PLC enabling the PLC to verify communication status with the head end.
17 | The Cameleon Head End provides system-wide interlock checking for device operations.
18 | The Cameleon Head End provides the capability for an operator to override the RLCS state in effect and return the system to its previous operating state.
19 | The Cameleon Head End provides a mechanism by which an operator with sufficient privilege can override an interlock to operate a device.
20 | The PLCs provide local supervisory control and data acquisition for lane signals, swing gates, DSS and VMS.
21 | The PLCs provide a supervisory control and data acquisition interface between the field devices and the Cameleon Head end.
22 | The PLCs monitor the heartbeat signal from the Cameleon Head end to verify communication status.
23 | The PLCs provide a local Human Machine Interface (HMI) to facilitate local control and monitoring of attached field devices.
24 | The PLCs provide local interlock checking for device operations. Local interlocks are a subset of system-wide interlocks for the devices locally attached to the PLC.
25 | The PLC local HMI provides a mechanism by which an operator with sufficient privilege can override an interlock to operate a device.
26 | The PLCs provide the ability to place malfunctioning devices in an offline mode.

## Approvals
Executed by: |  | Date:
Observer's Initials: |  | Date:
Approvals
The following signatures indicate approval of the testing that was executed for the RLCS System Integration and Acceptance Test, developed for the City of Calgary, and that all issues have been identified and documented.
| City of Calgary Representative |  | Date:
| ICx Representative |  | Date: