## 2010
04 Potter Fell

01 Kentmere West Ridge

## 2009
Id	Patrol No.	Patrol	Date	Volunteer	Report Comments	Act	Discussed	Action Agreed	Feedback	ToDo

670		Hugill	14-Jan	Tony Bushby	various BW discs faded		10-Apr
					Stone stile at 4515 0036 off Browfoot lane needs re-build	Y		Done by R

671		K'mere Valley	16-Jan	Kings	F'post at 4568 0493 N end of boggy field loose	Y	10-Apr	checked 18/2 ok
					F'post at 4563 0602 Hartrigg Fm loose	Y		checked 18/2 ok
					signs of rot on FB near Rooke Howe	Y		Due full survey this year

672		Potter Fell	21-Jan	Graham R	Route round East View - when to be properly marked?	Y		End Apr
					Water trough overflowing and flooding path between
					Craggy and Littlewood	Y		Sorted out ok

673		Mid Kmere	28-Jan	J Fish	no new probs	N	10-Apr

674		R'heath	06-Feb	P Cook	no new probs	N	10-Apr

675		Scout Scar	10-Feb	Harold	no probs	N	10-Apr

676		Crook W	11-Feb	Graham R	Rotting kissing gate at YewTree Fm GR4508 9555 but		10-Apr	Sue will look at
					ok for now	?
					rotten bottom step on wood stile at Boxtree barn
					60cm x 12.5cm	Y		task in to replace by wicket gate

677		Winster	16-Feb	R/Carolyn	F'post still missing near Barker Knott Fm	Y	10-Apr	passed to Steve Tatlock
					No Footpath sign on new field gate next to ladder stile
					at GR4174 9491 confusing	Y		Sue removed sign and now waymarked
								with 3 posts
678		Ratherheath	18-Feb	Bruce	Waymarking at gate at 4836 9391 between C'wck Hall		10-Apr	Done by R
					and Fell Gate needs improving	Y
					Wood Br near Ashes Lne parking - anti-slip slats need
					replacing or a mesh fitting	Y		Done by R
					tree guards at 2 placescuold be removed	N		not ours

679		K'mere valley	18-Feb	J fish	Spoil heap erosion - some edge collapsed recently	Y	10-Apr	Photos taken and shown to Steve

680		K'mere E	22-Feb	Richard	Concrete slab breaking up on Byway below BHB	Y	10-Apr	To be improved when Gatescarth work done

681		Craggy Hund	04-Mar	Elaine	Staveley Park tree enclosure - some may need releasing	Y	10-Apr	Sue will speak to Mr Parks

682		Cross No 18	08-Mar	Richard	FP blocked at 4554 9020 by hedge laying debris	Y	10-Apr	Sue will look at
					BW SW of Cross church flooded	Y		Sue will look at

683		Wither No 17	09-Mar	Richard	Permitted path f'post at needs resetting	Y	10-Apr	Done by R

684		Cross no 9	14-Mar	Richard	No probs	N	10-Apr

685		Crook Cct	09-Mar	Bruce	BW 577030 flooded S of Bonfire Hall and hedging will	N	10-Apr
					needcutting back
					BW 577036 flooded N of Lindreth Brow	n

686		Wither No3	22-Mar	Tony Hill	Branch across FP W of Bellart How 4480 8398	Y	10-Apr	done

687		Cross No 9	23-Mar	Malcolm	ROW thru Esp Ford not clear needs proper waymkg	Y	10-Apr	Sue will look at

688		Undbarrow	25-Mar	Elaine	Nothing particular	N	10-Apr

689		Wain Potter	31-Mar	Graham R	Gate prob at No4?	Y	10-Apr	Sorted by R
					Wire fence not on map across route from 7 to 8	Y		change route map (by hand in short term)
								Also new stile to go in near summit
690		Wither No2	19-Mar	C Banks	No probs	N	10-Apr

691		R'heath	29-Mar	Delia K	No probs	N	10-Apr

692		Wither No 1	24-Feb	M Fieldhouse	No probs	N	10-Apr

693		Wither No 1	06-Mar	howard Hunt	GR 4514 8460 5" diam tree suspended across permitted		10-Apr	gone
					path
					GR 4240 8517 kissing gate post loose	Y		broken, Dave to replace

694		Wither No 1	06-Apr	Chris Banks	birch tree across permitted path to Whibarrow Scar	Y	02-May	still there but lowered
					Rails at start of path need re-instating	N
					logs on FP in Buckhouse Wood	Y		gone
					9"x9" supporting post rotted needs replacing 4240 8515	y		as 693
					fence at stile at 4239 8562 needs replacing	y		2 rails and post needed
					waymark at 4248 8580 needs replacing	y		done

695		Longs East	12-Apr	Peter Uren	CROW furniture good	N	02-May
					illegible sign at Buckbarrow crag	N

696		Wither No2	12-Apr	Howard Hunt	4" diam dead tree across path at head ht 4397 8639	Y	02-May	done 3/5

697		K'mere W	19-Apr	Peter Uren	Wall gap on Low Lane	N	02-May	not our prob, not a hazard
					Cattle feeder encroaching BW	N
					Ditch needs digging out near Hallow Bank to OverEnd	Y		done june
					Gate on Low Lane distorted and not latching properly	Y		Fixed by R 21/5
					Short finger post needs replacing at OverEnd	N		is OK
					Erosion at bottom of pitching at Yoke?	N
					Cut off at start of Garburn needs clearing	Y		garburn WP this year?

698		Green Qtr	20-Apr	Bruce	Waymarking of FP near Tills Hole	?	02-May
					Flooded sections of BW near Well Foot - clear wall hole?
					Sign near Well Foot damaged, support broken	N		farmers problem
					Blocked culverts on Corclose Lane plastic pipes	Y	27-May	Bellie has seen and will task field team

699		Winster	19-Apr	Sallie	Stone stile wood supports near Birks Br loose	Y	02-May	Done

700		Ratherheath	18-Apr	Tony Hill	Manure etc on ROW in Ashes Coppice	n	02-May
					Stile at Knott Hill awkward	Y		Job sheet in to replace/repair

701		Wither No3	16-Apr	B Dawson	No probs	N	02-May

702		Hugill	27-Apr	Elaine	F'post at Hugill Hall 4511 9951 does not pointto stile	Y	02-May	Reset correctly 4/6

703		Wither No 1	13-May	Chris Barnett	Kissing gate/field gate post broken GR4240 8518	Y	02-May	Task in for Dave to do
					Tree across permitted path to Whitbarrow Scar	Y		Already reported to Sue

704		Potter Fell	10-May	Jeremy	High Elf Howe Br post and rail need sorting	Y	02-May	Sorted 4/6
					Gate near Nether Hse GR 5120 0012 top rail broken and
					bottom hinge pin out of post due to rot	Y		Dave to look at
					Waymarking into Nether Hse farmyard from N no good	y		Sue to look at /discuss
					Stile at Garnett Br BW bottom step rotted 3'x6"x2"	Y		Step changed 4/6
					Waymk needed at BW/FP junc nr E View	Y		Dave?
					Waymk post needed at E View	Y		Dave?
					Kissing gate rails at Taggleshaw loose in gnd	Y		Sorted 4/6

705		K'mere Valley	18-May	Graham R	Various flooded sections of track and some erosion	Y	27-May	Steve will look at
					where running down track

706		Cross No 9	12-May	Barry Winton	Badger Sett earth on track near church 9100 4437	N	02-Aug	OK Sue checked
					Esp Ford - owner complains of camping	Y		Sue to speak to farmer
					Broad Oak waymarking N of Fm yellow discs?	N		to be looked at re diversion
					Hubbersty head going NW from Rd - stream floods path	Y		Sue to look at

707		Bannsdle E	24-May	Peter Uren	Problems with route sheet	Y	02-Aug	Will correct route sheet
					All CROW items OK	N

708		Underbarrow	02-Jun	Graham R	Strained gatecatches nearRedscar could not be found	N	02-Aug

709		Whitbarrow N	30-May	Sallie S	Nothing	N	02-Aug

710		Wither No1	10-Jun	H Hunt	8" tree across permitted path	N	02-Aug	already reported

711		Bannisdle W	05-Jun	Sallie	CROW gate at 5115 0319 locked	Y	02-Aug
					other parts of patrol route from White Pike difficult	Y		change patrol sheet

712		Sleddle Forest	24-Jun	J Fish	Br near Skeggles Water4794 0319 one broken deck	N	02-Aug
					plank at E end ( not CROW item)
					badly broken Br at 4765 0299 beams would take new	?		Sue may discuss possible retoration with
					decking (not CROW item)			Sara
					Query on 5' wicket gate			change patrol sheet
					Broken gate on BWat 4795 0272 photo	Y		Sue to raise task to replace

713		Craggy Hund	20-Jun	Betty stubbs	No w'mkr at Side Hse to High Hundhowe	N	02-Aug
					Water running under stile at Piked Howe	Y		R or S to check

714		Wither No 3	30-Jun	Barry Winton	Bridle catch needs screws	Y	02-Aug	Barry will fix - done
					2 gates need oiling	Y		Barry will do - done
					FPs 583022, 023, 024 need cutting back	Y		done by P Cook

715		Cunswick Scar	08-Jul	Harold	No probs	N	02-Aug

716		Scout Scar	10-Jul	Jeremy	Wall by Tanyard Beck squeeze stile starting to collapse	Y	02-Aug	checked ok
					Gamblesmire lane gate top bar broken	N		UCR and still useable
					3 way f'post S of Cunswick Hall one finger missing	Y		Task to replace
					Electric fence sign needed N of C Hall	N
					Ladder stile in field W of Scar Wood unsteady	Y		Elaine will check in Sept
					Gate at G'mire Lne C'Scar broken etc	N		not ours
					W'mkr needed in Barrowfield Wood at Track junc	Y		Sue will check

717		Potter Fell	13-Jul	C ath Dixon	Gate above Nether Hse Fm broken/ hinge broken	Y	02-Aug	Already tasked on Dave
					Craggy gate catch missing	N		not to be replaced

718		Scout Scar	14-Jul	Harold	Gamblesmire 3 way f'post at C Hall finger off	Y	02-Aug	see 716

719		Wither N 3	22-Jul	Malcolm	No probs	N	02-Aug

720		Cross No9	24-Jul	C Barnett	No probs	N	02-Aug

721		K'mere W	25-Jul	Graham R	Maybe clear Garburn drainage later in year	Y	02-Aug	forwarded to Steve to consider

722		Wither No 1	27-Jul	Tony Hill	FP disc needed at GR 4248 8579 on 583029 where
					crosses BW 583012 and gate drops	Y	02-Aug	R to check

723		Crook Cct	28-Jul	Carolyn/Mark	Confusion of route W of Mountjoy Wood due to braken	N	02-Aug
					Flooding of BWsnear ford and Bell hill	Y		Sue will discuss w/Dave Bell
					finger rotten/loose on 3 way f'post at St Caths Church	Y		done by R
					Stone stile E of Broom on Broom Lne broken steps	Y		task on Dave to check/repair
					Various suggested w'mking	Y		R to look at/do as necessary

724		Hugill	02-Aug	Sallie	Waymarking at Hugill Hall	?	16-Nov
					Waymarking at Rawgill	Y		Mark improved – waiting for wall rebuild		Mark

725		Ratherheath	06-Aug	Jeremy	Metal gate at Moss Side only has one hinge	Y	16-Nov	ROW Survey item
					W'mkr needed at FP junc nr Bank End	N
					Top rail of gate on Crook Rd to Fell Gate rotten	N		no action at this time
					Wood field gate at Capplerigg Fm dilapidated	Y		job sheet in
					Stone stile at Knot Hill steps very narrow	Y		task to replace already in hand
					Him Balsam on Ashes Lane nr camp site	N		now on HB map
					Way'mkg at Plumbgarths Fm would be useful	N
					Stile in field nr Cunswick Tarn wobbly	Y		is it permanent? Sue to check
					Wood 3 bar gate nr C Hall dilapidated	N		not on DL
					gatepost on K gate in Staveley at Stocks Fm rotting	Y		task raised
					Awkward 1st step on stile on by-pass	?		Dave B to look at
					Narrow steps on stone stile near Ashes fm -not on DL	?		BD to look at
					F'post at same place tied to wall and wobbly	Y		Firmed up

726		Mi K'mere	11-Aug	Carolyn	No probs	N	26-Oct

727		Wither No3	16-Aug	H Hunt	paths 583006 and 58022 heavily overgrown	Y	16-Nov	006 cleared by Chri/Peter 022 alreadycut

728		Crook W	21-Aug	Tony hill	F'post broken at Outrun Nook	Y		sue asked to put in for replacement
					V high 1st step at stile between Outrun Nook and
					Borwick Fold	Y		Large stone either side?
					Dales Way discs need replacing	Y		Done

729		K'mere Valley	26-Aug	Shaws	Sign at Reservoir Cottage off post again	Y	26-Oct	re-attached by R
					Gate at Rook Howe dilapidated but useable	Y		Steve to raise task
					Erosion worse	Y		Checked , confirmed more gone recently
								Visited with Steve 26/10 - move stone back
								to widen path
730		Gn Qtr	25-Aug	J Fish	Ladder stile N of Gn Qtr at Access land boundary		26-Oct
					support rotten	Y		Steve will look at
					W'mkrs in L'sleddle Valley BW faded	Y		next patrol?
					Gate at 4794 0272 rotten, previously reported	Y		task in hand

731		K,mere E	03-Sep	Graham R	Large washout on UCR	N	16-Nov

732		Sallows Sour	04-Sep	Graham R	Work needed on Garburn drainage	Y	26-Oct	planned for early 2010

733		Wither No1	07-Sep	H Hunt	tree across permitted path to Whitbarrow scar	N		Awaits estate action

734		K'mere W	09-Oct	Carolyn	Drainage work needed on Garburn	Y	26-Oct	planned for early 2010
					Remove erosion control barriers at zig-zag?	Y		remove when doing WP
					Peat track short-cut - landscape to prevent use?	Y		place big boulders when do WP

735		K'mere E	11-Oct	Peter U	Some drainage will be needed on BOAT	Y	16-Nov	02/07/10
					No Climbing sign out of gnd on floor at ladder stile	Y		BMC will do next year

736		Scout scar	09-Oct	Elaine	Rotten rail/post at stile in Scar wood - post needed,		16-Nov
					stile still ok to use	Y		done
					finger off post at Gamblesmire lane S of Hall	y		done
					Waymarking/ obscured post in forest at track	Y		done

737		Wither 3	16-Oct	Sallie	Shaky stile supports at 4481 8393 near Bellart Howe	Y	16-Nov	Kissing gate post broken - reported to Sue/Dave

738		Potter Fell	17-Oct	Peter U	Ladder stile at Black Beck needs new top plank 20x4x1.5	Y	16-Nov	R to get wood and fix
					Broken gate above Tenter Howe	Y		already on task (not onDL)

739		Under barrow	10-Sep	Tony Hill	Spring wrong way round on gate near Beckside	N	16-Nov	Deliberate for when moving horses
					N of Fallen Yew - broken step stile support	Y		Repaired
					Adjacent field gate slam stoop out of alugnment	N		Not a problem to walkers

740		Crook Cct	09-Nov	Graham R	Extensive flooding of BWs in Bell Hill area	Y	16-Nov	Already on the books to resolve
					Top rail of gate at tyhe Broom4587 9248 broken	y		Job sheet in already

741		Craggy Hund	09-Nov	Carolyn	F'post near Hundhowe - finger missing	N	16-Nov	w'mkrs on post instead
					bottom rail of fence at stile above Hundhowe needs nails	Y		fixed
					W'mkr post below Ghyll Pool loose	Y		fixed

742		Hugill	17-Nov	J Fish	wall collapse onto BW off Grassgarth Lne	N	22-Feb	Not a problem for walkers or riders
					slippery steps on wood stile SE of High Hse 4391 0037	Y		R to put wire on – wait and see
					post out of gnd 200m N of High Hse at BW junc	Y		Mark and Richard reset
					GR 4382 0074	Y		R to fix
					ladder stile near K'mere Tarn supports rotted but sound	N		Leave
					w,mkr post at Browfoot Fm loose	Y		R to fix – Mark to check way marking
					Fly tipping at SD 45456 02742	N		Mark to check		Mark

743		Mid K'mere	26-Nov	Sid Conway	No new probs	N	22-Feb
					Unnecessary trench across path	Y		Mark to check		Mark

744		crook west	30-Nov	Mark	Stile E of Outrun Nook - high 1st step and broken gate	Y	22-Feb	emailed Dave, Sue to suggest re-build		Unknown
					Waymark post out of gnd W of Borwick Fold	N		Leave as ground too stony to fix
					BW off Back Lane flooded	N

745		Green Qtr	02-Dec	Graham R	Sign at Well Foot	N	22-Feb
					Br/culvert at Spring Wood blocked	Y		Seen by Dave and on his list – done
					BW catch at Staveley Head Fell weld broken and
					extender bent	Y		asked for new one - Mark will fit it – done

746		Wither No 3	05-Dec	Malcolm	Wool on trees at Witherslack Primary School	N	22-Feb

747		Cartmell N	25-Nov	Carolyn	Tree over ROW line at 4200 9230 but can walk round it	Y	22-Feb	Mark and Carolyn cleared enough to restore DL

748		U'barrow	08-Dec	Carolyn	Wall by stile at 4610 9173 collapsed needs re-build	Y	22-Feb	Carolyn/Mark fixed
					Gate near Kirby Hse - barbed wire top of gate	Y		C/M fixed

749		Mid K'mere	11-Dec	Catherine D	Bridle catch on gate at Staveley Head Fell broken	Y	22-Feb	Mark to replace – done
					dead trees at 4510 0175 in guards	N		wait to see what comes out in spring		Unknown

750