## SummaryEffort
Summary of Effort
Guideline | In Scope | IMUM Steps (Do not change literals) | Project Effort Percentage | Unit Count | Unit Effort
| Yes | Project Planning | 5% | 0 | 0
| Yes | Analyze | 10% | 0 | 0
| Yes | Design | 20% | 0 | 0
| Yes | Configure | 50% | 3163 | #REF!
| Yes | Deploy | 10% | 0 | 0
| Yes | Operate | 5% | 0 | 0
|  | Total | 100% | 3163 | #REF!
DO NOT CHANGE
OK TO CHANGE

## Configure_Estimation
Task # | IUM Phase | Task Name | Task Description | Deliverable | Unit Count | Unit Effort | Total Unit Effort | Assumption | On-site Effort % | OffShore Effort % | Onsite Resource Rate | Offshore Resource Rate | Total Onsite Cost | Total Offshore Cost | Total Cost
1 | Project Planning | See Project Tasks tab. See Summary Effort for Effort |  |  |  |  | #REF! |  | 100 | 0 | 300 | 35 | #REF! | #REF! | #REF!
2 | Analyze | See Project Tasks tab. See Summary Effort for Effort |  | Data Model |  |  | #REF! |  | 100 | 0 | 300 | 35 | #REF! | #REF! | #REF!
3 | Design | See Project Tasks tab. See Summary Effort for Effort |  | Data Model |  |  | #REF! |  | 100 | 0 | 300 | 35 | #REF! | #REF! | #REF!
4 | Configure | Prepare Development Environment | Create NZ environment.. Users, DBs, groups, network drive | Dev Environment | 1 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
5 | Configure | Deploy DB objects | Deploy the NZ Physical Data model on Netezza | DDLs | 1000 | 0.1 | 100 |  | 20 | 80 | 300 | 35 | 6000 | 2800 | 8800
6 | Configure | Create Unit Test scripts | Create Unit Test scripts based on the test plan | Test Scripts | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
7 | Configure | Migrate Informatica ETL jobs | Simple | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
8 | Configure | Migrate Informatica ETL jobs | Medium | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
9 | Configure | Migrate Informatica ETL jobs | Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
10 | Configure | Migrate Informatica ETL jobs | Very Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
11 | Configure | Other ETL | Simple | Code | 845 | 1 | 845 |  | 20 | 80 | 300 | 35 | 50700 | 23660 | 74360
12 | Configure | Other ETL | Medium | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
13 | Configure | Other ETL | Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
14 | Configure | Other ETL | Very Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
15 | Configure | Migrate Datastage ETL jobs | Simple | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
16 | Configure | Migrate Datastage ETL jobs | Medium | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
17 | Configure | Migrate Datastage ETL jobs | Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
18 | Configure | Migrate Datastage ETL jobs | Very Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
19 | Configure | PL/SQL Conversion | Simple | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
20 | Configure | PL/SQL Conversion | Medium | Code | 17 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
21 | Configure | PL/SQL Conversion | Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
22 | Configure | PL/SQL Conversion | Very Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
| Configure | Build BO Universe | Medium | Code | 300 | 2 | 600 |  | 20 | 80 | 300 | 35 | 36000 | 16800 | 52800
23 | Configure | Migrate Unix wrapper scripts | Simple | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
24 | Configure | Migrate Unix wrapper scripts | Medium | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
25 | Configure | Migrate Unix wrapper scripts | Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
26 | Configure | Migrate Unix wrapper scripts | Very Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
27 | Configure | Oracle to Netezza data movement scripts | Simple | Code | 1000 | 0.1 | 100 |  | 20 | 80 | 300 | 35 | 6000 | 2800 | 8800
28 | Configure | Oracle to Netezza data movement scripts | Medium | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
29 | Configure | Oracle to Netezza data movement scripts | Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
30 | Configure | Oracle to Netezza data movement scripts | Very Complex | Code | 0 | #REF! | #REF! |  | 20 | 80 | 300 | 35 | #REF! | #REF! | #REF!
31 | Configure | Populate Development Environment | Load the development environment | Dev Environment | 0 | 0 |  |  | 20 | 80 | 300 | 35 | 0 | 0 | 0
[5 empty] | 3163 | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF!
32 | Deploy | See Project Tasks tab. See Summary Effort for Effort |  | Data Model |  |  | #REF! |  | 100 | 0 | 300 | 35 | #REF! | #REF! | #REF!
33 | Operate | See Project Tasks tab. See Summary Effort for Effort |  | Data Model |  |  | #REF! |  | 100 | 0 | 300 | 35 | #REF! | #REF! | #REF!