## Sheet1
2.00	DEMOLITION/ TEMPORARY WORKS.
	Note: Ensure weather tightness, structural stability and protection of the building, neighbouring buildings, garden walls etc during all operations. All demolitions to be in accordance with BS 6187.
	Site Clearance: Removal of trees, shrubs and hedges to be in accordance with HSE/Arboriculture and Forestry Advisory Group Saftey Guides.
	Items to be retained: All items designated to remain in the property of the client are to be protected by the contractor until end of contract.
	All demolitions as per dwgs : 416.002-003
2.01	Separation of house, allowing safe co-existance of inhabitants and contractors: The flat will not be occupied during the works, however the upper floors of the building [Flats B and C] will remain occupied during the works and precautions must be taken at all times to safeguard the inhabitants of the building.
2.02	Entrance Hall: The neighbouring owners will use the front door, and hall, leading to the stairs to the upper flats. Seal against dust by building a temproary dustproof screen with door across hallway.
2.03	Front window: This is suggested for use as the Contractors entrance. Carefully remove central sash window, and put aside for refurbishment and re-installation at end of contract. Protect existing frame, and surrounding brickwork and windows. Install temporary door with good locking to window opening. Contractor can also use windows in Bedroom 3 [which are to be replaced].
2.04	Front Garden: It is proposed that all materials will enter the site through this opening. Remove existing planting. Build temporary raised platform, steps, ramp, hording, etc, as necessary to create safe, secure, access to house for workers and (sometimes heavy!) materials.
	Get approval of proposed temporary works from client/architect before constructing.
2.05	Services: Disconnect, remove and cap off all services and drainage as appropriate at kitchen, utility and bathroom. NB: Pipework to be re-routed as required for the duration of the works.
2.06	Electrics: Disconnect and make safe relevant existing electrical fittings as required.
2.07	Internal fittings. and finishes: Strip out and remove:- WC/bathroom fittings/appliances, un-utilised electrics, plumbing, boiler, gas, internal wall and floor finishes, in areas affected by the works. [NB - The following items are to be retained and re-installed in new postions; oven, dishwasher, washing machine, dryer, boiler, bath, radiators in bedrooms and living room, doors to existing bedrooms, kitchen and living room, existing engineered flooring on lower ground.] [CLIENTS WILL REMOVE FITTED KITCHEN AND NARROW BATHROOM CABINET].
2.08	Damp on Lower Ground: Allow for damp proofing works by specialist sub-contractor and prepare the site as required to all affected areas. All as outlined in damp report [see 1.04].
2.09	Structural Walls: Allow for removing structural walls [incl. any doors and windows in walls to be removed] as marked dwg 416.002-003. Allow here for all temporary props to support structure above [all to be approved by structural engineer prior to any structural alterations being carried out]. NB - Salvage bricks in good condition for re-use.
2.10	Tiled Floors [Ground Floor Hall]: Remove existing floor tiles, taking care so as not to damage existing skirtings. [REMOVAL OF EXISTING FLOOR BOARDS / SUB FLOOR OMITTED].
2.11	OMITTED: Timber Floors [Ground Floor]: Remove existing floor boards and expose existing floor joists, taking care so as not to damage existing skirtings.
2.12	Raised Floors [Lower Ground Floor]: Remove existing flooring/sub-floor and expose existing floor joists. NB - The raised floor might be lowered - to be agreed on site.
2.13	Existing slabs [Lower Ground Floor]: Excavate locally for new drainage runs/connections, taking care not to undermine existing footings and drainage runs. Make good on completion.
2.14	Existing paving slabs [external]: Remove existing concrete paving slabs externally, taking care not to undermine existing drainage runs. Set aside undamaged paving slabs and stack them halfway down the garden in position to be agreed with clients. [EXCAVATION OMITTED].
2.15	Existing balcony and stair [external]: Carefully dismantle existing balcony, balustrade and staircase - to be re-installed once structural steels in rear wall have been installed, and once it has been cleaned and painted. Note that prior to re-installation new foundations below posts are likely to be required as per Structural Engineer's drawing 17194.S-01 and clause 4.01.
2.16	Existing internal doors: Retain all existing doors and set aside for re-use [to be refurbished ready for decoration and upgraded with intumescent seals etc] except entrance door G/D1 which is to be replaced. NB - Suitability of the existing doors must be confirmed by building control authorities. New doors may be required if existing doors don't meet FD30 requirements.
2.17	Existing external windows/doors: Retain existing timber sash windows G/W2-G/W4 to front of building on ground floor [to be refurbished and upgraded with double glazing] and LG/W2-LG/W4 on lower ground floor [to be retained]. All other existing windows and doors to be removed ready for replacement windows/doors
2.18	Internal Walls: Allow for removing partition walls as marked on dwg 416.002-003, including removing existing plasterboard/plaster lath finishes to kitchen walls between flat A and flat B.
2.19	Internal Stair/Landing: Allow for removing part of existing stair, landing and partition wall as marked on dwg 416.002-003.
2.20	Internal Ceilings: Allow for removing ceilings throughout lower ground and ground floor.
2.21	Pipework: Allow for removing the existing internal pipework, external rwp's, gutters and gulley's as required and allow for temporary re-routing for the duration of the works.
2.22	Living room fireplace: Allow for chimney sweep and smoke test of existing chimney. Expose existing brickwork in recess and brush wall with suitable wire brush. Fill in with new bricks to match as required. Clean well with warm water, ready for application of brick sealant [TBC]. All in preparation for new gas burner.