## Sheet1
	Planning
	Master thesis project

	Planned
	Completed
	Failed to proceed as planned

	Current week					X
	Task/Completed \ Week number	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
Preparation	Gain familiarity with the X project

	Gain insight into X scalability issues

	Gain insight into X security issues

	Investigate possible thesis subjects in X

	Determine my role in the X project

	Determine thesis subject

	Literature study based on thesis subject and role in X

	Make planning based on role and thesis subject

Technology background	Literature study on services, write appropriate chapter

	Literature study on services, write appropriate chapter

	Literature study on, write appropriate chapter

	Define and work out use cases

Theoretical model	Write theoretical approach to fullfill research goal

	Create model of theoretical approach

	Create time-sequence diagrams of theoretical approach

	Create generic class diagram of theoretical approach

	Wrapup theoretical model

Reference implement.	Design reference implemenation

	Prepare framework for implemenation

	Make reference implementation

	Gather results from reference implementation

Wrapping up	Write conclusions (answer research question)

	Write future work and reccomendations

	Finalize thesis and other documents (no further research)