Recipients: / CFCU (Ministry of Finance) / SPO (Ministry of Justice) / EC Representation / November 2007	COMPLETION REPORT / Project financed under PHARE Programme / Bulgaria / Project Title: “Support to the Implementation of the Strategy for Reform of the Judiciary through the Introduction of Information Technologies Phase II” / Contract No: Project EuropeAid/121595/D/SER/BG / Project performance period: / 01 December 2006 – 30 November 2007 / PLANET S.A. (Leader), SOFTWARE AG (Partner)

INTERIM REPORT
Project Title: Project Number: Country: Beneficiaries: Name of the Contractor: Project Office Address: Project Office Tel. number: Project Office Fax: Contact person: Signed:	Support to the Implementation of the Strategy for Reform of the Judiciary through the Introduction of Information Technologies Phase II Project EuropeAid/121595/D/SER/BG Bulgaria Ministry of Justice Registry Agency (executive agency of Ministry of Justice) PLANET S.A., SOFTWARE AG 20 Serdica Street - 1000 Sofia +359-2-9871 300 +359-2-9811 411 Elio VOCI, Team Leader

Date of report: Author of report: Quality Control:	September 2007 Elio VOCI, Team Leader Dimos Kontoravdis, Project Director
SPO CFCU EC REPRESENTATION	[name] / [name] / [name] / [name]	[signature] / [signature] / [signature] / [signature]	[date] / [date] / [date] / [date]

Annex 8: Technical Specifications and Functional Specifications of Contract 9, Phase 2 (2005)
Annex 9: System Administrators Entry Test report
Annex 10: Short-term experts' Mission reports

List of Acronyms
BJ	Bulgarian Judiciary
BJIS	Bulgarian Judiciary Information System
BPM	Business Process Management
PBS	Bankruptcy Proceedings System
CA	Contracting Authority
CD	Chief Directorate
CFCU	Central Financing and Contracting Unit
CoE	Council of Europe
CSCS	Conviction Status Certificate System
DBMS	Database Management System
EC	European Commission
ECDL	European Computer Driving License
EDIS	Extended Decentralised Implementation System
EU	European Union
IS	Information System
IST	Information Services and Technologies
IT	Information Technologies
ITIL	Information Technology Infrastructure Library
ISTD	Information Services and Technologies Directorate
JAPC	Judiciary Automation Policy Committee
LAN	Local Area Network
MCEO	Military Counter Espionage Office
MCP	Microsoft Certified Professional
MCSA	Microsoft Certified System Administrator
MD	Ministry of Defence
MOC	Microsoft Official Curriculum
MoJ	Ministry of Justice
MP	Military Police
NIJ	National Institute of Justice
NPD	National Police Directorate
NSI	National Statistical Institute
PA	Public Administration
PoD	Places of Detention
PPO	Public Prosecutors' Office
PRAG	Practical Guide to contract procedures financed from the General Budget of the European Communities in the context of external actions
RA	Registry Agency
RDITC	Research and Development and IT Committee
SJC	Supreme Judiciary Council
SRITC	Scientific Research and IT Committee
TA	Technical Assistance
UIFS	Unified Information Filling System
UIS	Unified Information System
UISCC	Unified Information System to Counter Crime
URS	Unified Registry System
USAID	US Agency for International Development
WAN	Wide Area Network
# Executive summary and recommendations
.
# Review of Progress and Performance at completion
## Policy and programme context
The design of the Bulgarian Judiciary (BJ) IT Strategy has been elaborated by specialists from the Ministry of Justice, PHARE funded IT consultants and other specialists in the IT sector. The IT Strategy for the period 2003-2007 was approved by the Supreme Judicial Council in April 2003 and has been updated recently. Actual reference document is the Judiciary IT Strategy 2006-2009, which sets the priorities for the implementation of the IT technologies in Bulgarian Judiciary.
Component 1 of this project (preparation of Technical Specifications) directly address the areas identified in the PHARE multi-annual (2004-2006) project 2006/018-343.07.01 “SUPPORT FOR FURTHER IMPLEMENTATION OF THE STRATEGY FOR REFORM OF BULGARIAN JUDICIARY”, last revised in July 2006.
More specifically, the scope of this component is the Sub-project IV “Support of the Implementation of the Strategy for Reform of the Judiciary through Introduction of Judicial Information Technologies – Third Stage”, Component IV-2 “Judicial Business Software Applications Development and Supply of Hardware, Communication Equipment and Standard Software”:
- Phase 1, Year 2 (2005), Contract 9: Financial Management, Human Resources' Management, Judicial Inspectorate Management, and Security Guard Management Systems
- Phase 2, Year 3 (2006), Contract 11: Judiciary IT e-learning, Central Electronic Archive, International Penal and Civil Cooperation Systems, and systems harmonisation
## Objectives achieved
### Overall objective and purpose
The Contract will support the MoJ, Supreme Judicial Council and Registry Agency to continue the implementation of Judiciary System modernization and IT Judiciary Strategy by meeting the specific objectives as follows:
No	Objective description and indicators	Degree of achievement and issues
1	To prepare comprehensive needs analysis and budgetary estimations for the supply of hardware and software required for the establishment and for the completion of the comprehensive IT systems for the Bulgarian judiciary.	Partially achieved, pending only the finalisation of budgetary estimation for the Phase 3 (2006) of the multi-annual PHARE Project.
2	To prepare the Technical Specifications for the supply of hardware and software required for the establishment and for the completion of the comprehensive IT systems for the Bulgarian judiciary.	Ongoing. / No issues are foreseen to date.
3	To participate in Phare Supply Tender Procedure for tendering of hardware and software required for the establishment and for the completion of the comprehensive IT systems for the Bulgarian judiciary.	The constraints on the project conclusion might affect the participation of the independent evaluators to the tender(s) evaluation, in case the tender evaluation period(s) start after the project conclusion. The participation to the evaluation of tender for Contract 11 (2006) appears unlikely to date. / Further, the terms of participation of the independent evaluators to the tender(s) evaluation shall be clarified in light of the currently applicable regulations. The adoption of Bulgarian Law on Public Procurement and/or MoJ regulations might make the participation of external evaluators to the tenders' evaluation problematic or even impossible.
4	To provide technical training courses, improving technological knowledge and skills of the staff in judiciary, MoJ and RA.	The identification of trainees achieved an unpredictably large consensus, resulting in nearly 2'600 applicants to technical training. 1'639 staff have attended the technical courses, with an average participation of 61% of applicants invited. / Every effort will be made to deliver the technical training to all the applicants, regardless of their location. / Great concern derives from the extremely low number of candidatures to participate as prospective trainers, around 25 to date.
5	To evaluate the computer skills of the staff in the Judiciary.	No issues are foreseen to date.
6	To prepare set of proposals and recommendations for improvement of the computer skills of the staff in the judiciary.	No issues are foreseen to date.

### Results
The following results have been achieved during the reporting period:
- Product 2.1-1: Technical Specifications for the Phase 2 (2005), Contract 9 of the multi-annual PHARE Project[1] 2006/018-343.07.01.
  [1] See §2.1 Policy and programme context
- Product 4.2-4: Start of training courses for SysAdmin Level 2
  Entry tests to select the candidate trainees according to their actual skills have been organised, and applicants selected and organised in classes.
Please refer to Annex 2 Summary performance data for more details.
## Activities undertaken
### Component 0: Project Management
The inputs allocated for the team of non-key experts have been modified, and the team extended. The two pools are now composed as follows:
Profile	Expert	Approval date	Last reallocation date	Days approved
IT Architect	Lubomir N. Dimov 01-03-2007 120 / Javor Petrov 01-03-2007 30
Software Expert	Tsetska Kyriakova 01-03-2007 120 / Nikolaj Vapirev. 01-03-2007 120 / Toddor Velev 01-03-2007 120 / Stoyanka Misheva 26-04-2007 03-08-2007 20
Infrastructure Expert	Martin Antonov 01-03-2007 03-08-2007 98 / Elli Koulitcheva 01-03-2007 120

Table 1: Composition of Pool 1
Profile	Expert	Approval date	Last reallocation date	Days approved
Training Expert	Elena Gerdjikova 01-03-2007 11-06-2007 36 / Radoslav Yoshinov 01-03-2007 120
Lecturer ECDL	Daniel Kamburov 26-04-2007 03-08-2007 60 / Ivan Garnizov 26-04-2007 03-08-2007 60 / Petar Parvanov 26-04-2007 03-08-2007 60 / Arsenia Grigorova 26-04-2007 03-08-2007 50 / Boyanka Stefanova 26-04-2007 03-08-2007 60 / Monka Kotseva 26-04-2007 03-08-2007 60 / Dimitar Petrov 26-04-2007 03-08-2007 50 / Yanislav Zhelev 26-04-2007 03-08-2007 50 / Mariya Monova-Zheleva 26-04-2007 03-08-2007 60 / Antonina Krumova 23-05-2007 40 / Galina Gardeva 23-05-2007 40 / Mariya Dimitrova 23-05-2007 40 / RalitsaTsakarova 23-05-2007 40 / Veselina Spasova 23-05-2007 40 / Tsvetozar Nikolov 11-06-2007 03-08-2007 20 / Kalinka Ilieva 11-06-2007 03-08-2007 20 / Nataliya Avramova 11-06-2007 03-08-2007 20 / Nelly Vankova 11-06-2007 03-08-2007 25 / Petar Petrov 11-06-2007 03-08-2007 20 / Rossen Djendov 11-06-2007 03-08-2007 20 / Tsvetan Chernev 11-06-2007 03-08-2007 20 / Svetoslav Stefanov 11-06-2007 03-08-2007 25 / Valentin Litov 11-06-2007 03-08-2007 20 / Ventislav Dimitrov 11-06-2007 03-08-2007 20 / Yosko Stoyanov 11-06-2007 03-08-2007 20
Lecturer Microsoft	Antony Stefanov 26-04-2007 03-08-2007 30 / Hristo Hristov 26-04-2007 03-08-2007 30 / Ivan Hadjiski 26-04-2007 03-08-2007 36 / Krasimir Donchev 23-05-2007 03-08-2007 30 / Orlin Marinov 26-04-2007 03-08-2007 30

Table 2: Composition of Pool 2
The need for effective and dynamic communication with the project partners increased exponentially with the start of the technical training, which received about 2'600 applications from the staff of the judiciary.
In order to provide the prospective trainees with a tool to acquire detailed information on the training contents, its planning, and its result, a project web site has been prepared. It is published in two languages (English and Bulgarian) at http://rejis.cc.bas.bg[2].
[2] The hosting of the web site is provided by courtesy of the Computer Centre of the Bulgarian Academy of Science.
### Component 1: Elaboration of Needs Analysis
No progress has been achieved during the reporting period.
The only pending product in this component is the Budgetary Estimation relative to the Component IV-2, Contract 11 described under the Sub-Project IV, Year 3 (2006) of the PHARE multi-annual fiche 2004-2006[3]. Its completion is planned in the next reporting period.
[3] http://ec.europa.eu/enlargement/fiche_projet/index.cfm?page=410708&c=BULGARIA
### Component 2: Preparation of Technical Specifications
#### Technical Specifications for Contract 9 (2005)
Following the design of the systems to be realised and their itemisation, the project Team completed drafting the detailed Technical Specifications.
The full package of the Technical Specifications is composed of:
The section with the General Requirements, which specifies requirements common to more than one lot such as:
  - - The conditions of delivery
  - - Installation and acceptance
  - - Warranty
  - - Maintenance and Support
  - - Training
One section per each individual lot, namely:
  - Lot 1: Enterprise Resource Planning
    The objective of this Lot is the supply of hardware and software for the implementation of an Enterprise Resource Planning (ERP) System in the Bulgarian Ministry of Justice (MoJ) and the Supreme Judicial Council (SJC).
    This section is composed of the Technical Specifications for the System to which a subsection with the Functional Specifications of the ERP system is annexed.
  - Lot 2: Other Management Information Systems (Judicial Inspectorate and Security Guard)
    The objective of this Lot is the supply of hardware and software for the implementation of:
    1. the Management Information System for the Judicial Inspectorate, an independent unit of the Bulgarian Ministry of Justice, and
    2. the Management Information System for the Bulgarian Ministry of Justice, General Directorate Security Guard.
  This section is composed of the Technical Specifications for the Systems to which two subsections are annexed, one with the Functional Specifications of the Judicial Inspectorate MIS and one with the Functional Specifications for the GD Security Guard.
  - Lot 3: Convoy Tracking System (GD Security Guard)
    The objective of this Lot is the supply of hardware, software and services for the implementation of the Convoy Tracking System for the Bulgarian Ministry of Justice, Directorate General Security Guard.
    This section is composed of the Technical Specifications for the System to which a subsection with the Functional Specifications of the GD Security Guard CTS is annexed.
  - Lot 4: Servers, Workstations and Peripherals
    The objective of this Lot is the supply of Servers, Workstations, Computer Peripherals and Office Automation Equipment for the Bulgarian Ministry of Justice.
  - Lot 5: Networking
    The objective of this Lot is the supply of passive and active networking equipment for Structured Cabling for Local Area Network.
  - Lot 6: Workstations and Peripherals
    The objective of this Lot is the supply of specialized Workstations and Computer Peripherals for the Bulgarian Ministry of Justice, GD Security Guard.
Every individual lot section includes, when applicable, the evaluation grid proposing the scoring of the items as well as the formula which will take into account the technical quality of the solution offered in combination with its total cost.
The Total Cost of Ownership (TCO) is preferred, when applicable, to the offered bid cost.
The full document is in line with the relevant Project Fiche and has been elaborated in close cooperation with the Beneficiary. It was delivered both in English and Bulgarian language.
#### Technical Specifications for Contract 11 (2006)
The activities related to the preparation of Technical Specifications for Contract 11 (2006) has been started with investigations on the expected purpose of the component systems.
### Component 4: Training of Staff
The training methodology identified six different profiles of trainee, for each of which a specific curriculum and training approach has been prepared:
- Profile 1: Judge
- Profile 2: Judge Assistant
- Profile 3: Clerk
- Profile 4: Future Trainer
- Profile 5: System Administrator Level 1
- Profile 6: System Administrator Level 2
Access yo courses for System Administrators has been subjected to Entry Test, according to the Training Methodology. All the applicants have sat the tests, and a further profile 'System Administrator Level 0' has been introduced for those System Administrators who did not score the minimum.
The number of candidates substantially exceed the number of 1'400 staff foreseen in the ToR. The following table summarises the current situation:
Profile	Applicants	Trained or scheduled to date
1: Judge	870	478	55% of applicants
2: Judge Assistant	285	195	68% of applicants
3: Clerk	1,486	966	65% of applicants
4: Future Trainer	26
5: System Administrator Level 1[4]	83	62	75% of applicants
6: System Administrator Level 2[5]	11	7	64% of applicants
7: System Administrator Level 0[6]		19
Total:	2,761	1,727	63% of applicants
[4] 77 out of 83 applicants have sat the Entry Test. 62 of them scored enough to access the courses. Those who scored the maximum were promoted to participate in the Training of System Administrators Level 2.
[5] All the 11 applicants have sat the Entry Test. 7 of them have scored enough to access the courses. Courses will include the trainees from the profile System Administrators Level 1 who scored the maximum.
[6] The group of System Administrators Level 0 is composed of the 15 applicants for Level 1 who sat but did not pass the Entry Test, and the 4 applicants for Level 2 who sat but did not pass the Entry Test.

Only 26 candidatures have been collected for Future Trainer. The imbalance between staff to be trained and future trainers constitutes a serious concern for the sustainability of the whole approach.
Please refer to Annex 7: Training Programme for all details.
A telephone hotline and a web site http://rejis.cc.bas.bg were prepared, to provide general information about the project and specific information about the training of the judiciary staff such as courses that are provided for each trainee profile, training locations, personal schedule, etc.
The traffic measured on the website is summarised below:
	Number of visits
Week	Unique	Reloading	Total
28 May – 03 June	123	54	177
04 – 10 June	69	30	99
11 – 17 June	68	43	111
18 – 24 June	93	15	108
25 June – 1 July	47	14	61
Total June	400	156	556
02 – 08 July	35	7	42
09 –15 July	20	7	27
16 – 22 July	20	4	24
23 – 29 July	18	5	23
Total July	93	23	116
30 July – 5 August	13	4	17
6 – 12August	4	0	4
13 – 19August	6	1	7
20 – 26August	31	31	62
Total August	54	36	90
Total Quarter	547	215	762

## Resources and budget used
Please refer to Annex 4 Resource Utilisation for the Reporting Period.
## Assumptions and risks
The project approach is based on the following assumptions:
- The MoJ acts on behalf of all the project partners, and constitutes the only interface to the project team for what concerns the project management and the preliminary approval of all deliverables and project products.
- The applicable tender procedure is based on the Bulgarian Law on Public Procurement
- The tender document has to be published in Bulgarian. For the purpose of this project, the developed Technical Specifications will be submitted in English and translated into Bulgarian as will all the required reports.
- The developed Technical Specifications should be considered as recommendations of the Consultant to the Beneficiary, who is the ultimate authority for the provision of the tendering documents to the Contracting Authority.
- The supplies provided through the tenders financed or co-financed by the Phare Programmes are intended to be exempt of VAT, customs fees, and other duties.
- Contracts are awarded to the 'most economically convenient' offers. During the evaluation of the bids, the evaluators will give to the bids scores, which will be combined according a known formula. The resulting score will determine the winning bid.
Most of the assumptions above have been clarified by Beneficiary and Contracting Authority, some still require further study. Additional assumptions are:
- The Government of Bulgaria, the MoJ and the SJC will maintain a consistent policy and will be committed to the reform of the judiciary, ensuring the appropriate allocation of State and EU funds to this sector through the MoF.
- The MoJ will ensure the sustainability of its IT staff so as to maximize the benefits from project implementation.
- The MoJ and the RA will ensure timely approval and implementation of project recommendations.
- Those responsible for other initiatives in the judiciary sector will maintain close coordination and cooperation in order to ensure the uniformity and timeliness of project results.
- The Beneficiaries (especially the MoJ business departments, the RA and its nationwide IT structure) and other counterparts will closely cooperate for implementing the agreed activities and will be engaged and willing to act promptly on proposals and issues suggested within the project.
- The Beneficiaries will facilitate the implementation of the project (i.e. by ensuring the availability of staff, sufficient secretarial and administrative support, access to information and requested material, etc.)
- The country-wide telecommunications infrastructure will be available in order for the systems procured under the Phare projects that will be evaluated to be successfully implemented; the infrastructure will have the necessary technical characteristics in terms of, for example, bandwidth, transmission speeds and capacity.
Apart from the assumptions mentioned above, we have identified a number of measures to counter possible risks that may delay or prevent successful or timely achievement of the project objectives.
The identified risks and proposed actions to minimise their impact are set out below:
Risks	Potential adverse impact	Risk level	Risk mitigation strategy
Insufficient will to implement/enforce the key elements of the project	High	Low	This risk will be counteracted by high level leadership intervention. In particular, the Consultant will seek close collaboration with senior staff from the Beneficiaries and other related organizations, in order to develop a project culture of “joint commitment” and interest among project members, throughout the course of the project.
Lack of satisfactory number of qualified and experienced specialists in beneficiary organizations involved in current project (due to more attractive remuneration in private sector)	Medium	Medium	The Consultant will try to minimise this risk by transferring knowledge to the employees of the MoJ and RA at an early stage and by supporting them for the whole duration of the project. Additionally, the Consultant will provide experts that will initially cover this gap and as the project evolves they will transfer knowledge and expertise to the existing beneficiary staff.
Staff turnover within the Beneficiary	Medium	Medium	In order to minimise the loss of institutional memory, the Consultant will produce deliverables that will capture both tacit and explicit knowledge, so as to ensure that new staff will be able to make full use of the knowledge that has been provided.
Lack of the Project Management Structure	High	Low	We will minimize the impact of this risk by providing the authorities with support in setting up the management structure and working teams and defining the relevant work procedures.
Delays in the adoption of recommendations by the MoJ and RA	High	Low	We will minimise the impact of this risk by carefully understanding the organisational culture and procedures currently in place, and by suggesting ways of improving the relevant procedures in order to avoid bottlenecks and delays.
Lack of cooperation between the Beneficiaries’ Departments, among the Beneficiaries and with other counterparts	High	Medium	This risk will be counteracted by developing well prepared, structured consultation meetings with the Beneficiaries and all stakeholders involved in the project in order to facilitate close cooperation. Emphasis will be placed on communicating the importance of working together for effectively achieving judiciary reform.
Incompatible design principles in related projects thus affecting the design of the Technical Specifications	Medium	High	The Consultant will elaborate the Technical Specifications based on widely accepted principles. Complementarity, integration and compatibility will be at the centre of the produced Technical Specifications. Wherever necessary, corrective actions will be suggested to keep this risk at minimum.
The implementation of the project is hindered by delays in the implementation of related projects	High	Medium	We will minimise the impact of this risk by carefully understanding the cause of the delay in the implementation of the related project and by suggesting appropriate measures for effectively encountering this delay. Close collaboration with senior officials in the MoJ, the RA and the other Beneficiaries and with those responsible for related projects will also be our key priority in order to build a broad consensus and interest in swiftly implementing the project, thus avoiding any delays.
Risks that are related to project administration procedures and staff commitment: / Consultant does not have full access to all documentation and to all staff able to comment it / No free access to top level staff (within reason) / Fast reaction not always guaranteed for all administrative requirements from the contractor regarding: acceptance of new / CVs, authorisations, invitations, availability of resources, etc / Limited participation of key persons of MoJ, RA, to the project activity	Medium	Medium	In order to minimise the effects of these risks the Consultant will mobilize project team members at an early stage to develop a collaborative team-spirit including updating/ finalization of the overall project work plan. In addition, a crucial element is to develop a “joint commitment” culture with the staff of the Beneficiaries. Promoting the project within the Beneficiaries and establishing first-class relationships with the administrative, management and IT staff is of paramount importance.
Short time limits for the implementation of the project	High	High	We will monitor the project progress closely using the following instruments: / an aggregate Project work plan for the project’s activities with specification of tasks and inputs necessary for each activity, / a detailed team member mobilisation plan for the project’s implementation phase, / periodic meetings between the team leader and the other experts in order to review progress and obstacles reported and to fine tune the work plan, / periodic meetings between the Team Leader and the MoJ to review the Project objectives, work plan, obstacles and achievements and mainly to motivate and implicate them in the project achievement

## Management and coordination arrangements
The Activities indicated in the Experts' Timesheet refer to the WBS indicated in Annex 3: Updated Work plan.
## Key Quality/Sustainability issues
Magistrates were expecting to be offered training with accommodation in hotel in the training place. The training methodology was based on a longer training with daily sessions limited to four hours, also in light of the limited resources available for travel and accommodation. This required daily commuting, and resulted in travel inconvenience for some magistrates based in remote locations. In order to limit the impact of this, in some locations the training was compressed into fewer, full day sessions.
A relatively high number of applicants, mainly magistrates, did not respect the course planning, in many cases agreed by the same applicants. This resulted in uneven numbers of trainees in the courses – some classes were overloaded, others had lower participation.
The candidatures for Future Trainers are extremely scarce: only 26 prospective trainees applied as future trainers from nearly 2'600 staff who expressed their will to attend the technical courses offered, jeopardising the sustainability of the vocational training process in the judiciary.
The number of trainees who declined attendance in the training for System Administrators Level 1 after they applied for the training and passed the entry tests is relatively high. The most common reasons that they stated were either personal reasons or heavy workload in the court. While the personal reasons are understandable and by nature unpredictable, it is more difficult to accept the heavy workload in the court as a reason to not attend the course, since applicants and the courts were informed at the application time about the scope and implications of this kind of courses.
Because the final tests for System Administrators were official Microsoft tests, they were in the English language. There were trainees who had difficulties taking the final test successfully because they did not have sufficient knowledge of the English language. In that regard, although they were very satisfied with the courses and they considered that they knew the material well, they admitted that they had difficulties understanding the test questions and failed on the final tests.
# Lessons learned
## Policy and programme context

## Process of project planning/design

## Project scope
(objectives, resources, budget, etc)
## Assumptions and risks

## Project management/coordination arrangements and stakeholder participation

## Project financing arrangements

## Sustainability

## Results to be delivered
The following table summarises the deliverables of this project.
Deliverable		Project products		Delivery date / Planned in the previous period Planned in the current period Actual
0.1	Inception Report					12 Feb 07
0.2	First Interim Report					06 Mar 07
0.3	Second Interim Report					04 Jun 07
0.4	Third Interim Report			31 Aug 07		05 Sep07
0.5	Final Report			26 Nov 07	26 Nov 07
1.1	Current Status of Judiciary IT and Gap Analysis	1.1-1 The Global Design of the Judiciary IT System / 1.1-2 Current Status of the Judiciary IT / 1.1-3 Gap Analysis				31 May 07
1.2	Need Analysis and Budgetary estimation	1.2-1 Budgetary Estimations for Phase 2 (2005)[7] 31 May 07 / Budgetary Estimations for Phase 3 (2006)3 05 Sep 07 28 Sep 07 / 1.2-2 Action Plan 31 May 07
2.1	Technical Specifications for Phase 2 (2005)	2.1-1	Technical Specifications for Phase 2 (2005)	03 Jul 07		16 Jul 07
2.2	Technical Specifications for Phase 3 (2006)	2.1-2	Technical Specifications for Phase 3 (2006)	26 Sep 07	31 Oct 07
3.1	Independent tender evaluation report	3.1-1 Participation in evaluation of Tender for Contract 9 (2005) / 3.1-2 Participation in evaluation of Tender for Contract 11 (2006) N/A N/A
4.1	Training methodology, programme, materials	4.1-1 Training methodology / 4.1-2 Trainee evaluation methodology / 4.1-3 Lecturer assessment methodology / 4.1-4 Training syllabi (core) / 4.1-5 Training programme and materials				13 May 07
4.2	Training courses	4.2-1 Training courses for Users / 4.2-2 Training courses for Trainers / 4.2-3 Training courses for SysAdm Level 1 / 4.2-4 Training courses for SysAdm Level 2		23 Oct 07	02 Nov 07
4.3	Training report and recommendations	4.3-1 Training report / 4.3-2 Recommendations on further trainings		12 Nov 07	19 Nov 07
[7] See §2.2.2 Results, Product 1.2-1

For a detailed description of the planned activities please refer to Annex 5 Plan of Operations for the Next Reporting Period (Work Programme)
## Activity schedule

### Component 2: Preparation of Technical Specifications
The Technical Specifications will be completed for the systems identified in the Multi-annual programming of the Phare Programme for Bulgaria[8] as it is specifically anticipated under three different Financial Memoranda of Phare 2004, 2005 and 2006 under the same title: 'Support for Further Implementation of the Strategy for Reform of Bulgarian Judiciary':
[8] Ref. “Candidate Systems subject to Functional Analysis”, project deliverable 1.1
1. S4 - Judiciary IT e-Learning System
2. S5 - Central Electronic Archive
3. S6 - International Penal and Civil Cooperation Systems
### Component 4: Training of staff
Forecast tasks for these groups can be summarised as follows:
- Elaboration of training schedule of the additional courses for Profiles 1,2 and 3 and delivery of training
- Elaboration of training schedule and delivery of training for the Trainers
- Elaboration of training schedule and delivery of training for the System Administrators Level 0
- Completion of the courses for the System Administrators Level 1
- Completion of the courses for the System Administrators Level 2
For a detailed calendar see Annex 3: Updated Work plan.
## Special activities to support sustainability
#### Legal & policy sustainability
Special attention will be paid during the implementation of the project to the relevant EC recommendations.
Project technical proposals will be in compliance with the Interchange of Data between Administrations (IDA[9]) EC Programme recommendations, and the PEGSCO (Pan-European eGovernment Services Committee) guidelines[10], which endorsed the recommendations supported by the IDABC[11] Expert Group on Interoperability and by the PEGSCO Technical Working Group (TWG).
[9] IDA is a Community Programme established with a Community Decision in 1995 and managed by the European Commission's Enterprise and Industry Directorate General.
[10] http://ec.europa.eu/idabc/en/document/6420
[11] IDABC (http://ec.europa.eu/idabc/en/home) takes advantage of the opportunities offered by information and communication technologies: - to encourage and support the delivery of cross-border public sector services to citizens and enterprises in Europe, - to improve efficiency and collaboration between European public administrations and, - to contribute to making Europe an attractive place to live, work and invest.
IDA recommendation of use of open standards will be enforced, with special reference to ISO 26300 Open Document Format (ODF), which is the only open international standard intended or suitable for office documents[12].
[12] OpenDocument or ODF, short for the OASIS Open Document Format for Office Applications, is an open format for saving and exchanging office documents such as memos, reports, books, spreadsheets, databases, charts, and presentations. This standard was developed by the OASIS industry consortium and based upon the XML format originally created by OpenOffice.org. ODF was approved as an OASIS standard on May 1, 2005, and was approved for release as an ISO and IEC International Standard (ISO/IEC 26300) on May 8, 2006.
Project training proposals will be in compliance with the reports «The European Union High Level Group for Employment and Social Dimension of the Information Society (ESDIS)» from Oct. 5, 2001 and «The European Union High Level Task Force on Skills and Mobility» from Dec.14, 2001 which identified in ECDL[13] the appropriate example for computer literacy certificate. This is the chosen by the most of the European governments certificate for their administrations and legal systems.
[13] The ECDL Foundation (http://www.ecdl.com) is the global governing body of the world's leading end-user computer skills certification programme, the European Computer Driving Licence (ECDL), which is known as the International Computer Driving Licence (ICDL) outside Europe. The ECDL Foundation is a not-for-profit organisation dedicated to helping to raise the general level of computer skills in society and providing access for all to the Information Society.
Being ECDL a non-vendor based certificate, the ECDL Foundation does not provide training or course materials directly. It does, however, formally approve course materials produced by certain courseware providers. Approval indicates that the training materials cover the syllabus of the programme.
#### Financial sustainability of the designed IT systems
In the respect of the BJ IT Strategy provisions, of the principles expressed in the Project Fiche and financing agreement, of the relevant EU regulations and EC recommendations, the adoption of Open Source software will be preferred.
A collection of documents, publications, reports and links is available on IDA website; among these is a list of Open Source Policies in EU Member States and worldwide[14].
[14] http://ec.europa.eu/idabc/en/document/1677/471
Annex 1: Updated Logframe Matrix
Intervention Logic	Verifiable Indicators	Source of Verification	Assumptions
Overall Objective
To support the MoJ, Supreme Judicial Council and Registry Agency to continue the implementation of Judiciary System modernization and IT Judiciary Strategy	Further improvement of EC assessment of the Bulgarian Judiciary Reform	EC Monitoring Report on the advancements in Bulgarian Judiciary Reform	Bulgarian Government maintains consistent policy for the Reform of the Bulgarian Judiciary / National legislation in line with EU legislation and best practice enacted / Consistent support of the Ministry of Finance (Managing EU funds Directorate and CFCU) / Commitment of the MoJ and Supreme Judicial Council (SJC) to continue with judicial reform and in particular with further development of the Information Systems in the Judiciary / Completion of PHARE EDIS accreditation process
Specific Objectives
Basing on the updated IT strategy and on the Financial Agreement, to prepare a comprehensive needs analysis and budgetary estimations for the supply of hardware and software required for the establishment of the comprehensive BJ IT system.	A detailed design of the comprehensive BJ IT system, the Needs Analysis Report for the supply of hardware and software elaborated. / Budgetary Estimations for the supply of hardware and software, Action plan to implement the comprehensive BJ IT system elaborated.	Project Reporting	Close co-ordination with other initiatives in the sector / Close co-ordination between the MoJ, the RA, and their nationwide IT structure
Preparation of technical specifications for the supply of hardware and software required for the establishment of the comprehensive BJ IT system.	Technical Specifications of hardware and software to be procured under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2, Phase 2 elaborated / Technical Specifications of hardware and software to be procured under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2, Phase 3 elaborated	Project Reporting / Tender for Phase 2 issued / Technical Specifications for Phase 3 accepted by the Contracting Authority	Timely approval and implementation of recommendations by the Beneficiaries / Effectively and timely performed activities for all related PHARE projects
Participation in the evaluation of Supply Tender for hardware and software required for the establishment of the comprehensive BJ IT system.	Participation of independent evaluators and observers in the Tender Evaluations under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2 held within the time frame of this project.	Independent Evaluation Reports for Tenders under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2	Effectively and timely performed activities for the PHARE multi-annual project 2006/018-343.07.01, Component IV-2
Provision of technical training courses, improving technological knowledge and skills of the staff in judiciary, Ministry of Justice and Registry Agency	Training programme formulated / Number of Users trained / Number of Trainers trained / Number of System Administrators trained	Project Reporting / Attendance certificates issued / Certificates issued for successful exams passed	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Initial skills of the Trainers and System Administrators sufficient to attend the requested training courses
Evaluation of computer skills of the User staff of the judiciary	Results of concise tests taken by the User trainees after successful completion of each respective course / Detailed Training Report	Project Reporting / Attendance certificates issued	Only keyboard skills exist among some of beneficiary’s User staff and no formal training programme has been implemented so far
Preparation of detailed report of the IT knowledge of the staff and to prepare set of suggestions and recommendations for its improvement	Detailed Training Report	Project Reporting	Timely approval and implementation of recommendations by MoJ and RA
Results
Submitted Current Status and Gap Analysis of BJ IT system related to the scope of this Contract / Submitted Needs Analysis and Budgetary Estimation of BJ IT system related to the scope of this Contract	The Global Design of the Judiciary IT System, the Analysis of the current status of development and functioning of BJ IT systems, the Gap Analysis of BJ IT systems elaborated / Budgetary Estimations for the supply of hardware and software elaborated / Action Plan for the procurement of the hardware and software elaborated	Project Reporting	Close co-ordination with other initiatives in the sector / Close co-ordination between the MoJ, the RA and their nationwide IT structure
Developed Technical Specifications for the hardware and software required for the establishment and for the completion of the comprehensive IT systems for the Bulgarian judiciary, and proposed to be tendered under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2 / Phase 2 (2005) / Phase 3 (2006)	Technical Specifications of hardware and software to be procured under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2, Phase 2 and Phase 3 elaborated	Tender for Phase 2 issued / Technical Specifications for Phase 3 accepted by the Contracting Authority	Timely approval and implementation of recommendations by the Beneficiaries / Effectively and timely performed activities for all related PHARE projects
One or two experts from the Consultant shall participate as independent evaluator(s) in the Supply Tender Procedure under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2	Number of Tender Evaluations that the Consultant participates under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2	Independent Evaluation Reports	Effectively and timely performed activities for the PHARE multi-annual project 2006/018-343.07.01, Component IV-2
Training programmes provided to the judiciary, to the Ministry of Justice (MoJ) and Registry Agency (RA) for technical IT training of staff of the judiciary;	Training programme formulated	Project Reporting	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Sustainability of the Beneficiaries’ IT staff
Technical IT training for improvement of computer skills provided to 1400 judges, prosecutors, judicial clerks, officers and officials from the judiciary, Ministry of Justice and Registry Agency.	Number of users (judges, prosecutors, judicial clerks, officers and officials from the judiciary, Ministry of Justice and Registry Agency) trained	Project Reporting / Attendance certificates issued	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities
Technical IT training of trainers provided to 320 future trainers from all courts and Public Prosecution Offices in the Judiciary System.	Number of trainers trained	Project Reporting / Attendance certificates issued	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Initial skills of the Trainers and System Administrators sufficient to attend the requested training courses / Sustainability of the Beneficiaries’ IT staff
Specialised Microsoft technical IT training provided to 80 System Administrators in the judiciary, Ministry of Justice and Registry Agency. All successfully trained officials shall be duly certified according to training accomplished.	Number of System Administrators trained	Project Reporting / Attendance certificates issued	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Initial skills of the Trainers and System Administrators sufficient to attend the requested training courses / Sustainability of the Beneficiaries’ IT staff
Advanced specialised Microsoft technical IT training provided to 10 specialised central System Administrators in the Ministry of Justice and Registry Agency. All successfully trained officials shall be duly certified according to training accomplished.	Number of specialised central System Administrators trained	Project Reporting / Attendance certificates issued	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Initial skills of the Trainers and System Administrators sufficient to attend the requested training courses / Sustainability of the Beneficiaries’ IT staff
Tests provided and carried out to evaluate computer skills of the trained staff in the judiciary under each of the above categories;	Training tests elaborated and carried out	Project Reporting / Certificates issued for successful exams passed	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Initial skills of the Trainers and System Administrators sufficient to attend the requested training courses / Sustainability of the Beneficiaries’ IT staff
Submitted detailed report outlining status of the computing skills of the staff in the judiciary, Ministry of Justice and Registry Agency.	Detailed Training Report	Project Reporting	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities
Submitted set of recommendations for improving IT knowledge and skills of the staff in the judiciary, Ministry of Justice and Registry Agency	Detailed Training Report	Project Reporting	Commitment from the Beneficiaries that the personnel will be available to participate in the training activities / Sustainability of the Beneficiaries’ IT staff

Annex 2: Summary performance data
Result description and indicators	Planned target/achievement for the reporting period	Progress/issues	Action required
Submitted Current Status and Gap Analysis of BJ IT system related to the scope of this Contract	Achieved	100% Completed	None
Submitted Needs Analysis and Budgetary Estimation of BJ IT system related to the scope of this Contract	This result is achieved for what is concerning the Needs Analysis and the Budget Estimation of the Component IV-2, Contract 9 described under the Sub-Project IV, Year 2 (2005) of the Phare multi-annual fiche 2004-2006[15].	70% completed[16] / No issues foreseen at this stage	None
Developed Technical Specifications for the hardware and software required for the establishment and for the completion of the comprehensive IT systems for the Bulgarian judiciary, and proposed to be tendered under the PHARE multi-annual project 2006/018-343.07.01, Component IV-2 / Phase 2 (2005) / Phase 3 (2006)	This result includes two distinct targets. / The development of the proposed Technical Specifications for Component IV-2, Contract 9 (see above) has been completed, while the development of the proposed Technical Specifications for Component IV-2, Contract 11 is ongoing and expected to be completed as described in §3.1 Results to be delivered	70% completed / Needs identified basing on Beneficiary requests might fall outside the scope of the Phare multi-annual fiche 2004-2006	Beneficiary might need to request an amendment of the Phare multi-annual fiche 2004-2006 in order to allow the Consultant to include the additional systems in its proposed Technical Specifications.
Training programmes provided to the judiciary, to the Ministry of Justice (MoJ) and Registry Agency (RA) for technical IT training of staff of the judiciary;	Achieved	100% Completed	None
Technical IT training for improvement of computer skills provided to 1400 judges, prosecutors, judicial clerks, officers and officials from the judiciary, Ministry of Justice and Registry Agency.	1'584 staff trained up to date.	90% Completed / The Beneficiary institutions submitted candidatures of prospective trainees by far exceeding the expected target of 1'400 staff: nearly 2'600 staff applied for participating to the training programme.	The Consultant will try to extend the planned training to accept all the candidatures. / This might impose a reduced flexibility toward those trainees who, invited in a course, are not participating at the specified date/time.
Technical IT training of trainers provided to 320 future trainers from all courts and Public Prosecution Offices in the Judiciary System.	This result is planned for the next reporting periods.	Not started / The Beneficiary institutions identified only 26 prospective trainers	The Consultant has no means to increase the willingness of staff to apply as trainer.
Specialised Microsoft technical IT training provided to 80 System Administrators in the judiciary, Ministry of Justice and Registry Agency. All successfully trained officials shall be duly certified according to training accomplished.	Applicants for these training courses have sat a Entry Test aiming to assess their initial knowledges, and their capacity of successfully achieving to the final certification after training.	85% Completed / Some of the prospective trainees has not passed the Entry Test. They have been scheduled for a customised, simplified course tailored on their current knowledges.	None
Advanced specialised Microsoft technical IT training provided to 10 specialised central System Administrators in the Ministry of Justice and Registry Agency. All successfully trained officials shall be duly certified according to training accomplished.	Applicants for these training courses have sat a Entry Test aiming to assess their initial knowledges, and their capacity of successfully achieving to the final certification after training.	15% Completed / Some of the prospective trainees has not passed the Entry Test. They have been scheduled for a customised, simplified course tailored on their current level of knowledge.	None
Tests provided and carried out to evaluate computer skills of the trained staff in the judiciary under each of the above categories;	Performed during the delivery of training courses.	90% Completed	None
Submitted detailed report outlining status of the computing skills of the staff in the judiciary, Ministry of Justice and Registry Agency.	This result is planned for the next reporting periods.	Not started	None
Submitted set of recommendations for improving IT knowledge and skills of the staff in the judiciary, Ministry of Justice and Registry Agency	This result is planned for the next reporting periods.	Not started	None
[15] http://ec.europa.eu/enlargement/fiche_projet/index.cfm?page=410708&c=BULGARIA
[16] Budgetary estimation for Phase 2 (2005) has been completed. Budget estimation for Phase 3 (2006) has been postponed, in agreement with the Beneficiary, to the next quarter in order to give priority to the completion of Technical Specifications for the first budget.

Annex 3: Updated Work plan
The following chart represents the detailed project work plan for the overall project duration.
Please note that the Work Breakdown Structure (WBS) used in the following charts is the following:
x – Component
x.y – Project Product
x.y-z – Project Output
Dx-y – Deliverable (as milestone)
Task

Annex 4: Resource Utilisation for the Reporting Period
The WBS in this table refers to the one presented in the Second Progress Report, Annex 3 Updated Work plan. This is also the coding used in Timesheets for June - August 2007. Please note that the WBS has been changed respect to the one presented in the First Progress Report, to reflect the real organisation of work.
Activities implemented		Time Frame Inputs / Months Key Experts Non-key Experts Incidentals [EUR] / Jun 2007 Jul 2007 Aug 2007 Planned Used Planned Used Planned Used
Component 0: Project management & reporting
0.3	Allocation and management of resources				13	10	--	--	--	--
0.4	Relationships with project counterpart				12	2	--	2	--	--
0.5	Reporting on project progress				11	10	15	0	--	--
Total:					36	22	15	2	--	--
Component 1: Elaboration of Needs Analysis
1.4	Preparation of budgetary estimation				10	1	12	0	--	--
1.5	Preparation of Action Plan				0	4	0	0	--	--
Total:					10	5	12	0	--	--
Component 2: Preparation of Technical Specifications
2.1	Preparation of Technical Specifications for Contract 9 (2005)				33	70	125	160	--	--
2.2	Preparation of Technical Specifications for Contract 11 (2006)				17	20	190	82	--	--
Total:					50	90	315	242	--	--
Component 4: Training of staff
4.6	Training courses for Users				8	0	500	604	9,000	14,119
4.8	Training courses for SysAdm Level 1				26	24	120	85	30,000	14,585
4.9	Training courses for SysAdm Level 2				7	9	35	9	8,000	172
4.10	Training report				4	11	50	26	0	0
Total:					45	44	705	724	47,000	28,876
Grand Total:					141	161	1047	968	47,000	28,876

Annex 5: Plan of Operations for the Next Reporting Period (Work Programme)
Activities		Time Frame Inputs / Months Personnel / Sep 2007 Oct 2007 Nov 2007 Key Experts Non-key Experts Incidentals
Component 0: Project management & reporting
0.3	Allocation and management of resources				6	--	--
0.4	Relationships with project counterpart				3	--	--
0.5	Reporting on project progress				25	--	--
Total:					34	--	--
Component 1: Elaboration of Needs Analysis
1.4	Budgetary Estimations				8	6	--
Total:					8	6	--
Component 2: Preparation of Technical Specifications
2.2	Preparation of Technical Specifications for Contract 11 (2006)				36	65	--
Total:					36	65	--
Component 4: Training of staff
4.6	Training courses for Users				2	140	3,000
4.7	Training courses for Trainers				2	28	2,600
4.8	Training courses for SysAdm Level 1				2	58	7,000
4.9	Training courses for SysAdm Level 2				4	68	1,400
4.10	Training report				20	22	--
4.11	Recommendations				16		--
Total:					30	316	14,000
Grand Total:					108	387	14,000

Annex 6: Updated Resource Utilisation
Inputs		Initial Planned	Realised
Key Long-term experts
KE1, Team Leader	Elio VOCI	200	200
Key Short-term experts
KE2, Technical Specifications Advisor	Ioannis SIDIROPOULOS	120	144
KE3, Contracts Management Advisor	Gerard O'NEILL	120	120
KE4, Training Advisor	Dobromir PAPAZOV	120	120
Independent Evaluator		50	--
Non-key experts
IT Architect	Lubomir N. Dimov	1100	147
	Javor Petrov		30
Software Expert	Tsetska Kiriakova		147
	Stoyanka Misheva		47
	Nikolaj Vapirev		120
	Toddor Velev		140
Infrastructure Expert	Martin Antonov		120
	Elli Koulitcheva		120
Total Pool 1		1100	871

Inputs		Initial Planned	Realised
Key Long-term experts
KE1, Team Leader	Elio VOCI	200	200
Key Short-term experts
KE2, Technical Specifications Advisor	Ioannis SIDIROPOULOS	120	144
KE3, Contracts Management Advisor	Gerard O'NEILL	120	120
KE4, Training Advisor	Dobromir PAPAZOV	120	120
Independent Evaluator		50	--

Non-key experts
IT Architect	Lubomir N. Dimov	1100	147
	Javor Petrov		30
Software Expert	Tsetska Kiriakova		147
	Stoyanka Misheva		47
	Nikolaj Vapirev		120
	Toddor Velev		140
Infrastructure Expert	Martin Antonov		120
	Elli Koulitcheva		120
Total Pool 1		1100	871

Training Expert	Elena Gerdjikova	900
	Radoslav Yoshinov
Lecturer ECDL	Antonina Krumova
	Arsenia Grigorova-Stankova
	Boyanka Stefanova
	Daniel Kamburov
	Dimitar Petrov
	Galina Momceva-Gardeva
	Ivan Garnizov
	Mariya Dimitrova
	Mariya Monova-Zheleva
	Monka Kotseva
	Petar Parvanov
	RalitsaTsakarova
	Veselina Spasova
	Yanislav Zhelev
	Tsvetozar Nikolov
	Kalinka Ilieva
	Nataliya Avramova
	Nelly Vankova
	Petar Petrov
	Rossen Djendov
	Tsvetan Chernev
	Svetoslav Stefanov
	Valentin Litov
	Ventislav Dimitrov
	Yosko Stoyanov
Lecturer Microsoft	Antony Stefanov
	Hristo Hristov
	Ivan Hadjiski
	Krasimir Donchev
	Orlin Marinov
Total Pool 2		900
Total Non-key experts		2000	2000

Annex 7: Training Programme

The following tables summarise the courses delivered or scheduled.

The decimals in the values relative to the System Administrators 1 and 2 is due to the fact that the program for these profiles are composed of four distinct courses, and invitation and attendance is monitored on a per-course basis. Values are obtained as one fourth of the measured occurrences.