## Resource Utilization
Monthly Resource Availability
Legend | The date the work order appears in the internal system | [9 empty] | Legend & Colour Codes
TAT | Total Available Time | [9 empty] | W |  | Working Day
TUT | Total Unplanned Training | [9 empty] | U |  | Unplanned Training
TPT | Total Planned Training | [9 empty] | T |  | Planned Training
TH | Total Holidays | [9 empty] | H |  | Holiday
TL | Total Leave | [9 empty] | L |  | Leave
2007-08-01
Name | Effective Resource Availability |  | TAT (Days) | TUT (Days) | TPT (Days) | TH (Days) | TL (Days) | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F
| Productivity | Hours | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Ashwini | 100% | 132 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
Siba | 100% | 132 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
Suraj | 100% | 114 | 19 | 0 | 0 | 1 | 3 | W | W | W |  |  | W | W | W | W | W |  |  | W | W | H | W | W |  |  | W | W | L | L | L |  |  | W | W | W | W | W
Yadvendra | 100% | 132 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
Ujjwal | 100% | 102 | 17 | 0 | 0 | 1 | 5 | W | W | W |  |  | W | W | W | W | W |  |  | L | L | H | L | L |  |  | L | W | W | W | W |  |  | W | W | W | W | W
Vikas | 100% | 132 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
Pradeep | 100% | 120 | 20 | 0 | 0 | 1 | 2 | W | W | W |  |  | W | W | W | W | W |  |  | W | W | H | W | W |  |  | W | W | W | L | L |  |  | W | W | W | W | W
Shilpa | 100% | 132 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
Suma | 10% | 13.2 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
| 0% | 0 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
| 0% | 0 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
| 0% | 0 | 22 | 0 | 0 | 1 | 0 | bar: W 1 to F 31
| 0% | 0 | 21 | 1 | 0 | 1 | 0 | W | W | W |  |  | W | W | W | W | W |  |  | W | W | H | W | U |  |  | W | W | W | W | W |  |  | W | W | W | W | W
| 0% | 0 | 21 | 0 | 1 | 1 | 0 | W | W | W |  |  | W | W | W | W | W |  |  | W | W | H | T | W |  |  | W | W | W | W | W |  |  | W | W | W | W | W
Total |  | 1009.2 | 296 | 1 | 0 | 13 | 10
2007-09-01
| Effective Resource Availability |  | TAT (Days) | TUT (Days) | TPT (Days) | TH (Days) | TL (Days) | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU
| Productivity | Hours | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Ashwini | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Siba | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Suraj | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Yadvendra | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Ujjwal | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Vikas | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Pradeep | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Shilpa | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Suma | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
| 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
| 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
| 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
| 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
| 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: SA 1 to SU 30
Total |  | 1680 | 280 | 0 | 0 | 0 | 0
2007-10-01
Name | Effective Resource Availability |  | TAT (Days) | TUT (Days) | TPT (Days) | TH (Days) | TL (Days) | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W
| Productivity | Hours | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Ashwini | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Siba | 100% | 108 | 18 | 0 | 0 | 0 | 2 | bar: M 1 to W 31
Suraj | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Yadvendra | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Ujjwal | 100% | 90 | 15 | 0 | 0 | 0 | 2 | bar: M 1 to W 31
Praveena | 50% | 60 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Pradeep | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Shilpa | 100% | 120 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Suma | 0% | 0 | 18 | 0 | 0 | 0 | 2 | bar: M 1 to W 31
Biswajit | 50% | 60 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Manendar | 50% | 60 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
| 0% | 0 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
| 0% | 0 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
| 0% | 0 | 20 | 0 | 0 | 0 | 0 | bar: M 1 to W 31
Total |  | 978 | 271 | 0 | 0 | 0 | 6
2007-11-01
Name | Effective Resource Availability |  | TAT (Days) | TUT (Days) | TPT (Days) | TH (Days) | TL (Days) | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F
| Productivity | Hours | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Ashwini | 100% | 114 | 19 | 0 | 0 | 3 | 1 | H | L |  |  | W | W | W | H | H |  |  | W | W | W | W | W | W |  | W | W | W | W | W |  |  | W | W | W | W | W
Siba | 100% | 78 | 13 | 0 | 0 | 3 | 7 | H | W |  |  | W | W | W | H | H |  |  | W | W | W | W | W | L |  | L | L | L | L | L |  |  | L | W | W | W | W
Suraj | 0% | 0 | 19 | 0 | 0 | 3 | 1 | H | W |  |  | W | W | W | H | H |  |  | W | W | W | W | W | W |  | W | W | W | W | W |  |  | L | W | W | W | W
Yadvendra | 100% | 66 | 11 | 0 | 0 | 3 | 9 | H | W |  |  | L | L | L | H | H |  |  | L | L | L | L | L | L |  | W | W | W | W | W |  |  | W | W | W | W | W
Ujjwal | 80% | 81.6 | 17 | 0 | 0 | 3 | 3 | H | L |  |  | W | L | W | H | H |  |  | L | W | W | W | W | W |  | W | W | W | W | W |  |  | W | W | W | W | W
Pradeep | 100% | 114 | 19 | 0 | 0 | 3 | 1 | H | W |  |  | W | W | W | H | H |  |  | L | W | W | W | W | W |  | W | W | W | W | W |  |  | W | W | W | W | W
Shilpa | 100% | 108 | 18 | 0 | 0 | 3 | 2 | H | W |  |  | W | W | W | H | H |  |  | W | W | W | L | W | W |  | W | W | W | W | L |  |  | W | W | W | W | W
Suma | 0% | 0 | 16 | 0 | 0 | 3 | 4 | H | W |  |  | W | W | W | H | H |  |  | W | W | L | W | W | W |  | W | L | L | W | W |  |  | W | L | W | W | W
Praveena | 50% | 42 | 14 | 0 | 0 | 3 | 6 | H | W |  |  | W | W | L | H | H |  |  | L | L | L | L | L | W |  | W | W | W | W | W |  |  | W | W | W | W | W
Manendra | 50% | 51 | 17 | 0 | 3 | 3 | 0 | H | W |  |  | W | W | W | H | H |  |  | W | W | W | T | T | T |  | W | W | W | W | W |  |  | W | W | W | W | W
Biswajit | 50% | 57 | 19 | 0 | 0 | 3 | 0 | H | W |  |  | W | W | W | H | H |  |  | W | W | W | W | W | W |  | W | W | W | W | W |  |  | W | W | W | W | L
| 0% | 0 | 20 | 0 | 0 | 3 | 0 | bar: TH 1 to F 30
| 0% | 0 | 20 | 0 | 0 | 3 | 0 | bar: TH 1 to F 30
Total |  | 711.6 | 222 | 0 | 3 | 36 | 34
2007-12-01
Name | Effective Resource Availability |  | TAT (Days) | TUT (Days) | TPT (Days) | TH (Days) | TL (Days) | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M
| Productivity | Hours | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Ashwini | 100% | 96 | 16 | 0 | 0 | 1 | 3 |  |  | W | W | W | W | W |  |  | W | W | L | L | L |  |  | W | W | W | W | W |  |  | W | H | W | W | W |  |  | W
Siba | 100% | 114 | 19 | 0 | 0 | 1 | 0 | bar: SA 1 to M 31
Suraj | 100% | 102 | 17 | 0 | 0 | 1 | 1 |  |  | W | W | W | W | W |  |  | W | W | W | L | W |  |  | W | W | W | W | W |  |  | W | H | W | W | L |  |  | L
Yadvendra | 100% | 114 | 19 | 0 | 0 | 1 | 0 | bar: SA 1 to M 31
Ujjwal | 100% | 114 | 19 | 0 | 0 | 1 | 0 | bar: SA 1 to M 31
Pradeep | 100% | 90 | 15 | 0 | 0 | 1 | 4 |  |  | W | W | W | W | W |  |  | W | W | W | W | W |  |  | W | W | L | L | L |  |  | L | H | W | W | W |  |  | W
Shilpa | 100% | 96 | 16 | 0 | 0 | 1 | 3 |  |  | L | L | L | W | W |  |  | W | W | W | W | W |  |  | W | W | W | W | W |  |  | W | H | W | W | W |  |  | W
Suma | 0% | 0 | 16 | 0 | 0 | 1 | 3 |  |  | W | W | W | W | L |  |  | L | W | W | W | W |  |  | W | W | W | W | W |  |  | L | H | W | W | W |  |  | W
Praveena | 100% | 108 | 18 | 0 | 0 | 1 | 1 |  |  | W | W | W | W | W |  |  | L | W | W | W | W |  |  | W | W | W | W | W |  |  | W | H | W | W | W |  |  | W
Manendra | 100% | 108 | 18 | 0 | 0 | 1 | 1 |  |  | W | W | W | W | W |  |  | W | W | W | W | W |  |  | W | L | W | W | W |  |  | W | H | W | W | W |  |  | W
Biswajit | 100% | 0 | 0 | 0 | 0 | 1 | 16 |  |  | L | L | L | L | L |  |  | L | L | L | L | L |  |  | L | L | L | L | L |  |  | L | H | L | L | L |  |  | W
| 0% | 0 | 19 | 0 | 0 | 1 | 0 | bar: SA 1 to M 31
| 0% | 0 | 19 | 0 | 0 | 1 | 0 | bar: SA 1 to M 31
Total |  | 942 | 211 | 0 | 0 | 12 | 32
2008-01-01
Name | Effective Resource Availability |  | TAT (Days) | TUT (Days) | TPT (Days) | TH (Days) | TL (Days) | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH | F | SA | SU | M | TU | W | TH
| Productivity | Hours | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Ashwini | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Siba | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Suraj | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Yadvendra | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Ujjwal | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Vikas | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Pradeep | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Shilpa | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Suma | 0% | 0 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Praveena | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Manendra | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Biswajit | 100% | 114 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
| 0% | 0 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
| 0% | 0 | 19 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31
Total |  | 1254 | 266 | 0 | 0 | 0 | 0 | bar: TU 1 to F 4; M 7 to F 11; M 14 to F 18; M 21 to F 25; M 28 to TH 31

## Functional Testing Phase
Test Case Execution Phase 1
Project | Resource | Actual Start Date | Actual End Date | Actual Effort Hrs | Total # TCs | # TCs Executed |  | # TCs Passed | Pass % | # TCs Failed | Fail % | # TCs Blocked | # TCs Researching | # TCs Modified during Testing | # TCs Added during testing | Status | Total Issues | Issues Open | Issues Closed | Issues Rejected | Issue Status
[7 empty] | % Complete |  |  |  | Fail %
OS-3.22 Intl | 0 | 0 | 0 | 1 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 4 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 3 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 1 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## Project Management
Project | Project Phase | Project Status | PLANNING |  |  |  |  | CURRENT STATUS
|  |  | Estimated Start Date | Estimated End Date | Estimated Hrs | Assigned Date | No. Of Resources | Actual Start Date | Actual End Date | Duration in Days | Total Actual Effort Hrs | % Complete | Status | Schedule Variance | Effort Variance
Phase
[16 empty] | TCC | Test Case Creation Phase
OS-3.22 Intl | REG | Inprogress | 2007-10-30 | 2007-12-07 | 1356 | 2007-10-30 | 10 | 2007-10-30 | 2007-12-18 | 48 | 905 | 96.15% | Inprogress | 28.9474 | 0.3326 | FUN | Functional Testing Phase
[8 empty] | 0 | 0 | 0 | 0 | 0% |  | #VALUE! | #VALUE! | REG | Regression Testing Phase
[16 empty] | ACC | Final Accpetance Testing Phase
Project | Total # TC created | Total # TC Executed | Total # Issues Found | Total # Issues Closed | Total # Issues Rejected | Defect Found Rate | Defect Rejected Rate | Issue Fixed Ratio | Available Hours | Utilized Hours | Team Productivity
OS-3.22 Intl | 138 | 2899 | 90 | 31 | 16 | 0.031045 | 0.51613 | 0.34444 | 1208 | 905 | 74.92%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
CURRENT STATUS = IF([Project Phase]="TCC",'Test Case Creation Phase'!C5,IF('Project Management'!$[Project Phase]="FUN",'Functional Testing Phase'!C5,IF('Project Management'!$[Project Phase]="REG",'Regression Testing Phase'!C5,'Final Acceptance Testing Phase'!C5)))
Actual End Date = IF([Project Phase]="TCC",'Test Case Creation Phase'!D5,IF('Project Management'!$[Project Phase]="FUN",'Functional Testing Phase'!D5,IF('Project Management'!$[Project Phase]="REG",'Regression Testing Phase'!D5,'Final Acceptance Testing Phase'!D5)))
Note on B5: dsuma: Enter the Testing Phase as mentioned. TCC - Test Case Creation Phase FUN - Functional Testing Phase REG - Regression Testing Phase ACC- Final Acceptance Testing Phase
Note on B6: dsuma: Enter the Testing Phase as mentioned. TCC - Test Case Creation Phase FUN - Functional Testing Phase REG - Regression Testing Phase ACC- Final Acceptance Testing Phase

## Test Case Creation Phase
Test Case Creation
Project | Resource | Actual Start Date | Actual End Date | Total Effort Hrs | Actual Effort Hrs | Actual Review Hrs | Actual Rework Hrs | Total # TCs | # TCs Created | TCs Reviewed By | # TCs Modified after Review | # TCs Added after Review | % Complete | Status | Defect %
| 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0% |  | 0%
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
| 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0% |  | 0%
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
Formulas:
Actual Start Date = MIN([Actual Start Date, row below]:C30)
Actual End Date = MAX([Actual End Date, row below]:D30)

## Regression Testing Phase
Test Case Execution Phase 2
Project | Resource | Actual Start Date | Actual End Date | Actual Effort Hrs | Total # TCs | # TCs Executed |  | # TCs Passed | Pass % | # TCs Failed | Fail % | # TCs Blocked | # TCs Researching | # TCs Modified during Testing | # TCs Added during testing | Status | Total Issues | Issues Open | Issues Closed | Issues Rejected | Issue Status
[7 empty] | % Complete |  |  |  | Fail %
OS-3.22 Intl | 45 | 2007-10-30 | 2007-12-18 | 904 | 3015 | 2899 | 96.15% | 2846 | 86.23% | 53 | 8.475% | 113 | 0 | 100 | 138 | Inprogress | 90 | 43 | 31 | 16 | Open
Cabinet | Ashwini | 2007-10-30 | 2007-11-06 | 14 | 107 | 105 | 98.13% | 104 | 97.2% | 1 | 0.9346% | 2 | 0 | 0 | 15 | Inprogress | 4 | 1 | 0 | 3 | Open
Admn-Acc | Yadvendra | 2007-10-30 | 2007-11-02 | 16 | 57 | 57 | 100% | 57 | 100% | 0 | 0% | 0 | 0 | 3 | 0 | Complete | 1 | 0 | 1 | 0 | All Closed
Admn-Acc | Biswajit | 2007-10-31 |  | 23 | 96 | 86 | 89.58% | 86 | 89.58% | 0 | 0% | 10 | 0 | 0 | 0 | Inprogress | 1 | 0 | 1 | 0 | All Closed
Admn-Setup | Suraj | 2007-10-30 | 2007-12-12 | 47 | 233 | 232 | 99.57% | 220 | 94.42% | 12 | 5.15% | 1 | 0 | 6 | 0 | Inprogress | 19 | 5 | 14 | 0 | Open
Fault Mgmt | Shilpa | 2007-10-30 | 2007-11-29 | 97 | 344 | 344 | 100% | 344 | 100% | 0 | 0% | 0 | 0 | 15 | 0 | Complete | 2 | 0 | 0 | 2 | All Closed
Fault Mgmt | Praveena | 2007-10-31 | 2007-11-05 | 25 | 54 | 54 | 100% | 54 | 100% | 0 | 0% | 0 | 0 | 0 | 54 | Complete | 0 | 0 | 0 | 0
Com Int/HSP | Siba | 2007-10-30 |  | 32 | 65 | 65 | 100% | 65 | 100% | 0 | 0% | 0 | 0 | 32 | 0 | Complete | 4 | 4 | 0 | 0 | Open
Security | Suraj | 2007-10-30 | 2007-11-05 | 4 | 8 | 8 | 100% | 8 | 100% | 0 | 0% | 0 | 0 | 6 | 3 | Complete | 0 | 0 | 0 | 0
AFT | Pradeep | 2007-10-30 | 2007-11-15 | 39 | 120 | 106 | 88.33% | 102 | 85% | 4 | 3.333% | 14 | 0 | 0 | 0 | Inprogress | 14 | 6 | 2 | 6 | Open
Game Supt | Ashwini | 2007-10-30 | 2007-11-28 | 28 | 140 | 140 | 100% | 140 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Fault Mgmt | Pradeep | 2007-10-30 | 2007-12-18 | 11 | 101 | 101 | 100% | 101 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Com Int/HSP | Manendar | 2007-10-30 | 2007-12-07 | 46 | 85 | 84 | 98.82% | 78 | 91.76% | 6 | 7.059% | 1 | 0 | 20 | 0 | Inprogress | 6 | 4 | 2 | 0 | Open
Admn-Acc | Ujjwal | 2007-10-30 | 2007-12-12 | 40 | 106 | 106 | 100% | 102 | 96.23% | 4 | 3.774% | 0 | 0 | 0 | 0 | Inprogress | 0 | 0 | 0 | 0
Fault Mgmt | Manendar | 2007-10-31 | 2007-11-06 | 17 | 50 | 50 | 100% | 50 | 100% | 0 | 0% | 0 | 0 | 2 | 0 | Complete | 0 | 0 | 0 | 0
Cabinet | Yadvendra | 2007-11-02 | 2007-11-06 | 5 | 5 | 5 | 100% | 5 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Cabinet S9000 | Ashwini | 2007-11-05 | 2007-11-13 | 11 | 59 | 57 | 96.61% | 56 | 94.92% | 1 | 1.695% | 2 | 0 | 0 | 0 | Inprogress | 4 | 1 | 0 | 3 | Open
Progressive(Mikhon) | Ashwini |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Platform | Siba | 2007-11-12 | 2007-11-14 | 16 | 11 | 11 | 100% | 11 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 1 | 1 | 0 | 0 | Open
Perihperals(PRN) | Shilpa | 2007-10-30 | 2007-11-30 | 20 | 41 | 39 | 95.12% | 39 | 95.12% | 0 | 0% | 2 | 0 | 0 | 0 | Inprogress | 0 | 0 | 0 | 0
History | Suraj | 2007-11-15 | 2007-12-10 | 36 | 121 | 91 | 75.21% | 87 | 71.9% | 4 | 3.306% | 30 | 0 | 2 | 37 | Inprogress | 8 | 0 | 8 | 0 | All Closed
Money & Credit Handling | Ujjwal | 2007-11-15 | 2007-11-28 | 21 | 57 | 57 | 100% | 57 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Operational Features | Praveena | 2007-11-19 | 2007-11-30 | 8 | 18 | 18 | 100% | 17 | 94.44% | 1 | 5.556% | 0 | 0 | 0 | 0 | Inprogress | 0 | 0 | 0 | 0
RCG | Pradeep | 2007-11-15 | 2007-11-29 | 25 | 74 | 70 | 94.59% | 69 | 93.24% | 1 | 1.351% | 4 | 0 | 0 | 0 | Inprogress | 2 | 2 | 0 | 0 | Open
Ram Clear | Manendar | 2007-11-13 | 2007-11-13 | 2 | 10 | 10 | 100% | 10 | 100% | 0 | 0% | 0 | 0 | 10 | 0 | Complete | 0 | 0 | 0 | 0
Multipay Device | Ujjwal | 2007-11-23 | 2007-11-30 | 10 | 26 | 26 | 100% | 26 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Progressive(Internal) | Biswajit | 2007-11-26 | 2007-11-29 | 8 | 8 | 7 | 87.5% | 6 | 75% | 1 | 12.5% | 0 | 0 | 0 | 0 | Inprogress | 2 | 2 | 0 | 0 | Open
Peripherals(Hopper,coin etc.) | Ashwini | 2007-11-15 | 2007-12-07 | 24 | 67 | 67 | 100% | 67 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Diagnostics | Suraj | 2007-11-22 | 2007-12-07 | 19 | 96 | 96 | 100% | 96 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Fault Mgmt | Ashwini | 2007-11-05 | 2007-12-06 | 19 | 40 | 40 | 100% | 40 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Cabinet S9000 | Praveena | 2007-11-05 | 2007-11-13 | 8 | 53 | 53 | 100% | 53 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Admn-Setup | Biswajit | 2007-11-12 |  | 10 | 11 | 11 | 100% | 11 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Admn-Setup | Shilpa | 2007-10-30 | 2007-10-30 | 1 | 1 | 1 | 100% | 0 | 0% | 1 | 100% | 0 | 0 | 0 | 1 | Inprogress | 1 | 1 | 0 | 0 | Open
History | Shilpa | 2007-10-30 | 2007-10-30 | 1 | 1 | 1 | 100% | 0 | 0% | 1 | 100% | 0 | 0 | 0 | 1 | Inprogress | 1 | 1 | 0 | 0 | Open
History | Biswajit | 2007-11-15 |  | 20 | 38 | 35 | 92.11% | 34 | 89.47% | 1 | 2.632% | 3 | 0 | 0 | 20 | Inprogress | 2 | 2 | 0 | 0 | Open
Perihperals(PRN) | Ashwini | 2007-11-15 | 2007-12-03 | 33 | 91 | 91 | 100% | 90 | 98.9% | 1 | 1.099% | 0 | 0 | 0 | 0 | Inprogress | 3 | 1 | 0 | 2 | Open
Admn-Acc | Shilpa | 2007-11-17 | 2007-11-30 | 24 | 100 | 100 | 100% | 96 | 96% | 4 | 4% | 0 | 0 | 0 | 7 | Inprogress | 4 | 4 | 0 | 0 | Open
Perihperals(PRN) | Yadvendra | 2007-11-19 | 2007-11-26 | 13 | 35 | 28 | 80% | 27 | 77.14% | 1 | 2.857% | 7 | 0 | 2 | 0 | Inprogress | 2 | 1 | 1 | 0 | Open
RCG | Biswajit | 2007-11-15 | 2007-11-30 | 20 | 64 | 64 | 100% | 64 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Perihperals(PRN) | Manendar | 2007-11-20 | 2007-12-03 | 31 | 94 | 92 | 97.87% | 89 | 94.68% | 3 | 3.191% | 2 | 0 | 0 | 0 | Inprogress | 3 | 1 | 2 | 0 | Open
Operational Features | Ashwini | 2007-11-23 | 2007-11-30 | 2 | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0 | 2 | 0 | Complete | 0 | 0 | 0 | 0
Peripherals(Hopper,coin etc.) | Yadvendra | 2007-11-22 | 2007-11-30 | 33 | 140 | 105 | 75% | 104 | 74.29% | 1 | 0.7143% | 35 | 0 | 0 | 0 | Inprogress | 1 | 1 | 0 | 0 | Open
Progressive(Internal) | Siba | 2007-11-28 |  | 16 | 30 | 28 | 93.33% | 28 | 93.33% | 0 | 0% | 0 | 0 | 0 | 0 | Inprogress | 0 | 0 | 0 | 0
Diagnostics | Praveena | 2007-11-22 | 2007-12-07 | 25 | 138 | 138 | 100% | 138 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0
Game Supt | Shilpa | 2007-10-30 | 2007-11-28 | 1 | 1 | 1 | 100% | 0 | 0% | 1 | 100% | 0 | 0 | 0 | 0 | Inprogress | 1 | 1 | 0 | 0 | Open
Admn-Acc | Manendar | 2007-11-29 | 2007-12-07 | 3 | 18 | 18 | 100% | 14 | 77.78% | 4 | 22.22% | 0 | 0 | 0 | 0 | Inprogress | 4 | 4 | 0 | 0 | Open
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
OS- 3.22.01 | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
OS- 3.22.01 | Ashwini |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Yadvendra |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## Final Acceptance Testing Phase
Test Case Execution Phase 3
Project | Resource | Actual Start Date | Actual End Date | Actual Effort Hrs | Total # TCs | # TCs Executed |  | # TCs Passed | Pass % | # TCs Failed | Fail % | # TCs Blocked | # TCs Researching | # TCs Modified during Testing | # TCs Added during testing | Status | Total Issues | Issues Open | Issues Closed | Issues Rejected | Issue Status
[7 empty] | % Complete |  |  |  | Fail %
| 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
OS- 3.22.01 | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
OS- 3.22.01 | Ashwini |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Yadvendra |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0