## metadatadeliverables-2
No: | PM | Date | Post |  | Status | Deliverable
1.1 | 2 | 2004-10-01 | ATLAS | 0 | Done | Review and assess ATLAS documentation referring to HEP metadata use cases
4.1.1 | 4 | 2005-12-01 | ATLAS | 0 | dev | (Revise to: 'EGEE Metadata Catalogue interface for AMI') AMI Admin Tool
9.1 | 4 | 2004-12-01 | ATLAS | 0 |  | Initial EGEE Phase 1 release
2.1 | 5 | 2005-01-01 | ATLAS | 0 |  | Document AMI schema for metadata
3.1 | 7 | 2005-03-01 | ATLAS | 0 |  | Definition of Metadata service in AMI
5.1 | 10 | 2005-06-01 | ATLAS | 0 |  | Document monitoring requirements of AMI
7.1 | 14 | 2005-10-01 | ATLAS | 0 |  | Review AMI implementation
8.1 | 18 | 2006-02-01 | ATLAS | 0 |  | AMI throughput testing of database access via Metadata using AMI
8.1.1 | 18 | 2006-02-01 | ATLAS | 0 |  | Evaluation of AMI Metadata service from DC3
4.2.1 | 20 | 2006-04-01 | ATLAS | 0 |  | User Metadata writing capability code and user documentation in commisioning run
11.1 | 23 | 2006-07-01 | ATLAS | 0 |  | Produce a document on user access optimisation of data access via metadata in AMI
12.1.1 | 27 | 2006-11-01 | ATLAS | 0 |  | Evaluation of ATLAS metadata services in commissioning run
10.1 | 28 | 2006-12-01 | ATLAS | 0 |  | Review POOL and RLS for DD (ATLAS)
4.3.1 | 33 | 2007-05-01 | ATLAS | 0 |  | Production release
12.1 | 35 | 2007-07-01 | ATLAS | 0 |  | Final evaluation of ATLAS metadata components
6.1.2 | o |  | ATLAS | 0 |  | GridPP Metadata web pages
1.2 | 2 | 2004-10-01 | CDF | 1 | Done | Review and assess of CDF documentation referring to HEP metadata use cases
1 | 3 | 2004-11-01 | All | 1 | v1.0 | Review and assess all known documents referring to HEP metadata use cases
1.3 | 3 | 2004-11-01 | Generic | 1 |  | Review and assess documentation referring to HEP metadata use cases
2.2.1 | 4 | 2005-12-01 | CDF | 1 | draft | Document existing Dimension Editor
2.2 | 5 | 2005-01-01 | CDF | 1 |  | Document SAM schema for metadata
4.1.2 | 5 | 2005-01-01 | All | 1 |  | Review of EGEE Metadata Catalog
2 | 6 | 2005-02-01 | All | 1 |  | Documenting schema for metadata
2.3 | 6 | 2005-02-01 | Generic | 1 |  | Summary document of differences in schema for metadata between experiments
4.1.3 | 6 | 2005-02-01 | Generic | 1 |  | Design of Grid Services
4.1.4 | 6 | 2005-02-01 | CDF | 1 |  | Develop Dimension Editor
3.2 | 7 | 2005-03-01 | CDF | 1 |  | Definition of Metadata service in SAM
3.3 | 7 | 2005-03-01 | Generic | 1 |  | Architecture and Planning Report
3 | 8 | 2005-04-01 | All | 1 |  | Definition of Metadata service (including distinction by experiment)
4.1.5 | 8 | 2005-04-01 | All | 1 |  | Develop prototype Metadata Catalog
4.1 | 9 | 2005-05-01 | All | 1 |  | Initial minor release
4.1.6 | 9 | 2005-05-01 | All | 1 |  | Software and associated documentation
5.2 | 10 | 2005-06-01 | CDF | 1 |  | Document monitoring requirements of SAM
5.3 | 10 | 2005-06-01 | Generic | 1 |  | Document common monitoring requirements (using AMI and SAM documents)
5 | 11 | 2005-07-01 | All | 1 |  | Document common monitoring requirements
6 | 12 | 2005-08-01 | All | 1 |  | Assisting wider adoption of Metadata service (to be reviewed annually)
6.2 | 12 | 2005-08-01 | All | 1 |  | External Presentations
6.2.1 | 12 | 2005-08-01 | All | 1 |  | Submit documentation to the GGF-PNGA working group in GridForge?
6.3 | 12 | 2005-08-01 | All | 1 |  | External Project Integration Report (Confidential)
7.2 | 14 | 2005-10-01 | CDF | 1 |  | Review SAM implementation
7.3 | 15 | 2005-11-01 | Generic | 1 |  | Identify generic components
7 | 16 | 2005-12-01 | All | 1 |  | Review Metadata service definition
9.2 | 16 | 2005-12-01 | CDF | 1 |  | Final EGEE Phase 1 release
4.2.3 | 18 | 2006-02-01 | CDF | 1 |  | Optomised Dimension Editor
4.2.4 | 18 | 2006-02-01 | Generic | 1 |  | Review Architecture and Planning Report
8.2 | 18 | 2006-02-01 | CDF | 1 |  | SAM throughput testing of database access via Metadata using SAM
8.3 | 18 | 2006-02-01 | Generic | 1 |  | Common testing interface
8 | 19 | 2006-03-01 | All | 1 |  | Throughput testing of database access via Metadata
4.2.5 | 20 | 2006-04-01 | Generic | 1 |  | Design and Refactoring of Grid Services
4.2 | 21 | 2006-05-01 | All | 1 |  | 1st Major release
4.2.6 | 21 | 2006-05-01 | All | 1 |  | Software and associated documentation
11.2 | 23 | 2006-07-01 | CDF | 1 |  | Produce a document on user access optimisation of data access via metadata in SAM
11.3 | 23 | 2006-07-01 | Generic | 1 |  | Produce generic document on user access optimisation of data access via metadata
4.2.2 | 24 | 2006-08-01 | All | 1 |  | Prototype distributed metadata service with GANGA interface, delivery middleware and web services interface.
11 | 24 | 2006-08-01 | All | 1 |  | Produce documentation on user access optimisation of data access via metadata
9 | 28 | 2006-12-01 | All | 1 |  | Contribution to EGEE Development
9.3 | 28 | 2006-12-01 | Generic | 1 |  | Initial EGEE Phase 2 release
10.2 | 28 | 2006-12-01 | CDF | 1 |  | Review SAM and RLS functionality
4.2.2 | 30 | 2007-02-01 | CDF | 1 |  | Fully functional Dimension Editor
4.3.3 | 30 | 2007-02-01 | Generic | 1 |  | Review Architecture and Planning Report
10 | 30 | 2007-02-01 | CDF | 1 |  | Produce documentation on distributed databases
4.3.4 | 32 | 2007-04-01 | Generic | 1 |  | Design and Refactoring of Grid Services
4 | 33 | 2007-05-01 | All | 1 |  | Implementation of appropriate metadata
4.3 | 33 | 2007-05-01 | All | 1 |  | 2nd Major release
4.3.5 | 33 | 2007-05-01 | All | 1 |  | Software and associated documentation
12.2 | 35 | 2007-07-01 | CDF | 1 |  | Final evaluation of CDF metadata components
12.3 | 35 | 2007-07-01 | Generic | 1 |  | Final evaluation of metadata components (summary)
12 | 36 | 2007-08-01 | All | 1 |  | Final evaluation of metadata components
6.1 | o |  | All | 1 |  | Maintain collaborative resources ( to be reviewed quarterly)
6.1.1 | o |  | Generic | 1 |  | Wiki
6.1.3 | o |  | Generic | 1 |  | CVS repository
6.1.4 | o |  | Generic | 1 |  | Defect tracking
6.1.5 | o |  | CDF | 1 |  | Other resources for collaborative work
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0