Proposal to Conduct Mammal Surveys in

George Washington Birthplace National Monument,

Thomas Stone National Historic Site,

and Colonial National Historical Park

Ronald E. Barry

Department of Biology

Frostburg State University

Frostburg. MD 21532-1099

Cooperative Agreement

National Park Service

Northeast Region

August 2001

Overview

The National Park Service (NPS) has identified the need for surveys of mammals in three coastal national parks in the Northeast Region.  Acquiring such natural resource information is in compliance with the Vail Agenda mandate to the NPS's Natural Resource Inventory and Monitoring Program (NPS 1998).  One of the five long-term goals established by this program is to complete baseline inventories of basic biological and geophysical natural resources for the national parks.  During Phase I of the natural resource inventory the NPS has set an objective of documenting the presence of at least 80% of all plant and animal species (excluding invertebrates) occurring within a park's boundaries; the stated objective for the mammal survey of the parks of the Northeast Region is 90%.  Surveys will confirm the existence of currently listed species and document the presence of new ones.  The data collected provide important baseline information that can be used by natural resource specialists in monitoring programs to note changes and quantify trends in resources and relate variation in time to potential causes.  Such monitoring programs can result in management decisions that effect proper stewardship of the park system by NPS.

I propose to conduct surveys of mammals in 3 coastal parks: George Washington Birthplace National Monument (GEWA), Thomas Stone National Historic Site (THST), and Colonial National Historical Park (COLO).  GEWA consists of 551 acres (223 ha) on the coastal plain east of Fredericksburg, Virginia, in Westmoreland County.  The monument was authorized in 1930 and opened under the administration of the NPS in 1932.  It consists chiefly of open grasslands and forests, with 25 acres of marshes and estuaries.  THST consists of 297 acres (120 ha) in Charles County, Maryland, approximately 4 miles west of La Plata and 25 miles south of Washington, D.C.  The park opened in 1992 and is comprised largely of forests and open fields.

COLO encompasses approximately 9,327 acres (3,776 ha).  It is located in southern, coastal plain region of  Tidewater Virginia and is composed of Jamestown Island, Yorktown Battlefield, Swann’s Point and Green Spring and the 24 23-mile (38-km) Colonial Parkway that connects the island and battlefield.  More than one-half of the area consists of forest.  Over 30% is floodplain; 26% is wetlands (including forested) and managed fields constitute much of the park.  COLO contains approximately 30 miles (49 km) of shoreline along the James and York rivers, 24 miles (39 km) of perennial streams, and 30 miles (49 km) of intermittent streams and drainages.

The NPFauna (2001) database lists records of 22 species of mammals (orders Marsupialia, Insectivora, Chiroptera [2 species], Rodentia, Lagomorpha, Artiodactyla and Carnivora) in the GEWA.  The database lists 0 records of mammals for the THST and 26 species (orders Insectivora, Chiroptera [3 species], Rodentia, Artiodactyla, and Carnivora) for the COLO.

Project Description

Goal

The primary goal of the proposed project is to survey the mammals (excluding bats) of GEWA, THST and COLO with the purpose of documenting > 90% of the species that occupy each of these parks and describing the relative abundance does abundance, below he does mention distribution,  include distribution is this part of this proposal? of species of concern what is meant by spp of concern is this just another way to mean small mammals? And is it mammals or small mammals that he is surveying, does it include deer, need to clarify this.  A secondary goal associated with graduate student thesis projects is to provide information on mammal communities of the parks.

Objectives

Primary

1.  Review all natural resource studies that have occurred within the parks’ boundaries and all historical scientific material stored in the parks to develop a database of mammal species (excluding bats) that possibly occur in the parks. Shouldn’t studies adjacent to the park on adjoining public and private lands, e.g. US Navy, Newport News Waterworks, Newport News Park also be surveyed?  Shouldn’t local universities be checked for any student thesis that might not have been also deposited with the park?

2.  Conduct extensive surveys of the parks for, and catalog, the presence, distribution, and relative abundance (for species of concern) of mammal species in forests, grasslands, agricultural fields, riparian areas, marshes, rock outcrops, etc. at GEWA, THST and COLO.

Secondary (graduate student theses)

1.  Describe habitat-specific species diversity in the 3 parks.

2.  Assess the status of mammals within each of the parks and provide recommendations for monitoring mammal populations.

Methods

Historical records.-Initially we will establish an electronic database (Microsoft Access 2000) is this redudent vs. just getting an Access version of NPSpecies. Note below that NPFauna should be changed to NPSpecies. The park also has a GIS database with wildlife observations. I would think a GIS database should also be established or I guess coordinates in the MS Access database that can be converted into our GIS? of records of mammal species for each of the 3 parks from existing databases such as NPFauna (2001), park records, records of museums such as the U.S. National Museum (Smithsonian), university/college and local collections and museums, and published literature.  The database should be compatible with that of other national park units and NPFauna (2001) so that information can be used at the ecosystem and landscape levels (NPS 1998).  The database will contain at least the complete taxonomy (Wilson and Reeder 1993; Jones et al. 1997) and common name of each species, location (park) of each species, and source of the record.

Delineation of habitats.-The recognition of major habitat types will allow stratification of the sampling effort in the 3 parks.  This will ensure a representative and comprehensive survey of the small mammal fauna by increasing the efficiency with which individual species are detected, particularly those that are rare.  Habitats will be identified by GIS cover maps, if available, or aerial photos.  Will this be redudent with the NVC project for COLO, or should we at least have him use NVC classification? Or is that finer detail than needed. At a min. we have to be sure his habitats can be “crosswalked” to the NVC ecological classification. Topographic maps will be important WE also have aerial photography true color and hopefully by then leaf off and leaf on infrared aerial photography in identifying habitat potentially important to (or avoided by) certain species.  Major habitat types should include, but not be limited to, forests (deciduous, coniferous, mixed, and wetland), grasslands, agricultural fields, rock outcrops, riparian zones, and marshes also include for COLO woodlots, maintained lawn areas, ravines.  In addition, recognizable corridors (of various habitat types) will be identified and sampled.  Strata will be ground-truthed before final selection of sampling sites.  Because habitat changes over time, permanent boundaries of original strata will be delineated on GIS maps to permit long-term monitoring of animal populations and vegetation (NPS 2000). What role will GPS play in identifying locations for the GIS, what level of accuracy?

Sampling protocol.-Sampling sites will be located within well-defined habitat types (see above) to permit stratified sampling for developing a representative list of species and an efficient means for monitoring and managing populations.  In addition, unusual or less common or expansive habitats (e.g., bogs) will be sampled because they often harbor small populations or rare species important in monitoring the health of an ecosystem or landscape.  The number of sampling locations (sample units) within any single park will be dependent on the number, size and distribution of habitat types and constraints imposed by accessibility, equipment and personnel.  Historical records and site visits to a park, once habitats are defined, will be factors in determining the number of sampling locations.  Sampling on private property will occur only with the permission of the landowner.

To identify sampling points, systematic grids will be superimposed on park maps that depict habitat types (NPS 2000).  Points on a grid, within a habitat type, will be selected without replacement by the generation of random numbers (either computer-generated or from a random numbers table) representing grid cells (Rudran and Foster 1996).  Edge areas (habitat edge, roads, etc.) known to influence species richness and abundance of mammals (e.g., Cummings and Vessey 1994), portions of parks frequented by the public some spp of “concern” such as groundhogs in earthworks, deer in field are in public use area, and areas inaccessible to ground personnel we have a lot of wetlands with muskrats, minks etc. will they be using canoes or flat boats? will be removed from consideration as sampling locations.  Once selected on a map, a sampling location will be located in real space using differentially corrected GPS what level of accuracy, the park GIS is +/- 5 ft.  Before sampling begins, a review of sampling locations and times will be solicited I love it when they use that word…just kidding seeing if you read all of our BS from park management.

Sampling will rely on capture of small mammals using primarily Sherman and Tomahawk live traps (for larger shrews, mice and voles, squirrels, etc.) and pitfall trap arrays (for shrews and small mammals < 10 g -- Kirkland and Sheppard 1994).  Traps will be arrayed at sampling points in randomly positioned linear transects or grids, with the number of traps and trap spacing dependent on habitat type and patch size (Jones et al. 1996).  The trapping effort needed to account for > 90% of all species within each habitat will be determined by a species accumulation curve; once a plateau (asymptote) is reached, sampling will cease, at least for that sampling period.  This sampling regime will permit a measure of species richness and relative abundance for each park.  Locations for sampling small mammals will generate observations and signs of larger mammals; species, location and date for each such mammalian encounter will be recorded on data sheets for inclusion in the database for the park.  Tomahawk traps used for capturing larger mammals for species identification will be placed in locations where sign is detected or where habitat features suggest the presence of these species.  Remote cameras will be used to document the presence of large, secretive and elusive species.

Habitat at each sampling location will be characterized by such features [at randomly selected sites] as dominant vegetation, percent canopy cover, abundance of shrub and ground cover, degree of disturbance (e.g., primary or secondary forest or plantation, agricultural use of grassland, frequency of fire or flooding), substrate and soil type, presence of rock piles, topography and elevation (Barry et al. 1999; Boyce 2001; McDiarmid and Wilson 1996).  Temperature and precipitation for sampling dates will be obtained from the park weather station or the nearest available weather station if none exists within the park.

Captured individuals of small species (those in Sherman and pitfall traps) will be removed from traps (Jones et al. 1996), identified to species, weighed using a Pesola scale, and examined for age, sex, and reproductive condition.  Individuals captured in Tomahawk traps will be identified to species, and, if practical, weighed using a Pesola scale and examined for age, sex and reproductive condition.  Because recognition of individuals is necessary for determining relative abundances (NPS priority for species of concern) and measures of species diversity (graduate student theses projects), captured individuals may be marked by spot-shaving, hair-dyeing, ear-tagging (Monel #1 tags, National Band and Tag Co., Newport, Kentucky) or toe-clipping, (ASM 1998; Rudran 1996).  Release will be immediate at the capture location.  Live-trapping and handling procedures will be administered humanely (Rudran and Kunz 1996) and be consistent with the animal handling guidelines of the American Society of Mammalogists (ASM 1998).  Also, proper precautions will be taken by investigators to prevent human injury and exposure to disease, especially rabies, Lyme disease, hantaviral pulmonary syndrome (HPS), and human ehrlichiosis (Gage et al. 1995; Kunz et al. 1996; Mills et al. 1995).

Compilation and analysis of data.-Data on habitat and all mammals captured or observed (including sign) will be stored in an electronic database (Microsoft Access; see Deliverables below).  These data will be combined with historical data to determine the number of species in a park.  Current data will be used to determine distribution and habitat of species.  Associations of species with habitat type and variables, and determination of relative abundance, will rely on such customary statistical procedures as regression, ANOVA, chi-square, and log-likelihood analyses (Zar 1999).  Estimates of species diversity, richness and evenness for graduate student thesis projects will derive from customary models (e.g., Shannon-Wiener index, rarefaction, and Pielou’s J’ – Krebs 1999) to facilitate comparisons among habitats, parks and investigators and at various sample sizes.  Statistical analysis will be conducted at Frostburg State University (FSU).  The final report will include, for each park, records of all mammal species and their distributions, relative abundances of species of concern, survey methods and weather conditions, locations of voucher specimens, and recommendations for long-term monitoring for use by park management.

Project Coordination

Project personnel will include the project director (cooperator) and 3 graduate student investigators, one assigned to GEWA/THST and the other two to COLO.   The project director will oversee all activities.  Park staff will be notified beforehand by phone or e-mail of all project activities to be undertaken in the park.  Monthly schedules, developed in coordination with park management, will be produced by project investigators.  Schedules will be adhered to as closely as possible but be subject to change due to weather or unforeseen personnel circumstances; changes in schedule will be communicated in advance by project investigators.  The project director will obtain park permits and a state scientific research and collecting permit for conducting the research, collecting specimens, and depositing specimens in the mammal collection at Frostburg State University; investigators (subpermittees) will carry copies of the permits during sampling.  In addition, the project director will obtain approval from the Institutional Review Board/Animal Care and Use Committee at Frostburg State University to conduct the research.  Where park housing is available, project investigators may submit requests for overnight stays when this is necessary for survey work.  The project director will negotiate with park management and natural resource personnel any use of park equipment (e.g., GPS) that can facilitate data collection and contribute to the successful completion of the project.

Deliverables

Project description

The complete description of the project will submitted by 31 August 2001.

Species data

Field forms will be provided, upon request, to the NPS I & M Program.

Digital data sets will be produced in Microsoft Access format, using the NPS I & M template (www1.nature.nps.gov/im/apps/template/) or one specifically developed for the particular project.

GPS data

GPS coordinates, differentially corrected, will be provided in ArcInfo prefer the format be for AV3.2, AV8.1, shapefiles with associated attributes. NOTE: COLO has an SOP for creating new shapefiles/attributes, it would be a real time saver if our minimum fields are added to their field. format or as an ArcView file for all sampling locations and observation sites.

Metadata

Metadata will be provided in Dataset Catalog format (nonspatial data) or, with the cooperation of NPS data managers, in Federal Geographic Data Committee (FGDC) format (spatial data) found at www.fgdc.gov/metadata/metadata.html.

Voucher specimens

The mammal collection of the Department of Biology at Frostburg State University will be the repository of voucher specimens (Reynolds et al. 1996) and any salvagable individuals encountered in traps or as roadkills.  Where possible, individuals found dead will be prepared as voucher specimens.  Otherwise, voucher specimens of small mammals (shrews, voles, mice and rats) will be obtained from individuals captured live and euthanized by cervical dislocation or thoracic compression (ASM 1998) or selective kill trapping using Museum Special snap traps (Woodstream Corporation, Lititz, Pennsylvania).  Specimens of only those species for which no record exists for the park will be sought.  Moles, medium- and large-sized mammals will be documented as photo vouchers; photo vouchers or specimen vouchers from trap mortalities, roadkills or individuals found dead; or collection of sign.  Threatened and endangered species will not be sacrificed for voucher specimens; photo documentation will be made where possible and/or hair samples will be collected.  Specimens deposited at FSU will be catalogued in the University's database.

Reports

Progress reports will be submitted annually.  A draft of the final report will be submitted digitally to the Northeast Region, I & M Program.  The final report will be submitted digitally and in hard copy.  Any graduate student theses incorporating the work done to comply with the requirements of this agreement will be submitted in hard copy.  Normally Karish et al require quarterly update reports and the annual submission to the RPRS website (the old IAR). The quarterly reports are sent as emails or email attachments.  Final report format is important, use of Word 97/2000, font size, formatting for automatic TOC, page numbering. Also we have required a complete report submitted in Adobe PDF format, 600 dpi, color. How will the digital photographs, databases etc. be provided?

If the funds are available some other outputs should include a PowerPoint presentation suitable for conversion to the web and showing to park management and staff. Draft brochure checklist etc. Also, we should at a min. require at least a Park Science article.

Bibliographic citations

A reprint will be provided for each publication or thesis based on work completed under this agreement.

Project Timetable

Dates					Activities

31 August 2001			Submit proposal

January-May 2002			Obtain historical records of mammals for GEWA and THST, outline and 						ground-truth strata and establish sampling sites, establish sampling 						protocol, design database (template)

March-November 2002		Conduct survey of mammals at GEWA and THST, refine sampling 						protocol, establish procedures for data analyses

August – December 2002		Obtain historical records of mammals of COLO, outline and ground-truth 						strata and establish sampling sites, establish sampling protocol, design 						database (template), conduct survey of mammals

November 2002-January 2003	Prepare progress report

March-November 2003		Complete survey of mammals at GEWA and THST, compile data; 							conduct survey of mammals at COLO, refine sampling protocol, establish 						procedures for data analyses

November 2003-January 2004	Analyze data, prepare progress report

March – November 2004		Complete survey of mammals at COLO, compile and analyze data

November 2004-January 2005	Analyze data, prepare final report (with species data, GPS data, metadata)

Literature Cited

ASM.  1998.  Guidelines for the capture, handling, and care of mammals as approved by 	the American Society 	of Mammalogists.  Journal of Mammalogy 79:1416-1431.

Barry, R. E., K. A. Boyce, and A. C. Sucke.  1999.  Local distribution, habitat, and home 	range of the 	Appalachian cottontail (Sylvilagus obscurus) at Dolly Sods.  Final 	report submitted to the Nongame 	Wildlife and Natural Heritage Program, West Virginia Division of Natural Resources.

Boyce, K. A.  2001.  Distribution, seasonal home range, movements and habitat of the Appalachian cottontail, 	Sylvilagus obscurus, at Dolly Sods, West Virginia.  M. S. thesis, Frostburg State University, Frostburg, 	Maryland.

Cummings, J. R., and S. H. Vessey.  1994.  Agricultural influences on movement patterns of white-footed mice 	(Peromyscus leucopus).  American Midland Naturalist 132:209-218.

Gage, K. L., R. S. Ostfeld, and J. G. Olson.  1995.  Nonviral vector-borne zoonoses associated with mammals in 	the United States.  Journal of Mammalogy 76:695-715.

Jones, C., W. J. McShea, M. J. Conroy, and T. H. Kunz.  1996.  Capturing mammals.  Pp. 115-122 in 	Measuring and monitoring biological diversity: standard methods for mammals (D. E. Wilson, F. R. 	Cole, J. D. Nichols, R. Rudran, and M. S. Foster, eds.).  Smithsonian Institution Press, Washington, 	District of Columbia.

Jones, C., R. S. Hoffmann, D. W. Rice, M. D. Engstrom, R. D. Bradley, D. J. Schmidly, 	C. A. Jones, and R. J. 	Baker.  1997.  Revised checklist of North American mammals north of Mexico, 1997.  Occasional 	papers, Museum of Texas Tech University 173:1-20.

Kirkland, G. L., Jr., and P. K. Sheppard.  1994.  Proposed standard protocol for sampling 	of small mammal 	communities.  Pp. 277-283 in Advances in the biology of shrews (J. F. Merritt, G. L. Kirkland, Jr., and 	R. K. Rose, eds.).  Special Publication of the Carnegie Museum of Natural History 18, Pittsburgh, 	Pennsylvania.

Krebs, C. J.  1999.  Ecological methodology.  Second edition.  Addison Wesley Longman,Inc., Menlo Park, 	California, 620 pp.

Kunz, T. H., R. Rudran, and G. Gurri-Glass.  1996.  Appendix 2: Human health concerns.  Pp. 255-264 in 	Measuring and monitoring biological diversity: standard methods 	for mammals (D. E. Wilson, F. R. 	Cole, J. D. Nichols, R. Rudran, and M. S. Foster, eds.).  Smithsonian Institution Press, Washington, 	District of Columbia.

McDiarmid, R. W., and D. E. Wilson.  1996.  Data standards.  Pp. 56-60 in Measuring and monitoring 	biological diversity: standard methods for mammals (D. E. Wilson, F. R. Cole, J. D. Nichols, R. 	Rudran, and M. S. Foster, eds.).  Smithsonian Institution Press, Washington, District of Columbia.

Mills, J. N., T. L. Yates, J. E. Childs, R. R. Parmenter, T. G. Ksiazek, P. E. Rollin, and C. J. Peters.  1995.  	Guidelines for working with rodents potentially infected with hantavirus.  Journal of Mammalogy 	76:716-722.

NPFauna.  2001.  Species in parks: flora and fauna database.  http://ice.ucdavis.edu/nps/.

NPS.  1998.  Natural resource inventory & monitoring in national parks.  NPS Inventory 	and Monitoring 	Informational Brochure.  http://www.nature.nps.gov/im/imbroch.htm.

NPS.  2000.  Guidance for the design of sampling schemes for inventory and monitoring of biological 	resources in national parks.  National Park Service Inventory and Monitoring Program.

Reynolds, R. P., R. I. Crombie, R. W. McDiarmid, and T. L. Yates.  1996.  Voucher specimens.  Pp. 63-68 in 	Measuring and monitoring biological diversity: standard methods for mammals (D. E. Wilson, F. R. 	Cole, J. D. Nichols, R. Rudran, and 	M. S. Foster, eds.).  Smithsonian Institution Press, Washington, 	District of Columbia.

Rudran, R.  1996.  General marking techniques.  Pp. 299-304 in Measuring and monitoring biological diversity: 	standard methods for mammals (D. E. Wilson, F. R. Cole, J. D. Nichols, R. Rudran, and M. S. Foster, 	eds.).  Smithsonian Institution Press, Washington, District of Columbia.

Rudran, R., and M. S. Foster.  1996.  Conducting a survey to assess mammalian diversity.  Pp. 71-79 in 	Measuring and monitoring biological diversity: standard methods for mammals (D. E. Wilson, F. R. 	Cole, J. D. Nichols, R. Rudran, and M. S. Foster, eds.).  Smithsonian Institution Press, Washington, 	District of Columbia.

Rudran, R., and T. H. Kunz.  1996.  Appendix 1: Ethics in research.  Pp. 251-254 in Measuring and monitoring 	biological diversity: standard methods for mammals (D. E. Wilson, F. R. Cole, J. D. Nichols, R. Rudran, 	and M. S. Foster, eds.).  Smithsonian Institution Press, Washington, District of Columbia.

Wilson, D. E., and D. M. Reeder (eds.).  1993.  Mammal species of the world: a taxonomic and geographic 	reference.  Smithsonian Institution Press, Washington, District of Columbia.

Zar, J.H.  1999.  Biostatistical analysis.  Fourth ed.  Prentice Hall, Upper Saddle River, New Jersey.

Budget

Agency	FSU													Request	Match

I.  Personnel assignments and costs

A.  Dr. Ron Barry’s release time/summer stipend - $7,900/mo./yr.			$15,800        $15,800

B.  GEWA and THST: 2-semester research assistantship ($5,000) +

1-summer assistantship ($2,000) + January stipend (2nd yr. @ $1000)

for 1 graduate student        	   						    8,000	 7,000

C.  COLO: 2-semester research assistantship (@$5,000) + 1-summer

assistantship (@$2,000) + January stipend (2nd yr. @ $1,000) for 2

graduate students	  								  16,000          14,000

D.  Tuition waiver for 3 graduate students @ $3,600/yr./student for 2 yrs. each		           21,600

E.  Rabies vaccine – (3 series @ $240) + (1 booster @ $80) 		                   800

F.  Student health insurance (Sentry Student Security Plan – E. J. Smith &

Associates) for 3 graduate students @$300/yr./student for 3 students for

2 yrs. each		       	    							    1,800

I.  Total  									      	$42,400        $58,400

II.  Transportation*

A.  Roundtrip to GEWA and THST – (30 trips @ 505 mi/trip) +

(60 mi/trip local travel X 4/trip X 30 trips) = 22,350 mi @ $0.32/mi

(FSU institutional rate)  +  (120 bridge tolls @ $1.50/toll) 		   	  $6,259          $1,073

B.  Roundtrip to COLO – (40 trips @504 mi/trip) +

(22 mi/trip local travel X 4/trip X 40 trips) = 23,680 mi @ $0.32/mi	   	    6,441	 1,137

C.  Dr. Ron Barry’s travel – 12,000 mi @ $0.32/mi 			             		             3,840

II.  Total  									 	$12,700          $6,050

III.  Lodging**

Supplied by NPS.  If not, lodging expenses are needed for 90 nights

for GEWA/THST and 240 nights for COLO.

IV.  Equipment, supplies, services, etc.

A.  Sherman live traps – 300 @ $14.00 (-5%) + $100 shipping  		              $4,300

B.  Tomahawk single-door, collapsible (squirrel size) – 30 @ $30.00	       	       900

C.  Tomahawk single-door, collapsible (raccoon/feral cat size) – 6 @ $70.00 	       420

D.  Tomahawk single-door, collapsible (bobcat size) – 2 @ $170.00		       340

E.  TrailMaster TM 1500 Active IR trail monitor – 2 @ $260			       520

F.  TrailMaster TM 35-1 Camera Kit – 2 @ $290					       580

G.  TrailMaster TM Data Collector – 2 @ $250					       500

H.  SONY MVC-CD 1000 CD Mavica digital camera			   	    1,000

I.  Dell Inspiron 2100 notebook computer with 20 GB hard drive, 256 MB RA,

and extra battery          								    2,150

J.  3 Nokia 5185i cell phones @ $100						       300

K.  Pesola scales (3 ea. 30-g and 100-g, 2 ea. 10-g and 600-g)  		      	       340

L  5 silt fences (for pitfall arrays); 2’ X 100’ @ $18.00  				       100

M.  Miscellaneous supplies (flagging, bait, stakes, sampling bags, trap bedding,

specimen preparation supplies, map acquisition, ear tags, dye, computer

supplies, field gear, EpiPen epinephrine kits, photocopying, etc.), shipping

expenses for traps and other equipment and supplies, etc.             		    1,000

N. Equipment, supplies, and additional support (traps, densiometers,

compasses, measuring tapes, ear tags, Pesola scales, binoculars, night-vision

binoculars, aerial photo stereoscope, specimen storage and maintenance,

graduate faculty support, secretarial and technician support, photocopying

and duplicating services, mail, etc.)							           $4,000

O.  Computer services (data compilation and statistical analysis, report

preparation, e-mail, etc.)										 4,000

P.  Attendance, paper presentation at professional meetings @ $1,000/yr. for

2 yrs.										    2,000

IV.  Total  									 	$14,450          $8,000

Project Subtotal						    		        	$69,550

Indirect costs (15%)									$10,433

PROJECT TOTAL									$79,983      $72,450

*  Based on 15% of mileage provided by FSU (plus Ron Barry’s travel)

**  If park lodging is not available, additional support is sought for local lodging for

investigators

Budget Justification

Item #		Justification

I. A		Support for the project director (cooperator) for either course release and/or summer salary for 2 			years for project coordination, field work, data analysis, report preparation, etc.

I. B, C, D	Three graduate students are needed to conduct the proposed work within the proposed period.  Support in the amount of a stipend for 1 academic year, summer, and January is requested  for each of 3 students.  FSU will provide a 2nd year (including summer) of stipend for each student.

I. D		Graduate tuition and fees @ $200/credit X 36 credits/ student X 3 students

I. E		For 3 graduate students and project director (booster only)

I. F		Basic coverage (maximum $3,000 benefit/yr.) for graduate students

II. A, B	Reimbursement for use of vehicles by investigators to travel to, from, and within 					study sites.  FSU provides 15% of mileage.

II. C		FSU provides mileage for project director.

III.		If NPS lodging is not available, NPS support for such will be sought.

IV. A, B	Traps needed for simultaneous trapping of small mammals at 3 national parks

IV. C, D	Traps needed for simultaneous trapping of medium-sized mammals at 3 national park

IV. E, F, G	Remote detection units and cameras needed for documentation of larger, secretive and elusive 			mammals

IV. H		Camera needed for voucher specimens, confirmation of identifications of amphibians and 			reptiles in pitfall traps, etc.

IV. I	Computer needed for compilation, manipulation, storage, integration, and analysis of species data, GPS data, metadata, and field data

IV. J	Needed for safety and convenience of 3 graduate students who will be in the field simultaneously

IV. K		Additional scales needed for simultaneous trapping at 3 national parks

IV. L		Fencing needed to establish pitfall trap arrays (for capturing shrews and other small mammals     			< 10 g) at 3 national parks

IV. M		Self-explanatory

IV. N		Support from FSU’s Department of Biology

IV. O		Support from FSU’s Computing Services, Academic Computing, and departments of Biology 			and Mathematics

IV. P		Travel, registration, lodging, and meals for 3 graduate students and project director for 2 yrs.