U.S. ATLAS PROJECT OFFICE

Physics Department

UPTON, NEW YORK 11973

July 7, 2006

Dr. Thomas Ferbel

SC-25/Germantown Building
U.S. Department of Energy
1000 Independence Avenue, SW
Washington, D.C. 20585-1290

Dr. Peter Bond

Associate Laboratory Director

Brookhaven National Laboratory

Upton, NY  11973

SUBJECT:  U.S. ATLAS Research Program Quarterly Status Report

Dear Sirs:

Attached please find U.S. ATLAS Research Program Quarterly Status Report No. 7 for the period January-March 2006.

Sincerely yours,

Howard A. Gordon

U.S. ATLAS Deputy Research Program Manager

Head, U.S. ATLAS Project Office

Distribution:

Abolins, M.

Alam, S.

Aronson, S.

Baker, K.

Barnett, M.

Bensinger, J.

Blair, R.

Brau, J.

Butehorn, C.

Byon-Wagner, A.

Carolan, P. - DOE

Cleland, W.

Coles, M. – NSF

Crawford, G. - DOE

De, K.

Dodd, J.

Ernst, R.

Errede, S.

Feldman, G.

Ferbel, T. - DOE

Gilchriese, M.

Goldberg, M. – NSF

Grillo, A.

Harrison, M. – PAP

Hinchliffe, I.

Huth, J.

Kagan, H.

Kane, S.

Kirby, D.

Kogut, J. - DOE

Lankford, A.

Larsen, R. - PAP

Lissauer, D.

Lubatti, H.

Mantsch, P. – PAP

McFarlane, K.

Meyers, P. – PAP

Neal, H.

Nemethy, P

Ogren, H.

Oh, S.

Parsons, J.

Pilcher, J.

Polychronakos, V.

Price, L.

Pripstein, M. – NSF

Rizatdinova, F.

Rijssenbeek, M.

Rutherfoord, J.

Seiden, A.

Seidel, S.

Shank, J.

Shochet, M.

Skubic, P.

Sliwa, K.

Stroynowski, R.

Su, D.

Taylor, F.

Tuts, M.

Whitaker, S.

Willocq, S.

Wolbers, S. - PAP

Williams, H.

Willis, W.

Wu, S.L.

research program STATUS REPORT NO. 7

REPORTING PERIOD

January-March 2006

Table of Contents

1.	Executive Associate Project Manager’s Summary (J. Shank, BU)	4

2.	Technical Progress Reports	4

2.2 Software	4

2.3 Facilities	19

3.1 M&O Silicon	27

3.2 M&O TRT	30

3.3 M&O Liquid Argon	31

3.4 M&O Tile	38

3.5 M&O Muon	42

3.6 M&O Trigger	44

4.1 Inner Detector Upgrade R&D								  50

4.3 Liquid Argon Upgrade R&D								  59

3.	Financial Report (Chuck Butehorn, BNL)	62

# Executive Associate Project Manager’s Summary (J. Shank, BU)

The computing effort for this quarter was focused on the Computing System Commissioning (CSC) exercises. In the core software development are this meant getting release 12.0.0 out. This release had new functionality in data management areas such as conditions database, but the dominant effort was in upgrading the data management software to ROOT5. This was substantially more work than anticipated and required the concentration of all the core and Data management software experts. This work delayed released 12.0.0 and made for a rocky start to the CSC. The CSC simulation production did start using the continuously updated PanDA system. PanDA was deployed at a large scale at all the T1/T2 sites in the US and no real scaling limits were hit. In addition, we had an internal review of PanDA this quarter. This review was useful in identifying areas that needed further work and in the dropping of our DIAL software development as a separate product, but to incorporate some of the DIAL

technology directly into PanDA. 

Major ramp-up of the facilities capacity was carried out at the T1 and T2 centers during this quarter in order to match the CSC requirements.

# Technical Progress Reports

## 2.2 Software

2.2 Subsystem Manager's Summary

Srini Rajagopalan (Brookhaven National Laboratory)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release 12.0.0 for commissioning | 15-Mar-06 | 30-Apr-06 | 30-May-06 | Delayed (See #1) |
| Software available for DC3 | 15-Mar-06 | 15-Mar-06 | 30-May-06 | Delayed (See #2) |
| Release 12.0.x validated | 30-Aug-06 | [New] | 30-Aug-06 | On Schedule |

Note #1  Release 12 has been delayed to end of April with bug fixes releases expected to come out in May 2006.

Note #2  This is now part of Release 12, including the software allowing simulation with realistic geometry (as-built) and reconstruction for studies toward CSC notes. The expected release date has been delayed from numerous problems - mostly persistency problems with new version of ROOT to end of May.

Srini Rajagopalan (Brookhaven National Laboratory)

ATLAS continues to mature its software in readiness for several upcoming commissioning exercises, designed to stress test the software components and ensures its readiness for LHC startup. Release 12.0.0 was a significant milestone in the process adding components of realistic (as-built) simulation that will be used for production and studies in the coming months. The realistic effects include incorporation of realistic dead material and misaligned geometries as gained during the detector installation experience.

Release 12 also included a migration to new core software, in particular migrating to ROOT5. This migration was painful with persistency not supported as well as with ROOT4. This has caused Release 12 to now be delayed to the next quarter.

Within the U.S., there was a major reshuffling of the distributed data management activities around the recently initiated PanDA project. PanDA has now been in development for six months and the U.S. established a review to ensure that this project is in the path toward success. The review committee included David Malon (ANL), Paolo Calafiura (LBL), Kyle Cranmer (BNL), Shawn McKee (Michigan) and Dietrich Liko (CERN). Dietrich is also responsible for the ATLAS Distributed analysis software development. The major outcome of the review was to terminate the ongoing development of DIAL as the tool for distributed software and enhance the focus on PANDA to develop and deploy the suite of tools necessary for both production and distributed analysis.

In the application software, Dieter Best's contract at Indiana was terminated and a replacement for Dieter has been found - due to begin the next quarter. The replacement will also focus on development the expertise in tracking software.

2.2.1 Coordination

2.2.2 Core Services

Paolo Calafiura (Lawrence Berkeley Laboratory)

The focus of work during this quarter was preparation for release 12. In particular US ATLAS core developers worked on ROOT 5 migration, a new cleaner implementation of DataVector and DataList, a new generation of python-based job transformation, as well as porting the core software packages to gcc 3.4.4. Other important accomplishments were in the Gaudi error reporting and error handling service and in preparing the migration to the use of python module and auto-generated Configurable for job configuration.

2.2.2.1 Framework

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration of Seal plug-in Mechanism | 14-Nov-05 | -- | 14-May-06 | Delayed (See #1) |
| port of Gaudi and Control to gcc 3.4.4 | 1-Feb-06 | -- | 1-Feb-06 | Completed |
| python-accessible Property Repository | 1-Feb-06 | 1-Feb-06 | 1-Jun-06 | Delayed (See #2) |
| Full chain and Interactive Tutorials | 8-Feb-06 | -- | 8-Feb-06 | Completed (See #3) |
| use GaudiPython to provide interactive access to (selected) framework functionality | 8-Feb-06 | 8-Feb-06 | 8-Sep-06 | Delayed (See #4) |
| High-level job configuration design and tools | 14-Feb-06 | 14-Feb-06 | 14-Jun-06 | Delayed (See #5) |
| History & Property Mech Integ | 14-Feb-06 | 14-Feb-06 | 14-Jun-06 | Delayed (See #6) |
| Review ATLAS software documentation/workbook (Indiana) | 1-Mar-06 | -- | 1-Mar-06 | Delayed (See #7) |
| flexible job reinitialization | 1-Jun-06 | -- | 1-Jun-06 | On Schedule |
| port Gaudi and Control to 64-bit architectures | 1-Jul-06 | -- | 1-Jul-06 | On Schedule |
| Review ATLAS Python Scripts for usability (Indiana) | 1-Sep-06 | -- | 1-Sep-06 | On Schedule |
| common online/offline error reporting/handling | 31-Dec-06 | -- | 31-Dec-06 | On Schedule (See #8) |

Note #1  awaits for the integration of ROOT5 in athena

Note #2  basic functionality delivered. Now needs to be deployed and adapted according to users needs

Note #3  needs revision when migrating to project builds

Note #4-5  lack of manpower

Note #6  awaits history persistency

Note #7  awaits new hire

Note #8  new Gaudi error handling service mimics and perhaps improves upon online requirements

2.2.2.2 EDM Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration with POOL-Cache Manager | 31-Dec-05 | 31-Dec-05 | 6-Sep-06 | Delayed (See #1) |
| Support for History Objects | 14-Feb-06 | 14-Feb-06 | 14-Jun-06 | Delayed (See #2) |
| evaluate the need of object aliases and versioning in StoreGate | 14-Sep-06 | -- | 14-Sep-06 | On Schedule |
| Integrate CLID Database Generation | 14-Sep-06 | -- | 14-Sep-06 | On Schedule |
| support DataLinks across different stores | 23-Sep-06 | -- | 23-Sep-06 | On Schedule |
| Prototype Support for Integer Keys | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| update DataList, evaluate DataMap and association objects | 1-Dec-06 | -- | 1-Dec-06 | On Schedule (See #3) |

Note #1  low priority

Note #2  prototyped persistency using pickle. POOL needs Transient/Persistent separation

Note #3  DataList done

2.2.2.3 Detector Description

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| All Identifiers in DD database | 1-Oct-05 | 1-Jun-06 | 1-Jan-06 | Completed (See #1) |
| DC3 Detector Description Quality Control Tests Passed | 1-Jan-06 | 1-Jan-06 | 1-Oct-06 | Delayed (See #2) |
| All numbers in DB. All file-based info removed (Pitt) | 1-Mar-06 | 1-Mar-06 | 1-Sep-06 | Delayed (See #3) |
| CPU/Memory Optimization Effort Final Report (Pitt) | 1-May-06 | 1-May-06 | 1-Jul-06 | Delayed (See #4) |
| Initialization time performance study | 1-May-06 | 1-May-06 | 1-Jul-06 | Delayed (See #5) |
| Validation procedures established for DD versions (Pitt) | 1-Jun-06 | 1-Jun-06 | 1-Oct-06 | Delayed (See #6) |
| Database preemption system delivery date (Pitt) | 1-Sep-06 | -- | 1-Sep-06 | On Schedule |
| Geometry Database overrides | 1-Sep-06 | -- | 1-Sep-06 | On Schedule |

Note #1  We have now put the ID Dict file names in the DD database and are using that as a means of synchronizing ID dict to version. It is not as strong as what we ultimately hope to achieve (data lives in the database); but this has moved to lower priority (than LAR detector description).

Note #2-3  Delayed due to the press of LAr Detector Description issues.

Note #4  Nearly done. The LAr Readout geometry was identified as a significant memory consumer and we have nearly fixed this. We must now get this accepted by the LAr group. Pending this, we will write the report on memory and CPU consumption during initialization.

Note #5  Nearly done; see note 1.

Note #6  Delayed due to the press of LAr Detector Description issues.

Joe Boudreau (University of Pittsburgh)

We spent the last quarter in maintenance of the LAr Detector Description and the LAr Simulation.

Recently we have done a major study to improve the LAr Detector Description. The analysis and design is essentially done and the implementation has been carried out as well, so now it will be presented and hopefully accepted. The main idea is to assure a tight coupling of readout geometry and material geometry, all under version control. We insert a layer of realistic description of readout geometry between the database and the idealized abstractions that apply to the calorimeter as a whole. This supports misalignments in a way which is far less cumbersome than the existing system (LArDetDescr) which does not really even use GeoModel, at least, not as intended (by us).

Three test beam setups (H6 emec-only, H6 emec-hec, H6 fcal) have been fully integrated with Athena and are now being used for testbeam analysis. Readout geometry has been applied to these systems as well now.

We have performed some initial tests for putting HV imperfection maps of LAr EM barrel and endcap into COOL Conditions database using two mechanisms for payload data storage - pool.root files and relational database. The long term strategy is yet to be defined.

It is our responsibility to coordinate the ATLAS DB Release which is becoming an essential part of ATLAS s/w releases starting from 12.0.0, the work on integrating default DB releases into distribution kits is ongoing.

Miscellany:

* Duplication of LArHit collection in simulation is suppressed.

* Digitization was tried successfully with automatic geometry configuration.

2.2.2.4 Graphics

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Configuration Presets available in v-atlas | 1-Sep-06 | -- | 1-Sep-06 | On Schedule |

2.2.2.5 Analysis Tools

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| access ATLAS Data from python | 8-Feb-06 | 8-Feb-06 | 8-Sep-06 | Delayed (See #1) |
| access c++ classes from python | 8-Feb-06 | -- | 8-Feb-06 | Completed |
| runtime recompilation/reloading | 15-Sep-06 | -- | 15-Sep-06 | On Schedule |
| automatic generation of transformations | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Note #1  needs revisiting after ROOT5 migration

2.2.2.6 Grid Integration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Job Transformations in Python | 14-Feb-06 | 14-Feb-06 | 14-Jun-06 | Delayed (See #1) |
| error recovery in athena | 15-Jun-06 | -- | 15-Jun-06 | On Schedule |
| Prototype Implementation for Grid Monitoring Architecture | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| extract job metadata from athena | 15-Dec-06 | -- | 15-Dec-06 | On Schedule |
| Improve message formatting and filtering | 15-Dec-06 | -- | 15-Dec-06 | On Schedule |

Note #1  infrastructure ready. Needs to be deployed in release 12 preproduction

2.2.2.7 Core Service Usability

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| add and use help string to Gaudi Property | 18-Feb-06 | 18-Feb-06 | 18-Jun-06 | Delayed (See #1) |
| Configurable-based job configuration | 1-May-06 | -- | 1-May-06 | On Schedule |
| provide job-level properties a la SimFlags | 1-May-06 | -- | 1-May-06 | On Schedule |
| Integrated athena configuration and development environment | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |
| Job Configuration editor/browser/debugger | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Note #1  developer in charge left. Help string handling added in Gaudi. Need to develop tools to use it.

2.2.3 Data Management

David Malon (ANL)

A painful migration to ROOT5 and new associated dictionary infrastructure was undertaken and largely completed in this reporting period. The experience underscored the need for implementation of a transient/persistent separation model, and convinced many developers and software domain coordinators that ATLAS should not delay this transition any further.

The period saw an increasing shift toward readiness for commissioning. The greatest risk to database and event store deliverables in the coming year may come from the lateness of other components of ATLAS infrastructure, and especially the lack of trigger-related information in offline commissioning exercises. These and other late-arriving considerations (such as support for luminosity blocks and sufficient provenance management to allow cross section calculations) will likely lead to substantial pressure for rapid major development by the U.S. team in the latter half of 2006 and in 2007.

2.2.3.1 Database Services and Servers

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| User-level documentation for access to database services | 27-Mar-06 | -- | 27-Mar-06 | Completed |
| Database release model decoupled from software release | 30-Jun-06 | [New] | 30-Jun-06 | On Schedule |
| Completion of FroNTier (data caching technology) testing | 1-Sep-06 | [New] | 1-Sep-06 | On Schedule |
| LCG 3D service deployment at U.S. ATLAS Tier 1 | 1-Nov-06 | [New] | 1-Nov-06 | On Schedule |

2.2.3.2 Common Data Mgmt Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support for Placement Control | 7-Nov-05 | -- | 7-Aug-06 | Delayed (See #1) |
| Support for Multiple Transaction Contexts | 14-Nov-05 | -- | 22-May-06 | Delayed (See #2) |
| Technology evaluation and selection for DDM catalogs | 27-Feb-06 | -- | 27-Feb-06 | Completed |
| User-level documentation for Athena I/O infrastructure | 27-Mar-06 | 27-Mar-06 | 17-Jul-06 | Delayed (See #3) |
| Transient/persistent separation of DataHeader | 3-Apr-06 | -- | 3-Apr-06 | On Schedule |
| ROOT5/Reflex integration | 24-Apr-06 | [New] | 24-Apr-06 | On Schedule |
| Transient/persistent separation of EventInfo and TriggerInfo | 24-Apr-06 | [New] | 24-Apr-06 | On Schedule |
| Refactorization of persistence packages and services | 11-Sep-06 | [New] | 11-Sep-06 | On Schedule |

Note #1  December 2005: Agreement with ATLAS software management is to postpone this milestone until it is specifically requested or required by physics.

Note #2  December 2005: A limited version will be introduced into early 2006 releases, but a more general strategy awaits the outcome of a spring 2006 event store developers workshop.

Note #3  31 March 2006: Partially complete; completion pending documentation of Release 12 infrastructure, which was delayed by international ATLAS.

2.2.3.3 Event Store

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Job-level history object and configuration persistence prototype | 2-Oct-05 | -- | 7-Aug-06 | Delayed (See #1) |
| Schema evolution infrastructure prototype based upon transient/persistent separation | 27-Jan-06 | -- | 27-Jan-06 | Completed |
| Unique EDO Identification Infrastructure | 31-Jan-06 | 31-Jan-06 | 25-Sep-06 | Delayed (See #2) |
| Athena interface to set/get technology-specific attributes (POOL) | 27-Feb-06 | -- | 27-Feb-06 | Completed |
| Infrastructure to support stream- and run-level metadata | 27-Mar-06 | 27-Mar-06 | 25-Sep-06 | Delayed (See #3) |
| Transient/persistent separation of StoreGate support classes for EDM | 1-May-06 | -- | 1-May-06 | On Schedule |
| Event selector with scope-based retrieval support | 22-May-06 | -- | 22-May-06 | On Schedule |
| File/dataset association machinery | 22-May-06 | -- | 22-May-06 | On Schedule (See #4) |
| Strategy for run-level, stream-level, file-level metadata | 22-May-06 | 22-May-06 | 25-Sep-06 | Delayed (See #5) |
| Back navigation support for bytestream data | 7-Aug-06 | -- | 7-Aug-06 | On Schedule |
| Event store components for streaming studies | 25-Sep-06 | [New] | 25-Sep-06 | On Schedule |

Note #1  30 September 2005: Actual delivery may be later in the quarter because the prototype requires new versions of LCG dictionary software that will not be delivered to us until later in the quarter. December 2005: This milestone must be delayed until some time after the corresponding control framework history infrastructure is in place.

Note #2  31 March 2006: Delayed pending outcome of May 2006 Physics Analysis Tools workshop.

Note #3  31 March 2006: Delayed pending proposed ATLAS metadata task force.

Note #4  31 March 2006: We have enlisted the Glasgow group to contribute to this milestone.

Note #5  31 March 2006: Delayed pending proposed ATLAS metadata task force.

2.2.3.4 Non-Event Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DDM support for tile commissioning data | 13-Mar-06 | -- | 13-Mar-06 | Completed |
| Maintain NOVA for use by LAr calorimeter until COOL transition is complete | 1-Jul-06 | -- | 1-Jul-06 | On Schedule |

2.2.3.5 Collections, Catalogs, Metadata

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Athena Interface/Read/Write Access to Collection-Level Metadata | 19-Dec-05 | -- | 24-Jul-06 | Delayed (See #1) |
| Integration of Collection Support & Bookkeeping | 19-Dec-05 | -- | 24-Jul-06 | Delayed (See #2) |
| Tag database infrastructure for Tier0 scaling tests | 16-Jan-06 | -- | 16-Jan-06 | Completed |
| Evaluation of strategies for support of variable-length structures in tags | 27-Feb-06 | 27-Feb-06 | 25-Sep-06 | Delayed (See #3) |
| Transition POOL collections to CORAL AttributeLists and component library model | 17-Apr-06 | 17-Apr-06 | 7-Aug-06 | Delayed (See #4) |
| Support extensible collections, and collection reblocking | 22-May-06 | 22-May-06 | 7-Aug-06 | Delayed (See #5) |
| Tag test integration into Service Challenge 4 | 19-Jun-06 | [New] | 19-Jun-06 | On Schedule |
| Integration and support of event-level metadata in commissioning tests | 25-Sep-06 | -- | 25-Sep-06 | On Schedule |

Note #1 -2 December 2005: Redesign is pending a Spring 2006 event store developers workshop. An underlying component (AMI, from Grenoble) is behind schedule.

Note #3  31 March 2006: Delayed pending LCG major POOL collections infrastructure changes.

Note #4-5  31 March 2006: The revised LCG schedule calls for delivery of this functionality, along with major POOL collections infrastructure changes, in August 2006.

2.2.3.6 Distributed Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Bulk transfer tests based upon realistic T0->T1 model | 31-Mar-06 | -- | 31-Mar-06 | Completed (See #1) |
| Deployment of SC4 version of DDM infrastructure on Tier 1s | 31-Mar-06 | -- | 31-Mar-06 | Completed (See #2) |
| Initial tests of DDM in distributed analysis chain | 17-Apr-06 | -- | 17-Apr-06 | On Schedule (See #3) |
| DDM 0.2 on all Tier 1s | 10-Jun-06 | [New] | 10-Jun-06 | On Schedule |
| DDM support for LAr commissioning data | 15-Jun-06 | [New] | 15-Jun-06 | On Schedule (See #4) |

Note #1  T1->T1 also tested (BNL/Lyon)

Note #2  Deployment completed on 5 Tier1s. A June milestone extends this work to a later DDM version, and to all Tier1s.

Note #3  31 March 2006: DDM deployment is on schedule; distributed analysis components may not come until June

Note #4  Includes automatic procedure to define, populate, and transfer LAr datasets

2.2.3.7 Data Access Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Database representation on U.S. ATLAS Analysis Support Group | 30-Jan-06 | -- | 30-Jan-06 | Completed (See #1) |
| Provide database expertise as part of U.S. ATLAS Analysis Support Group | 1-Apr-07 | [New] | 1-Apr-07 | On Schedule |

Note #1  Jack Cranshaw is the current U.S. ATLAS Analysis Support Group database liaison.

2.2.4 Distributed Software

2.2.4.1 Distributed Analysis

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Physics data access tools | 9-Jan-06 | [New] | 9-Jan-06 | Completed (See #1) |
| Distributed analysis benchmarks for DIAL and PanDA | 15-Feb-06 | [New] | 15-Feb-06 | Completed (See #2) |
| PanDA/distributed analysis review | 8-Mar-06 | [New] | 8-Mar-06 | Completed (See #3) |
| Decide relative roles of PanDA and DIAL for DA | 15-Mar-06 | [New] | 15-Mar-06 | Completed (See #4) |

Note #1  Deliver physics data access tools for US and ATLAS physicists, integrated with the ATLAS distributed data management system DQ2. Data retrieval, search, and web browsing tools.

Note #2  System for benchmarking different distributed analysis systems and job processing back ends, including DIAL and PanDA, together with first measurements of PanDA performance for analysis.

Note #3  Review PanDA and its application for distributed analysis, the DIAL distributed analysis system and its integration with PanDA, and the needs/expectations of users, to guide future planning and development.

Note #4  In light of review outcomes, decide what roles PanDA and DIAL will have for DA in the US. The decision was taken to discontinue the development of DIAL and focus on PanDA for the delivery of DA capability.

Torre Wenaus (Brookhaven National Laboratory)

During the quarter PanDA and DIAL based distributed analysis tools were routinely available. PanDA performance for DA was poor, however, because resources were saturated with production and effective strategies for DA/production resource sharing were not yet in place (expected next quarter). DA benchmarking was implemented in DIAL, and used to compare performance of PanDA-based analysis relative to batch queue submission via DIAL. PanDA job latencies were long due to PanDA's use of saturated production resources.

A PanDA/DA review was held in March. Its charge included examining PanDA for distributed analysis (as well as production), the role of DIAL and its integration with PanDA, and the needs/expectations of users. The review outcome guided the decision thereafter to discontinue the development of DIAL and focus on PanDA as the basis for DA in the US (and potentially outside the US also).

The quarter also saw the full deployment and broad take-up of physics data access tools for end-users, enabling data search/retrieval over the grid and web-based browsing. The tools are fully integrated with the ATLAS data management system DQ2.

2.2.4.2 Production System

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Achieve <10% production error rate due to PanDA | 31-Jan-06 | [New] | 31-Jan-06 | Completed (See #1) |
| PanDA migration to ATLAS production DQ2 | 10-Feb-06 | [New] | 10-Feb-06 | Completed (See #2) |
| PanDA production scalability test | 20-Feb-06 | [New] | 20-Feb-06 | Completed (See #3) |
| Active disk space management | 28-Feb-06 | [New] | 28-Feb-06 | Completed (See #4) |
| PanDA deployment at Indiana U | 15-Mar-06 | [New] | 15-Mar-06 | Completed |

Note #1  Completed several weeks ahead of schedule. Typical error rates ~5% at end Jan.

Note #2  Migrate PanDA to the ATLAS-wide production instance of the DQ2 data management system at CERN. Completed smoothly in one day, with very good results on using a transatlantic DDM system for PanDA.

Note #3  Deliver maximal number of ATLAS production jobs the production system and US resources scale will permit, and examine PanDA performance and scalability. Done, with 11k jobs processed in 1 day with 2% error rate, and no scaling limits seen. This is ~4x the scaling limit of the previous system.

Note #4  Temporary in-house tools for active disk space management (cleanup at high water mark, volume rotation) implemented, pending delivery of DQ2 version supporting space management (expected next quarter).

Torre Wenaus (Brookhaven National Laboratory)

The PanDA production system had an active and successful quarter, its first full quarter in production, both in terms of production usage and ongoing development. It consistently demonstrated production operations requirements far lower (about half) than the previous US system and other current ATLAS systems. In a scaling exercise during ongoing production, PanDA processed 11k jobs in a day, with no scaling limits seen (or expected). This is ~4x the scaling limit seen with the previous system. Panda error rates were low, with a <10% target achieved early and a typical level of ~2-3% achieved by the end of the quarter, ahead of our expectations. Indiana U was added as a PanDA site, and integration work was underway for Teragrid and SLAC. PanDA development saw many functional enhancements in brokerage, data handling, pilot jobs and monitoring.

2.2.4.3 Production Support

Torre Wenaus (Brookhaven National Laboratory)

Production support continued to be an integral part of the production system, distributed analysis and distributed data management efforts, with all participants in those programs contributing to production support (and constituting the full production support effort). No specific production support milestones were called out in this quarter, it is an ongoing activity. Development activities have been successful thus far in providing automation and information discovery/tracking extensive enough to keep production support/operations manpower requirements low and manageable.

2.2.5 Application Software

Frederic Luehring (Indiana University)

For the January to March quarter, work continued in the generator, calorimeter, muon, and monitoring areas. For the tracking area a personal change was in process.

2.2.5.1 Generator Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| First version of EvtGen interface for inclusive decays with Pythia and Herwig | 11-Apr-06 | -- | 11-Apr-06 | On Schedule |
| Migrate to Herwig 6.510 | 11-Apr-06 | 11-Apr-06 | 31-Mar-06 | Completed |
| Migrate to Pythia 6.326 | 11-Apr-06 | 11-Apr-06 | 31-Mar-06 | Completed |
| Migration of production scripts to python | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Customized persistency for HepMC | 5-Jul-06 | -- | 5-Jul-06 | On Schedule |
| Evaluation of migration of Sherpa into atlas releases | 5-Jul-06 | -- | 5-Jul-06 | On Schedule |
| First version of enforced consistency of masses among all generators | 5-Jul-06 | -- | 5-Jul-06 | On Schedule |
| Herwig++ available and integrated | 5-Jul-06 | -- | 5-Jul-06 | On Schedule |
| Validated version of EvtGen interface for inclusive decays with Pythia and Herwig | 5-Jul-06 | -- | 5-Jul-06 | On Schedule |

Frederic Luehring (Indiana University)

ATLAS/Genser interface was updated to the latest version of the latter (1_3_0). At the same time the ATLAS interfaces of Pythia, Herwig, Lhapdf and Cascade were updated to the latest versions, 6.326, 6.510, 5.0.0, and 1.3.0 respectively. This version migration triggered an extensive validation process for the generators above, which involved the fix of several bugs in the code.

Assistance was provided to other Generators developers which resulted to the release of two new generator interfaces for ATLAS, one for Charybdis, and one for Dpemc.

The ATLAS CSC event generation production continued during that time, and several software tools were developed/debugged for supporting this production process.

Extensive interactions with the ATLAS user community took place, supporting them on their physics analysis tasks.

2.2.5.2 Tracking Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Understand existing b-tagging software. | 1-Aug-06 | 1-Aug-06 | 1-Oct-06 | Delayed (See #1) |

Note #1  Best's replacement (Jain) is unable to start until August 1.

Frederic Luehring (Indiana University)

Best's contract was terminated effective March 31, 2006. A search was undertaken to replace Best. This position was filled after the end of this quarter.

2.2.5.3 Calorimeter Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| clean-up of CaloCluster class & new fast CaloTower implementation | 11-Apr-06 | 11-Apr-06 | 31-Oct-06 | Delayed (See #1) |
| move cluster corrections into database, provide software framework for fill/retrieval | 11-Apr-06 | 11-Apr-06 | 31-Mar-06 | Completed |
| move hadronic calibration parameters into database | 3-May-06 | -- | 3-May-06 | On Schedule |
| improvement of Navigation package wrt performance and storage requirements | 5-Jul-06 | 5-Jul-06 | 31-Oct-06 | Delayed (See #2) |
| investigate data compression for CaloCluster | 5-Jul-06 | 6-Dec-06 | 31-Oct-06 | Delayed (See #3) |
| fast CaloTower implementation | 1-Aug-06 | [New] | 1-Aug-06 | On Schedule |
| implementation of new EDM for navigable four-momentum typed objects | 31-Oct-06 | [New] | 31-Oct-06 | On Schedule |
| testbeam converter support | 31-Oct-06 | [New] | 31-Oct-06 | On Schedule |
| use of conditioning data in reconstruction and simulations, esp. validation of "realistic" calo. | 6-Dec-06 | -- | 6-Dec-06 | On Schedule |
| conversion/transport of mySQL etc. testbeam conditions database to COOL | 1-Jan-07 | [New] | 1-Jan-07 | On Schedule |
| optimizations for commissioning/ATLAS data | 1-Jan-07 | [New] | 1-Jan-07 | On Schedule |

Note #1  Delayed to release 13.0.0.

Note #2  Release 13.0.0 is delayed to 26-Sep-06.

Note #3  Release 13.0.0 is delayed and so is this milestone.

Frederic Luehring (Indiana University)

Lampl has provided the reconstruction parameter versioning for CaloCluster corrections for release 12, in collaboration with BNL. In parallel he provided support for testbeam data converters (significant clean-up for FCal2004 and combined H6/H8 testbeams 2005), and started the design work to provide versioning for hadronic calibration constants, in collaboration with MPI. He also started to look into the conversion of the testbeam conditions database from mySQL to COOL. In addition he helps the USATLAS community with questions regarding electron/photon reconstruction and simulation software, as a member of the Analysis Support Group.

2.2.5.4 Muon Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Implement and Test new EDM for Muon reconstruction for 12.0.0 | 28-Apr-06 | -- | 28-Apr-06 | On Schedule |
| Implement and Test new EDM for Muon reconstruction for 13.0.0 | 12-Jul-06 | 12-Jul-06 | 26-Sep-06 | Delayed (See #1) |
| Implement and Test Truth EDM for 13.0.0 | 12-Jul-06 | 12-Jul-06 | 26-Sep-06 | Delayed (See #2) |
| Improve documentation of EDM packages | 31-Jul-06 | [New] | 31-Jul-06 | On Schedule |
| Finalise EDM design, and work on transient / persistent separation for 13.0.0 | 26-Sep-06 | [New] | 26-Sep-06 | On Schedule |
| Integration of new muon reconstruction packages for 13.0.0 | 26-Sep-06 | [New] | 26-Sep-06 | On Schedule |

Note #1-2  This item is delayed because release 13.0.0 is delayed until September.

Frederic Luehring (Indiana University)

The Event Data Model (EDM) has been updated for release 12.0.0, and in particular there have been some changes to get persistency working. For the raw data objects, we have introduced a "transient/persistent" split, which both reduces the size on disk, and provides a mechanism for reading old data. In a bid to make the code more accessible to newcomers, the CVS repository has been cleaned up and we have also been helping split off parts of Moore into smaller sub-packages, which use the new EDM. For 13.0.0, this process will continue, and there will be a big push to document the EDM, provide a transient/persistent split for more packages, and work on finalizing the EDM.

2.2.5.5 Monitoring Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| first functioning Gatherer | 1-Oct-05 | -- | 1-Oct-05 | Completed |
| first successful running of LAr partition with online display | 31-Jan-06 | [New] | 31-Jan-06 | Completed |
| initial discussions on data quality monitoring as separate from the Gatherer | 31-Jan-06 | [New] | 31-Jan-06 | Completed |
| irst successful running of complete online environment through full chain to display | 5-Feb-06 | [New] | 5-Feb-06 | Completed |
| first version of Gatherer for tdaq-01-06 | 6-Mar-06 | [New] | 6-Mar-06 | Completed (See #1) |
| Commit of Gatherer version incorporating further Run Control-related mods. in prep. for pre-release. | 31-Mar-06 | [New] | 30-Jun-06 | Delayed (See #2) |
| first draft of DQM requirements document to ATLAS MWG | 31-Mar-06 | [New] | 31-Mar-06 | Completed |

Note #1  tdaq-01-06 was later delayed but not as a result of anything related to the Gatherer.

Note #2  This work was delayed for reasons external this work.

Frederic Luehring (Indiana University)

Research by Haleh Hadavand continued in Jan-March 2006 in three categories. First, work proceeded to upgrade the Gatherer to be able to function in the actual data-taking environment. This included update to string manipulation and usage of run control facilities. Several problems with the structure of the Gatherer were identified. These were inherited from the previous developers of this tool. The work to rectify these progressed substantially in this period. Second, the data quality monitoring tools, which were originally envisioned to be part of the Gatherer effort, were realized to be a much larger project. In conjunction with Monitoring Working Group (MWG) discussion, we have split this off of Gatherer work, and the relevant requirements discussion was begun in this period. Haleh has been integrally involved in the requirements discussion and writing up of the D(ata)Q(uality)M(onitoring) in this period. Third, Haleh has been integrally involved in gaining further expertise for running online tools for LAr monitoring She successfully produced the first working setup of these tools with monitoring on one node in February.

2.2.6 Infrastructure Support

2.2.6.2 Librarian

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release NICOS version 1.1 with the better multiplatform support | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Setup mirror of ATLAS Pacman cache at BNL | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Install and support ATLAS releases and associated external software at BNL | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |
| Support ATLAS software nightly builds at BNL and CERN | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Alexander Undrus (Brookhaven National Laboratory)

In this quarter NICOS, control system of ATLAS nightly builds, successfully supported standard monolithic and experimental project-oriented nightly builds. NICOS ensured proper synchronization of project builds according to their hierarchy. The status of project builds (with number of failed compilations and tests) was reflected on the NICOS web pages. The build of doxygen documentation is set up for the main branch of the nightly builds with the summary reflected on NICOS web pages. Also the experimental ATLAS nightly builds with gcc344 compiler are started. The nightly builds were checked with about 70 unit and integration tests performed in the ATN testing framework integrated with NICOS. Many tests descriptions were migrated to new XML format (same as used by the RTT test system). At BNL new ATLAS software releases were promptly installed, usually in one to two days after CERN installation. The mirrors of ATLAS CVS repository and ATLAS nightly builds were supported. The LXR server, alxr.usatlas.bnl.gov, provided the collaboration-wide service for fast searches of ATLAS software.

2.2.7 Analysis Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Formation of Analysis Support Group | 15-Feb-06 | -- | 1-Feb-06 | Completed |
| Preparation of Analysis Support Centers Role and Implementation Document | 15-Feb-06 | -- | 15-Feb-06 | Completed |
| Selection of Analysis Forum conveners | 15-Feb-06 | -- | 15-Feb-06 | Completed |
| Signing of Analysis Support Center MOU | 1-Apr-06 | -- | 1-Apr-06 | On Schedule |
| Full operation of Analysis Forums | 1-Sep-06 | [New] | 1-Sep-06 | On Schedule |
| First analysis jamboree at each ASC | 1-Oct-06 | [New] | 1-Oct-06 | On Schedule |
| Follow-up with analysis jamboree participants | 1-Oct-06 | [New] | 1-Oct-06 | On Schedule |

Stephane Willocq (University of Massachusetts)

During the period Jan-Mar 2006, there was significant progress in establishing the US ATLAS Analysis Support organization. The experts for the Analysis Support Group were identified and ready to help users. Also, the conveners for the various Analysis Forums were identified and started their activities. MOU were drafted for the three Analysis Support Centers. A Beyond the Standard Model workshop took place at the LBL ASC, in conjunction with a 2-day ATLAS software tutorial.

## 2.3 Facilities

2.3 Subsystem Manager's Summary

Razvan Popescu (Brookhaven National Laboratory)

Hired Hiro Ito and assigned him to data management support, in particular FTS and DQ.

The recruitment effort continues. Several other interviews and offers had not yielded new hires.

2.3.1 Tier 1 Facilities

2.3.1.1 Management/Administration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Expand USATLAS Tier1 Engineering Staff | 30-Sep-06 | [New] | 30-Sep-06 | On Schedule (See #1) |

Note #1  Hire one computing professional (Hiro Ito) in support of data management operations.

2.3.1.2 Tier 1 Fabric Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Installation of Expanded LAN Infrastructure | 15-Jan-06 | -- | 15-Jan-06 | Completed |
| Expanded LAN Infrastructure Operational | 15-Feb-06 | -- | 15-Feb-06 | Completed |
| Expanded Facility Power and Cooling Capacity Available | 31-Mar-06 | -- | 31-Mar-06 | On Schedule (See #1) |

Note #1  New UPS/PDU systems have been delivered and are installed. Liebert rack-top cooling solutions are now in deployment.

Razvan Popescu (Brookhaven National Laboratory)

The BNL LAN backbone had been upgraded to 20Gb/sec to support the enhanced WAN connectivity. The lab's ESNet connection was upgraded to 10Gb/sec. Currently work in progress is focusing on providing the additional 10Gb/sec, on an alternate path, as designed. Delivery of redundant 20Gb/sec connection is expected in Q2'06.

240KVA of additional UPS backup power is currently functional in the computing center. The increment will be sufficient to support the computing capacity increase planned for 2006.

Additionally 135tons of A/C, using a novel rack-top solution is currently in the process of deployment.

2.3.1.3 Tier 1 Linux Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin CPU/dCache Disk Expansion Procurement | 1-Apr-06 | -- | 1-Apr-06 | On Schedule |
| CPU/dCache Disk Expansion Order Placed | 15-Apr-06 | -- | 15-Apr-06 | On Schedule |
| Begin CPU/dCache Disk Expansion Installation | 15-May-06 | -- | 15-May-06 | On Schedule |
| Central Disk Expansion Operational | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| CPU/dCache Disk Expansion Operational | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |

2.3.1.4 Tier 1 Storage Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| New Tape Subsystem Order Placed | 15-Dec-05 | -- | 15-Dec-05 | Completed |
| Begin Installation of New Tape Subsystem | 15-Jan-06 | -- | 15-Jan-06 | Completed |
| New Tape Subsystem Operational | 15-Feb-06 | -- | 15-Feb-06 | Completed |
| Begin Central Disk Expansion Procurement | 1-Apr-06 | -- | 1-Apr-06 | On Schedule |
| Central Disk Expansion Order Placed | 15-Apr-06 | -- | 15-Apr-06 | On Schedule |
| Begin Central Disk Expansion Installation | 15-May-06 | -- | 15-May-06 | On Schedule |

2.3.1.5 Tier 1 Wide Area Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| OSG 0.4.0 Deployed and Operational | 31-Dec-05 | -- | 31-Dec-05 | Completed |
| All required SC4 Software for Baseline Services Deployed | 31-Jan-06 | -- | 31-Jan-06 | Completed |
| BNL Wide Area Network Upgrade Operational | 28-Feb-06 | -- | 28-Feb-06 | Completed |
| 10Gbs BNL Tier 1 <-> Tier 0 Dedicated Connectivity Operational | 31-Mar-06 | -- | 31-Mar-06 | Completed |
| SC4 Set-up Complete and Basic Service Demonstrated | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |

2.3.1.6 Tier 1 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 500CPU, 150Disk, 200WAN=>Disk, 300Tape,200WAN=>Tape | 15-Feb-06 | -- | 15-Feb-06 | Completed |
| 1125CPU,525Disk,200WAN=>Disk,300Tape,200WFAN=>Tape | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |

2.3.2 Tier 2 Facilities

2.3.2.1 University of Chicago/Indiana

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 16 TB NFS storage reconfigured | 31-Mar-06 | [New] | 31-Mar-06 | Completed (See #1) |
| Benchmarks of ATLAS on candidate Tier2 platforms | 31-Mar-06 | [New] | 31-Mar-06 | On Schedule (See #2) |
| Dedicated ATLAS /home server deployed | 31-Mar-06 | [New] | 31-Mar-06 | Completed (See #3) |
| LCG Accounting System for US ATLAS - preparation and first installations | 31-Mar-06 | [New] | 31-Mar-06 | Completed (See #4) |

Note #1  Partly solved stability problems at UC Tier 2.

Note #2  Benchmarks of ATLAS software (KitValidation) on various platforms (Xeon, Opteron, single versus multi-core processors.

Note #3  Partly solved stability problems on UC cluster site.

Note #4  Preparations for deployment of LCG software to report accounting statistics into the LCG reporting systems.

Rob Gardner (University of Chicago)

During this period work performed on the Midwest Tier 2 facilities was focused on supporting on-going production needs of the PanDA team, supporting user analysis via local job submission tools (condor_submit), on-going work to re-configure the UC cluster filesystem to address Linux 2.6 kernel instabilities for NFS filesystems, on-going DQ2 support and custodial maintenance of ATLAS datasets, LCG accounting, and planning for summer MWT2 procurements.

Some items in brief:

* Preparations, initial installations and validation of LCG accounting tools; recipes created and support assistance for other US ATLAS facilities (Tier1, Tier2 centers).

* Benchmarks of ATLAS software (KitValidation) on various platforms (Xeon, Opteron, single versus multi-core processors.

* Development and testing of Condor group priority settings for the UC batch scheduler.

* On-going work in the OSG Integration Testbed - participation in ITB workshops, weekly meetings, and testbed deployments of the core OSG software stack.

* Validation of ATLAS production software on the OSG ITB.

* Procurement and deployment of systems backup server for UC site of the MWT2.

* Development, deployment and testing of system backup scripts.

* Reconfiguration of 12 TB storage system to use SLC 3.0 operating system over Rocks-based CentOS 4 (which has Linux 2.6 kernel leading to kernel panics serving the 64-node, Linux 2.4-based cluster).

* Hire of Dan Schrager to MWT2 technical staff.

* Deployment of DQ2 instance on UC Teraport cluster (MWT2 leveraged resource).

* Procurement of DQ2 server for use at IU AVIDD cluster (iVDGL prototype Tier2).

* Installation of DQ2 at IU.

* Deployment and validation of ATLAS software releases on UC Teraport cluster (resolving SUSE 9 platform, AMD64 issues).

* Continued development and on-going maintenance of ROCKS cluster management configuration.

* On-going operation and troubleshooting of GUMS server. Documentation of configuration example for other Tier2 centers.

* On-going operations and troubleshooting of US production system with its dependent services (DQ2).

* Deployment and testing of DotProject internal project reporting tool.

* Continued participation at weekly US ATLAS facilities and operations meeting.

* Continued participation in weekly OSG Integration meeting.

* Continued participation in weekly OSG Operations meeting.

2.3.2.3 Southwest

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| OU SWT2 Cluster running CSC production | 14-Apr-06 | [New] | 14-Apr-06 | On Schedule |
| UTA DPCC Cluster ready for Distributed Analysis | 9-Jun-06 | [New] | 9-Jun-06 | On Schedule |
| UTA SWT2 Cluster running CSC production | 15-Jun-06 | [New] | 15-Jun-06 | On Schedule |
| Reconfiguration of SWT2 Queues to balance managed production and distributed analysis users | 15-Jul-06 | [New] | 15-Jul-06 | On Schedule |

Kaushik De (University of Texas at Arlington)

The SWT2 facilities (UTA and OU) completed their purchase of new clusters from Dell. The clusters have identical configuration. The OU cluster is 25% of the UTA cluster.

Both institutions are in the process of setting up power and other infrastructure in their machine rooms dedicated to the new SWT2 clusters. Note DPCC at UTA is in old building - it will not move to the location of the rest of UTA SWT2.

We expect the new SWT2 clusters to become operational in the next quarter. In the meantime CSC production continues with old hardware at both institutions.

The UTA SWT2 cluster was upgraded to a dedicated 1GB network link to the outside. OU already has 1GB link. However, DPCC will remain restricted to 100 Mb.

2.3.3 Wide Area Network

Shawn McKee (University of Michigan)

The LHC-OPN (T0-T1 Networking) met in Amsterdam on January 30, 2006 to discuss current status and planning for the four working groups: Routing, Security, Operations and Monitoring. Shawn McKee, US ATLAS Networking, is organizing the Monitoring activity for the LHC-OPN and presented plans to create a prototype testbed for monitoring.

Progress continues on developing advanced networking capabilities through projects like UltraLight, Terapaths, Lambda Station and OSCARS. Initial planning for Super-Computing 2006 is beginning. Terapaths plans to release a beta version of its QoS management software in early summer 2006. Lambda Station has produced a CD for easy install of their software.

UltraLight is continuing to work on many network areas including utilization of 10GE links "disk-to-disk" with single servers. Industry is collaborating and support in the form of hardware has been provided by Myricom, 3Ware and AMD.

The networking pre-proposal to OSG (Open Science Grid) was not integrated into the final OSG proposal submitted in winter 2006.

Two proposals related to US ATLAS networking were submitted: one to NSF Physics at the Information Frontier called PLaNetS (Physics Lambda Network Services) and one to DOE SCiDAC called LHC-Monitoring Infrastructure. We hope to hear the results by early summer.

2.3.4 Grid Tools & Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Development of components for ATLAS production system (scheduler, broker) (Chicago) | 1-Oct-05 | -- | 1-Oct-05 | Completed |
| Integration with distributed data management services and infrastructure (Chicago) | 1-Nov-05 | -- | 1-Nov-05 | Completed |
| Development on as needed basis, components for distributed production and analysis focusing on distributed grid data management (Chicago) | 1-Feb-06 | -- | 1-Feb-06 | On Schedule |

2.3.4.2 Workflow Services

Rob Gardner (University of Chicago)

On-going work at University of Chicago on grid-based workflow services. This item covers contributions from M. Mabelli's work on the PanDA production system and its dependent integration to core grid infrastructure.

The deliverables and milestones achieved are as follows:

* Programming for USATLAS [[https://uimon.cern.ch/twiki/bin/view/ATLAS/PanDA][PanDA]] executor

* Development of the Brokerage package has been handed over to Tadashi: [[https://uimon.cern.ch/twiki/bin/view/ATLAS/PandaBrokerage][PandaBrokerage]]

* Development of the !JobScheduler in collaboration with Xin Zhao [[https://uimon.cern.ch/twiki/bin/view/ATLAS/PandaJobScheduler][PandaJobScheduler]]. The package has been split into two: the !JobScheduler itself (sender of pilots jobs) and the Pilot package.

* Development of the !JobScheduler itself

* New scheduling policies

* Improved stability

* Increased autonomy of the pusher (program sending pilot jobs)

* Coordination with Xin that is working on the Pilot development (new package that branched out)

* Packaging of the !PanDA packages (!PandaJS, !PandaSrv, !PandaJDE, Panda, auxiliary DQ-Client) together with Horst Severini. Provided the initial version of the packaging scripts and Pacman file templates; continued contributions with Horst in subsequent versions.

* Troubleshooting and support of USATLAS production activity

* Troubleshooting of different problems involving

* job submission at gatekeeper

* file transfer

* jobs submitted at the MWT2

* Maintenance of the USATLAS Capone executor (with Jerry Gieraltowski) [[https://uimon.cern.ch/twiki/bin/view/ATLAS/Capone][Capone]]:

* Release 1.2 is still the current one

* Minimal support for users

* Activity within the ATLAS worldwide collaboration

* Major involvement in the ATLAS !ProdSys protocol definition and partial contribution to its coding.

* Participation in the ATLAS monitoring effort led by John Kennedy (FZK-CERN).

* Grid activities (OSG and Interoperability efforts)

* Participation in the Glue Schema v1.2 effort:

* Writing of the Glue 1.2 documented, final draft (edited by Sergio Andreozzi)

* Involvement in the GIP (Generic Information Provider) activity within OSG

* Participation in the OSG monitoring and information system activity (MIG)

* Led the CE storage activity within OSG to define how disk space are seen from within the CE environment.

* Coordination of the meetings/discussions.

* Revision of the [[http://osg.ivdgl.org/twiki/bin/view/Integration/LocalStorageRequirements] [Local Storage Requirements]] document (with comments and contributions from various parties).

* Writing of the [[http://osg.ivdgl.org/twiki/bin/view/Integration/LocalStorageUse][Local Storage Use]] document. A guide for Grid users.

* Writing of the[[http://osg.ivdgl.org/twiki/bin/view/Integration/LocalStorageConfiguration][Local Storage Configuration]] document. A guide for OSG Site administration.

2.3.5 Grid Production

Kaushik De (University of Texas at Arlington)

The first quarter of 2006 was very busy with CSC production. We completed Release 11 validation and started large sample production. Over 10 million events were produced in ATLAS. We reached target rate of 2M events per week ATLAS-wide. U.S. Production contributed approximately 25% of the total.

During this period we also successfully migrated U.S. production from the Capone system to PanDA. In January, data were produced in parallel (duplicate events) with both systems. After this, PanDA was validated for official production and CSC production was stopped with Capone. PanDA uses DQ2 for data management and therefore became the first executor in ATLAS to use DQ2.

Unfortunately, a rare G4 bug was discovered after many samples had already been generated. Many of the event samples will be regenerated with a bug fix release 11.0.42.

2.3.5.1 Software Acceptance

Kaushik De (University of Texas at Arlington)

The operations team started to use the PanDA system for production in this quarter. They provided valuable feedback to the developers. We achieved a stable version of PanDA for CSC production in this quarter, through close collaboration between the production operations team and PanDA developers.

2.3.5.2 Deployment of Software Services

Kaushik De (University of Texas at Arlington)

Many ATLAS releases were installed, approximately bi-weekly cycle. PanDA was installed for production.

2.3.5.3 Validation and Hardening

Kaushik De (University of Texas at Arlington)

The primary production task during January and February was software validation. Various physics samples were run with each new release of Athena, every two weeks. Hundreds of bugs were reported to the Savannah system set up by ATLAS. Finally, the 11.0.41 release was accepted for massive production.

The PanDA production software, the Eowyn executor, and the DQ2 software were all validated by the production team. Many bug reports and feedbacks were sent to the software developers, leading to hardening of all the systems.

2.3.5.4 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Production (UTA) | 23-Jan-06 | -- | 23-Jan-06 | Completed |
| Start Release 12 Production (UTA) | 1-May-06 | -- | 1-May-06 | On Schedule |

Kaushik De (University of Texas at Arlington)

The PanDA shift team consists of Yuri Smirnov (BNL), Nurcan Ozturk (UTA), Mark Sosebee (UTA) and Tomasz Wlodek (BNL). Shifts are run 6 days a week. PanDA production proceeded smoothly with this shift team. More than 3 million events were processed in the U.S., covering dozens of physics channels, many production steps (evgen, simul, digit, recon, pileup), and dozens of software releases.

During the first 3 months of production, the PanDA development team provided critical support for operations.

Wensheng Deng provides full time support for DQ2 data management in the U.S. This played a critical role in successful CSC production.

In international ATLAS, Kaushik De is the Distributed Production Coordinator, Pavel Nevski coordinates Task and Job Definitions, and Alexei Klimentov coordinates DDM Operations.

## 3.1 M&O Silicon

3.1 Subsystem Manager's Summary

All spare pixel modules have been completed. The prototype service quarter panel at CERN is being readied for the 10% system test when End Section C arrives in May. OSU is loading 36 additional opto boards at collaboration request. The responsibility of this was to have been shared with Siegen but they are no longer able to complete that task. How to cover these costs within the collaboration is still being worked out.

The SCT four-barrel assembly was inserted into the TRT barrel assembly on 17-Feb-06. Connection of services is proceeding for testing prior to installation in the pit. Cable assembly, testing and installation continues and will continue well into the spring. Some major problems arose with the barrel and end-cap patch panel 1 assemblies. A resolution appears at hand.

The spare RODs have been fabricated and debugged.

3.1.1 Pixels

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Hot Modules

All spare pixel modules have been completed

Sector and Disk Production

All production sectors have been loaded on rings as part of production. One sector developed a cooling leak and was replaced with a spare sector. The leak has been repaired with epoxy and this has now become a spare. There are 3 spare sectors fully loaded. Some QC still remains to certify all 3 as usable if needed.

Preparations for 10% system test at CERN

24 spare opto boards have been loaded on the prototype service quarter panel that is now at CERN. A cold box has been designed to house the service quarter panel together with End section C for the 10% system test (box not yet produced). Adapter pipes and cables will be needed also. The box design has the end section in a horizontal position in order to allow cosmic ray running (following a study of rates in different orientations with typical scintillators). A plastic holder to support the end section in this box is being made (will also be used for holding during transport to CERN, anticipated on May 15).

Additional OPTO boards

The collaboration has requested that OSU load an additional 36 opto boards in order to instrument the spare locations in the service panels, so that modules can be assigned to them in case of failures in the service chain. The original plan was to share this burden with Siegen, but this institute is no longer able to produce boards. The cost of materials for this additional effort will come from the pixel collaboration common fund, while the labor cost in the US (approx. $10K) is still to be resolved.

3.1.1.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start of Pre-operations of Pixel Endcap (LBNL) | 1-May-06 | 1-May-06 | 15-May-06 | Delayed (See #1) |

Note #1  Pre-operations start when the endcap arrives at CERN. Delays in specification of capillaries have pushed back the transport date by 2 weeks.

3.1.1.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Spare Modules and Assemblies (LBNL) | 15-Sep-06 | -- | 15-Sep-06 | On Schedule |
| Spare Opto Board Production/Test Complete (OSU) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |

3.1.2 SCT

Alex Grillo (UCSC)

The four-barrel assembly was inserted into the TRT barrel assembly on 17-Feb-06. Connection of services is proceeding for testing prior to installation in the pit.

Cable assembly, testing and installation continues and will continue well into the spring. Some major problems arose with the barrel and end-cap patch panel 1 assemblies. A resolution appears at hand.

3.1.2.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Insertion of SCT Barrel into TRT Barrel | 23-Jan-06 | 28-Feb-06 | 17-Feb-06 | Completed |
| Complete Pre-Operations of SCT Inside ID (UCSC) | 10-May-06 | 28-Feb-06 | 10-May-06 | On Schedule |
| Start Installation of ID Barrel into UX15 (UCSC) | 11-May-06 | 11-May-06 | 15-Jul-06 | Delayed (See #1) |
| Complete Intial Test of ID Inside of UX15 (UCSC) | 15-Jul-06 | 1-Jul-06 | 15-Sep-06 | Delayed (See #2) |

Note #1  This is the new ATLAS schedule for installation of the ID barrel into UX15

Note #2  Given the delay in installation of the ID Barrel into UX15, the initial testing will also be delayed.

Alex Grillo (UCSC)

The four-barrel SCT assembly was finally inserted into the TRT on 17-Feb-06. This was delayed first by problems with TRT cooling pipes and then with some leaks in SCT cooling pipes. In the end, the insertion went quite smoothly. A few staves near the top and near the bottom of all four barrels are now being connected to services so that noise and cosmic ray tests can be run before the unit is moved to the collider hall.

Sofia is part of the Inner Detector Offline Commissioning group. She is the coordinator of the cosmic simulation production providing simulated/digitized/reconstructed data samples. The production of these specific samples will be used for digitization, tracking and alignment studies by the ATLAS ID software community.

Forest continues to operate the cooling system for the barrel in the surface building as tests are repeated with the integrated SCT/TRT. He has also been contributing to sorting out problems with patch panel installation inside the ATLAS detector.

The installation of cables in the pit has now shifted to the spliced TypeII and TypeIII cables which includes connecting them to the dummy patch panel 1 assemblies. This has uncovered problems with both the barrel and the end-cap patch panels. It turns out that the barrel patch panel and cable connection was prototyped with a “last prototype” cable and not the final production cable. The actual cable is about 0.5 mm thicker and does not fit properly in the clamp. Also, the full complement of clamps as well as clips to hold cable connectors securely in place were not available at CERN when installation started. In the case of the end-cap patch panel 1, apparently no prototyping had been done. This was very problematic because the design that had been worked out between Ned and the RAL mechanical engineers proved to be unworkable in the confines of the cryostat where installation must take place.

Once again there was insufficient communication between RAL engineers and CERN people resulting in the incorrect cable being prototyped for the barrel and a complete failure of RAL staff to prototype the end-cap assembly.

Sandra Ciocio, who is supervising the cable testing and installation, was squeezed between pressure from TC to keep installation on schedule and the need to get the installation right so that proper ground referencing and strain relief of the cables would be accomplished. After several weeks of discussions between RAL engineers, Sandra and Forest and others at CERN, and Ned, it appears that workable solutions are possible. Ned is traveling to CERN in mid-April to work out final details.

3.1.3 RODs

Abraham Seiden (UCSC)

The spare RODs have been fabricated and debugged.

3.1.3.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Spare RODs Completed | 1-May-06 | -- | 1-May-06 | On Schedule |

## 3.2 M&O TRT

3.2 Subsystem Manager's Summary

Harold Ogren (Indiana University)

During this period the final shake out of the electronics for the Barrel TRT was finished, cosmic ray runs were taken with both upper and lower segments of the barrel, and the SCT was successfully integrated with the Barrel TRT.

Service manifolds:

The remaining testing and installation of replacement parts for the services manifold was carried out during this period. The PEEK plastic pieces needed for the modified cooling and active gas manifolds were produced at Indiana University and shipped to CERN. The assembly of these pieces into phi segments for a sector of six modules was carried out by Kirill Egorov with testing help from Chuck Long from Hampton University.

At the end of this reporting period the upper and lower quarters of the service manifolds had been installed and were being tested in preparation for the covering of these areas by the heat spreader plates of the SCT.

Electronics and system testing:

Testing of the electronics by the University of Pennsylvania group proceeded during this time. All electronic channels on the Barrel were completed and detailed studies of the upper and lower sectors with cosmic rays were finished. Work continued on the endcap checkout.

3.2.1 TRT-Subsystem

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT Installed in TRT | 23-Jan-06 | -- | 11-Feb-06 | Completed (See #1) |
| SCT-TRT Joint Test Complete | 10-May-06 | 10-Jun-06 | 19-Jun-06 | Delayed (See #2) |
| Barrel and SCT Install in ATLAS | 11-May-06 | 11-Jul-06 | 16-Aug-06 | Delayed (See #3) |
| TRT Complete, EC-C Installed | 6-Jul-06 | 6-Jul-06 | 5-Oct-06 | Delayed (See #4) |
| EC-C Complete, EC-A Installed | 5-Aug-06 | 5-Aug-06 | 5-Oct-06 | Delayed (See #5) |

Note #1  Was installed in on Feb 17 .

Note #2  This will drag out until the ID is ready to go into the pit.

Note #3  Estimates vary when the services will be ready for us.

Note #4-5 schedule has shifted for endcap

3.2.1.1 TRT Pre-Operations

3.2.1.1.4 TRT-6 mod-check

Harold Ogren (Indiana University)

Members of our group- Kirill Egorov worked on the assembly of the Service manifolds.

The remaining testing and installation of replacement parts for the services manifold was carried out during this period. The PEEK plastic pieces needed for the modified cooling and active gas manifolds were produced at Indiana University and shipped to CERN. The assembly of these pieces into phi segments for a sector of six modules was carried out by Kirill Egorov with testing help from Chuck Long from Hampton University.

3.2.1.1.5 TRT-SCT in SR

Harold Ogren (Indiana University)

The SCT was successfully joined with the TRT on February 17. The following few weeks were taking up with testing of the SCT components and the preparation of the upper sector services for the covering of these areas by the SCT spreader plates. This was completed on time.

3.2.2 Common TRT/ID

## 3.3 M&O Liquid Argon

Ryszard Stroynowski (Southern Methodist University)

The commissioning of the front-end electronics is progressing slowly. In spite of extensive testing of individual components and of individual boards after their assembly, we find new problems in operations of the front-end system. All of these problems can be resolved by component replacement and repairs but all of them require a lot of attention. The problems encountered in operations of low voltage power supplies appear to have been resolved. The BNL team has found several underlying failure causes of the Power supplies units. All of these were related to local temperature excess. The plan for replacement of marginal components (capacitors and inductors) has been discussed with MDI and additional air cooling will have to be added by BNL. All units will have to be re-worked.

MDI will prepare the work plan but it is unlikely that all units will be available before the end of July. The commissioning of the tower builder and of the Level 1 receiver uncovered several problems related to the modified cabling of the EMEC inner wheel. It is likely that new boards correcting for cabling problems will have to be added to the base plane of the front-end crate to correct for these problems. The commissioning of the optical connections is progressing well. The work on fiber splicing and connectors for the barrel should be completed at the end of April. However, individual fibers will not be connected to the FEBs until the power supplies will be installed to minimize cabling cross over problems. A major part of commissioning includes organization of the data bases and rack wizard. This work follows the commissioning procedures and is progressing well. The transition to the UNICOS cryogenics operating system was successful. The BNL team will continue to consult with the CERN cryo group throughout the cryostat cooldown period. The preparations for the beam test in Protvino to verify performance of FCal components in high radiation is progressing well.

3.3.1 Mechanical Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commission Cryogenic Connection Lines to the Barrel at z=0 | 10-Jan-06 | -- | 10-Jan-06 | Completed |
| Commission Vacuum Pumps, Monitoring etc. for Barrel | 30-Jan-06 | -- | 30-Jan-06 | Completed |
| Phase 1&2 (Arizona) - Endcap (A+C) cold test in the pit | 15-Jun-06 | -- | 15-Jun-06 | On Schedule |

3.3.1.2 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commissioning of Endcap C in the Pit Complete | 1-Feb-06 | 1-Jun-06 | 1-Sep-06 | Delayed (See #1) |
| Commissioning of Pit Cryogenics Complete | 1-Mar-06 | 1-Mar-06 | 10-Apr-06 | Delayed (See #2) |
| Re-commissioning Underground Complete | 1-Mar-06 | 1-Mar-06 | 1-Nov-06 | Delayed (See #3) |
| Commissioning of Endcap A in the Pit Complete | 1-Aug-06 | 1-Aug-06 | 1-Nov-06 | Delayed (See #4) |

Note #1  Schedule change put higher priority on cryogenics for the toroid and solenoid than for the endcaps.

Note #2  Started with ~ 1 month delay

Note #3  Awaits endcap A connections

Note #4  has not started yet

3.3.1.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Barrel HV Operations (SB) | 1-Feb-06 | 1-Feb-06 | 1-Jul-06 | Delayed (See #1) |

Note #1  delivery of lv power supplies has been delayed

3.3.2 Electronic Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of the First Full Crate on the Truck Linked to USA15 | 30-Dec-05 | -- | 30-Dec-05 | Completed |
| Complete Commissioning of Barrel Optical Links (SMU) | 1-Mar-06 | 1-Mar-06 | 1-May-06 | Delayed (See #1) |
| Complete Commissioning of EndcapC Optical Links (SMU) | 1-Mar-06 | -- | 1-Jun-06 | Delayed (See #2) |
| Operation of all Crates on the Truck | 30-Apr-06 | 30-Apr-06 | 30-Jun-06 | Delayed (See #3) |
| Operation of all Crates on the Truck stand alone | 30-Apr-06 | 30-Apr-06 | 30-Jun-06 | Delayed (See #4) |
| Commissioning of Low Voltage Power Supplies on the Barrel Complete | 1-Jun-06 | 1-Jun-06 | 1-Aug-06 | Delayed (See #5) |
| Commissioning of Low Voltage Power Supplies on the Endcap C Complete | 1-Jul-06 | 1-Jul-06 | 1-Aug-06 | Delayed (See #6) |
| Commissioning of Low Voltage Power Supplies on the Endcap A Complete | 1-Aug-06 | -- | 1-Aug-06 | Delayed (See #7) |
| Complete Commissioning of EndcapA optical Links (SMU) | 1-Aug-06 | -- | 1-Aug-06 | On Schedule |

Note #1  delay for the magnet tests

Note #2  Schedule change postponed the installation of electronics on the endcaps for after the magnet tests are complete.

Note #3  delay for the magnet tests

Note #4  will work on the final configuration only

Note #5-7  late delivery from MDI

3.3.2.1 Pre-Operations and Commissioning

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Commissioning of Barrel Receiver System (Pitt) | 15-Nov-05 | -- | 15-Apr-06 | Delayed (See #1) |
| Completion of Documentation of Level 1 Trigger Interface for Liquid Argon and Tile Calorimeters (Pitt) | 1-Dec-05 | 1-Mar-06 | 1-Aug-06 | Delayed (See #2) |
| Complete Commissioning of Barrel Receiver System (Pitt) | 31-Dec-05 | 31-May-06 | 31-Jul-06 | Delayed (See #3) |
| Maintenance Procedures for Receiver Modules Complete (Pitt) | 31-Dec-05 | 15-Apr-06 | 15-Sep-06 | Delayed (See #4) |
| Start commissioning of EndcapC Receiver System (Pitt) | 1-Jan-06 | 15-May-06 | 15-Jul-06 | Delayed (See #5) |
| Complete Commissioning of EndcapC Receiver System (Pitt) | 1-Mar-06 | -- | 15-Jun-06 | Delayed (See #6) |
| Start Commissioning of EndcapA Receiver System (Pitt) | 1-May-06 | 30-May-06 | 30-Aug-06 | Delayed (See #7) |
| Complete Commissioning of EndcapA Receiver System (Pitt) | 30-Jun-06 | 30-Jun-06 | 30-Sep-06 | Delayed (See #8) |

Note #1  Need all FEC crates commissioned

Note #2  Documentation almost complete. Documents need to be updated with final versions of hardware.

Note #3-8  Need all FEC crates commissioned

Francesco Lanni (Brookhaven National Laboratory)

In the Jan-Mar period these are the main activities of the BNL group in the Front-end electronics:

1. Commissioning of the first 2 cooling sectors (K. Sexton, R. Burns, A. Hoffman) on the barrel calorimeter after the infrastructure installation by Technical Coordination was completed. Pre-operation of the final cooling circuits on the sectors above mentioned has started.

2. Continuing the development of tools and software for pre-operation and commissioning of the Front-end crate and power supply system [DCS]. PVSS software developed by D. Damazio controls and monitors the activity of the FE-crates as well as the 280V power supply racks in USA-15. First implementation of the interlock integration in our DCS system has been deployed.

3. Preparation of the EMF setup to pre-commission LVPS final units delivered to CERN. A minimal system with passive loads has been setup to verify the correct functionality of the LVPS units before installation on the detector and real PS commissioning (D. Damazio)

4. First implementation (S. Kandasamy) of the rack-wizard software and Oracle based DB system for installation and commissioning of each front-end component [work will continue for several months during the whole commissioning phase and subsequently for all calorimeter operations]

5. Participation (H. Ma, D. Damazio, H. Chen) to the LAr EM barrel expert week in March where several crates were for the first time powered up and exercised at the same time

6. Start working on accessing condition databases [COOL/POOL integration and communication with TDAQ and LAr online software] for commissioning and particularly in preparation for the upcoming expert weeks (H. Chen).

John Sondericker (Brookhaven National Laboratory)

During the week of March 20th Ms. Rehak carried out UNICOS commissioning tests of the ATLAS Nitrogen Refrigerator System as per BNL agreement with CERN following acceptance testing of the plant from Air Liquide. In spite of the all the difficulties brought on by bugs and lack of support throughout development of the control software, it took only a few days of running to reproduce similar refrigerator operating conditions to those of the original acceptance tests. We at BNL are elated and happy to gain success with what at times had seemed an impossible task while CERN Cryo enjoys their UNICOS standard controls and displays.

The refrigerator continued to be run for the next few weeks into the month of April to get some more operating time logged on the new system. Beyond the mechanical and reliability aspects of the running period, time was spent breaking in future CERN operators so that they understand and are comfortable with the differences found in BNL operating philosophies.

John Parsons (Columbia University (Nevis Laboratory))

Commissioning of the FEBs on the EM Barrel continues, though hindered by the lack of final LVPS. Several crates were successfully operated during the recent second EMB expert week.

Commissioning of the FEBs of the EC-C has started, led by Dominik Dannheim. The first EC expert week is planned for June.

Repairs of FEBs at CERN have been organized and started, using the infrastructure of the CERN SMT workshop. Jaro Ban has used this facility to repair a few dozen FEBs with faulty shaper chips. Spare FEB parts have been shipped to CERN, where they are being stored in the EMF.

The pre-series FEBs were shipped back to Nevis from CERN. The FEB accelerated lifetime test will soon get underway at Nevis using these FEBs.

Bill Cleland (University of Pittsburgh)

During the period Jan-Mar 2006, the Pitt group has continued its preparation for commissioning of the L1 branch, which is carried out as part of the commissioning of the front end crates. The EMB was moved into position in December 2005, and the commissioning with the final trigger cables will begin once the connectors have been mounted and the cables connected (currently scheduled for the EMB in May 06). Preparation for the commissioning includes development of the analysis program, which compares the pulse height and timing between signals read through the main readout and the L1 signals which are digitized in a special ADC, which will eventually be replaced by the L1 preprocessor. The program involves waveform reconstruction and determination of optimal filter coefficients for both branches. Developing this software is one of our major activities.

In January 06 a problem was discovered with the grounding of the transition modules. One of the ground shields which is connected to a pin on the DB37 connector on the transition module was connected to crate ground, in violation of the ATLAS grounding rules. This was traced to a layout error in the transition module. A simple modification to the boards was developed, which solved the problem, and all of the transition modules have since been modified.

As has been reported previously, we have experienced failures of transformers on the receiver board, at the level of 1-2 per thousand channels. We have now placed equipment and developed the expertise at CERN to replace these transformers, and all of the bad transformers have been replaced.

Strain reliefs for the trigger cables which enter and exit the receiver have been designed (with help from BNL) and fabricated in our machine shop at Pitt. We have provided supports both for the cables for which we are responsible (input to the receivers) and for the cables for which the L1 group are responsible (output to receivers and inputs to preprocessors). The final shipment of supports to CERN was made in January 2006.

In March 06 it was discovered that there are some discrepancies in the cabling of the EMEC and the specifications for the baseplanes and L1 summing in the front end crate. Two such instances have been found, and we are looking into possible solutions. One solution would involve the remaking of remapping boards for the receiver, and another would involve the remaking of certain layer sum boards. This issue will be discussed during the June liquid argon week.

3.3.2.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Long Term Burn-in of FEBs at BNL Complete | 1-Jun-06 | -- | 1-Jun-06 | On Schedule (See #1) |

Note #1  test moved to Nevis

3.3.3 Beam Test

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of the first production FEB in a System Crate | 30-May-06 | -- | 30-May-06 | On Schedule |
| Protvino Engineering Run (Arizona) | 25-Aug-06 | -- | 25-Aug-06 | On Schedule |

3.3.3.1 FCal Hadronic Tail Measurement

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FCal Electrical Test Bench Completed (Arizona) | 20-Apr-06 | 20-Apr-06 | 20-Aug-06 | Delayed (See #1) |

Note #1  We were forced to temporarily abandon this project when a different time-critical project demanded the manpower.

John Rutherford (University of Arizona)

In the last progress report it was noted that the ATLAS LArG calibration pulser board still had some problems. We uncovered one manifestation of the problem while analyzing the data we took in summer 2005 in the EMF facility at Point 1 at CERN. This test used a Front End Crate (FEC) of FCal warm electronics, an FCal baseplane, and the calibration pulser. We took nearly a gigabyte of calibration data and saw peculiar non-linearities. The Orsay group has now fixed the remaining pulser problem but a test is required to confirm that all is indeed working well. Rutherfoord will spend a few days at Orsay during the summer of 2006 to test the new calibration pulser in a FEC using the FCal baseplane. Further analysis of the EMF data continued in this quarter with an aim to extracting the input impedance of the preamps.

The FCal was slated to use 5 mA/25 ƒC preamps, one of the three types of warm preamps used in the ATLAS liquid argon calorimeters. It was discovered that not enough of these preamps were available and so we were asked if we could make do with a different type. While possible, it was concluded that it was far from optimal to change to one of the other two remaining preamp varieties. More recently a number of these preamps have been found. It appears that there are enough to populate the Front End Boards (FEBs) but not enough for the required spares. Hopefully more of these preamps will turn up.

The FCal Electronics Test Bench continues to make slow progress. The 64 tube electrodes are now completed. The digital section of the warm electronics was completed last quarter and good progress has now been made on the analog part. We were forced to stop this work however when we discovered we were running behind on another more time-critical project. Hopefully we can pick up again during the summer and complete the warm electronics.

We made a special effort to accelerate the analysis of the FCal Calibration Test Beam data taken in summer 2003 with the final FCalA modules. We invited our ITEP colleague, Andrei Artamonov, to visit us in Tucson for about one month and we hosted a short workshop with our Carleton colleagues Manuella Vincter, Mohsen Khakzad, Malachi Schram, and J.P.Archambeaux. With some ATHENA help from Walter Lampl we were able to get the latest release working at Arizona. We were then able to generate CBNTs for rapid turn-around of testing new code. More errors were found in the software, mostly mapping. A subtle one had all channels shifted by one in the phi index. This compromised previous studies of energy contained within a cluster radius.

While we have analyzed the energy linearity and resolution for electrons and pions, we have not yet used good tracking allowed by the Beam Position Chambers (BPCs) nor have we purified the samples using the extensive beam detector information. These beam detectors include not only the BPCs but also the pulse height and timing information from our trigger scintillators and hole veto, a ring-imaging gas Cerenkov counter, an iron/scintillator sandwich calorimeter behind the liquid argon cryostat, and a muon counter behind an iron and concrete beam dump. This means that the electron sample is contaminated by pions and the pion sample is contaminated by electrons. Some of the contamination is from spray off upstream beam elements. We insist on avoiding any biases in the calorimeter data so none of the purity cuts use calorimeter information. While the contamination is small, it can introduce small shifts in the energy peaks, broaden the resolution, and, in particular, artificially enhance the tails on the resolution function. Any real non-Gaussian tail contributes to the detector induced background to the missing ET signal. Therefore this is one of the primary measurements we want to extract from our data. We don’t want our measurement diluted with additional effects just because we were sloppy in the analysis.

The beam cleaning analysis is going well and should be completed soon. Then we can implement the tracking software and repeat all the calorimeter analyses with optimally cleaned samples.

In the last report we described the HV short found on one of the FCal3A summing boards. And we described our plans for remediation. During the transport of the EndCap A cryostat from building 180 to point 1, the jostling didn’t shake loose the debris which we guess is the cause of the short. So in February we attempted to burn the short with a special high-current pulser we designed and built specifically for this purpose. We had already conducted extensive (sometimes destructive) testing on a spare summing board and so understood the limits we could approach. The burning attempt failed. We still have the HV short. For this attempt the cryostat was filled with warm argon gas left from the cold tests in Building 180. It was decided to change the gas to warm, dry nitrogen and try again. This will be done after the cryostat is in the cavern with the extended TileCal built around it, but before the FEC is mounted on the FCal feedthrough. In the meantime we will run further tests on our spare summing board in argon and nitrogen atmospheres.

At the same time as the burning attempt we also repeated the full battery of tests on both FCalC (in the cavern) and FCalA (on the surface at Point 1). To our surprise, none of the shorts we found on electrodes during the cold tests are now visible. We don’t understand why they went away. In the past, all shorts developing in liquid argon remain after emptying the cryostat. We don’t know the likelihood these shorts will return during the next fill. Unfortunately during this latest round of testing we found a new type of failure. One of the four HV inputs to one of the FCal1C summing boards is now disconnected. From the Time Domain Reflectometer we can see that the disconnect is right where the HV pigtail meets the connector on the summing board. It could either be that a pin on the HV connector has come unsoldered or the constantan wire has come uncrimped from its socket. This failure means that one quarter of the electrodes served by this summing board have no HV. Because none of the affected tube groups are contiguous (that is, the failures are uniformly distributed within their phi slice) it will be straightforward to develop a software correction for this failure.

Also reported last quarter were preparations for our Protvino tests in their high intensity 60 GeV proton beam along with the HEC and EMEC communities. While the motivation for the HEC and EMEC is to test small samples of their modules for the higher luminosities we will see at an upgraded LHC, the FCal has an added goal: to test the FCal materials in the radiation background expected in 10 years of LHC running at nominal luminosity. The extensive Dubna materials testing program conducted in the late 1990s could reach only an equivalent of one year of nominal luminosity running.

Our small section of an FCal1 module (dubbed the FCalchik) is now complete except for inserting the electrode rods. We have tested the insertion of several rods and see no problems for those sixteen electrodes which will have the usual 250 micron gaps. More challenging will be the other sixteen electrodes which will have 100 micron gaps. Here we were unable to purchase 100 micron PEEK fiber so we will attempt to cut fibers from 100 micron PEEK sheet. The FCalchik has cooling loops embedded in the copper matrix outside of the area containing the electrodes.

We are now preparing for the technical run planned for CERN this summer. A big challenge stems from the dynamic range of intensities we plan to use at Protvino. We will need a scheme to measure the number of protons in each RF bucket so we can determine the instantaneous ionization and energy deposit in the calorimeters. It appears this challenge will fall on the Arizona group so we plan to start work on this as soon as classes are over.

## 3.4 M&O Tile

3.4 Subsystem Manager's Summary 	Larry Price (Argonne National Laboratory)

Sector commissioning continued after the holidays in January, but it became clear that the drawer electronics damage seen in December was not an isolated incident.  Damage was seen in four additional drawers, causing commissioning to be halted and an intensive evaluation of the low voltage power supplies (LVPS) begun.  An “experts week” was convened in February which uncovered an interaction between the LVPS and the Detector Control System (DCS) which permitted some of the voltages in the supplies to go to their maximum possible value, following a loss of control of the LVPS voltage-regulating feedback circuitry.  As a result, an ad hoc addition was made to the “bricks” of the LVPS to provide over-voltage protection and a revision to the mother board for the ELMB, the standard ATLAS controller was made and new parts ordered.

Commissioning of the cabling and other services continued in parallel with the intensive and unexpected LVPS work, as did installation of the MBTS scintillation counters and associated absorber.  Damaged 3-in-1 cards (at Chicago) and digitizer boards (at Stockholm) had to be repaired.  Additional work was done successfully on the LVPS to reduce the output noise level which was widening the readout pedestals beyond comfortable levels.

Considerable progress was made on software systems for commissioning, especially various forms of database and display software.

3.4.1 TileCal - Specific Costs

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Module-by-Module Commissioning of Barrel | 1-Dec-05 | -- | 1-Dec-05 | Completed |
| Complete Module-by-Module Commissioning of Barrel | 30-Apr-06 | 30-Apr-06 | 30-Aug-06 | Delayed (See #1) |
| Complete Initial Calibration of Barrel | 31-May-06 | 31-May-06 | 31-Oct-06 | Delayed (See #2) |
| Begin Module-by-Module Commissioning of Extended Barrels | 15-Jun-06 | 15-Jun-06 | 15-Jul-06 | Delayed (See #3) |
| Begin Barrel Data Taking with Cosmic Rays and Full DAQ System | 1-Jul-06 | 1-Jul-06 | 1-Aug-06 | Delayed (See #4) |
| Version 1.0 of Diagnostic/Monitoring Software | 31-Jul-06 | -- | 31-Jul-06 | On Schedule |

Note #1-4  The need to retrofit low voltage power supplies with safety and anti-noise protections have delayed module commissioning.

3.4.1.1 Pre-Operations 	Steve Errede (University of Illinois, Urbana-Champaign)

A. Contribution to the services manufacture and installation

David Forshier, a UIUC technician, stayed at CERN for 3 months and worked in the manufacturing and QC mainly of trigger cables. He also contributed considerably in the QA of services in the ATLAS detector in the cavern. This is was an important step to the milestone of having the whole Barrel TileCal detector connection to the USA15 counting room checked out and being able to start the complete testing from there.

B. Commissioning Activities

Irene Vichou, located at CERN, has been since the end of last year the run coordinator for the TileCal commissioning. She defines and overlooks the schedule of the commissioning operations for the TileCal detector as a standalone entity. In this role, she takes care of the interactions with the Technical Coordination and she tunes on a daily basis the activities of 5 teams that are responsible for services, FE electronics certification, final power and services connections, online and offline data quality control. The target is to certify TileCal for operation. At this moment, ~1/8 of the Barrel part of the detector has gone through the commissioning protocol and the procedures for doing this have been debugged.

In parallel she has been coordinating with Francesco Spano the phase II commissioning activities, i.e. the integration of TileCal with external systems (DAQ, DCS, Trigger and the Larg Calorimeter). Up to now there have been well-defined and limited scale exercises of integration such as to test functionalities or detect problems on the TileCal side.

Kaushik De (University of Texas at Arlington)

Hyeon Jin Kim is permanently stationed at CERN. She is on the TileCal commissioning shift team. She participated in weekly activities to test and commission the barrel. Kaushik De also continues to spend a majority of his time at CERN, working on ITC pre-operations issues.

Joey Huston (Michigan State University)

Work proceeded on ATLAS M&O at both Michigan State University and at CERN during the period January 2006 through March 2006. Technical staff Ron Richards and Mike Nila made one trip to CERN during this time for a period of about 3 weeks. Most of their effort was devoted to installation work on EBC, and in particular to the installation of the cryostat and of the MBTS scintillators and of the boronated polyethylene moderators. The installation plan worked very well once access was gained to the face of EBC. All of the cryostat scintillators for EBC were installed and connected except for those obstructed by LAr hydraulic jacks. Three of the 8 MBTS counters were installed. The remaining cryostat and MBTS counters on the EBC side will be installed in May/June during the next trip. Physicist Joey Huston also participated in some of this work. Some time was also spent in general preparations for transporting EBA to the pit.

James Pilcher (University of Chicago)

(a) Repair and Maintenance of FE Electronics

We maintain an electronics drawer at Chicago for testing and diagnosing the various PCBs in the drawer. A set of 45 repaired 3in1 cards was tested with the revised system and shipped to CERN.

New low voltage power supplies, prepared by the Prague group, are being installed in the calorimeter modules as part of the commissioning process. During the commissioning campaign in January, additional front-end electronics in 4 drawers was damaged by over-voltage from the supplies. This will require substantial repair work in the months ahead.  Continued evidence that power supplies were damaging drawer electronics caused a considerable reorientation of priorities in the whole TileCal collaboration.  Drawer commissioning paused for February and March and many people spent at least some of their time working to understand the behavior of power supplies and drawers.  Americans were included in this mobilization, including Kelby Anderson and Giulio Usai from Chicago and Larry Price and Leon Reed from Argonne.

(b) Commissioning and Integration work

A team of 5 Chicago people continue in full time residence at CERN working on commissioning and integration. This team consists of one postdoc, one graduate student, two BSc technical assistants, and one full time electronics technician. They were supplemented by periodic visits of faculty members and research personnel based in Chicago.  David Miller, a Chicago BSc technical assistant is in charge of a team responsible for making the connections to the calorimeter modules.

Giulio Usai made a number of investigations into reduction of the ripple observed at the output of the low voltage power supplies which increases the pedestal width of measured signals at a level that will compromise the contribution of TileCal to the muon trigger.  Giulio tried several methods of reducing the ripple and settled on a system of ferrite chokes on the output cables of the supply.  Solutions with ferrites at the inputs would have taken less space but proved to introduce new instabilities in the supplies.

(c) Calibration and Monitoring

Calibration and monitoring is an integral part of the commissioning process. Martina Hurwitz, a Chicago graduate student, is co-leader of a team responsible for processing and reviewing the calibration data taken after a calorimeter module is connected to services in USA15. She has set up monitoring histograms and reviewed all the calibration data collected to date.

3.4.2.1 Pre-Operations 	Kaushik De (University of Texas at Arlington)

Since the completion of the installation of the ITC scintillators, we have started working on QC testing and calibration. We obtained permission to use a Cs-137 radioactive source in Building 175 and tested some gap scintillators with MobiDick (with the help of our Clermont colleagues). Sufficient signal (factor of 2 over pedestal) was observed. We saw good uniformity in signal over various parts of the counter. We have asked for permission to use the Cs source in the pit. The plan includes testing a sample of all 3 types of scintillators installed on the EBC - gap, cryostat and MBTS. We will also test simultaneously for light leaks.

Robert Stanek (ANL)

Continuing commissioning of barrel is being done as power supplies are produced. Cooling is now enabled on the barrel and this makes things a lot easier for moving around. EBC we are modifying daisy chain cables for the missing HV CANbus capacitors and are awaiting cable tray and schleps installation in order to proceed with commissioning of this detector. Power supplies also need to be produced in abundance for this to happen, by the way.

Larry Price (ANL)

Software development for commissioning has focused on the database storage and access systems for commissioning data including monitoring and performance histograms.  In a collaborative effort with the group from Rio de Janeiro, a powerful web system has been developed for displaying historically the plots indicating the performance of the system during commissioning.  Allowance has been made for extending the system to use during cosmic ray data taking in August.

## 3.5 M&O Muon

3.5 Subsystem Manager's Summary

Frank Taylor (MIT)

Installation and Phase II commissioning of chambers for the Big Wheel (BW)-Side C and the EIL4 stations continued in B180 at CERN. At the end of March 06, the mechanical integration of ten BW sectors, corresponding to the installation of 50 EM chambers, was completed. In addition, six EIL4 stations (A13, C13, A5, C5, A1, C1) were integrated and tested and two of them (EIL4A13 & C13) were installed in the ATLAS cavern.

Some difficulties have been encountered in the quality of the optical fibers that connect the CSM to the readout DAQ. In some instances the fibers appear to break following very careful and gentle handling during installation on the BW sectors. Discussions with the Israeli vendor are underway

The rate of BW sector installation has reached 2/month, however a steady rate of 3/month will be needed in order to complete Side A by the end of September 06. The inventory of parts needed for the BW sectors is being closely managed. The most problematic items are obtaining timely delivery of BW sector aluminum and EIL4 frames. Another factor which influences our rate of integration is the sharing of material and personnel resources in B180, where the installations of TGC BWs, MDT BWs and EIL4s are simultaneously being conducted. Improvements in both the delivery of sector and frame material and the management of resources in B180 have recently been made.

3.5.1 MDT Pre-operations, Operations & Maintenance

Frank Taylor (MIT)

MDT pre-operations progresses in B180. Teams from each of the US MDT chamber construction sites are in residence at CERN. Tasks are well-defined and expertise gained so that the sector and EIL4 assemblies have become routine.

3.5.1.1 MDT Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete all 16 EIL4 MDT-TGC Assemblies | 14-Mar-06 | 14-Apr-06 | 1-Aug-06 | Delayed (See #1) |
| Start SW Side C Assembly in B191 | 1-May-06 | -- | 1-Oct-06 | Delayed (See #2) |
| Complete all 16 Sectors BW-C | 30-Jun-06 | -- | 30-Jun-06 | On Schedule (See #3) |
| Start of Phase 111 Commissioning in UX15 | 1-Aug-06 | -- | 1-Aug-06 | On Schedule (See #4) |
| Start of Phase 3 Commissioning in UX15 | 1-Aug-06 | -- | 1-Aug-06 | On Schedule (See #5) |
| Complete 12 Sectors BW-A | 30-Sep-06 | -- | 30-Sep-06 | On Schedule (See #6) |
| Pre-operations of MDT Chambers - Phase 2 (Boston) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule (See #7) |
| Pre-operations of MDT Chambers - Phase 2 (MIT) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule (See #8) |
| Complete all 16 Sectors BW-A (Additional 4) | 15-Jan-07 | -- | 15-Jan-07 | On Schedule (See #9) |

Note #1  Delayed. Two EIL4 stations (EIL4A13, EIL4C13) are now installed in UX15, four are ready for installation (EIL4A05, EIL4C05, EIL4C01, EIL4A01) and four more are being prepared for installation (Sectors 1 and 9).

Note #2  The SW is significantly delayed - primarily due to the delays of integrating the ECTs. The plan for the SW construction is to start the tooling construction and commissioning in B191 after ECTA exits for its 80-degree cold test in Jun-06. Following the completion of ECTC in late summer 06 the SW team will start installation of chambers in the first SW.

Note #3  The progress-to-date extrapolates to this completion date. The top watched item is the completion of the delivery of the last small wheel sector.

Note #4  This is the best estimate at the present time. The critical path for the MDT installation and commissioning is set by the installation and commissioning of TGC1 that has to go in first.

Note #5  Scheduled date is the best estimate at this time. However, the TGC1 C-side wheel has to be installed first and many items of tooling need to be designed, constructed and commissioned. Discussions have started with the ATLAS commissioners and within the US community on how to organize this task.

Note #6  A plan has been made and is being closely watched that has the completion of Side A at the end of Sep-06. In order to succeed the timely delivery of aluminum for the sectors is needed as well as additional storage space in B180. The concrete blocks for the storage space are being rigged into place.

Note #7  Steve Ahlen has developed an analysis to find tracks in the random trigger data routinely taken during Phase II commissioning. From these data, chamber misalignments and various operational parameters and anomalies have been observed and studied.

Note #8  A student from MIT has been working on the Phase II commissioning of MDTs in B180 since November. He will be in residence at CERN until the end of June.

Note #9  Plans are in place to finish the BW-A by October 06 - a tenable plan assuming the availability of sector aluminum and Pakistani crew.

3.5.2 CSC Pre-Operations, Operations & Maintenance

Frank Taylor (MIT)

All CSCs have been shipped to CERN along with all on-chamber electronics and test equipment. The Phase I integration station is being setup in B184 and the BNL, UAz crews are getting started. To do is the test the chambers and alignment components following their integration with the support frames.

3.5.2.1 CSC Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Installation & Phase 11 Commissioning on SW in Bldg 191 | 1-Jun-06 | 1-Jun-06 | 1-Oct-06 | Delayed (See #1) |

Note #1  Delayed because the ECTs are delayed in B191. The integration of the CSCs with their spacer frames has started at CERN. This work is expected to be complete by 30-Aug-06, well in time for the SW installation.

3.5.3 Alignment System Pre-Oper.'s, Operations & Maintenance

Frank Taylor (MIT)

The commissioning of alignment parts continues ahead of the critical path. A good team has been formed at CERN to carry out this work.

3.5.4 Muon Endcap Common Costs

Frank Taylor (MIT)

On track and closely monitored. A means to pay for gas consumption has to be worked out.

3.5.4.2 Muon Endcap Common Costs Operations

Frank Taylor (MIT)

The cost of gas for the MDT Phase II commissioning has been estimated. To date the actual costs are lower than expected. The gas consumption is being closely monitored.

3.5.5 Monitoring & Calibration

Frank Taylor (MIT)

Work continues on setting up the monitoring and calibration centers at Michigan and Boston. Bing Zhou, UoM, is playing a key role.

## 3.6 M&O Trigger

3.6 Subsystem Manager's Summary

Andrew Lankford (University of California, Irvine)

Pre-operations activities consisted of hardware and software commissioning support of detector commissioning and of commissioning of other TDAQ subsystems, and operations of the Pre-series system. Operations activities consisted of hardware and software maintenance and routine operations.

3.6.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Operations Supervisor RoI Builder Support | 1-Mar-06 | -- | 1-Mar-06 | Completed (See #1) |

Note #1  Operations of the Supervisor RoI Builder installed in the Pre-Series are now being supported.

Andrew Lankford (University of California, Irvine)

Pre-Ops Hardware Commissioning

The TTC system for the Pre-Series was commissioned. Work progressed on commissioning TDAQ networks.

Pre-Ops Software Commissioning

Dataflow, Event Filter, and HLT software were commissioned on the Pre-series system. Automated test procedures were commissioned.

Pre-ops Detector Support

Support for detector monitoring continued. Readout Subsystems for the Tile and Liquid Argon calorimeters were commissioned.

Pre-Ops TDAQ Support

Readout Links were tested. A new HLT release was tested, and many HLT algorithms were debugged.

Pre-ops Operations

The Pre-series system was operated in support of pre-operations activities.

3.6.1.1 Supervisor RoI Builder

Robert Blair (ANL)

Jim Schlereth implemented a new LVL1 source option in Jan 2006 for the supervisors. This would service a new type of LVL1 source which would originate from a Local Trigger Processor and would consist of a group of LVL1 Event IDs contained in a message handled by the Data Collection message passing system. The type can be selected at configuration time just as the other LVL1 Source type options. This will be required for early operation when LVL1 will not be available or possible.

Changes were made to incorporate new Finite State Machine (FSM) transitions in Feb 2006. Both the Supervisor and RoI Builder applications are run controlled and must respond to FSM transitions to be synchronized with the other applications which they must interact (L2PU, DFM and LVL1 trigger). The major transition affected was the STOP, for which various checks were added to attempt to flush all outstanding events from buffers before a timeout expired, in which case the application would issue a warning, but make the transition gracefully.

3.6.1.3 Programming Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of a multi-node test bed for integ/testing/debug & performance Optimization of HLT code (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| Support of HLT SW installation in point 1(HLT installation image) (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |

Bernard Pope (Michigan State University)

Gianluca Comune has continued to work in HLT/PESA core software development. He has completely rewritten the "Steering" infrastructure in order to improve performance and add new important features like a new improved "data navigation" mechanism, a "Trigger data persistency" approach and infrastructure that allows one to "record" Trigger objects in the Trigger data stream in order to allow trigger-aware physics analyses. This is the major goal for release 12 and the CSC data challenge that will be performed based on this release. (See “Steering the ATLAS High Level Trigger”, G. Comune et al., CERN-ATL-COM-DAQ-2006-016. This paper was presented at the CHEP06 (Mumbai) Online computing session by G. Comune.)

At the same time Comune has invented and developed an approach to Trigger physics performance optimization that is now become the official mechanism in the Trigger collaboration and it is going to be used by all physicists interested in assessing the impact of online selection strategies on their physics analyses.

Unfortunately, Comune left ATLAS at the end of March 2006. It is hoped that the new MSU postdoc Alessandro Di Mattia will continue Comune’s work on the Steering infrastructure.

DCS for TDAQ racks is ready to be moved to SDX1 and installation was planned in February. The note on DAQ/HLT rack DCS was updated. Ermoline reported on the status of rack DCS during the DAQ/HLT-I Coordination meeting in February. The initial installation is foreseen in USA15 where the coolers have already been delivered. An abstract of the "ATLAS DAQ/HLT rack DCS" was submitted to the Pisa Meeting on Advanced Detectors. The updated DCS note was also discussed with David Francis and Helmet Burckhart and their comments have been included in the revised note.

Andrew Lankford (University of California, Irvine)

Pre-Ops Hardware Commissioning

Unel commissioned the first TTC (Timing, Trigger, and Control) crate. Ciobataru used a custom network monitoring tool to map the configuration of the ATLAS networks at Point 1. He also started a study of a commercial monitoring tool (sFlow) that is capable of examining network traffic and monitor traffic patterns. This study involves development of software to analyze sFlow data.

Pre-Ops Software Commissioning

Wheeler studied the efficiency of the new protocols into and out of the Event Filter for very small events (as will be present during detector commissioning). Unel continued analysis of data from Dataflow performance measurements on the Pre-series system, including studies of the output of data through the SFO (Subfarm output) subsystem and of the impact of Monitoring. Wheeler started preparations for a round-the-clock shakedown of the Pre-series system to study completeness of functionality and operational issues. This will be followed by a week of 24x7 operations in April. She also investigated use of a cluster at Manchester for future Large Scale Tests. Bold tested the impact of data corruption on the HLT Steering controller.

Pre-ops Detector Support

Kolos continued to lead the Monitoring group as it defined new monitoring tools required. Unel commissioned Readout Subsystems for the Tile and Liquid Argon Calorimeters.

Pre-Ops TDAQ Support

Unel participated in studies of the Readout Link XOFF mechanism and other Readout Links studies.

Pre-ops Operations

Unel coordinated operation of the Pre-series system. Stancu participated in network operations of the Pre-series system.

Werner Wiedenmann (University of Wisconsin, Madison)

Tests were run on the pre-series using the newly developed Python scripts for automatic testing. dos Anjos provided support for these scripts. With the feedback from tests in the pre-series the logging and debugging facilities of these scripts were improved and automatic ssh-key scanning and agent checking was added.

Tests were performed with HLT release HLT-03-00-03. Problems were debugged with the initialization of some services in multiple threads and the reconfiguration of the Athena Application Mgr when cycling through states.

Together with developers from different detector communities problems in the

HLT algorithms T2Calo, muFast and TrigL2CosmicMuon were debugged. Together with developers from event filter a problem in reading and writing the Level-2 result in bytestream data was found.

3.6.2 Operations

Andrew Lankford (University of California, Irvine)

Ops Hardware Maintenance

Development of test platforms for the RoI Builder progressed. Maintenance was performed on the test platform for networking.

Ops – Software Maintenance

Improvements were made to many software packages, including RoI Builder and LVL2 Supervisor applications, Monitoring software, several HLT infrastructure packages, and database configuration, as well as for release testing.

Ops - Operations

Operations of installed infrastructure at Point 1 and of TDAQ test labs continued. Tests of round-the-clock (24x7) operation using the Pre-series system are planned.

3.6.2.3 Programming Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support event read out library for detector commissioning & Cosmic Run (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| Support for HLT Application Framework for detector commissioning & Cosmic Run (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| Support of Level 2 Framework for detector commissioning & Cosmic Run (PSC) (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |

Bernard Pope (Michigan State University)

DCS for TDAQ racks is ready to be moved to SDX1 and installation was planned in February. The note on DAQ/HLT rack DCS was updated. Ermoline reported on the status of rack DCS during the DAQ/HLT-I Coordination meeting in February. The initial installation is foreseen in USA15 where the coolers have already been delivered. An abstract of the "ATLAS DAQ/HLT rack DCS" was submitted to the Pisa Meeting on Advanced Detectors. The updated DCS note was also discussed with David Francis and Helmet Burckhart and their comments have been included in the revised note.

Andrew Lankford (University of California, Irvine)

Ops Hardware Maintenance

Ciobataru and Stancu worked on maintenance of the test platform used for switch evaluation and testing. This work included incorporating features that will allow study of networks in the presence of packet loss.

Ops – Software Maintenance

Kolos made improvements to some Monitoring software tools in response to feedback from detector communities. He began preparations for the next TDAQ software release, including development of a testing procedure. Kolos implemented a new scheme for using Monitoring services to distribute events for Online Monitoring from ATLAS to the computing cluster at CERN. Bold and Kolos participated in development of a naming convention for all Monitoring histograms, for instance for trigger algorithm developers and for detector groups. Bold documented the naming convention. He updated the Histogramming services to check conformance with the convention and to adapt to changes in the interfaces of the GAUDI framework. He added interactive commands support to the Histogram Dispatcher (histmon) package, as well as performing maintenance and testing. Wheeler and Negri participated in the formation of a new Event Filter Performance and Measurements Group, which began development of an exhaustive set of tests and measurements of Event Filter code in each major TDAQ software release. This group will also be involved in Large Scale Tests later this year. Unel updated the database generation package, in preparation for the next TDAQ software release and to create the ROS commissioning databases. He began participation in Global Release Coordination.

Ops - Operations

Unel coordinated system administration activities at Point 1 and in TDAQ test labs. Stancu worked with the Sysadmin group in establishing the scheme for allocating IP subnets in the TDAQ network, including a scheme for assigning multiple IP addresses to the same network interface. Many personnel contributed to preparation for a test on the Pre-series system of round-the-clock operations.

Werner Wiedenmann (University of Wisconsin, Madison)

dos Anjos provided for the Level-2 processing unit in the TDAQ repository fixes for compilation with gcc-3.4.4 and for changes in the ROS schema. For the event format package the automatic unit test suite was improved and several bug fixes were applied to the event format library.

For the forthcoming TDAQ release 1.6.0 dos Anjos restructured the Level-2 packages to reduce dependencies. Files which are necessary for exporting the Level-2 API have been separated from files which are only necessary for package implementation. Unified interfaces to the HLT algorithm framework were defined for Level-2 and Event Filter and the abstract interfaces were placed in the TDAQ common repository. The Level-2 packages were modified to adhere to these new HLT interface definitions. With the introduction of templated applications also the packages had to be updated to comply to changes in the application control interface.

For development and testing with the offline release series 11 the l2pu_test application and the athenaMT script were updated. For the HLT framework the PSC were updated to support recent changes in the offline framework and to allow cycling through the TDAQ state machine. The event loop manager was rewritten to inherit from a common component for Level-2 and Event Filter. Both systems can extend this common component with system specific actions. athenaMT supports now most of the command line switches which are also used with the standard offline application "Athena". To simplify code maintenance the implementation of the PSC which contained also an interface to the online monitoring was refactored. The documentation for athenaMT was updated to reflect all the changes. The "new athenaMT" was presented in different meetings to developers.

To work with offline release 11.5.0 the setup and build of HLT with project builds was investigated. Updates to the PSC and python configuration scripts were necessary to comply with changes in offline.

3.10 M&O Technical Coordination

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commission Round Special Scaffolding used for Calorimeter in situ installation | 30-Jun-05 | -- | 30-Jul-06 | Delayed (See #1) |
| Commission Round Scaffolding on the Tile Front Face | 30-Sep-05 | -- | 30-Jul-06 | Delayed (See #2) |
| 30% Barrel Muon Installed | 30-Mar-06 | -- | 30-Mar-06 | Completed |
| Finish Round Scaffolding Production | 30-Mar-06 | -- | 30-Mar-06 | Delayed (See #3) |
| Complete EC-C Mechanical Assembly | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |
| Start Big Wheel Assembly Side C | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |
| Barrel Toroid Field Test | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Complete EC-A Mechanical Assembly | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Solenoid Field test | 31-Jul-06 | -- | 31-Jul-06 | On Schedule |
| Install Barrel Part of Inner Detector | 30-Aug-06 | -- | 30-Aug-06 | On Schedule |

Note #1-2  Prototype was tested. Currently in production. Will need the EC to commission them.

Note #3  Schedule changed

Subsystem Manager's Summary 	David Lissauer (Brookhaven National Laboratory)

ATLAS Upgrade: Meetings were held with the ATLAS management (Peter Jenni, Steinar Stapnes, and Marzio Nessi) to discuss the organization of the ATLAS upgrade. They offered me the responsibility for organizing the execution of the ATLAS upgrade.  In the next EB I will be appointed as the ATLAS Upgrade Project Office Leader.  This is a major responsibility as the ATLAS upgrade is expected to include a complete replacement of the ATLAS Inner Detector and major upgrade of the Liquid Argon calorimeter. The upgrade will need to be organized much more tightly than the current ATLAS experiment, as it will involve an ongoing experiment.  A large fraction of the responsibility will be with outside collaborators and CERN will have a major role in support of the Project Office and the upgrade in general.  One of the first tasks will be to assemble the team, which we plan to recruit from the major collaborating labs and CERN.  During April 2006 I went to the Rutherford Lab, NEKHEF among other places to see the level of support that we can expect.  The US has an opportunity here to play a major role in the ATLAS upgrade – this effort is well advanced in the US.

ATLAS as built:  Discussions on how to collect the detail information and update the models for ATLAS as built took place.  Sue Duffin (BNL) has started to summarize the information starting from the Barrel Calorimeter position and the Barrel Toroid.

Barrel Calorimeter Services & Commissioning:  Installation of services is continuing. The Calorimeter (both Tile and LAr) cables are completed.  Liquid Argon is being delivered to the underground storage tanks in preparation for the calorimeter cool down and filling. The Inner detector services are being installed slowly the delay is caused mostly by the availability of cables and the access difficulty.

Barrel Muon Chamber Installations:  Barrel Muon chambers installation is slowly gaining speed. We expect to finish the installation of sector 12 and 14 by early March 2006 and the installation of sector 2 and 8 have started.

BCAM Installation:  A monitoring system to determine the position of the EC calorimeter relative to the Barrel is being installed. It consists of a number of BCAM cameras produced at Brandeis University. The installation of the cameras on the barrel took place and discussions on the installation of the reflectors on the EC took place.

EC-A Calorimeter:  The mechanical assembly of EC-A has started. The saddle with the first 18 Tile modules has been lowered to the pit and placed on the truck for assembly. The LAr is expected to come down in a few weeks and the mechanical assembly was expected to be finished by June 2006.

EC-C Calorimeter Placement and Assembly:  The EC -Calorimeter has been moved to a position inside of the Barrel Toroid. This will allow starting the preparation for a Big Wheel installation on side C.  In the mean time preparation for EC-A assembly is on going and EC-A assembly is expected to be ready before the end of May. In parallel installation of services on EC-C has started.

EC Calorimeter Docking:  Meetings took place to finalize the procedure for docking the end cap calorimeter. This involves, in addition, the procedure to assume good contact and position reproducibility between openings, and also the installation of the shims on the EC Gap calorimeter in order to minimize the gap between the barrel and EC.  BNL and CERN have now calculated using the latest survey results for the individual gap variations, and the shims are being prepared for the first docking. At which time we will leave a slightly larger gap than we hope to finally have. After the first docking we will re-shim to minimize the gap.  The level of the gap we can afford to leave is determined by the expected effect of the magnetic field during the field measurements.

EC Muon Integration:  Discussions took place to determine the small wheel and JD integration and assembly status.  The project is behind schedule and we will have a major review of the JD small wheel assembly and installation in the near future.

JD Assembly:  Discussions were held between A. Gordeev and C. Pai from BNL on how to update the design of the JD Wheel. The procedure for turning the JD disk is nearly complete. The production of the tooling has started and next week the CERN safety group will review the procedures. We expect that one will be able to turn the JD disk in a few weeks.

LHC Schedule:  Had some interesting discussions with the machine people in charge of the machine installation. They have on the order of 450 magnets in the tunnel with another 1300 to go. The rate now is 20/week and they expect to bring it up to 24 per week. This means that the magnet installation will be completed in May ’07. They have on order a partial connection of 200 magnets but not a single magnet that has been tested completely and accepted. The effort here is going to be increased significantly and will allow under very optimistic assumptions to have first beam in early ’08.  At that time the machine will probably not be completed, for example, some collimators will be missing – which mean that only low luminosity running will be possible.  (That is all we can probably absorb at the start).  After a short run the plan is to have a shut down for some months to complete the machine and restart with high luminosity. The new schedule with new dates will come out in June/July ‘07.

Magnetic Field Workshop:  In preparation for the magnetic field mapping that will take place in June, we discussed some of the implications of having the JD in place for the measurements. Detail calculations of the field with and without the JD disc have been performed and the result shows minor differences due to the JD. It was agreed that we would use only one JD during the field measurements essentially to confirm the results of the calculations.

Pixel Installation: I convened a task force to study which side the pixel insertion should take place. The task force studies have been concluded in a meeting with the decision that the pixels will be installed from side C. The next step is to understand access conflicts with the big wheels assembly that will take place in the coming weeks.

Technical Management Board:  The TMB meeting reviewed the status of the ATLAS installation and production.  In general there is good progress and actions are being taken to correct slippages in the assembly of certain items.  Corrective actions that were taken during the month of April 2007 include increase resources for end cap MDT and TGC sectors assembly, more effort on Pixel assembly and corrective actions.

4.1 Inner Detector Upgrade R&D

Subsystem Manager's Summary	Abraham Seiden (UCSC)

This quarter work has continued on new detector types, electronics, development of stave structures and optoelectronics. In additional a number of Upgrade proposals have been submitted to the ATLAS Upgrade steering group to be incorporated more clearly into ATLAS planning.  Also, an Upgrade project within the Technical Coordination at CERN has been set up to lead the infrastructure work.

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| System Design for GOL finished (SMU) | 1-May-06 | -- | 1-May-06 | On Schedule |
| Pin Candidates Identified (Oklahoma) | 6-May-06 | -- | 6-May-06 | On Schedule |
| Submission of SiGe test chip (UCSC) | 10-May-06 | -- | 10-May-06 | On Schedule |
| Finish fab of 3-D detectors (Hawaii) | 30-May-06 | -- | 30-May-06 | On Schedule |
| Preliminary Wire Link Tested (Ohio State) | 31-May-06 | -- | 31-May-06 | On Schedule |
| Prelinary Fiber Link Tested (Ohio State) | 31-May-06 | -- | 31-May-06 | On Schedule |
| Working Stave (LBL) | 1-Jun-06 | -- | 1-Jun-06 | On Schedule |
| First Pin Irradiation (Oklahoma) | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Measurement of 3-D sensors (New Mexico) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |

4.1.1 Detectors

Hartmut Sadrozinski (UCSC)

4.1.1 Detectors

4.1.1.1 Innermost Pixel Layer

Fabrication of 3D pixel sensors for bump bonding to ATLAS readout chips is ongoing with 10 wafers in production. Large leakage currents were suppressed with forming gas anneal. Imperfect contacts were observed due to thin insulating films on the metals, and are being investigated.

Charge collection efficiency tests were done with a 1060 nm IR laser on ATLAS-pitch sensors irradiated with reactor neutrons. At 8.6 x 1015 neq/cm2, the collection efficiency with a 3-electrode per pixel sensor was 35%. The charge collection efficiency was found to be approximately inversely proportional to the fluence.

UNM tested 3D sensors (a 200 micron by 100 micron n-to-n pitch with p columns midway between) with an IR laser, concentrating on the magnitude and uniformity of the collected signal and the depletion voltage. The depletion voltage increases from 15 V pre-radiation to 125V after a fluence of 1015/cm2 55 MeV protons. Charge collection efficiency is about 88% for that fluence. The p-electrode shows very uniform signal collection within the pixel cell, while the n-electrode shows poor isolation between neighboring electrodes due to the oxide surface charge.

4.1.1.2 Investigation of Strip Technology

The measurements of electrical parameters (interstrip isolation and capacitance) and breakdown behavior on p-type test strip detector, as built and after moderate gamma irradiation, is yielding the first results. The aim is to evaluate the differences between Float Zone (FZ) and Magnetic Czochralski (MCz) bulk material, and different treatment of the surface (different p-spray doses).

A decision was made to fabricate the next batch of test detectors with combined p-stop and p-spray to improve pre- and post-rad performance simultaneously.

The test set-up for charge collection efficiency measurements using a source is being exercised for both positive and negative signals.

The design and layout of new 3 cm long detectors to be manufactured on 6" wafers by a commercial manufacturer was finished and the design transferred to Micron Semiconductors for initial design checking.

4.1.1.3 Short Strips

Manual probing of n-type stripixel detectors has been completed and three detectors have acceptable behavior. The manual probing is being used to pre-select detectors prior to mounting on detector motherboards. Manual probing of p-type wafers will resume this summer.

Industrial production of 15 motherboards has begun in Milano.

Final layout of the Viking readout board is complete and its production is to follow that of the motherboards in Milano.

Geometric and performance parameters have been supplied to Hamamatsu for production of short strip detectors for stave development.

4.1.1.1 Innermost Pixel Layer

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

3-D Sensor studies:

Testing with pixel electronics: A flip-chip assembly of a 2005 3-D sensor with an FE-I3 pixel chip was received at LBNL (May 2006) after neutron irradiation carried out in Prague in 2005. This sensor had internal shorts and could not be depleted when it was first assembled. The neutron irradiation was done to type-invert the n-bulk and therefore to have a depletion zone around the n+ electrodes even with no bias voltage. This was successful. It is still not possible to apply more than 3V bias due to the internal shorts, but even with such low voltage the sensor is now sensitive to Am241 irradiation and the correct charge peak is seen by the chip.

Alex Grillo (UCSC)

For Sherwood Parker - U of Hawaii

1. Fabrication of ATLAS pixel sensors for bump bonding to readout chips

The initial goal, after yield and lab tests, is to place single-chip detectors in a beam line for an ATLAS / FP420 CERN beam test.

By 1 Jan., 10 wafers, having test devices and ATLAS pixel-pitch sensors with sets of 2, 3, and 4 signal and bias electrodes per pixel, had been processed to the point where back-side doping, oxide bonding to a support wafer, and field oxide growth, among other steps, had been completed, and one set of electrode holes had been etched, doped, and filled with polycrystalline silicon. (Note: Each wafer will have quite a few more sensors than are planned to be bump-bonded for the beam test.)

During the following 3 months the second set of holes was etched, doped, and filled. A special layer of test aluminum was deposited and patterned on 3 of the wafers. It was designed to contact all electrodes, but in large groups, so testing could be done with a reasonable number of probe points while keeping enough subdivision to provide diagnostic information. The first thing seen was large leakage currents along the edges - something not seen before. However, when the next normal step in the fabrication process was run, a forming gas anneal, the currents went back to normal. This observation led to experimenting with some of the parameters of that anneal.

Further tests showed two of the wafers had imperfect contacts, as if there was an insulating film between the top of the electrodes and the metal layer, similar to what had been seen with devices from an earlier run. The other wafer did not have such large regions of poor contact, but may have had them in limited regions. The test metal was removed and visual evidence of a dielectric film was seen. Etching steps were tried on this layer and the test metal was replaced. Improvement was seen in some, but not all contacts. (Analysis tests should next be run to determine whether this is an oxide or nitride layer.)

2. Irradiation results.

Irradiation with reactor neutrons and tests of ATLAS-pitch sensors were performed, and tests started on sensors irradiated to a level of bulk radiation damage equivalent to 3.7, 5.98, and 8.6 x 1015 1 MeV equivalent neutrons per sq. cm. - so up to approximately 1.6 x 1016 protons per sq. cm - an exposure equivalent to about 28 years at 4 cm. and a luminosity of 1034. Charge collection efficiency tests were done with a 1.060 micron infra-red laser having a spot size of 500 microns at -10 C. At 8.6 x 1015, the collection efficiency with a 3-electrode per pixel sensor was 35%. The charge collection efficiency for this data set was approximately proportional to 1 / fluence.

While neutrons provide a good test of bulk damage radiation hardness, we should also do similar ones using charged particles and with an applied bias voltage during the irradiation to test for effects of oxide damage.

For Sally Seidel - U of New Mexico

UNM activities during the period January 1, 2006 through March 31, 2006 concentrated on laser testing of the 3D sensor. These tests included measurements of signal collection magnitude and uniformity and depletion voltage. Preliminary results were presented by Martin Hoeferkamp at the International Workshop on 3D and p-type Detectors in Trento, Italy, on February 13, 2006.

Signal collection and depletion voltage were measured by completely flooding the 3d sensor chip with a uniform 1064 nm laser spot and scanning the bias voltage from zero to beyond the full depletion point. The signal pulse heights from the n-electrode and the p-electrode arrays were read out on an oscilloscope as the laser was pulsed with a fast (0.5 ns risetime) short duration (100 ns) pulser. Three 3d sensors of the design type known as single_off14_100 were tested. The geometry for these utilizes a 200 micron by 100 micron n-to-n pitch with p columns midway between. Of the three, one was a non-irradiated sensor, one a sensor irradiated to a fluence equivalent to 2 x 1014/cm2 55 MeV protons, and one a sensor irradiated to 1015/cm2 55 MeV proton-equivalent. The most highly irradiated sensor was measured at -20C, the others at 0C.

The signal collection results, normalized to the non-irradiated values, are 95% for the 2 x 1014/cm2 sensor and 88% for the 1015/cm2 sensor. Depletion voltages are about 15V in the non-irradiated case, about 58V for the 2 x 1014/cm2 sensor, and about 125V for the 1015/cm2 sensor. During the position scans the 1064 nm laser was focused to a spot of diameter approximately 10 microns. This laser spot was scanned across one electrode cell while the output was measured with a Picoprobe, to characterize the uniformity of signal collection. As of March 31 this test had only been completed on the non-irradiated sensor. Results on the p-electrode show very uniform signal collection within the pixel cell in both the x- and y-position scans. The signal drops to 50%, as expected, as the laser reaches a point halfway to the next electrode. The n-electrode scan shows poor isolation between neighboring electrodes due to the oxide surface charge. This was confirmed by leakage current measurements.

4.1.1.2 Investigation of Strip Technology

Hartmut Sadrozinski (UCSC)

The measurements of electrical parameters (interstrip isolation and capacitance) and breakdown behavior on p-type test detector, as built and after moderate gamma irradiation, is yielding the first results. The aim is to evaluate the differences between Float Zone (FZ) and Magnetic Czochralski (MCz) bulk material, and different treatment of the surface (different p-spray doses). A decision was made to fabricate the next batch of test detectors with combined p-stop and p-spray to improve pre- and post-rad performance simultaneously.

The test set-up for charge collection efficiency measurements using a source is being exercised for both positive and negative signals.

The design and layout of new 3 cm long detectors to be manufactured on 6" wafers by a commercial manufacturer was finished and the design transferred to Micron Semiconductors for initial checking.

4.1.1.3 Short Strips

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Purchase Order Released (SB) | 30-May-06 | 30-May-06 | 8-Jun-06 | Delayed (See #1) |

Note #1  P.O. should be going out within a week. P.O. was delayed several weeks

at Stony Brook while awaiting approvals.

David Lynn (Brookhaven National Laboratory)

Stripixel Detectors

Manual probing of n-type stripixel detectors has been completed and three detectors have acceptable behavior. The manual probing is being used to pre-select detectors prior to mounting on detector motherboards. Manual probing of p-type wafers will resume this summer.

Industrial production of 15 motherboards has begun in Milano.

Final layout of the Viking readout board is complete and its production is to follow that of the motherboards in Milano.

Short Strips for Stave development

We have chosen Hamamatsu to produce the detectors. Geometric and performance parameters have been supplied to Hamamatsu. Paperwork for order has been submitted through Stony Brook University but is currently awaiting final approval.

4.1.2 Front-End Electronics

Alex Grillo (UCSC)

Irradiations on the 130 nm pixel test chip were carried out at the LBNL 88" cyclotron with both 55MeV protons and 32MeV light ion cocktail for SEU studies. Total dose achieved with protons was approximately 70MRad. No changes were observed at the few % level after such dose. Results of the SEU tests are still being analyzed.

SiGe test structures from three IBM technologies were irradiated with neutrons at Ljubljana but delays in returning the parts to Santa Cruz have resulted in no post-rad testing as yet. Test structures for the gamma irradiation have been electrically tested and they will be irradiated at the cobalt source at BNL in early May. The design of the demonstration IC on the IHP technology is progressing well and is on track for submission prior to the deadline of 18-Apr.

4.1.2.1 Deep Sub Micron for Pixels

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Deep Submicron electronics for pixel upgrade

0.13µm pixel test chip: Irradiations were carried out at the LBNL 88" cyclotron with both 55MeV protons and 32MeV light ion cocktail for SEU studies. Total dose achieved with protons was approximately 70MRad. No changes were observed at the few % level after such dose. The chip contains digital register chains using different flip-flop designs that were tested for SEU tolerance. Tests were carried out with ion beams up to LET of 20MeV/mg. Results are still being analyzed.

4.1.2.2 SiGe for Strips

Alex Grillo (UCSC)

SiGe test structures from three IBM technologies were irradiated with neutrons at Ljubljana. We expected to receive back at Santa Cruz in March or early April for post-radiation electrical testing, however, there is a problem finding a shipping company that will handle the irradiated parts. Even though we have done this many times before, now that Slovenia has joined the EU there are more bureaucratic difficulties in handling these types of shipments and our collaborators in Ljubljana have not been able to find a company to make the shipment. This is still a problem. In the mean time, these parts are being stored at cold temperature to minimize any annealing of the damage.

Test structures for the gamma irradiation have been electrically tested and they will be irradiated at the cobalt source at BNL in early May. The test structures for proton irradiations are being electrically tested now. That irradiation is expected to take place at CERN in June when the PS turns on.

The design of the demonstration IC on the IHP technology is progressing well but is not yet complete. Deadline for submission is 18-Apr and we are confident we will meet that. All the parts of the design are actually complete. Final checks are underway.

4.1.3 Optical Readout

4.1.3.1 Diode Receivers

Flera Rizatdinova (Oklahoma State)

The TrueLight PIN Diode array is a natural candidate for the first irradiation session. The equipment (fibers, PCBs) necessary for the prototype test stand has been purchased in preparation for the radiation test that will be later this summer (August).

Patrick Skubic (University of Oklahoma)

To accomplish our goal to identify PIN arrays that can survive the SLHC radiation environment we are performing a literature search to identify possible vendors. We have received a sample of two single-channel InGaAs/InP devices from Fermionics for further evaluation. Such devices would be used by ATLAS only if silicon devices were found to be inadequate. In preparation for the radiation test later this summer, we have purchased needed components including fiber cables and connectors. We have received a test stand system from Ohio State U. and are currently setting it up. This will allow us to make baseline BER measurements for single-channel devices for comparison with measurement made by other institutions.

4.1.3.2 Fiber Drivers

Jingbo Ye (Southern Methodist University)

The goal of this project is to evaluate the CERN GOL chip both in lab and in radiation environments. We have designed and fabricated the test boards which include a FPGA based overall control board that generates test patterns, performs error detection, and monitors beam conditions; the GOL carrier board; an adaptor board for long range (a few meters) signal transmission for the radiation test; some driver/receiver boards; and a dedicated power supply board for multi-channel (up to 64) current measurement during irradiation. All the boards are now under test in lab. Preliminary results show that they all function. More detailed tests await the software development in the FPGA. After this the in lab test on the GOL will be carried out. We are on schedule as in the proposal we sent in.

K.K. Gan (Ohio State University)

One of the goals of the R&D program is to identify the PIN and VCSEL arrays that can survive in the intense SLHC radiation environment. We have identified four vendors who fabricate arrays with suitable specifications and have purchased samples from each. To establish baselines for future array evaluation, we studied the optical and electrical performance of several pre-packaged single channel devices from the array vendors. The next step is to study the arrays.

4.1.3.4 Multiplexers and Interconnect Circuits

K.K. Gan (Ohio State University)

Another important goal of the R&D program is to measure the bandwidth of the infrastructure of the current pixel optical link. The two critical components in the infrastructure are micro twisted pair cables and fiber ribbons. The former transmit the LVDS signals between the optical components and the pixel modules. The latter transmit optical signals between the optical components and the counting room. The ribbons consist of several meters of radiation-hard, low bandwidth SIMM fibers spliced to about 100 m of radiation tolerant, medium bandwidth GRIN fibers. At the SLHC, we expect to transmit data at ~ 1 Gb/s, significantly more than the current 40 Mb/s.

We have constructed a prototype test system to measure the bandwidths of the critical infrastructure components and have measured the rise and fall times versus cable length of several types of fiber and micro twisted pair. Also we have studied “eye” diagrams of pseudo random bit streams for each cable type and length. Our preliminary conclusion is that the micro twisted pairs can reliably transmit signals at up to 640 Mb/s and the fibers at rates greater than 1 Gb/s. Therefore the existing infrastructure satisfies the needs of the SLHC. We are currently constructing an improved test system for a more through study including bit error rate testing and jitter measurements.

4.1.4 Modules

4.1.4.1 Stave Structures

Carl Haber (Lawrence Berkeley Laboratory)

This effort is collaboration between BNL and LBNL. The BNL group has added physicist manpower to the effort in this period.

The effort here focused on the following fronts:

1) Test of the first 6 module stave based upon CDF geometry but with ATLAS electronics. Tests continued in this period with excellent noise and uniformity observed on the stave. Somewhat better even than when modules are pre-tested individually. We attribute this improvement to the better engineered ground and power distribution found on the stave (relative to the module test configuration)

2) Preparations for testing of serial power on the 6 module stave. A new bus cable to support serial powering was designed and submitted for fabrication. This will be tested in collaboration with the Rutherford colleagues in early summer 2006

3) Design of an ATLAS specific 1 meter stave. In collaboration with W. Miller this effort has proceeded well (see 4.1.4.3)

4) Development of DAQ for multimodule stave tests. The National Instruments modules were obtained by BNL and LBNL. A full LabView control package was written and is being debugged.

5) Design of a 3 cm detector the ATLAS 1 meter stave was completed and quotes from the vendor for fabrication were received.

6) A proposal to carry out this stave development was written and submitted to the ATLAS Upgrade steering group for approval

7) Abstracts are being submitted to the IEEE NSS and the Hiroshima meeting describing the stave development

4.1.4.2 Hybrids

Carl Haber (Lawrence Berkeley Laboratory)

Additional hybrid were assembled and tested in this period. Hybrids were sent to RAL for testing there with serial power electronics.

A new hybrid layout was initiated with the following goals: reduce hybrid area by ~40% or integrate serial powering into the hybrid with no increase in area

4.1.4.3 Cooling Channels

Carl Haber (Lawrence Berkeley Laboratory)

Considerable activity continued in this area in collaboration with W. Miller. A viable stave design was found with less than 60 microns gravitational sag and sufficient thermal performance to meet specs. Effort included the design and simulation of the end fixation structure including pins and inserts. This effort is moving towards a fabrication plan for the 1 meter stave which should result in usable structure around the end of calendar 2006.

The proposed stave design is characterized by a particular choice for the carbon fiber facing lay-ups, a core material, cooling tube material and geometry, and end fixation structures.

Considerable documentation is being compiled in the form of status reports to track this activity.

4.1.4.4 Powering Schemes

Carl Haber (Lawrence Berkeley Laboratory)

The RAL group has proposed a serial powering circuit comprised of COTS components. It has been tested on large PC boards with existing ATLAS SCT modules and performs well.

Working together LBNL and RAL have recast this in a miniaturized hybrid layout which is designed to integrate directly to the existing ATLAS hybrid. This layout is also consistent with a future DC-DC conversion circuit as well. This powering hybrid works together with the new bus cable design mentioned in 4.1.4.1 as well. The powering hybrid is being fabricated in the UK and will be tested here on the second (serial powered) stave in early summer 2006

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

DC-DC: A prototype DC-DC converter IC was fabricated in 0.35um HV CMOS from Austria Microsystems. Unfortunately there is a problem with the body contacts of the transistors in this chip and it cannot be operated as designed in order to supply power to real devices. Work is in progress to characterize the individual transistors in this chip and compare to simulation.

4.3 Liquid Argon Upgrade R&D

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Eliminate Layer Effect (Arizona) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |

Francesco Lanni (Brookhaven National Laboratory)

Availability of the funds in FY06 came to most institutions involved significantly late (Mar to May 06) in some cases. Nevertheless all the activities started successfully their programs, and achieved preliminary results, of some relevance in few cases. In other cases activities and milestones were reprioritized and reassigned to adjust dynamically for the late availability: an example is 4.3.2.3 where some radiation testing has being delayed by a few months while higher priority was given to the design of the “full-slice” board to test dataflow issues. In other cases recent technology advancements encouraged us to review or enlarge the scope of the R&D plans: an example can be found in 4.3.4 where recent progress in communication systems (e.g. ATCA communication system) would boost the performance of the signal processing in the ROD and DAQ systems.

4.3.1 Layer Buildup due to Radiation

John Rutherfoord (University of Arizona)

US ATLAS Upgrade R&D funding for Liquid Argon was loaded into our account at the end of March 2006, too late to spend any of it, so we have no financial activity to report for the first quarter of calendar year 2006.

But we have lots of activity to report, albeit less than we had planned, for lack of funds. In December we finished our equivalent 2.3 LHC run year (2.3  107 seconds) exposure with our FCal1 electrode which had a 50 mCi beta source (90Sr) embedded in a cavity within the rod. The activity simulated the conditions of an FCal1 electrode at EM shower maximum at ƒØ= 4.7 at full LHC design luminosity of 1034 cm-2 s-1. In addition we have two other FCal1 electrodes, one with a 2 mCi beta source and one with no source. Except for the strength of the source all three electrodes are identical. All three are read out. We analyzed this data in January and, at the same time, overhauled the experimental apparatus to allow use of a getter bequeathed to us by our colleagues at Brookhaven. In all previous work the best argon purity we attained was about 0.25 ppm O2 equivalent as measured by our oxygen gas analyzer. (We recently purchased a new oxygen gas analyzer and now run the two in parallel. At roughly the same time we had the old one recalibrated. The new one measures an impurity level of about twice our old one. We presume the calibration on one or both is off.)

We started up the system again with the new getter but using the old, worn-out cartridge in order to test our new protocol and get used to our procedures. The old cartridge seems to be working at some level because the purity levels are better than we’ve ever seen in the past, or order 0.1 ppm as measured by the old oxygen analyzer. With this improved purity we expected to read higher currents from our FCal-style electrodes. But, to our surprise, the currents were significantly smaller.

In order to understand these findings we plan to polish the electrode rods and perform another run but with the new getter cartridge. The surface appearance of the rods degrades with time, probably due to some chemical reaction catalyzed by the betas. Before we start using Allain Gonidec’s filter we want to understand the performance with the Brookhaven getter.

4.3.2 Readout Electronics

4.3.2.2 Development of Analog Front-End

Francesco Lanni (Brookhaven National Laboratory)

In preparation of the studies of the IBM SiGe devices (5AM, 7HP, 8HP both bipolar and resistors) we organized the test-station and installed and debug the software from USSC (B. Hackenburg). Also re-design of the front-end preamplifier in SiGe BiCMOS technology has started. Focus was on the 7WL technology while awaiting for the results of the irradiation measurements. Linearity, dynamic range, noise and power consumption issues and preliminary results prepared and presented at the SMU workshop. Design is of course still in process.

4.3.2.3 Digital Readout System

Gustaaf Brooijmans (Columbia University (Nevis Laboratory))

To mitigate the late arrival of funds we traded some of the engineers' time with another project to get started (we had budgeted 50% FTE engineering + corresponding technician help for FY06 and received about 65% of the requested funds). This allowed us to develop a design for the digital dataflow on the next generation FEB. The design uses a small (8x64 bits) DPRAM to multiplex the data from 4 channels (14 bits each) + a bunch crossing code. The write and read addresses in this DPRAM are managed by a control logic based on gray codes. From the DPRAM the data is transmitted into a multiplexer where it is stored in triply redundant form to be able to recover from upsets. It is then sent over an optical link using IBM 8B10B encoding. The design uses two independent clocks: the first is linked to the accelerator and drives the ADCs and therefore the writing of the data into the DPRAM, while the second, derived from a crystal running slightly faster than 4 times the bunch crossing clock, drives the reading from the DPRAM and the transmission over the optical link. To test this architecture, a board with an FPGA (Altera Stratix GX) and an optical transmitter (Agilent HFBR-772) was designed and the layout was completed. An auxiliary board needed for communications was designed as well. Both designs were verified extensively and production was launched (using forward funding). The assembled boards arrived at Nevis at the end of March.

4.3.2.4 Optical Data Link

Jingbo Ye (Southern Methodist University)

We are progressing in two fronts:

1. The evaluation of the SoS technology, ELT layout and many parameter measurements, through a test chip we designed and submitted in October 2005. The test chips were delivered to SMU end of January 2006. The test boards design, fabrication and chip wire-bonding took place from November 2005 to March 2006. Now we are debugging these boards. We may have made a mistake in the channels that measure pico-ampere transistor off current and may have to re-make that board.

2. The design of LoCV1, the Link-on-Chip version one. The function blocks of LoCV1 are the PLL, the 8B/10B Encoder, the (20:1) Serializer, the Clock Unit, and the Control/Configure Unit. We decided on one design of the PLL (self biasing) and carried out extensive simulations on schematics and post layout levels. According to simulation, this PLL is fast and stable enough for LoCV1. We designed the Serializer circuit and simulated it. It researches the required speed. The design of the Clock Unit is under way, and will be followed by the Encoder and the Control/configure Unit.

We are on schedule of LoCV1 as in the proposal we sent in. The submission of LoCV1 is planned to be early next year. The evaluation and measurements of the test chip will be carried out from now to September.

4.3.3 Trigger

4.3.3.1 L1 Trigger Interface

Francesco Lanni (Brookhaven National Laboratory)

Started to investigate if would be possible to handle all the L1 information directly at the level of Back-End (and inside the ROD)

4.3.4 Next Generation ROD

4.3.4.1 Next Generation ROD (BNL)

Francesco Lanni (Brookhaven National Laboratory)

for H. Chen

Evaluate the data rate required to transfer data from the next generation all digital FEB to ROD, with 40MHz 16bits sampling on 128 channels, each FEB will need 81.92 Gbits/sec data throughput, we need parallel fiber to implement this high speed data link, industry standard parallel fiber MPO/MTP connector is a good candidate, which has 12 fibers and is about 15mm wide.

To interface with high speed optical link, SERDES is another crucial part to the design of next generation ROD, FPGA is playing a leading role on integration of the high speed SERDES, RocketIO X of Xilinx provides 10.3125 Gbps transceiver and Stratix II GX from Altera has 6.375 Gbps transceiver. Considering limited board area, power consumption and high density integration of SERDES, FPGA is better than discrete SERDES chips.

Since next generation FEB will be fully digital, this raised another question: can we perform level 1 trigger summing digitally? We explore the possibility of digital trigger summing design, estimate the time delay to perform trigger summing on ROD, to control the total delay within the current trigger timing delay budget (2.5us) is still a big challenge.

In system level design, ATCA is a novel platform, which complies with the PICMG 3.0 standard. The ATCA system provides a high speed serial switched fabric backplane, 8U size card, and an efficient cooling system that can guarantee 200W power consumption on each slot, 3kW per chassis. We have one ATCA crate in the lab and are going to evaluate the performance of this system.

4.3.5 Radiation Hard Low Voltage Power Supplies

4.3.5.1 Radiation Hard Low Voltage Power Supplies (BNL)

Francesco Lanni (Brookhaven National Laboratory)

for J. Kierstead

The possibility of using components from Vicor Corp. factorized power architecture has been investigated. Irradiation testing has been started on two of the products. One was a single Vicor VTM module powered from a regulated 48 volt power supply. The VTM module provides isolation but no regulation. The input was monitored and the irradiation was interrupted at selected doses when the output was measured At a total dose of between 500-600 Grays the input current dropped to zero.

A similar evaluation board was used in a noise test. The board was used to power the -4 volt input of a current generation FEB board to test for coherent noise and provided a satisfactory result. In process is a prototype board that would provide +4, -4, +11 and +6 using two pairs of PRM and VTM Vicor modules in parallel for each voltage. This would give data on both the behavior of the modules when operated in parallel and on the noise characteristics in powering multiple FEB board(s).

# Financial Report (Chuck Butehorn, BNL)