SAMPLE AGENCY METERING PLAN TEMPLATE

The following sample agency metering plan template was developed solely as an example.  Agencies should develop their own metering plans based on what they feel are the major steps and milestones for their particular agency to successfully deploy an agency-wide metering program.

This sample plan is based largely on the items identified on pages 16 and 17 of the document Guidance for Electric Metering in Federal Buildings (DOE/EE-0312) and consists of high-level goals and milestones.  The actual actions required to satisfy these goals will be more complex than the brief summarized milestones presented in this sample plan, so agencies should carefully consider all the elements required in the completion of their milestones and goals.

The format used is, again, just a sample.  Agencies are free to develop their own formats.  The following suggestions are offered, regardless of format used:

- Plans should be brief.  Highly detailed documents not only require additional time to develop, but also additional time to monitor and modify when needed.  However, enough detail/description should be provided so individuals outside the agency energy programs are able to reasonably understand the intent and outcomes.

- Each plan element should include at least a milestone completion date and identify individuals or organizations responsible for the noted actions.

A companion milestone chart for the milestones called-out in this sample appears below.

Department of Metering Plan

August 3, 2006

PLAN ELEMENT 1: EPAct Metering Requirement

OBJECTIVE: Complete the installation of standard meters and advanced meters by September 30, 2012, in compliance with the requirements of the Energy Policy Act of 2005 (Public Law 109-58), Section 103, Energy Use Measurement and Accountability.

MILESTONES:

Milestone 1-1: Complete all bureau metering plans by March 30, 2007.

Discussion: Most agencies consist of bureaus/services/administrations/etc. that manage their own facilities.  Because facilities in these individual organizations often operate under different circumstances, the agency may desire to have these sub-agency level organizations develop metering plans that best address their particular needs and modes of operation.

Milestone 1-2: Complete all site-level metering plans by December 28, 2007.

Discussion: As is the case for milestone 1-1 above, the sub-agency level organizations may delegate the planning activity to the site-level.  This approach allows the sites to develop plans based on existing infrastructure, operating model, utility environment, etc.

Milestone 1-3: Provide metering training (to cover establishing site objectives, design, procurement, operations, and data analysis) to site level leads by September 28, 2007.

Discussion: As the metering planning requirement works down to the sub-agency and/or site levels, many individuals not previously exposed to (advanced) metering will be required to make informed decisions.  Training individuals before critical decisions are made will ensure the systems eventually installed will not only satisfy the legislated requirement, but that the metering systems accomplish their desired objectives.

Milestone 1-4: By September 30, 2010, realize the following minimum annual electric energy usage and/or cost reductions through the application of metered data:

- 3 percent reduction through cost allocation programs.

- 10 percent reduction through low-cost/no-cost corrective actions (re-commissioning/value re-commissioning) identified through on-going data analysis and resulting actions.

- Full agency-wide participation in utility-offered time-based rate programs where available.

Discussion: Including a (stretch) performance-oriented goal establishes an agency’s intent to utilize metered data to improve operations and reduce costs, not to simply comply with EPAct 2005 requirement.  Coordinate with milestone 2-1 (if used).  These agency goals should be addressed by the sub-agencies and sites as they develop their metering plans.

Milestone 1-5: Complete cost installation of standard meters and advanced meters where cost effective per the table below:

| FY | Standard Meters (where cost effective) | Advanced Meters (where cost effective) |
| --- | --- | --- |
|  | Cumulative # of Buildings Metered | Cumulative % of Electric Metered | Cumulative # of Buildings Metered | Cumulative % of Electric Metered |
| 2007 |  | 10 |  | 5 |
| 2008 |  | 20 |  | 25 |
| 2009 |  | 40 |  | 50 |
| 2010 |  | 60 |  | 70 |
| 2011 |  | 80 |  | 85 |
| 2012 |  | 100 |  | 100 |

Discussion: Inclusion of the above table in your agency metering plan is strongly recommended.  An update of this table reflecting actual installation progress and revised goals (as necessary) will be a part of each agency’s annual reporting requirements to FEMP for inclusion in the annual report to Congress per the section “Performance Measures” in Guidance for Electric Metering in Federal Buildings (DOE/EE-0312).  Agency reports are due to FEMP each year on January 1.

PLAN ELEMENT 2: Metering Program Structure

OBJECTIVE: Identify and address the key metering program technical and financial issues to ensure robust metering installations and continued operations.

MILESTONES:

Milestone 2-1: Determine agency metering objectives by September 29, 2006.

Discussion: Agency metering objectives may vary by sub-agency and site; however, the agency objective can assist the sites in concentrating on strategies that offer the greatest opportunity, such as cost allocation and participation in demand response/time-of-use programs. These primary objectives can be used by the agency as it develops design guidance and equipment specifications (should it take that route).

Milestone 2-2: Complete survey of existing agency metering infrastructure by March 30, 2007.

Discussion: Agencies will need to survey existing meters, metering systems, and metering capabilities [e.g., energy management and control system (EMCS) capabilities], and identify current uses/status of these metering systems as well as current staff and funding allocations.

Milestone 2-3: Develop metering installation financing plan by June 29, 2007.

Discussion: Address how sub-agencies and/or sites will finance the design, procurement and installation of metering system hardware and software.  While it will be helpful to have an estimated resource requirement up-front, agencies will likely have to base the financing plan on a general estimate, evaluate the various funding options available, and develop a financing portfolio.

Milestone 2-4: Develop design guidance [and equipment specifications] for metering program planning, equipment and hardware, and software and tools in support of the agency metering objectives.  Complete guidance [and specifications] by September 28, 2007.

Discussion: Agencies may choose to issue guidance at a high level so the design and specification processes are not repeated at the site-level.  Technical guidance can be prioritized and phased.

Milestone 2-5: Identify agency-wide site support requirements by March 31, 2008.

Discussion: Assess the requirements for and availability of staff to support on-going metering programs in all phases (i.e., operations, maintenance, and data analysis); consider the various options for providing support requirements (i.e., subscription services, agency centralized metering programs, dedicated on-site staff, etc.); include support requirements in agency annual budgeting process.

PLAN ELEMENT 3: Agency Policy Guidance to Bureaus

OBJECTIVE: Issue agency-wide policy-oriented guidance to assist bureaus and sites in developing metering plans.

MILESTONES:

Milestone 3-1: Develop and distribute to bureaus guidance to develop bureau metering plans by September 29, 2006.

Discussion: Provide guidance to bureaus so they can develop their own metering plans (and satisfy milestone 1-1).  Consider providing a template with examples as well as information on overall agency metering goals, milestones, and planned policy developments.

Milestone 3-2: Issue guidelines and criteria for bureaus to assess the practicability of building and equipment electric (advanced) metering applications.  Complete by December 29, 2006.

Discussion: Provide to bureaus guidelines and procedures deemed acceptable for determining the practicability of (advanced) meters at individual buildings and on individual buildings’ systems.  Guidelines should include methods to estimate cost of metering systems and savings/benefits realized, agency specific cost effectiveness thresholds, building types requiring metering and building exclusions.  See section “Metering Cost Effectiveness” in the Guidance for Electric Metering in Federal Buildings (DOE/EE-0312) for general guidance on this topic.

Milestone 3-3: Issue guidance for installation managers and information technology staff regarding how the agency will address the metering system’s communications requirements.  Complete by September 28, 2007.

Discussion: There will be a number of issues requiring guidance to the bureaus and sites regarding the planning, design, and operation of advanced metering systems.  Using this plan element structure, the agency would identify the critical issues and develop guidance accordingly.  Examples of other issues to consider include

- program resource budgeting

- contracting for metering support services – data collection, storage, analysis, etc.

- integrating metering program into site O&M contract services

- recommended organizational location of metering program within facilities management organization

Milestone 3-4: Establish periodic metering program progress reporting requirements.  Complete by December 29, 2006.

Discussion: Agency should determine appropriate reporting interval based on need to know and ability to use feedback.  Consideration should be given to annual Department of Energy and Office of Management and Budget reporting requirements.

Milestone 3-5: Issue guidelines and criteria for bureaus to assess the practicability of non-electric advanced metering applications.  Complete by September 29, 2006.

Discussion: While EPAct 2005 Section 103 is interpreted to apply to electric metering only, agencies should strongly consider the potential benefits from the selective application of other energy/utility meters such as steam, water, and natural gas.  Addressing these metering opportunities at this time will allow economies of scale to reduce the overall cost and improve overall cost effectiveness of their application.

PLAN ELEMENT 4: Metering Implementation

OBJECTIVE: Develop timeline for bureaus to design and install (advanced) meters at sites in accordance with EPAct 2005 requirements.

MILESTONES:

Milestone 4-1: Complete building and equipment screenings for (advanced) metering applications by September 28, 2007.

Discussion: Screenings are an integral part of the overall site metering plan development and should be completed early in the process.

Milestone 4-2: Develop timeline for installation of meters across the building inventory by December 28, 2007.

Discussion: One approach to developing a timeline may be to establish goals based on percent of the building inventory completed and/or percentage of cumulative electric load metered across the agency.  See the section “Performance Measures” in Guidance for Electric Metering in Federal Buildings (DOE/EE-0312).  Consider incorporating the buildings and/or installations into the timeline on a priority basis.

Milestone 4-3: Complete installation of fully operable and operationally integrated advanced metering systems at the top quartile priority sites by December 31, 2008.

Discussion: Installation of metering systems may take several years, especially for the agencies with large building square footage inventories.  Prioritizing meter applications will help phase the installations across the agency, while also helping to realize the greatest benefits earlier in the process.  Fully operable and operationally integrated systems are those that are completely installed and staffed, with timely data analysis resulting in recommendations for actions and their execution.

Milestone 4-4: Annually review and update as necessary metering program plan and metering installation plans to reflect changing electric rates and screening assumptions (as directed by the agency guidance).  Complete by August 3, 2007; August 1, 2008; August 7, 2009; August 6, 2010; and August 5, 2011.

Discussion: Annual program reviews are strongly recommended because there are many issues and occurrences that can result in the need to modify the metering plans, including

- unanticipated policy, financing, design, procurement, etc. issues

- lessons learned

- changing utility markets.

# Text boxes

The milestone timeline figure above is a sample timeline.  Inclusion of a milestone timeline in the individual agency metering plans is recommended but not required.

While a milestone timeline chart can summarize a metering plan’s main activities and critical milestones, agencies should present their metering plans in the format they feel is most effective.

This document provides a sample template – not a required format!

The milestones in this document are examples of the types of milestones agencies may want to consider and include.  Each agency plan will reflect milestones suited to their particular needs.  Agencies should present their metering plans in the format they feel is most effective.