Underground Storage Tank Cleanup Fund

Pay For Performance

Condition of Payment

| Claim Number: |  |  |
| --- | --- | --- |
| Claimant: |  | (the “Claimant”) |
| Site Address: |  | (the “Site”) |
| Agency Overseeing Corrective Action: |  | (the “Regulator”) |
| Agency Representative: |  |  |
| Consultant: |  | (the “Consultant”) |

1.  Acceptance of Condition of Payment.  To expedite site remediation and reimbursement of eligible corrective action costs and in consideration of participating in this Pay For Performance pilot program, the Claimant agrees to perform corrective action at the “Site” in accordance with the terms and conditions set forth in this “Condition of Payment” and Attachment A, “Regulatory Requirements.”  Claimant’s signature herein constitutes an acceptance of this Condition of Payment.  Claimant’s signature shall also signify that:  (1) Claimant concurs that site characterization is complete within the “Area of Concern,” as defined in Figure 1; (2) Claimant shall bear all costs and expenses associated with any additional Site investigation to optimize a treatment system or to determine the cause of a failed treatment system without a right of reimbursement from the Underground Storage Tank Cleanup Fund (the “Fund”); and, (3) Claimant agrees to be responsible for the remediation of all petroleum contamination within the Area of Concern regardless of whether the contamination was identified during the site characterization.  The Fund has concluded that the payments associated with achieving the Remediation Milestones, described in Sections 4 and 15 below, constitute reasonable and necessary costs for corrective action.  Acceptance of this Condition of Payment does not waive the right of the Fund or any existing or future regulatory authority to take any action against the Claimant, including enforcement action, with respect to the Site.

2.  Remediation Target Levels.  The Remediation Target Levels are the concentrations to be achieved for specified chemicals (“Chemicals of Concern,” or “COCs”).  These COCs and their respective concentrations are listed in Table 1 of Attachment B, “Payment Schedule.”  The chemical concentrations shown are identified as “Preliminary Active Remediation Goals” (“PARGs”), which are further described in Attachment A, Section 2.  However, the achievement of PARGs does not guarantee that the Regulator will necessarily determine that Site closure is appropriate or that no further action is required.

3.  Payment Terms.  The Claimant agrees that the total fixed price contract amount for this Condition of Payment is the amount specified in Attachment B, Section 1.  The Fund shall make payments to Claimant when the Fund, after consultation with the Regulator, has determined that the Remediation Milestones described in Section 4 below have been achieved.  Remediation Milestone Payments shall be made pursuant to the schedule described in Section 15 below.

- Remediation Milestones.  Remediation Milestones shall be determined based upon the percentage of contaminant reduction achieved in specified monitoring wells from measured Baseline Data levels.  The procedure for calculating the percentage reduction is shown in the example provided in Attachment C.  The Baseline Data and the monitoring wells are further described below in Sections 5, 8, and 9.  The Fund agrees to authorize payments in accordance with the procedures set forth in Section 15 below.  If the Fund, after consultation with the Regulator, concludes that a Remediation Milestone has been attained, then the Fund will reimburse the Claimant the percentage of the total fixed price that corresponds to the Remediation Milestone attained.  If the Fund, after consultation with the Regulator, concludes that a Remediation Milestone has not been attained, then the Claimant shall not submit an invoice for that Remediation Milestone until the Claimant has demonstrated attainment of the Remediation Milestone to the satisfaction of the Fund.   The Claimant may request that the Fund Manager or the Division Chief review any Fund decision of non-attainment of Remediation Milestones by following the decision review procedures set forth in Article 5 of the Fund regulations.

5.  Baseline Data.  The Baseline Data for this Condition of Payment shall consist of the results of a Baseline Sampling Event of the wells identified in Attachment A, Section 3.  The Baseline Data shall be used as the reference for measuring reductions in the concentrations of the COCs.  The Baseline Sampling Event shall be conducted no more than thirty (30) days after the Claimant’s acceptance of this Condition of Payment.  All sampling and sample handling shall be conducted in accordance with the directives issued by the Regulator.  Split sampling, as described in Section 11 below, is required for this Baseline Sampling Event.  The Claimant’s results from the Baseline Sampling Event shall be provided to the Regulator and the Fund within fifteen (15) days of the Baseline Sampling Event.  As explained further in Section 6 below, “Start Work Notice,” the Baseline Data shall be approved by the Fund, after consultation with the Regulator, before startup of the remediation system.  Alternatively, if the remediation system is already operating, then the Baseline Data shall be approved by the Fund, after consultation with the Regulator, before this project converts to a Pay For Performance project.  If more than sixty (60) days have elapsed between the date of the Baseline Sampling Event and the remediation system startup, another Baseline Sampling Event must be scheduled and conducted before system startup.  Split sampling is also required for this additional Baseline Sampling Event.  However, the Fund, after consultation with the Regulator, may waive the requirement to conduct another Baseline Sampling Event.  The Baseline Data described in this Section are to be distinguished from any baseline data that were obtained before this Condition of Payment was accepted by the Claimant.  Such data obtained prior to acceptance of this Condition of Payment is identified hereinafter as “Pre-acceptance Baseline Data”.

6.  Start Work Notice.  After the Fund and the Regulator have received the Claimant’s Baseline Data, the Fund, after consultation with the Regulator, shall have the right, if exercised within fifteen (15) days of receipt of these data, to contest the Baseline Data, the timing of the Baseline Sampling Event, and/or the sampling method used.  At this time the Regulator or the Fund may also decide to change the wells designated as Key or Perimeter Monitoring Wells, as provided in Sections 8 and 9, respectively.  The Fund, after consultation with the Regulator, shall also have the right to require an additional round of split sampling, as prescribed by Section 11 below, if the results of the split sampling show a concentration difference of 100 percent or greater between the split samples when comparing the “sum of the COCs” for the wells sampled in the Baseline Sampling Event.  (The method for calculating the “sum of the COCs” is described in Attachment C.)  If an additional round of split sampling is required, and this additional round continues to show a concentration difference of 100 percent or greater, then the Fund, after consultation with the Regulator, may require the Claimant to perform another Baseline Sampling Event.  The Fund shall reimburse the Claimant on a time-and-materials basis for the eligible costs incurred in conducting any additional round of split sampling or Baseline Sampling Event.

If the Fund, after consultation with the Regulator, agrees with the accuracy of the Baseline Data, including the reliability thereof, then the Fund will issue a “Start Work Notice” to the Claimant.  If the Fund, after consultation with the Regulator, does not agree, then the Fund shall informally meet with the Claimant in a good faith attempt to address the Fund’s concerns.  In the event such concerns cannot be satisfied, the Fund may terminate this Condition of Payment pursuant to Section 7.E below.

Unless the Fund and the Claimant agree upon other terms and conditions in writing, eligible remediation activities relating to the Scope of Work described in Section 1 of Attachment A that are incurred after the issuance of the Start Work Notice shall be reimbursed or paid pursuant to the terms of this Condition of Payment

7.  Termination

A.	The Fund may terminate this Condition of Payment if a comparison of the Pre-acceptance Baseline Data and the Baseline Data of the Key Monitoring Wells shows that the sum of the COCs (identified in Table 1 of Attachment B) from these wells has decreased fifty (50) percent or more.  Alternatively, the Fund may terminate this Condition of Payment if the Baseline Data of the Key and Perimeter Monitoring Wells show that the COC concentrations of each well are at or below their respective PARGs.

B.  The Claimant may terminate this Condition of Payment if a comparison between the Pre-acceptance Baseline Data and the Baseline Data of the Key Monitoring Wells shows that the sum of the COCs (identified in Table 1 of Attachment B) from these wells has increased fifty (50) percent or more.

C.  If the Termination provision described in Subsection A or B above is invoked, the Fund’s reimbursement responsibility under this Condition of Payment shall be to pay for the eligible costs of any Baseline Sampling Event conducted and any eligible costs associated with this event.  Such costs shall be paid on a time-and-materials basis.

D.	If there is evidence of a new release or migration of off-site contamination onto the Site, then the Fund, after consultation with the Regulator, shall informally meet with the Claimant to discuss this alleged change in Site conditions.  If the Fund, after consultation with the Regulator, agrees that Site conditions have changed in this manner, then the Fund and the Claimant may terminate or re-negotiate this Condition of Payment.  If the Fund, after consultation with the Regulator, does not agree with the Claimant that Site conditions have changed, then the Claimant shall have the right to request a Fund Manager or Division Chief decision pursuant to the procedures set forth in Article 5 of the Fund Regulations with respect to this matter.

E.  The Fund also reserves its right to unilaterally terminate this Condition of Payment for good cause shown upon providing fifteen (15) days’ written notice to the Claimant and the Regulator and detailing the cause(s) for its proposed termination.  During that notice period the Fund, after consultation with the Regulator, shall informally meet with the Claimant to discuss the cause(s) for its proposed termination in a good faith attempt to address the cause(s).  Such notice period may be extended by mutual agreement of the Fund and the Claimant.  If the cause(s) are not addressed to the satisfaction of the Fund before expiration of the original or extended (if applicable) notice period, then the Fund’s proposed termination becomes effective at that time.  The Fund reserves the right to determine whether to reimburse the Claimant for any costs incurred up to the date of termination.  Its reimbursement determination shall depend on the cause(s) for termination, including but not limited to, the Claimant’s malfeasance or nonfeasance to comply with the terms of this Condition of Payment, and any intentional or negligent acts or omissions committed by the Claimant that the Fund has determined are contrary to law or this Condition of Payment.

F.	The Fund and the Claimant each have the right to terminate or renegotiate this Condition of Payment if an event occurs that is not within the control of the Claimant, who is affected by such event and who could not, by reasonable diligence, have avoided such effect.  Such an event shall be considered a "Force Majeure" event, and shall include, but not be limited to, the following: fire, flood, explosion, act of God, act of a public enemy, war, blockade, public riot, or similar catastrophe.  However, before the right to terminate or renegotiate this Condition of Payment may be exercised, the Fund shall first meet with the Claimant in a good faith attempt to address the consequences of such an event.  If it is decided to terminate this Condition of Payment, the Fund shall determine which costs incurred to date by Claimant shall be eligible for reimbursement based on Claimant’s submittal of such costs for payment.  If it is decided to renegotiate this Condition of Payment, Attachment B, the Payment Schedule, shall be amended in writing to reflect the renegotiation outcome.  Such amendment shall be deemed a part of this Condition of Payment and is hereby incorporated by this reference.

- Key Monitoring Wells.  The monitoring wells that are to be used to monitor the progress of the reduction of the contamination levels of the COCs are identified in Attachment A, Section 4, as the “Key Monitoring Wells.”  Following its review of the Baseline Data, the Regulator or the Fund may decide to change the wells designated as Key Monitoring Wells by requiring new and/or different monitoring wells to be installed and sampled as Key Monitoring Wells.  The Fund shall reimburse the Claimant on a time-and-materials basis for the eligible costs for installing any such additional monitoring wells and conducting the associated sampling and analysis.  If the Claimant disagrees with the Regulator’s or the Fund’s decision, the Claimant shall have the right to request a Fund Manager or Division Chief decision pursuant to the procedures set forth in Article 5 of the Fund Regulations with respect to this matter.

- Perimeter Monitoring Wells.  The monitoring wells that are to be used to evaluate the perimeter groundwater conditions of the Area of Concern are identified in Attachment A, Section 5, as the “Perimeter Monitoring Wells.”  Following its review of the Baseline Data, the Regulator or the Fund may decide to change the wells designated as Perimeter Monitoring Wells by requiring new and/or different monitoring wells to be installed and sampled as Perimeter Monitoring Wells.  The Fund shall reimburse the Claimant on a time-and-materials basis for the eligible costs for installing any such additional monitoring wells and conducting the associated sampling and analysis. If the Claimant disagrees with the Regulator’s or the Fund’s decision, the Claimant shall have the right to request a Fund Manager or Division Chief decision pursuant to the procedures set forth in Article 5 of the Fund Regulations with respect to this matter.

10. Adequacy of Monitoring Wells.  If, after the Fund has issued a Start Work Notice, the Regulator or the Fund concludes that one or more of the groundwater monitoring wells is not representative of groundwater quality in the vicinity of the monitoring location, then the Regulator or the Fund may require the installation and sampling of one or more new monitoring wells.  These new monitoring wells will be designated as Key or Perimeter Monitoring Wells and will be included in their respective monitoring well categories.  The Fund shall reimburse the Claimant on a time-and-materials basis for the eligible costs for installing any such additional monitoring wells and conducting the associated sampling and analysis.

11. Split Samples.  The Claimant shall provide a minimum of seven (7) days’ written notice to the Fund and the Regulator before conducting any sampling event proposed for the development of the Baseline Data or the evaluation of the attainment of Remediation Milestones for purposes of Remediation Milestone Payments.  Such notice shall be provided to enable the Regulator to conduct split sampling.  If split samples are taken, and the results indicate different concentration levels for any COC in one or more monitoring wells sampled, then the samples with the higher concentration levels shall be used.  However, such higher concentration samples shall not be used if the sum of the COCs for the wells sampled shows a difference of 100 percent or greater between the split samples.  For example, if the sum of the BTEX COCs for the wells sampled is 4500 for one split sample and 9000 or greater for the other split sample, then a second round of split sampling must be performed.  The Regulator shall forward to the Claimant the invoices for all split sample work for payment.  The eligible costs for split sample work that exceeds the scope of work included in the negotiated fixed price for this Condition of Payment shall be paid by the Fund on a time-and-materials basis.

12. Verification Sampling. The Fund shall have fifteen (15) days from receipt of the 100% Milestone Attained report results (as described in Section 15.E below) to approve the 100% Milestone Attained payment request.  However, the Regulator may require the installation and sampling of a reasonable number of additional monitoring wells and/or soil borings to confirm attainment of the 100% Milestone Attained remediation milestone.  If such additional wells and/or soil borings are required, the Fund, after consultation with the Regulator, shall have fifteen (15) days from the receipt of the sampling results from these additional wells and/or soil borings to approve the 100% Milestone Attained payment.  This Condition of Payment includes the cost for installation of one additional well.  The Fund shall reimburse the Claimant on a time-and-materials basis for the eligible costs for installing any additional monitoring wells and/or soil borings and conducting the associated sampling and analysis.  In either case the 100% Milestone Attained payment under this Condition of Payment shall not be payable until the results from all monitoring wells confirm that the concentrations for the COCs are at or below their respective PARGs for each and every monitoring well.  Payment of the remaining percentage of the total corrective action fixed price set forth in Attachment B of this Condition of Payment shall be made in accordance with the procedures described in Section 15.F below.

13. Finality of Condition of Payment and Fixed Price; Price Exception. This Condition of Payment shall be final and shall not be terminated except pursuant to the terms and conditions described in Section 7 above.  In addition, the total corrective action fixed price identified in Attachment B, Section 1, shall not be increased except where one or more of the situations described in Subsections D and/or F of Section 7 is present.  In this event the procedures applicable to those sections shall be followed.  In all other situations the fixed price shall not be increased.  These other situations include, but are not limited to: unanticipated iron fouling of a system, inadequate winterization, well clogging because of biological activity or sedimentation, increased costs, loss of utilities, modification to the system to meet the remediation goals, the presence of additional on-site contamination not identified in the site assessment, and changes in regulatory requirements from any regulatory agency, including the Regulator.

14. Changes in Contaminant Levels.  The Claimant shall notify the Fund and the Regulator telephonically, with confirmation in writing, as soon as practicable after the Claimant becomes aware of any significant change in contaminant levels.  For purposes of this Section “any significant change” includes, but is not limited to, the following:

A.  An increase of total contaminant concentrations has occurred in any well greater than thirty (30) percent from the last measured concentrations for that well.

B.  Unanticipated measurable free product is found in any monitoring well.

C.  The remediation system has been shutdown for more than a week regardless of the cause.

D. A significantly increased risk of impact or an actual impact to sensitive receptors, such as elevated VOCs in the ambient air, in water distribution lines, or in water supply wells, has occurred.

15. Performance Criteria and Payment Schedule:  Payments shall be made when the Fund determines that the performance criteria described below have been achieved.  A letter from the Regulator assessing whether such performance criteria have been achieved must accompany the Claimant’s written payment request.

A.	Start-up Milestone:  The Fund shall reimburse the Claimant the percentage set forth in Attachment B, Section 2.A, when all of the following criteria below have been satisfied and reported in the “Start-up Milestone Report.”

- The remediation system has been installed and functionally tested.  The Claimant shall provide the Regulator with forty-eight (48) hours’ written notice to observe the installed, functioning system.

- The Remediation System Start-Up and As-Built Drawings have been submitted to the Fund and the Regulator.

- As specified in Section 3 of Attachment A, groundwater samples have been taken from each Key Monitoring Well and lab results for these samples have been submitted for inclusion in the Baseline Sampling Event.

- The concentrations of the COCs in the groundwater samples analyzed, pursuant to Section 15.A.3 above, for each Key Monitoring Well have been calculated to define the Baseline Data.

B.	25% Milestone:  The Fund shall reimburse the Claimant the percentage set forth in Attachment B, Section 2.B, when there has been attained a 25% reduction of the sum of the COCs for BTEX from the Baseline Data levels in the Key Monitoring Wells.  This reduction shall be documented in the “25% Milestone Report.”  Note:  Any of the quarterly monitoring reports described in this Section 15 may serve as a remediation milestone report if identified as such.

C.  50% Milestone:  The Fund shall reimburse the Claimant the additional percentage set forth in Attachment B, Section 2.C, when there has been attained a 50% reduction of the sum of the COCs for BTEX from the Baseline Data levels in the Key Monitoring Wells.  This reduction shall be documented in the “50% Milestone Report.”

D.	75% Milestone:  The Fund shall reimburse the Claimant the additional percentage set forth in Attachment B, Section 2.D, when there has been attained a 75% reduction of the sum of the COCs for BTEX from the Baseline Data levels in the Key Monitoring Wells.  This reduction shall be documented in the “75% Milestone Report.”

E.	100% Milestone Attained:  The Fund shall reimburse the Claimant the additional percentage set forth in Attachment B, Section 2.E, when the specified PARGs have been attained for each COC identified in Table 1 of Attachment B in each of the Key and Perimeter Monitoring Wells, except as otherwise provided in Section 12 above.  Accordingly, each Key and Perimeter Monitoring Well must have concentrations below the PARGs for each COC.  The attainment of PARGs for each well shall be documented in the “100% Milestone Attained Report.”

- 100% Milestone Maintained:  The Fund shall reimburse the Claimant the remaining percentage set forth in Attachment B, Section 2.F, when the specified PARGs have been maintained for each COC identified in Table 1 of Attachment B in each of the Key and Perimeter Monitoring Wells for a period of four (4) consecutive quarterly sampling rounds after the remediation system has been shut down.  Accordingly, each Key and Perimeter Monitoring Well must have concentrations below the PARGs for each COC.  If these levels are not maintained for four (4) consecutive quarterly sampling rounds, then the remediation system shall be re-started and operated until the PARGs are once again attained for each well and COC.  Once the PARGs have again been attained, the remediation system shall be shut down and monitored until the PARGs have been maintained for a period of four (4) more consecutive quarterly sampling rounds.  If the levels are again not able to be maintained following shutdown of the remediation system, the Claimant forfeits all rights to payment of this remaining percentage.  The maintaining of the PARGs for each well for the applicable time periods specified above shall be documented in the “100% Milestone Maintained Report.”

16. Entire Understanding.  This Condition of Payment contains the entire understanding between the Fund and the Claimant with respect to the subject matter hereof and supersedes all prior or contemporaneous written or oral negotiations and understandings between them regarding the subject matter hereof.  This Condition of Payment may be amended only in a writing signed by the Claimant.

17. Authority to Sign Condition of Payment.  The person signing this Condition of Payment represents and warrants that he/she has the express authority, right and power to sign this Condition of Payment.

________________________________________			_________________________

Claimant	Date

# Attachment A

## Regulatory Requirements

(Example)

1.	Scope of Work: This Pay For Performance Condition of Payment applies to the following Scope of Work:

A.  Start-up Report:  The Start-up Report shall include a table of well construction details for all monitoring, soil vapor extraction, and air sparging wells.  In addition, the Start-up Report shall include the following information:

- A brief written summary of the field activities that were performed to install and start-up the remediation system.

- As-Built Drawings of the remediation system.

- A copy of the Start-Up Report required by the San Joaquin Valley Unified Air Pollution Control District.

- A table presenting the remediation system operational data collected during the start-up period.  This table should include flow rates, vacuum applied, extraction wells in use, and any other data used to calculate relevant information presented.

B.  Monthly Operation and Maintenance (O&M) monitoring of soil vapor remediation system:

- O&M monitoring shall be consistent with the requirements of the San Joaquin Valley Unified Air Pollution Control District and all other legally required permits for the operation and maintenance of the remediation system.

- Effluent soil vapor samples shall be collected on a monthly basis.  These samples shall be analyzed for TPHG and Benzene, Toluene, Ethylbenzene, and total Xylenes (BTEX) in accordance with the procedures prescribed by United States Environmental Protection Agency (“USEPA”) Method TO14.

C.  Quarterly Sampling of all groundwater monitoring wells:

- Quarterly sampling shall be conducted for all Key Monitoring Wells and Perimeter Monitoring Wells

- Groundwater samples shall be analyzed for TPHG by USEPA method 8015, and for BTEX by USEPA method 8260.

- Except for the last monitoring round before final payment is requested, a Key Monitoring Well may be eliminated from the monitoring program if each COC identified in Table 1 of Attachment B is detected at a level at or below its corresponding PARGs in groundwater samples for four consecutive monitoring rounds.  However, all Key and Perimeter Monitoring Wells must be sampled in the last monitoring round before final payment may be requested.

D.  Reporting of O&M and Monitoring Results:

- Reports describing O&M and groundwater monitoring results (“O&M and Groundwater Monitoring Reports”) shall comply with all applicable permit requirements.

- All quarterly O&M and Groundwater Monitoring Reports shall be submitted to the Fund and the Regulator within forty-five (45) days of the sampling event.  These reports shall contain the following information:

- A brief description of the field activities that occurred during the previous quarter.

- The amount of remediation system downtime, if any, including the causes of the shutdowns.

- Identification of active soil vapor extraction wells and air sparging wells.

- Discussion of any significant modifications or additions made to the remediation system.  The reasons for the changes shall be discussed and the As-Built Drawings modified.

- Figures showing the Site plan, groundwater gradient maps, Rose diagrams, all monitoring and remediation wells on-site and off-site, and iso-concentration contours for TPHG and Benzene.

- A table presenting the cumulative depths to groundwater, groundwater elevation, and analytical data for each monitoring well.  This table should reference the PARG for each COC.

- A Time-Trend plot of Total COCs in wells used to determine the Baseline Data.  The Baseline Data shall be included on the plot.

- A table presenting the well construction details, current depth to groundwater, and an assessment of whether the well screens are submerged.

- A table showing the observed and cumulative influent and effluent analytical data for the soil vapor remediation and groundwater treatment systems.

- Time-trend plots for soil vapor remediation system effluent concentrations.

- A table presenting mass removal data for Total Petroleum Hydrocarbons as Gasoline (TPHG) and Benzene.  This table should include mass removal rates observed and cumulative mass removed during the monitoring period.

- Time-trend plots of cumulative mass removal of TPHG and Benzene.

- A table presenting cumulative soil vapor remediation system operational data.  This table shall include flow rates, vacuum applied, extraction wells in use, and any other data collected for use in relevant calculations.

- All field data sheets and analytical reports

2.  PARGs:  The Remediation Milestone PARGs in this Condition of Payment are as follows:

A.  Groundwater Contamination in Perimeter Monitoring Wells: Groundwater PARGs in the Perimeter Monitoring Wells are presented in Table 1 of Attachment B.

B.  Groundwater Contamination in Key Monitoring Wells: Groundwater PARGs in Key Monitoring Wells are presented in Table 1 of Attachment B.

C.	Free Product in Key and Perimeter Monitoring Wells: Free product shall be removed from the Key and Perimeter Monitoring Wells in the delineated Area of Concern.

D.	Surface Water: Surface water has not been impacted at this Site.  In the event that the Claimant or its Consultant discovers a surface water impact, he/she shall notify the Fund and the Regulator, and other appropriate regulatory agencies, within twenty-four (24) hours of such discovery.  Such notice shall be provided telephonically with confirmation in writing.

3.   Baseline Data: The baseline monitoring points for this Condition of Payment shall consist of monitoring wells MW-1, MW-2, MW-3, MW-4, MW-8, MW-9 and MW-10.  All such wells shall be sampled in accordance with the USEPA methods specified in Section 1.C.3 above.  Any free product present shall be removed prior to sampling.

4.  Key Monitoring Wells:  Key Monitoring Wells to assess the progress of the reduction of contamination levels shall consist of wells MW-1, MW-3, and MW-8.  Groundwater samples shall be analyzed for the COCs in Table 1 of Attachment B using the methods specified in Section 1.C.3 above.

5.	Perimeter Monitoring Wells:  Perimeter Monitoring Wells shall consist of wells MW-2, MW-4, MW-9 and MW-10.  These wells shall be analyzed for the COCs listed in Table 1 of Attachment B using the methods specified in Section 1.C.3 above.

6.	Groundwater Treatment System Monitoring: Water sample lab data used to support a payment request for attainment of Remediation Milestones shall show the COCs that were present during the Baseline Sampling Event.  Samples shall be analyzed using the methods specified in Section 1.C.3 above.  Remediation Milestone reports shall include tables showing contaminant concentrations in the monitoring wells sampled and graphs showing total reduction in contamination from Baseline Data.  The data graphed and method of calculation of data shall also be provided.

Attachment B

#### Payment Schedule

(Example)

1.  	Fixed Price:  The Claimant agrees that the total corrective action fixed price to achieve PARGs, as set out in this Condition of Payment, is $__________.

2.	Remediation Milestone Payments:  Payments shall be made when the Fund determines that Remediation Milestones have been attained.  The Payment Schedule, as described in the subsections of Section 15 in the Condition of Payment and referenced below, and the corresponding percentages of the total price that will be reimbursed to the Claimant, are as follows:

Remediation

Subsection		Milestone		Payment (%)

A.	15.A.		Start-up			25

B.	15.B.		25%			 	10

C.	15.C.		50%			 	10

D.	15.D.		75%			 	15

E.	15.E.		100% attained		 	15

F.	15.F.		100% maintained	 	25

Table 1

| Chemicals of Concern (“COCs”) | Preliminary Active Remediation Goals (“PARGs”), ppb |
| --- | --- |
| TPHG | 500 |
| Benzene | 10 |
| Toluene | 50 |
| Ethylbenzene | 50 |
| Xylenes | 200 |

Attachment C

### Sample Calculation of Attainment of Remediation Milestones

This example shows how to calculate whether a remediation milestone has been attained.  Two different methods are used, depending on which milestone is involved.  The first method applies to the intermediate remediation milestones; the second applies to the 100% milestone.

Intermediate Remediation Milestone Calculation:

Intermediate Remediation Milestones are the 25%, 50% and 75% milestones.  The calculation method described here is a simplified method that provides a rough measure of the total mass of hydrocarbons present at a site at the initiation of remediation (i.e., the Baseline Data) and as remediation progresses.  Although PARGs have been established for Total Petroleum Hydrocarbons (TPH) as well as BTEX, normally only BTEX concentrations will be used to assess completion of the Intermediate Remediation Milestones.

Assume for this example that the Baseline Sampling Event yields the following results for Monitoring Wells 1 through 4 (all in units of ppb):

COC		 MW-1		MW-2		MW-3		MW-4		PARG

TPH		180,000	68,000		75,000 	10,000		1000

B		  34,000	  9,800		16,000		  4,800		  100

T		  39,000	  4,600		24,000		     320		  200

E		    3,000	  3,000		     970		     200		  500

X		  15,000	  9,200 	  5,100		     510		  300

Total BTEX	 91,000	26,600		46,070 	  5,830		1,100

Add the Total BTEX concentrations calculated for each well to derive the “sum of the COCs” for the BTEX Chemicals of Concern (“COCs”) for all of the wells for this Baseline Sampling Event.  This addition yields a total of 169,500.

Next, calculate the amount by which the Baseline BTEX concentrations must be reduced to reach PARGs.  This amount is the difference between 169,500 and 4,400 (1,100 x 4 MWs) or 165,100.

Then, multiply this difference (165,100) by 25% to calculate the amount by which the difference must be reduced to reach the 25% Milestone.  This reduction amount is 41,275.  Thus, the 25% Milestone is reached when the Baseline BTEX concentrations have been reduced to 123,825 (165,100 - 41,275).

The 50% and 75% Milestones are calculated in a similar fashion.  Accordingly, the values are 82,550 and 41,275, respectively.

100% Milestone Attained Calculation:

Calculation of the 100% Milestone Attained remediation milestone is determined by evaluating whether PARGs have been attained for each COC at each monitoring well, including the PARG for TPH.  For example, the PARG for benzene of 10 ppb would need to be attained for each monitoring well.  Hence, for MW-1, the final measured value of benzene would have to be 10 ppb or less.  MW-1 would also have to show that each of the other COCs was at or below its respective PARG.  A similar result would be required for MW-3 and MW-4 in order to satisfy the 100% Milestone Attained remediation milestone.