Technical Progress Report

02.01 PHYSICS Jul-Sep 2004

2.1 Subsystem Manager's Summary

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete event generation for DC2 | 1-Jul-04 | 20-Oct-04 | 31-Jul-04 | Completed |
| complete Production for Rome | 5-Feb-05 | -- | 5-Feb-05 | On Schedule |
| start DC3 event generation | 1-Dec-05 | 1-Jul-04 | 1-Dec-05 | On Schedule |

Ian Hinchliffe (Lawrence Berkeley Laboratory) 
Event Generation for DC2 was completed on 31 July. This was somewhat later than orginally planned. The delays are due to the overall atlas schedule; the tools necessary for the generation were supplied in time to meet the original scehdule.

Almost immediately, work began on the event generation to produce data to be used for analyses to be presented at the Physics meeting in Rome in June 2005.

It is intended to use Sherpa for this production (for the first time). Much interaction with the authors has been required to facilitate its inteegration into Athena. 

Jimmy will also be used for the first time. The interface to athena has been implimented, updated and validated to ensure that all the necessary parameters can be parsed correctly.

Interactions with the LCG Genser project have continued as they continue to develop. The new structure function package LHAPdf is being supported. The atlas interfaces will need to be modified to take this into account

Technical Progress Report

02.02 SOFTWARE Jul-Sep 2004

2.2 Subsystem Manager's Summary

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DC2 Phase 1 (simulation) starts | 1-Apr-04 | -- | 1-Sep-04 | Completed |
| DC2 Phase 2 (reconstruction) starts | 1-Jun-04 | -- | 1-Dec-04 | Delayed (See #1) |
| Software Release 9 | 15-Jun-04 | -- | 15-Nov-04 | Delayed (See #2) |
| Software deployed for reconstruction of DC2 and CTB data | 30-Jun-04 | -- | 30-Nov-04 | Delayed (See #3) |
| Integrated software available for CTB | 28-Jul-04 | -- | 28-Jul-04 | Completed |
| DC2 phase2 (reconstruction) ends | 31-Jul-04 | -- | 15-Feb-05 | Delayed (See #4) |
| Software deployed for Mar-2005 Physics Workshop | 1-Dec-04 | -- | 15-Feb-05 | Delayed (See #5) |
| Computing Model Paper | 31-Dec-04 | -- | 31-Dec-05 | Delayed (See #6) |
| Software available for DC3 | 30-Sep-05 | -- | 30-Dec-05 | Delayed (See #7) |

Note #1  Delayed pending availability of all software components

Note #2  Delayed awaiting completion of several software components

Note #3  DC2 has been delayed. CTB software available but being optimized

Note #4  Delayed due to delayed start of phase-2

Note #5  Delayed awaiting completion of many software components

Note #6  Delayed due to DC2

Note #7  DC2 delayed.... DC3 delayed


Srini Rajagopalan (Brookhaven National Laboratory) 
The primary focus during this quarter was the start up of the DC2 simulation production -- though delayed due to many reasons including continued developments to the simulation programs. The digitization software has also been released and the reconstruction software for DC2 exercises is now scheduled for October 2004. Core software delivered by U.S. include the infrastructure for pile-up event (overlay of multiple events) production, event mixing infrastructure and the much awaited event persistency. Persistency of Event data has been demonstrated relying on LCG based POOL framework. In addition to the Data Challenge, much of the required software for the Combined Test-Beam has been delivered. The U.S. continues to play a major role in not only the core software, but reconstruction, simulation and establishing the framework for physics analysis effort.

2.2.1 Coordination 
2.2.2 Core Services 
2.2.2.1 Framework

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Object Browser Integrated with Analysis Tools | 30-Mar-04 | -- | 30-Nov-04 | Delayed (See #1) |
| Pile-up Support for DC2 Production | 30-Mar-04 | -- | 30-Aug-04 | Completed (See #2) |
| Support for Reconstruction on Demand | 30-Mar-04 | -- | 30-Jul-05 | Delayed (See #3) |
| Evaluate Mech for Job Config/History | 30-Jun-04 | -- | 30-Dec-04 | Delayed (See #4) |
| Pile-up Support for DC2 Production Validated | 30-Jun-04 | 30-Oct-04 | 30-Sep-04 | Completed |
| Integration of Seal plug-in Mechanism | 30-Sep-04 | -- | 30-Sep-05 | Delayed (See #5) |
| Support Physics Analysis | 30-Sep-04 | -- | 30-Sep-04 | Delayed (See #6) |
| Synchronize Gaudi Release with | 30-Sep-04 | -- | 30-Sep-04 | Delayed (See #7) |
| History & Property Mech Integ | 30-Dec-04 | -- | 30-Dec-04 | On Schedule |
| Support for Reconstruction on Demand | 30-Dec-04 | 30-Dec-04 | 30-Dec-05 | Delayed (See #8) |

Note #1  delayed to release 10 cycle for lack of manpower

Note #2  DC2 start delayed to September. Memory optimization yet to perform.
Core software effort for pile-up work complete. There may be changes required once support for Truth information propagation is added. Those, if any, will be added as a new task

Note #3  rescheduled for lack of manpower both in Atlas and in the rest of the Gaudi project.

Note #4  Priority lowered, not needed before DC3

Note #5  Done for dictionary loading. Priority lowered for integration in Gaudi

Note #6  this is a priority for release 10. We will study the new requirements arising from the first round of analysis code in release 9

Note #7  porting to Gaudi release 15 has been delayed to mantain a stable developers environment during the completion of DC2. Should be done by release 10 (Feb 05)

Note #8  very low priority. The LHCb solution in Gaudi is not directly reusable in our code. Delay perhaps indefinetely

2.2.2.2 EDM Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Prototype Support for Integer Keys | 30-Sep-03 | -- | 30-Mar-05 | Delayed (See #1) |
| Support for Persistent Inter-Object Relationships | 30-Dec-03 | -- | 30-Sep-04 | Completed |
| Support for History Objects | 30-Mar-04 | -- | 30-Mar-05 | Delayed (See #2) |
| Integrate CLID Database Generation | 30-Jun-04 | -- | 30-Jun-05 | Delayed (See #3) |
| Integration with POOL-Cache Manager | 30-Jun-04 | -- | 30-Jun-05 | Delayed (See #4) |
| Data Objects Fully Accessible from | 30-Sep-04 | 30-Sep-04 | 31-Dec-04 | Delayed (See #5) |

Note #1  HLT group agreed to reschedule this non-vital performance optimization.

Note #2  transient part complete but no persistency yet. Rescheduled to DC3

Note #3  delayed to DC3

Note #4  this in a non critical optimization, that will probably will be delayed or even canceled

Note #5  access to Data Object from python prompt soon to appear in the repository

2.2.2.3 Detector Description

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Accelerated Access to Geometry Tree | 30-Mar-04 | -- | 30-Sep-04 | Completed |
| Geometry Configuration System Available | 30-Jun-04 | -- | 1-Sep-04 | Completed |
| Native GeoModel Material Integration Service Available | 30-Jun-04 | 30-Jun-04 | 30-Jun-05 | Delayed (See #1) |

Note #1  This milestone relates to services provided for the purpose of track reconstruction. It has been delayed because simulation issues are 
considered more pressing.

2.2.2.4 Graphics

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Deployment of Graphics for use in 2004 Test-Beam Runs | 30-Mar-04 | -- | 30-Sep-04 | Completed |
| Integration of Graphic Tools within Athena | 30-Mar-04 | -- | 30-Dec-04 | Delayed (See #1) |

Note #1  Plans for this have still not gathered maturity, while a tool integrated with Athena is highly desirable. The U.S. has no participation in this effort.

2.2.2.5 Analysis Tools

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Deployment of an Analysis Framework with Basic Functionalities | 30-Mar-04 | 30-Sep-04 | 31-Dec-04 | Delayed (See #1) |

Note #1  Significant progress has been made in the deployment of an Analysis Framework. A prototype is expected to be deployed for DC2 by Sep 2004.
Further delays in DC2 and release 9 push this to year end

2.2.2.6 Grid Integration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration with Ganga | 30-Sep-03 | 30-Sep-04 | 30-Sep-05 | Delayed (See #1) |
| Prototype Implementation for Grid Monitoring Architecture | 30-Sep-03 | 30-Sep-04 | 30-Sep-05 | Delayed (See #2) |
| Integration with Distributed File Replication Service | 30-Mar-04 | 30-Sep-04 | 30-Sep-05 | Delayed (See #3) |

Note #1  This activity is partly covered under Distributed Analysis Tools and a prototype is expected to be deployed for use in DC3.

Note #2  This is work is partly covered under Grid Tools and Services to provide monitoring of jobs submitted on the Grid. No capability within Athena exists due to lack of any assigned resources.

Note #3  The integration has been delayed due to lack of manpower. Work on standalone distributed file replication services are in progress and needs to be completed before an integration with Athena can be established.

2.2.3 Database 
David Malon (ANL) 
The preponderance of U.S. database effort in this reporting period has been devoted to development of the capabilities necessary to allow ATLAS to prototype the data flow aspects of its computing model in Data Challenge 2. The international ATLAS schedule for that Data Challenge has been slipping substantially, but the database components--and the U.S. components in particular--are on schedule to be ready well before they will be needed for deployment in an ATLAS Tier 0/Tier 1 exercise.

2.2.3.1 Server and Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Replication Machinery for Database-Resisdent Data Sufficient for DC2 | 30-Mar-04 | -- | 10-Dec-04 | Delayed (See #1) |
| Embedded Server Support and Extraction Protocols | 30-Jun-04 | -- | 29-Oct-04 | Delayed (See #2) |
| Evaluation of Distributed Oracle Deplayment Possibilities | 30-Sep-04 | -- | 26-Nov-04 | Delayed (See #3) |
| Define relational client library interface | 31-Oct-04 | [New] | 31-Oct-04 | On Schedule |
| Prototype relational client library implementation | 30-Nov-04 | [New] | 30-Nov-04 | On Schedule |
| Support distributed database deployment for DC2 | 31-Mar-05 | [New] | 31-Mar-05 | On Schedule |

Note #1  awaiting Orsay components for updating tag databases

Replication machinery sufficient for DC2 conditions data is complete.

Note #2  delayed because unneeeded for DC2. DC2-critical activities have been given priority.

Note #3  awaiting launch of recently-endorsed LHC-wide distributed database deployment projectg

2.2.3.2 Common Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Initial Suite of ATLAS POOL Acceptance Tests | 30-Jul-03 | -- | 7-Jan-05 | Delayed (See #1) |
| Athena I/Fs for Physical Placement Control Defined | 30-Sep-03 | -- | 25-Jan-05 | Delayed (See #2) |
| Athena/POOL Support for Physical Placement Control Delivered | 30-Sep-03 | -- | 25-Jan-05 | Delayed (See #3) |
| Content Characterization/Aggregation Model | 30-Mar-04 | -- | 15-Oct-04 | Delayed (See #4) |
| Strategy for Transaction Granularity | 30-Mar-04 | -- | 15-Oct-04 | Delayed (See #5) |
| Schema Evolution Requiements Defined | 30-Jun-04 | -- | 15-Oct-04 | Delayed (See #6) |
| Support for Multiple Transaction Contexts | 30-Jun-04 | -- | 25-Feb-05 | Delayed (See #7) |
| POOL multi-catalog support | 31-Jul-04 | [New] | 31-Jul-04 | Completed |
| Refactor PoolSvc/OutStream sharable properties | 31-Jul-04 | [New] | 31-Jul-04 | Completed |
| Support for Placement Control | 30-Sep-04 | -- | 25-Jan-05 | Delayed (See #8) |
| Test Suite for Prototype POOL Schema Evolution | 30-Sep-04 | -- | 25-Jan-05 | Delayed (See #9) |
| Support for Cross-Type Conversion | 30-Dec-04 | -- | 30-Dec-04 | On Schedule |
| Documentation Stand-down | 11-Jan-05 | [New] | 11-Jan-05 | On Schedule |
| Athena user access to POOL configuration options | 31-Jan-05 | [New] | 31-Jan-05 | On Schedule |

Note #1  Delayed to correspond to POOL Spring 2004 release with new functionality.
New plan is to integrate these with DC2 readiness tests.

Note #2  Pending January 2004 DC2 event store readiness workshop.
Delayed until after DC2.

Note #3  Pending January 2004 DC2 event store readiness workshop.
Delayed until after DC2.

Note #4  delayed until after DC2

Note #5  delayed until after DC2

Note #6  delayed until after DC2

Note #7  delayed until after DC2

Note #8  Delayed until after DC2.

Note #9  delayed until after DC2 and POOL 2 release

2.2.3.3 Event Store

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Athena SEAL/POOL Demonstrably Capable of Supporting Prototype Event Model | 30-Sep-03 | -- | 16-Jul-04 | Completed (See #1) |
| Support for Collection-Level and Subsample Extraction | 30-Mar-04 | -- | 2-Jul-04 | Completed (See #2) |
| Deep Copy Support for Event Extraction | 30-Jun-04 | -- | 30-Sep-04 | Completed (See #3) |
| Tier 0 readiness tests defined | 31-Jul-04 | [New] | 31-Jul-04 | Completed |
| Depth-of-Copy Support for Event Extraction | 30-Sep-04 | -- | 30-Sep-04 | Completed (See #4) |
| Unique EDO Identification Infrastructure | 30-Sep-04 | 15-Oct-04 | 28-Feb-05 | Delayed (See #5) |
| Tier 0 readiness tests passed | 1-Oct-04 | [New] | 1-Oct-04 | On Schedule |
| Database Tier 0 exercise complete | 24-Nov-04 | [New] | 24-Nov-04 | On Schedule |
| Database Support for Express Streams | 30-Dec-04 | -- | 30-Dec-04 | On Schedule |

Note #1  Delayed pending outcome of ATLAS DC2 event model task force (Spring 2004)

Some compromises to the event model were needed to compensate for POOL/ROOT limitations and some custom converters were needed for difficult constructs, but an EDM sufficient for DC2 has been demonstrated.

Note #2  Delayed pending delivery of POOL utilities.

POOL utilities have been delivered.

Note #3  This work is nearly complete, with some POOL collections and StoreGate integration tasks remaining.

Note #4  Utilities and tests have been delivered for two levels of extraction.
More general mechanisms will be introduced later.

Note #5  Delayed until after DC2.

2.2.3.4 Non-Event Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Generalized Support for NOVA Loading from Non-AGE Sources | 30-Dec-03 | -- | 30-Mar-04 | Completed |
| Generation of Transient NovaObject Classes from Structure Definitions | 30-Mar-04 | -- | 30-Mar-04 | Completed |
| NOVA Schema Definition Consistent with Event Store Data | 30-Jun-04 | -- | 30-Jun-04 | Completed |
| Maintain NOVA through period of geometry database transition | 30-Jun-05 | [New] | 30-Jun-05 | On Schedule |

2.2.3.5 Collections, Catalogs, Metadata

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Athena Interface for Writing/Reading Event-Level Metadata (tags) | 30-Sep-03 | -- | 28-May-04 | Completed |
| Collection Cataloging Deployed | 30-Sep-03 | 30-Jul-04 | 31-Jan-05 | Delayed (See #1) |
| Athena Interface/Read/Write Access to Collection-Level Metadata | 30-Dec-03 | -- | 15-Oct-04 | Delayed (See #2) |
| Collection Merging Deployed | 30-Dec-03 | -- | 2-Jul-04 | Completed |
| Collect Replication/Distribution Infrastructure Deployed | 30-Mar-04 | -- | 10-Dec-04 | Delayed (See #3) |
| Integration of Collection Support & Bookkeeping | 30-Mar-04 | 30-Jul-04 | 10-Dec-04 | Delayed (See #4) |
| Support for Collection Subsetting (skims) based upon Server-Side Processing | 30-Mar-04 | -- | 2-Jul-04 | Completed |
| Attribute Lists Capable of Supporting File/Location Lists | 30-Jun-04 | -- | 30-Jun-04 | Completed |
| Content Categories/Aggregates Represented in Event-Level Metadata | 30-Jun-04 | -- | 15-Oct-04 | Delayed (See #5) |
| Collection integration with Athena registration streams | 31-Jul-04 | [New] | 31-Jul-04 | Completed |
| Regression tests for collection utilities | 31-Jul-04 | [New] | 31-Jul-04 | Completed |
| Collection integration with ATLAS physics tags | 15-Oct-04 | [New] | 15-Oct-04 | On Schedule |

Note #1  Moved to Summer 2004 in the POOL work plan; ATLAS-specific work will 
probably not be a U.S. responsibility (Grenoble should do this).

POOL has added a model collection catalog to its 2004 work plan. ATLAS will wait for this.

Note #2  Pending January 2004 DC2 event store readiness workshop.
Delayed until after DC2. Not needed for combined test beam because this metadata will also be available from the conditions database.

Note #3  Joint U.S./Orsay responsibility, on the critical path for DC2.

Delayed corresponding to ATLAS DC2 Phase II delays

Note #4  Principally a Grenoble responsibility, with some U.S. involvement on the collections end. On the critical path for DC2.

Note #5  Delayed until after DC2.

2.2.4 Application Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Geometry Model Based Detector Description used for Reconstruction | 30-Sep-03 | 30-Oct-04 | 30-Dec-04 | Delayed (See #1) |
| ATLAS Complete GEANT4 Validation | 30-Dec-03 | -- | 30-Dec-04 | Delayed (See #2) |
| Prototype Definition of AOD | 30-Dec-03 | -- | 30-Jul-04 | Completed |
| Prototype Definition of ESD | 30-Dec-03 | -- | 30-Jul-04 | Completed |
| Prototype Definition of Event-Level Physics Metadata (tag) | 30-Dec-03 | 30-Jul-04 | 30-Jul-05 | Delayed (See #3) |
| RTF Recommendations Implemented | 30-Dec-03 | 30-Jul-04 | 30-Dec-04 | Delayed (See #4) |
| Extract Module Alignment Constants | 30-Mar-04 | 30-Jul-04 | 30-Dec-04 | Delayed (See #5) |
| Combined Testbeam Event Display Available | 30-Jun-04 | -- | 30-Sep-04 | Completed |
| Initial Implementation of AOD and ESD Available | 30-Jun-04 | -- | 30-Nov-04 | Delayed (See #6) |
| Initial Implementation of ESRAT Completed | 30-Jun-04 | -- | 30-Nov-04 | Delayed (See #7) |
| Support for Alignment in Readout Elements | 30-Jun-04 | -- | 30-Dec-04 | Delayed (See #8) |
| Access to Alignment in Reconstruction | 30-Sep-04 | -- | 30-Sep-04 | Delayed (See #9) |
| Second Version of Combined Testbeam Implementation Available | 30-Sep-04 | -- | 30-Sep-04 | Completed |

Note #1  Completed except for Caloriemter which have been postponed to July 2004.

Note #2  Many phased of the G4 validation ongoing. First phase of comparison of basic results with G3 completed. Full G4 validation integrating new G4 software and DC2 results expected end of the year.

Note #3  Awaiting outcome of AOD-ESD task force

Note #4  Well in progress. Calorimeter completed, RTF recommended EDM for Tracking delayed due to lack of manpower

Note #5  Delayed from lack of information from all sub-systems

Note #6  Delayed pending recommendations for AOD-ESD task force

Note #7  This has been delayed with a formation of a search committee and call for nominations.

Note #8  Delayed due to lack of sufficient manpower

Note #9  Some alignment information is already existing in Athena. Other delayed due to either lack of information and appropriate conditions infrastructure to save these time-varying alignment constants

2.2.4.1 Simulation

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Validate pile-up | 15-Jul-04 | -- | 15-Dec-04 | Delayed (See #1) |
| US DC2 Production Commitment completed for simulation/digitization/pile-up | 15-Aug-04 | 15-Sep-04 | 15-Dec-04 | Delayed (See #2) |

Note #1  DC2 delayed

Note #2  DC2 delayed

2.2.4.3 Combined Reconstruction

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| US DC2 production commitment for reconstuction completed | 15-Oct-04 | -- | 15-Dec-04 | Delayed (See #1) |

Note #1  DC2 delayed

2.2.4.4 Analysis

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Form US Atlas Analysis Support Group | 1-Jul-04 | -- | 1-Jul-04 | Completed |
| Deliver PhysicsAnalysis prototype. | 15-Jul-04 | -- | 15-Jul-04 | Completed |
| First analysis results from DC2 data | 1-Dec-04 | -- | 1-Dec-04 | On Schedule |
| First round of collecting user input for Analysis Support. | 1-Dec-04 | -- | 1-Aug-04 | Completed |
| Validate GEANT4 Physics with DC2 data | 15-Dec-04 | -- | 15-Dec-04 | On Schedule |

2.2.4.6 Combined Testbeam Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| First CTB data available with preliminary analysis | 15-Sep-04 | -- | 15-Sep-04 | Completed |
| Final CTB data available with preliminary analysis | 15-Dec-04 | -- | 15-Dec-04 | On Schedule |
| Final CTB data available with prelimminary analysis | 15-Dec-04 | -- | 15-Dec-04 | On Schedule |

2.2.5 Software Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Testing Releases with New Compiler Versions | 30-Jul-03 | -- | 31-Dec-04 | Delayed (See #1) |
| Release Version 3.0 of NICOS nightly control system | 1-Jul-04 | -- | 1-Jul-04 | Completed |
| Create new (4.0) version of NICOS for incremental nightly builds | 30-Nov-04 | [New] | 30-Nov-04 | On Schedule |
| Install and support ATLAS releases and associated external software at BNL | 31-Dec-04 | -- | 31-Dec-04 | On Schedule |
| Support of ATLAS software nightly builds at BNL and CERN | 31-Dec-04 | -- | 31-Dec-04 | On Schedule |

Note #1  The Milestone was delayed because new compiler versions were not available. 
In September new gcc 3.2.3 complier became available and the experimental nightly builds of ATLAS software were started with gcc 3.2.3.


Alexander Undrus (Brookhaven National Laboratory) 
During this quarter more reliable "local" scheme for nightly builds of ATLAS software at CERN was implemented: the builds are performed on a local disk and then copied to AFS area for worldwide use. As a result the nightly builds became more stable, with the number of failed (due to technical reasons) releases dropped from 15% to about 2%. The creation of doxygen documentation is started for each nightly build. The number of nightly integration tests were increased to 40. 
At BNL new ATLAS software releases were promptly installed, usually in one to two days after CERN installation. The mirrors of ATLAS CVS repository and ATLAS nightly builds were supported.

Technical Progress Report

02.03 FACILITIES Jul-Sep 2004

2.3 Subsystem Manager's Summary 
2.3.1 Tier 1 Facility 
2.3.1.1 Management/Administration 
Bruce Gibbard (Brookhaven National Laboratory) 
At the beginning of the reporting period Alexander Withers, a new hire, began work at the Tier 1 center. He will be involved in work associcate with monitoring and resource management of the Linux farms. Also during the reporting period Rich Baker left BNL and Razvan Popescu was selected to replace him as the US ATLAS Facilities Deputy Manager.

2.3.1.2 Tier 1 Fabric Infrastructure 
Bruce Gibbard (Brookhaven National Laboratory) 
During the reporting period additional air conditioning was installed in the US ATLAS area of the computing facility. This equipment was purchase out of Laboratory GPP funds and corresponded to increases driven primarily by the growth in the size of the ATLAS Linux processor farm. This should be adequate to meet cooling needs for the next few years. The rapid growth in need for redundant infrastructure servers (GridFTP, SRM, DB, etc.) which has been demonstrated by DC2 operations has lead to reorganization of the support for such servers to both strengthen their cyber security and streamline their hardware maintenance and system administration.

2.3.1.3 Tier 1 Linux Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Initial dCache Functionality Operational | 15-Dec-04 | [New] | 15-Dec-04 | On Schedule |

Bruce Gibbard (Brookhaven National Laboratory) 
Using funds available late in the fiscal year, 32 to additional dual processor 3.1GHz nodes were purchased and put into service with the primary objective of enhancing the compute resources available to individual and small group users. These nodes are being procured with 2 GBytes of memory. 48 similar nodes procured earlier with 1 GByte were upgraded to 2 GBytes reflecting the observed appetite of Athena for memory. The new 32 nodes will actually be received and commissioned early in the next quarter.

During the reporting period in discussion with the DC2 production team and representative individual users a set of condor based queues reflecting agreed priorities where established. These will assign priorities to three groups of users (DC2 production, individual US ATLAS users, and general Grid3 users) across three groups of Linux modes (48x3.1 GHz machines, 32x3.1 GHz machines and 48x700 MHz machines).

2.3.1.5 Tier 1 Wide Area Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| HRM / SRM operational for HPSS access | 1-Nov-04 | [New] | 1-Nov-04 | On Schedule |
| dCache SRM operational | 15-Dec-04 | [New] | 15-Dec-04 | On Schedule |
| Robust Data Transfer Service Challenge I complete | 1-Feb-05 | [New] | 1-Feb-05 | On Schedule |

2.3.1.6 Tier 1 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DC2 Tier 0 - Tier 1 exercise complete | 31-Dec-04 | [New] | 31-Dec-04 | On Schedule |

Bruce Gibbard (Brookhaven National Laboratory) 
During the reporting period the Tier 1 facility was operated in support of production for Data Challenge 2 (DC2) as well as in support of a growing number of individual and small groups of users. A call up list was established to assure that issues with in the facility affecting DC2 could be effectively dealt with on a 7x24 basis. This call up list was communicated to the IGOC at Indiana and worked well. During this period the Tier 1 was one of the leading produces of DC2 data with in the US Grid and the US Grid produced approximately 30% of the compute cycles delivered to ATLAS although its assign level of delivery was only 20% of the total.

2.3.2 Tier 2 Facilities

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Tier 2 Fabric Upgrade Fully Operationsl for DC2 | 25-Mar-04 | -- | 25-Mar-04 | Completed |
| Permanent Tier 2 Sites A & B Selection Complete | 1-Jul-04 | 1-Nov-04 | 1-Jan-05 | Delayed (See #1) |

Note #1  Uncertainty regarding the funding mechanism for Tier 2's delay action in this area. The selection process is now back on track but for 3 sites instead of 2 and with a delay in completion of four months.

2.3.2.1 Tier 2-A "Currently Indiana/Chicago Prototype"

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| UC Tier2 prototype Center deployed and DC2 ready | 1-May-04 | -- | 1-Jun-04 | Completed (See #1) |

Note #1  Final DC2 configuration delayed by NFS fileserver problems. The basic cluster was functional during the current period and performed adequately. There were problems with the machine room air conditionin that caused some downtimes; this was mitigated by replacement of compressors serving the space.

2.3.2.2 Tier 2-B "Currently Boston Prototype"

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| BU Tier 2 Fabric Upgrade for DC2 Complete | 5-Mar-04 | -- | 5-Apr-04 | Completed |

Saul Youssef (Boston University) 
During this quarter, in addition to routine operations, we went through an extensive planning exercise with colleagues in Physics, the Center for Computationas Science and Scientific Computing and Visualization center in order to be ready to expand over the next few years. We secured

a) Space for an expanded Tier 2 center in the Physics Research Building
b) Made preliminary plans for power, air conditioning, networking and physical security
c) Agreements with other groups at BU who are interested in contributing resources
d) Coordination with Harvard re: a large storage facility to be associated with our site via the 144 fiber NoX metro ring.
d) Approval of the plans from the University

2.3.3 Wide Area Network 
2.3.4 Grid Tools & Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| GCE 2.0: DC2 Alpha | 1-Feb-04 | 1-May-04 | 1-Jun-04 | Completed (See #1) |
| GCE 2.0: DC2 Delivery | 1-Mar-04 | 15-May-04 | 1-Jul-04 | Completed (See #2) |

Note #1  Initial milestone delayed by serveral factors - problems with the ATLAS software distribution kit, Pacman3-beta, and problems with large scale DC2 job testing.

Note #2  Reverted GCE-Server and Capone back to Pacman2 packaged based system. Capone functionality in full end to end system of production system brought into functionality during this period.

2.3.4.1 Grid Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Capone Distributed Processing Design | 1-Apr-04 | -- | 1-Apr-04 | Completed |
| Capone Distributed Processing Design | 1-Apr-04 | -- | 1-Apr-04 | Completed |
| VDC schema for DC2 transformations deployed, ready for DC2 | 1-Apr-04 | -- | 1-Apr-04 | Completed |
| VDC schema for DC2 transformations deployed, ready for DC2 | 1-Apr-04 | -- | 1-Apr-04 | Completed |

Rob Gardner (University of Chicago) 
Development Test Grid (DTG) was re-organized to work with the Grid3dev software environment. This work was done with USCMS, iVDGL and others.
A parallel development environment with VOMS, MDS, Ganglia is used.

Oversight from from Ed May of Argonne laboratory continues. 

Machines from the DTG are from ANL, UC, and IU.

2.3.4.2 Workflow Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Capone "stub" prototype delivered | 31-Mar-04 | -- | 31-Mar-04 | Completed |
| Delivery of DC2 ready Capone + GCE system | 1-May-04 | -- | 1-Jul-04 | Completed (See #1) |

Note #1  Full end-to-end functionality of integrated services (VDC, RLS, DQ, Windmill, Capone, GCE) complted during by this milestone.


Rob Gardner (University of Chicago) 
Implementation of first instance of Grid3 executor, Capone. Specific 
components delivered:

* message passing interface - done
* job submission modules - done, for Grid3 submission as well as stub.
* job monitoring components - significantly improved job satus monitoring which scales (improved interaction with Condor-G)
* job schedulers (several algorithms impleted; a shortcoming is that they do not use dynamic information such as queue depth).


Work continued on development of GCE (Grid Component Environment) based tools for job submission to Grid3 sites.

2.3.4.3 Data Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| RLS services deployed at to US ATLAS locations | 30-Apr-04 | 30-Apr-04 | 30-May-04 | Completed (See #1) |
| VDC services deployed, development and productoin | 1-Jun-04 | -- | 1-Jun-04 | Completed (See #2) |

Note #1  We started with two, jointly registered RLS services. We found interference with Don Quijote, its interactions (heavier than expected) which was solved with RLS patches from the ISI/Globus group, and using a single RLS server.

Note #2  Production VDC server deployed at BNL.

2.3.4.4 Monitoring Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Capone Job Monitor | 1-Aug-04 | [New] | 15-Aug-04 | Completed (See #1) |

Note #1  A Capone-viewer of the ATLAS production database was developed by a. Vanaichine. These are a set of php-myAdmin queries tailored to provide pertinent information about job and failure statistics by Capone submitter and Grd3 site.

2.3.4.5 Production Frameworks

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DC2 message schema implemented in Grid3/Capone execution system | 1-Apr-04 | -- | 1-Jun-04 | Completed (See #1) |
| Capone grid submission at DC2 scale | 1-Jun-04 | [New] | 1-Jul-04 | Completed (See #2) |

Note #1  Several changes and ambiguities in the ATLAS messaging delayed completion of the message parsing interface in Capone. Finished when schema stabilized.

Note #2  Scalability test with actual DC2 workflow and significant scale.

2.3.4.6 Analysis Frameworks 
Rob Gardner (University of Chicago) 
US ADA Progress report
2004 quarter 3
David Adams
November 17, 2004

There was significant progress in US contributions to ADA (ATLAS
distributed analysis) in the third quarter of 2004. Version 0.92
of DIAL was released with the following enhancements:
1. The mechanism for creating gsoap-based web services was
improved so it is now easy to add new services and clients.
A single executable is the basis for all services.
2. The handling of external packages was greatly improved.
3. The problem causing crashes in the previous version was
traced back to use of a ROOT executable built without
the pthread library.
4. The first DC2 transformations were provided.

The ARDA architecture and draft of the ARDA design documents were
released during the quarter. We invested considerable effort into
understanding these documents and how to fit ARDA into the ADA
model. We wrote extensive responses to both documents.

The GANGA python wrappers for the DIAL classes wer completed, most
notably finding a connection between python print method and the
C++ ouput stream.

For more information on all the above, see the ADA home page
http://www.usatlas.bnl.gov/ADA

2.3.5 Grid Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DC2 GTS Version Ready for Production | 1-Apr-04 | -- | 2-Jul-04 | Completed |
| Start ATLAS DC2 | 1-Apr-04 | -- | 24-Jun-04 | Completed |
| DC2 50% Complete | 15-Jun-04 | -- | 7-Oct-04 | Delayed (See #1) |
| Start DC2 on Grid3 | 24-Jun-04 | -- | 14-Jul-04 | Completed |
| DC2 Production Goals Achieved | 27-Aug-04 | -- | 15-Dec-04 | Delayed (See #2) |
| Computing Model Document Complete | 3-Jan-05 | -- | 3-Jan-05 | On Schedule |

Note #1  Startup delay plus other factors is will delay DC2 about 3.5 months.

Note #2  Overall ATLAS DC2 schedule has slipped 3.5 months.


Kaushik De (University of Texas at Arlington) 
DC2 production started during this period. All the necessary software and hardware were deployed and brought on line. The production team worked closely together with the GTS team to make the transition from a development to a production system. Grid3 resources from ATLAS and non-ATLAS sites were fully used for DC2. The new production system evolved into a fully functioning system, with many iterations to improve performance. Many problems were discovered and solved with the software and hardware infrastructure as we ramped up to production scale. There were some delays with systems not fully in U.S. control. Overall, DC2 was a success in the U.S. and met all major objectives.

Technical Progress Report

02.09 SUPPORT Jul-Sep 2004

2.9 Subsystem Manager's Summary 
Jim Shank (Boston University) 
SubSystem Manager's summary July-Sept., 2004

This quarter the main activity was the massive production for the ATLAS Data Challenge 2 (DC2). This involved getting the Grid3 environment set up to run the ATLAS generation and simulation software. This was done on approximately 15 of the Grid3 sites that were selected for the most compatibility (OS, WAN access from compute elements, etc.). During this quarter we succeeded in doing 80% of the CPU-intensive Geant4 simulation part of DC2 that was assigned to us by agreement with ATLAS. Many problems with grid middleware, software distribution, DB servers and other components were encountered and solved. Much of this experience is needed to prepare the important Computing Model document which is now on schedule for completion at the end of CY 2004.

In addition, the Combined Test Beam (CTB) continued in this quarter and a branch of the ATLAS software has been used for the processing and analysis of this data. Improvements/bug fixes in this branch have continued in this quarter and are expected to continue throughout the testbeam period up to Nov., 2004.