U.S. ATLAS PROJECT OFFICE

Physics Department

UPTON, NEW YORK 11973

April 6, 2006

Mr. Thomas Ferbel

SC-25/Germantown Building
U.S. Department of Energy
1000 Independence Avenue, SW
Washington, D.C. 20585-1290

Dr. Samuel Aronson

Associate Laboratory Director

Brookhaven National Laboratory

Upton, NY  11973

SUBJECT:  U.S. ATLAS Research Program Quarterly Status Report

Dear Sirs:

Attached please find U.S. ATLAS Research Program Quarterly Status Report No. 6 for the period October-December 2005.

Sincerely yours,

Howard A. Gordon

U.S. ATLAS Deputy Research Program Manager

Head, U.S. ATLAS Project Office

Distribution:

Abolins, M.

Alam, S.

Aronson, S.

Baker, K.

Barnett, M.

Bensinger, J.

Blair, R.

Butehorn, C.

Byon-Wagner, A.

Carolan, P. - DOE

Cleland, W.

Coles, M. – NSF

Crawford, G. - DOE

De, K.

Dodd, J.

Ernst, R.

Errede, S.

Feldman, G.

Ferbel, T. - DOE

Gilchriese, M.

Goldberg, M. – NSF

Grillo, A.

Harrison, M. – PAP

Hinchliffe, I.

Huth, J.

Kagan, H.

Kane, S.

Kirby, D.

Kogut, J.

Lankford, A.

Larsen, R. - PAP

Lissauer, D.

Lubatti, H.

Mantsch, P. - PAP

Meyers, P. – PAP

Neal, H.

Norton, S.

Ogren, H.

Oh, S.

Parsons, J.

Pilcher, J.

Polychronakos, V.

Price, L.

Pripstein, M. - NSF

Rijssenbeek, M.

Rutherfoord, J.

Seiden, A.

Seidel, S.

Shank, J.

Shochet, M.

Skubic, P.

Slattery, P.

Sliwa, K.

Sondericker, J.

Stroynowski, R.

Taylor, F.

Tuts, M.

Whitaker, S.

Willocq, S.

Wolbers, S. - PAP

Williams, H.

Willis, W.

Wu, S.L.

research program STATUS REPORT NO. 6

REPORTING PERIOD

October-December 2005

# Table of Contents

Table of Contents	3

1.	Executive Associate Project Manager’s Summary (J. Shank, BU)	4

2.	Technical Progress Reports	4

2.1 Physics	4

2.2 Software	5

2.3 Facilities	16

3.1 M&O Silicon	22

3.2 M&O TRT	26

3.3 M&O Argon	28

3.4 M&O Tile	35

3.5 M&O Muon	38

3.6 M&O Trigger	43

3.	Financial Report (Chuck Butehorn, BNL)	46

# Executive Associate Project Manager’s Summary (J. Shank, BU)

The emphasis in this quarter continued to be preparations for the Computing System Commissioning (CSC) exercises which will start in early 2006. The ramp up in hardware and personnel begun last quarter continued this quarter with new hardware ordered and scheduled for full deployment in early 2006. All 3 Tier 2 centers also purchased new CPU and disks this quarter for production operations in early 2006. All our facilities continue to be available as part of the Open Science Grid.

The main software development effort was on the Production and Distributed Analysis (PanDA) system. This is a new effort, using existing experienced developers who were actively involved in our successful Data Challenge 2 production system. The lessons learned from DC2 were applied to the PanDA development and a PanDA prototype was delivered on time this quarter following an aggressive schedule.

The area of Analysis Support (WBS 2.2.7) was added this quarter, managed by Stephane Willocq. Its immediate responsibility will be to establish a coherent Analysis Support Group that can provide the technical expertise, analysis forums that can encourage performance/physics discussions in U.S. and beefing up the Analysis Support Centers in providing technical assistance to all U.S. institutes.

# Technical Progress Reports

## 2.2 Software

2.2 Subsystem Manager's Summary

Srini Rajagopalan (Brookhaven National Laboratory)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release 11.0.0 software for Commissioning | 30-Sep-05 | -- | 15-Dec-05 | Completed (See #1) |
| Release 12.0.0 for commissioning | 15-Mar-06 | 15-Mar-06 | 30-Apr-06 | Delayed (See #2) |
| Software available for DC3 | 15-Mar-06 | -- | 15-Mar-06 | On Schedule |

Note #1  Release 11.0.0 has been released. There are ongoing bug fixes which will be completed by the end of the year. In addition, there are minimal functionalities in Release 11.0.0 for use in commissioning. More significant developments geared toward cosmic ray commissioning are ongoing and a major release is expected in February-March 2006.

Note #2  Release 12 has been delayed to end of April with bug fixes releases expected to come out in May 2006.

Srini Rajagopalan (Brookhaven National Laboratory)

The focus for the software development is the upcoming cosmic ray commissioning and the computing system commissioning (CSC). The U.S. is participating actively within these areas. Within the U.S., we have reorganized ourselves with the approaching turn on to prepare ourselves to provide optimal support to U.S. physicists.

From the experience gathered from Data Challenge 2 (DC2) exercises, the U.S. has reorganized itself in the area of production and distributed analysis. A new Level 3 organization has been created with Torre Wenaus as its manager. Given the importance of data management, production and distributed analysis using U.S. grid and computing resources, the U.S. distributed software team has come up with a new design for the production and distributed software. This new design addresses the shortcomings and failure observed in DC2 and brings together the software for production and distributed analysis. A prototype has been tested and delivered in December 2005 and a full scale system is expected to be deployed for the upcoming ATLAS CSC.

The application software (renumbered to WBS 2.2.5) has been reorganized. It reflects the research program funded effort in the area of tracking, calorimeter, muons and other core application software. The emphasis on these kernel application software reflects the importance of establishing a solid foundation to build the U.S. physics analysis effort. We have also merged the Generator effort into Application software - Generator in previous WBS appearing under "Physics".

The area of Analysis Support has now been established. With the outcome of a task force recommending a model to support U.S. based analysis, we have established a Level 3 organization on Analysis Support (2.2.7). This area is managed by Stephane Willocq (U. Mass, Amherst). Its immediate responsibility will be to establish a coherent Analysis Support Group that can provide the technical expertise, analysis forums that can encourage performance/physics discussions in U.S. and beefing up the Analysis Support Centers in providing technical assistance to all U.S. institutes.

2.2.1 Coordination

2.2.2 Core Services

2.2.2.1 Framework

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration of Seal plug-in Mechanism | 14-Nov-05 | 14-Nov-05 | 14-May-06 | Delayed (See #1) |
| Assist in setting up help forum for ATLAS software (Indiana) | 1-Dec-05 | [New] | 1-Dec-05 | Completed |
| Support for Reconstruction on Demand | 30-Dec-05 | -- | 30-Dec-05 | Completed (See #2) |
| port of Gaudi and Control to gcc 3.4.4 | 1-Feb-06 | -- | 1-Feb-06 | On Schedule |
| python-accessible Property Repository | 1-Feb-06 | -- | 1-Feb-06 | On Schedule |
| Full chain and Interactive Tutorials | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |
| use GaudiPython to provide interactive access to (selected) framework functionality | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |
| High-level job configuration design and tools | 14-Feb-06 | -- | 14-Feb-06 | On Schedule |
| History & Property Mech Integ | 14-Feb-06 | -- | 14-Feb-06 | On Schedule |
| Review ATLAS software documentation/workbook (Indiana) | 1-Mar-06 | [New] | 1-Mar-06 | On Schedule |
| flexible job reinitialization | 1-Jun-06 | -- | 1-Jun-06 | On Schedule |

Note #1  awaits for the integration of ROOT5 in athena

Note #2  the deliverable is complete but its scope has been somewhat reduced to be able to run an algorithm tool as needed from the Atlantis event display. If it become a requirement we may provide a general Reconstruction on Demand service like Gaudi's DataOnDemand

2.2.2.2 EDM Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| new DataVector | 31-Aug-05 | -- | 30-Nov-05 | Completed |
| Integration with POOL-Cache Manager | 31-Dec-05 | -- | 31-Dec-05 | On Schedule |
| Support for History Objects | 14-Feb-06 | -- | 14-Feb-06 | On Schedule |

2.2.2.3 Detector Description

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| All Identifiers in DD database | 1-Oct-05 | 1-Oct-05 | 1-Jun-06 | Delayed (See #1) |
| DC3 Detector Description Quality Control Tests Passed | 1-Jan-06 | -- | 1-Jan-06 | On Schedule |
| All numbers in DB. All file-based info removed (Pitt) | 1-Mar-06 | [New] | 1-Mar-06 | On Schedule |
| CPU/Memory Optimization Effort Final Report (Pitt) | 1-May-06 | [New] | 1-May-06 | On Schedule |
| Initialization time performance study | 1-May-06 | -- | 1-May-06 | On Schedule |
| Validation procedures established for DD versions (Pitt) | 1-Jun-06 | [New] | 1-Jun-06 | On Schedule |

Note #1  This is still an important item. However this semester we have been mostly busy with preparing the misaligned LAr calorimeter AND in fact helping everybody in the LAr get ready to use this in simulation. And so this has been delayed.

Joe Boudreau (University of Pittsburgh)

The last quarter of 2005 was mostly spent preparing the realistic detector LAr detector description (adding misalignments material), and resolving clashes; also preparing and debugging the first run of full simulation with a geomodelized LAr. Restoring the functionality of calibration hits in the geomodelized simulation took a lot of our time. Vakho was especially active in these areas. This delayed the completion of the identifier==> oracle db milestone.

2.2.2.5 Analysis Tools

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| access Atlas Data from python | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |
| access c++ classes from python | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |

2.2.2.6 Grid Integration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Job Transformations in Python | 14-Feb-06 | -- | 14-Feb-06 | On Schedule |
| error recovery in athena | 15-Jun-06 | -- | 15-Jun-06 | On Schedule |

2.2.2.7 Core Service Usability

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| add and use help string to Gaudi Property | 18-Feb-06 | [New] | 18-Feb-06 | On Schedule |
| Configurable-based job configuration | 1-May-06 | [New] | 1-May-06 | On Schedule |
| provide job-level properties a la SimFlags | 1-May-06 | [New] | 1-May-06 | On Schedule |

2.2.3 Data Management

David Malon (ANL)

The database WBS area reflects some reorganization in support of the distributed software effort; for example, some milestones that were previously categorized as "common data management software" are now explicitly listed as "distributed data management."

This WBS area remains 1 FTE below planned U.S. staffing levels.

2.2.3.1 Database Services and Servers

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Deployment of connection indirection layer | 10-Oct-05 | -- | 10-Oct-05 | Completed |
| Architecture for database deployment on OSG | 14-Nov-05 | -- | 14-Nov-05 | Completed |
| 3D testbed slice test (Tier0/1/2) | 12-Dec-05 | -- | 12-Dec-05 | Completed (See #1) |
| Grid database access test using transport-level security | 12-Dec-05 | -- | 12-Dec-05 | Completed |
| User-level documentation for access to database services | 27-Mar-06 | -- | 27-Mar-06 | On Schedule |

Note #1  3D slice test was descoped by LHC-wide LCG3D project to exclude Tier 2 centers for now. A new milestone is pending, based upon emerging LCG3D plans.

2.2.3.2 Common Data Mgmt Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Don Quijote tools for data aggregation | 1-Nov-05 | -- | 1-Nov-05 | Completed |
| Transformation and software release descriptions in database | 1-Nov-05 | -- | 1-Nov-05 | Completed |
| Support for Placement Control | 7-Nov-05 | 7-Nov-05 | 7-Aug-06 | Delayed (See #1) |
| Support for Cross-Type Conversion | 14-Nov-05 | -- | 14-Nov-05 | Completed (See #2) |
| Support for Multiple Transaction Contexts | 14-Nov-05 | 14-Nov-05 | 22-May-06 | Delayed (See #3) |
| Schema evolution machinery deployed, with examples | 21-Nov-05 | -- | 21-Nov-05 | Completed |
| Dataset selection catalog prototype implemented | 15-Dec-05 | -- | 15-Dec-05 | Completed |
| Technology evaluation and selection for DDM catalogs | 27-Feb-06 | -- | 27-Feb-06 | On Schedule |
| User-level documentation for Athena I/O infrastructure | 27-Mar-06 | -- | 27-Mar-06 | On Schedule |
| Transient/persistent separation of DataHeader | 3-Apr-06 | [New] | 3-Apr-06 | On Schedule |

Note #1  December 2005: Agreement with ATLAS software management is to postpone this milestone until it is specifically requested or required by physics.

Note #2  Cross-type conversion is possible via the transient/persistent separation machinery. A more ambitious mechanism should be added to the milestone list.

Note #3  December 2006: A limited version will be introduced into early 2006 releases, but a more general strategy awaits the outcome of a spring 2006 event store developers workshop.

2.2.3.3 Event Store

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Job-level history object and configuration persistence prototype | 2-Oct-05 | 2-Oct-05 | 7-Aug-06 | Delayed (See #1) |
| Event store I/O performance tuning | 12-Dec-05 | -- | 12-Dec-05 | Completed (See #2) |
| Processing stage specification as a retrieval scope | 19-Dec-05 | -- | 19-Dec-05 | Completed (See #3) |
| Schema evolution infrastructure prototype based upon transient/persistent separation | 27-Jan-06 | -- | 27-Jan-06 | On Schedule |
| Unique EDO Identification Infrastructure | 31-Jan-06 | -- | 31-Jan-06 | On Schedule |
| Athena interface to set/get technology-specific attributes (POOL) | 27-Feb-06 | -- | 27-Feb-06 | On Schedule |
| Infrastructure to support stream- and run-level metadata | 27-Mar-06 | -- | 27-Mar-06 | On Schedule |
| Transient/persistent separation of StoreGate support classes for EDM | 1-May-06 | [New] | 1-May-06 | On Schedule |
| Event selector with scope-based retrieval support | 22-May-06 | [New] | 22-May-06 | On Schedule |
| File/dataset association machinery | 22-May-06 | [New] | 22-May-06 | On Schedule |
| Strategy for run-level, stream-level, file-level metadata | 22-May-06 | [New] | 22-May-06 | On Schedule |

Note #1  30 September 2005: Actual delivery may be later in the quarter because the prototype requires new versions of LCG dictionary software that will not be delivered to us until later in the quarter.

December 2006: This milestone must be delayed until some time after the corresponding control framework history infrastructure is in place.

Note #2  Initial performance tuning is complete, but yielded a speedup of only 20%. A more extensive program of optimization will be undertaken after transient/persistent separation of the event data model is in place.

Note #3  December 2006: Processing stage specification as an OutStream property has been added to ATLAS releases. The corresponding scope-based retrieval machinery is being redesigned in the context of the ATLAS Architecture Team, and should get a new milestone in spring 2006.

2.2.3.4 Non-Event Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DDM support for tile commissioning data | 13-Mar-06 | [New] | 13-Mar-06 | On Schedule |

2.2.3.5 Collections, Catalogs, Metadata

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Tag database support for access to upstream processing stages | 24-Oct-05 | -- | 24-Oct-05 | Completed |
| Performance evaluation of collection-based versus sequential (file-based) event access | 16-Dec-05 | -- | 16-Dec-05 | Completed |
| Athena Interface/Read/Write Access to Collection-Level Metadata | 19-Dec-05 | 19-Dec-05 | 24-Jul-06 | Delayed (See #1) |
| Collection replication tests using LCG 3D infrastructure | 19-Dec-05 | -- | 19-Dec-05 | Completed |
| Integration of Collection Support & Bookkeeping | 19-Dec-05 | 19-Dec-05 | 24-Jul-06 | Delayed (See #2) |
| Tag database infrastructure for Tier0 scaling tests | 16-Jan-06 | -- | 16-Jan-06 | On Schedule |
| Evaluation of strategies for support of variable-length structures in tags | 27-Feb-06 | -- | 27-Feb-06 | On Schedule |
| Transition POOL collections to CORAL AttributeLists and component library model | 17-Apr-06 | [New] | 17-Apr-06 | On Schedule |
| Support extensible collections, and collection reblocking | 22-May-06 | [New] | 22-May-06 | On Schedule |

Note #1  December 2006: Redesign is pending a Spring 2006 event store developers workshop. An underlying component (AMI, from Grenoble) is behind schedule.

Note #2  December 2006: Redesign is pending a Spring 2006 event store developers workshop. An underlying component (AMI, from Grenoble) is behind schedule.

2.2.3.6 Distributed Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Bulk transfer tests based upon realistic T0->T1 model | 31-Mar-06 | [New] | 31-Mar-06 | On Schedule |
| Deployment of SC4 version of DDM infrastructure on Tier 1s | 31-Mar-06 | [New] | 31-Mar-06 | On Schedule |
| Initial tests of DDM in distributed analysis chain | 17-Apr-06 | [New] | 17-Apr-06 | On Schedule |

2.2.3.7 Data Access Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Database representation on U.S. ATLAS Analysis Support Group | 30-Jan-06 | [New] | 30-Jan-06 | On Schedule |

2.2.4 Distributed Software

2.2.4.1 Distributed Analysis

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DIAL Panda integration - Panda implemented as DIAL back end | 15-Oct-05 | [New] | 15-Oct-05 | Completed (See #1) |

Note #1  Panda successfully implemented in DIAL as a processing back end for distributed analysis.

Torre Wenaus (Brookhaven National Laboratory)

During the quarter the distributed analysis effort was focused in a new direction -- Panda -- as part of the overall reorganization of distributed software in US ATLAS. The Panda project was initiated in the last quarter to develop a distributed processing system handling the full spectrum of usages from managed large scale production to individual job submission and interactive distributed analysis. During the quarter there were two principal objectives for distributed analysis: 1) Develop a distributed analysis service based on direct injection of analysis work to Panda, and 2) integrate DIAL with Panda and evaluate how Panda can leverage DIAL. The first objective was met with the development of pathena, a command line tool following the style of command line invocation of Athena, but submitting the Athena job to Panda with inputs and outputs specified via DDM datasets. The second objective had two parts: first and foremost to implement Panda as a processing back end behind the DIAL interactive analysis environment, and secondly to implement a prototype of hierarchical job management within Panda using DIAL's job hierarchy. The first objective was met, and the second not. Panda effort was heavily focused on bringing it into production and there was not enough time (or priority) to implement the job hierarchy prototype. Both the pathena and DIAL analysis front ends to Panda were functional but job turnaround was too slow due to long latency for job start while the Panda system was saturated with production jobs (as it always was). Strategies were in development at the end of the quarter to address this problem in the next quarter.

2.2.4.2 Production System

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Panda integration with ATLAS prodsys | 15-Oct-05 | [New] | 15-Oct-05 | Completed (See #1) |

Note #1  Panda successfully integrated as an ATLAS production system executor via the ExInt interface to the Eowyn supervisor.

Torre Wenaus (Brookhaven National Laboratory)

During the period the Panda distributed production/analysis system was developed from a first proof-of-principle prototype to a deployed production tool that took over ATLAS production in the US in December. The first prototype deployed in September had first implementations of all major components, DQ2 integration, and was able to process test jobs. The mid-October milestone was to add integration of ATLAS prodsys (an interface to the Eowyn supervisor), and process real ATLAS jobs. This milestone was met on time. The mid-November milestone was to have Panda operating smoothly for ATLAS production processing, which was met as well. Panda ran in pre-production mode in parallel with US ATLAS production based on the old Capone executor system. The most important milestone of the period was to have Panda take over full responsibility for production by mid-December, and this too was met. By early December Panda was debugged and validated for production, and it took over from Capone shortly thereafter.

2.2.4.3 Production Support

Torre Wenaus (Brookhaven National Laboratory)

Production support activity during the quarter consisted of direct participation by all distributed software personnel in the operation and debugging of the distributed software systems used in production during the quarter: Panda, DDM/DQ2, pathena, DIAL, and ancillary tools and services.

2.2.4.5 Trigger

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Define US Role in Trigger Software. | 15-Oct-05 | -- | 15-Oct-05 | On Schedule |

2.2.5 Application Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Install and support ATLAS releases and associated external software at BNL | 30-Dec-05 | -- | 30-Dec-05 | Completed |
| Release first stable version of ATN (ATLAS Testing Nightly Tool) | 30-Dec-05 | -- | 30-Dec-05 | Completed |
| Support ATLAS software nightly builds at BNL and CERN | 30-Dec-05 | -- | 30-Dec-05 | Completed |

Frederic Luehring (Indiana University)

For the Oct-Dec quarter we were support Ed Moyse to work on the Muon EDM, Haleh Hadavand to work on monitoring, and Dieter Best to work on Application Support & b-tagging/tracking.

2.2.5.1 Generator Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| First version of EvtGen interface for inclusive decays with Pythia and Herwig | 11-Apr-06 | [New] | 11-Apr-06 | On Schedule (See #1) |
| Migrate to Herwig 6.510 | 11-Apr-06 | [New] | 11-Apr-06 | On Schedule |
| Migrate to Pythia 6.326 | 11-Apr-06 | [New] | 11-Apr-06 | On Schedule (See #2) |
| Migration of production scripts to python | 30-Jun-06 | [New] | 30-Jun-06 | On Schedule (See #3) |

Note #1  For 12.0.0

Note #2  For release 12.0.0

Note #3  For use with 12.0.X production

Frederic Luehring (Indiana University)

Several bug fixes have been applied to the main event generators, Pythia and Herwig. ATLAS is using a patched version of both Pythia and Herwig as the authors could not release a version in time. Software tools have been developed, mostly focusing on testing and validating the physics consistency of the HepMC event structure. These tools are heavily used for the ATLAS CSC event generation.

The basic infrastructure to import events generated by Sherpa into the ATLAS detector simulation/reconstruction was put in place. The ATLAS/AlpGen interface was updated to the latest version of the latter. Extensive interactions with the ATLAS user community took place as bugs were reported, diagnosed and fixed in various packages as McAtNlo, Comphep and Generator Modules. Several job submission scripts and the necessary job options were developed, used for the production of the generated event samples, as they are defined by the CSC project.

2.2.5.2 Tracking Infrastructure

Frederic Luehring (Indiana University)

D. Best gave a workshop on using Athena to do b-tagging on Dec. 20, 2005.

2.2.5.3 Calorimeter Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| clean-up of CaloCluster class & new fast CaloTower implementation | 11-Apr-06 | [New] | 11-Apr-06 | On Schedule (See #1) |
| move cluster corrections into database, provide software framework for fill/retrieval | 11-Apr-06 | [New] | 11-Apr-06 | On Schedule (See #2) |
| move hadronic calibration parameters into database | 3-May-06 | [New] | 3-May-06 | On Schedule (See #3) |

Note #1  For 12.0.0.

Note #2  For release 12.0.0.

Note #3  For Munich Hadronic Calibration Workshop.

Frederic Luehring (Indiana University)

Walter Lampl was hired to work on the calorimeter software starting on 01-Jan-06

2.2.5.4 Muon Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Implement and Test new EDM for Muon reconstruction for 12.0.0 | 28-Apr-06 | [New] | 28-Apr-06 | On Schedule (See #1) |

Note #1  For release 12.0.0

Frederic Luehring (Indiana University)

For the Oct-Dec quarter, Moyse mainly worked on the Muon Event Data Model, in particular ensuring that it could be persisified, and that it contained the required information. Moyse started work on cleaning some aspects of the Muon CVS repository, and also did general maintenance to keep Muon reconstruction working. Additionally, work started on new mechanisms to handle "schema evolution" within the ATLAS EDM, and Moyse represented the Tracking community in these discussions. Moyse helped start the migration of MOORE to the new tracking EDM.

2.2.5.5 Monitoring Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| first functioning Gatherer | 1-Oct-05 | [New] | 1-Oct-05 | Completed |
| first functioning Gatherer | 31-Oct-05 | [New] | 31-Oct-05 | Completed |

Frederic Luehring (Indiana University)

Research by Haleh Hadavand began Sep. 2005 to develop software on the ATLAS Gatherer which is designed to facilitate distributed monitoring of

HLT data. Early work involved learning the tools available from 2004 test-beam and modifying them so that they would compile and run with late 2005 HLT and tdaq releases. A first running and fairly stable version was accomplished by year-end. Work also began during this period to understand how to employ the full set of TDAQ tools to run actual online monitoring irrespective of the Gatherer. The Gatherer work was geared toward a fully usable and released version for May 2006. The other online work was geared towards performing online monitoring during Winter Commissioning periods.

2.2.5.6 Application Support

Frederic Luehring (Indiana University)

D. Best did this work for this quarter.

2.2.6 Infrastructure Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release NICOS version 1.1 with the better multiplatform support | 30-Jun-06 | [New] | 30-Jun-06 | On Schedule |
| Setup mirror of ATLAS Pacman cache at BNL | 30-Jun-06 | [New] | 30-Jun-06 | On Schedule |

2.2.6.2 Librarian

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release NICOS version 1.1 with the better multiplatform support | 30-Jun-06 | [New] | 30-Jun-06 | On Schedule |
| Setup mirror of ATLAS Pacman cache at BNL | 30-Jun-06 | [New] | 30-Jun-06 | On Schedule |

Alexander Undrus (Brookhaven National Laboratory)

In this quarter NICOS, control system of ATLAS nightly builds, successfully supported standard monolithic and experimental project-oriented nightly builds. In project oriented nightly builds ATLAS software was split into eight projects. NICOS ensured proper synchronization of project builds according to their hierarchy. The status of project builds (with number of failed compilations and tests) was reflected on the summary NICOS web page so the ATLAS software The nightly builds were checked with about 70 unit and integration tests performed in the ATN testing framework integrated with NICOS. At BNL new ATLAS software releases were promptly installed, usually in one to two days after CERN installation. The mirrors of ATLAS CVS repository and ATLAS nightly builds were supported. The LXR server, alxr.usatlas.bnl.gov, provided the collaboration-wide service for fast searches of ATLAS software.

2.2.7 Analysis Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Formation of Analysis Support Group | 15-Feb-06 | [New] | 1-Feb-06 | On Schedule |
| Preparation of Analysis Support Centers Role and Implementation Document | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule |
| Selection of Analysis Forum conveners | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule |
| Signing of Analysis Support Center MOU | 1-Apr-06 | [New] | 1-Apr-06 | On Schedule |

Stephane Willocq (University of Massachusetts)

During the period Oct-Dec 2005, a chair was selected for the Analysis Support Group and several discussions took place within the US ATLAS Collaboration to define the implementation of the analysis support model. The current model includes an Analysis Support Group consisting of 'on-call' software and detector performance experts, a set of three Analysis Support Centers (ANL, BNL, LBNL), and a series of Analysis Forums for discussion of analysis development, issues, etc. A Beyond the Standard Model workshop + ATLAS software tutorial to be held at LBNL in Jan 2006 was in the planning phase.

## 2.3 Facilities

2.3 Subsystem Manager's Summary

Razvan Popescu (Brookhaven National Laboratory)

Tier1:

In collaboration with ITD Network Group we have defined the USATLAS subnets configuration that will allow safe and effective transfer of data between CERN - BNL and the US Tier2 centers. The procurement of equipment had been started. Implementation of the new topology will tak place in the first quarter of 2006, in time for testing during SC4.

Various alternatives for dCache expansion are under consideration. Maximum performance testing of the current dCache systems will provide the necessary information for determining the scale of the 2006 acquisitions.

The procurement of the tape system upgrade -- 1 SL8500 library and 10 LTo-3 tape drives, had started. Orders were places and the integration of new equipment will be completed in time for SC4. The HPSS software was successfuly upgraded to version 5.1

The OSG v0.4 release slipped into Jan 2006 delaying the planned deployment in Dec '05.

SC3 service phase was completed -- LCG-wide problems related to difficult interoperation between FTS and dCache were uncovered.

Tier2:

The preparations for site upgrades during the first quarter of 2006 are on schedule. The dCache instalations at UC, BU, UTA are operational. Newly acquired processors and storage expansions will arrive and be integrated in Q1'06.

WAN:

Tier1's connectivity to CERN's OPN and to US Tier2s will be upgraded to 20Gb/s. The plans have been defined and procurements started.

2.3.1 Tier 1 Facilities

Razvan Popescu (Brookhaven National Laboratory)

In collaboration with ITD Network Group we have defined the USATLAS subnets configuration that will allow safe and effective transfer of data between CERN - BNL and the US Tier2 centers. The procurement of equipment had been started. Implementation of the new topology will take place in the first quarter of 2006, in time for testing during SC4.

Various alternatives for dCache expansion are under consideration. Maximum performance testing of the current dCache systems will provide the necessary information for determining the scale of the 2006 acquisitions.

The procurement of the tape system upgrade -- 1 SL8500 library and 10 LTo-3 tape drives, had started. Orders were places and the integration of new equipment will be completed in time for SC4. The HPSS software was successfully upgraded to version 5.1

The OSG v0.4 release slipped into Jan 2006 delaying the planned deployment in Dec '05.

SC3 service phase was completed -- LCG-wide problems related to difficult interoperation between FTS and dCache were uncovered.

2.3.1.2 Tier 1 Fabric Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Procurement of expanded LAN Infrastructure | 1-Dec-05 | -- | 1-Dec-05 | Completed (See #1) |
| Expanded LAN Infrastructure Order Placed | 15-Dec-05 | -- | 15-Dec-05 | Completed |
| Begin Installation of Expanded LAN Infrastructure | 15-Jan-06 | -- | 15-Jan-06 | On Schedule |
| Expanded LAN Infrastructure Operational | 15-Feb-06 | -- | 15-Feb-06 | On Schedule |
| Expanded Facility Power and Cooling Capacity Available | 31-Mar-06 | -- | 31-Mar-06 | On Schedule |

Note #1  Procurement orders had been placed, with expected delivery dates in the first quarter of 2006.

2.3.1.3 Tier 1 Linux Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin CPU/dCache Disk Expansion Procurement | 1-Apr-06 | -- | 1-Apr-06 | On Schedule |
| CPU/dCache Disk Expansion Order Placed | 15-Apr-06 | -- | 15-Apr-06 | On Schedule |
| Begin CPU/dCache Disk Expansion Installation | 15-May-06 | -- | 15-May-06 | On Schedule |
| Central Disk Expansion Operational | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| CPU/dCache Disk Expansion Operational | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |

2.3.1.4 Tier 1 Storage Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Procurement of New Tape Subsystem | 1-Dec-05 | -- | 1-Dec-05 | Completed |
| New Tape Subsystem Order Placed | 15-Dec-05 | -- | 15-Dec-05 | Delayed (See #1) |
| Begin Installation of New Tape Subsystem | 15-Jan-06 | -- | 15-Jan-06 | On Schedule |
| New Tape Subsystem Operational | 15-Feb-06 | -- | 15-Feb-06 | On Schedule |
| Begin Central Disk Expansion Procurement | 1-Apr-06 | -- | 1-Apr-06 | On Schedule |
| Central Disk Expansion Order Placed | 15-Apr-06 | -- | 15-Apr-06 | On Schedule |
| Begin Central Disk Expansion Installation | 15-May-06 | -- | 15-May-06 | On Schedule |

Note #1  Order was placed after the holidays -- during the first decade of Jan '06

2.3.1.5 Tier 1 Wide Area Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| OSG 0.4.0 Deployed and Operational | 31-Dec-05 | -- | 31-Dec-05 | Delayed (See #1) |
| Service Challenge III - service phase | 31-Dec-05 | -- | 31-Dec-05 | Completed |
| All required SC4 Software for Baseline Services Deployed | 31-Jan-06 | -- | 31-Jan-06 | On Schedule |
| BNL Wide Area Network Upgrade Operational | 28-Feb-06 | -- | 28-Feb-06 | On Schedule |
| 10Gbs BNL Tier 1 <-> Tier 0 Dedicated Connectivity Operational | 31-Mar-06 | -- | 31-Mar-06 | On Schedule |
| SC4 Set-up Complete and Basic Service Demonstrated | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |

Note #1  The OSG 0.4.0 release was not available before the end of January 2006

2.3.1.6 Tier 1 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 500CPU, 150Disk, 200WAN=>Disk, 300Tape,200WAN=>Tape | 15-Feb-06 | -- | 15-Feb-06 | On Schedule |
| 1125CPU,525Disk,200WAN=>Disk,300Tape,200WFAN=>Tape | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |

2.3.2 Tier 2 Facilities

2.3.2.2 Boston University/ Harvard

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| dCache Installation | 15-Jan-06 | -- | 15-Jan-06 | On Schedule |

2.3.3 Wide Area Network

2.3.4 Grid Tools & Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Development of components for ATLAS production system (scheduler, broker) (Chicago) | 1-Oct-05 | [New] | 1-Oct-05 | On Schedule |
| Integration with distributed data management services and infrastructure (Chicago) | 1-Nov-05 | [New] | 1-Nov-05 | On Schedule |
| Development on as needed basis, components for distributed production and analysis focusing on distributed grid data management (Chicago) | 1-Feb-06 | [New] | 1-Feb-06 | On Schedule |

2.3.5 Grid Production

2.3.5.4 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Production (UTA) | 23-Jan-06 | [New] | 23-Jan-06 | On Schedule |
| Start Release 12 Production (UTA) | 1-May-06 | [New] | 1-May-06 | On Schedule |

## 3.1 M&O Silicon

3.1 Subsystem Manager's Summary

Alex Grillo (UCSC)

Pixel pre-operations activities have started, focused on preparation for 10% system test at CERN. The prototype service quarter panel under construction at LBL will be used in this system test. Additional electrical tests are being performed on this panel in preparation for this. Maintenance activities include building of spare components.

The SCT four-barrel assembly is complete and ready for insertion into the TRT. This insertion has been delayed until Jan-06 because of leaks in the TRT gas manifolds. Cable assembly, testing and installation continues. Other issues regarding systems electrical engineering are being worked as they arise.

The spare RODs have been fabricated and testing has started. The B-layer crates for Pixels have been ordered.

3.1.1 Pixels

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Pre-operations activities have centered around preparation for 10% system test at CERN. The prototype service quarter panel under construction at LBL will be used in this system test. Additional electrical tests are being performed on this panel in preparation for this.

Maintenance activities include building of spare components. Spare disk modules and sectors are being produced.

3.1.1.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start of Pre-operations of Pixel Endcap (LBNL) | 1-May-06 | -- | 1-May-06 | On Schedule |

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Activities at CERN

A set of dummy Type 1 cables has been requested to be able to connect power to prototype sectors and staves before the service prototype service quarter panel is shipped to CERN.

Prototype service quarter panel has been tested electrically by sequentially operating a module through each of the panel connectors.

3.1.1.3 Maintenance

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Hot Module spares

12 bare modules have been requested from the pixel collaboration for a supplemental production of disk modules. This action has been started in response to degradation of modules loaded on 2 sectors, which caused the sectors to be qualified as spares. It is now desirable to have at least one more high quality sector to complete the 6th disk. This is a production of additional spares.

3.1.2 SCT

Alex Grillo (UCSC)

The four-barrel assembly is complete and ready for insertion into the TRT. This insertion has been delayed until Jan-06 because of leaks in the TRT gas manifolds.

Cable assembly, testing and installation continues and will continue well into the Spring.

Other issues regarding systems electrical engineering are being worked as they arise.

3.1.2.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Insertion of SCT Barrel into TRT Barrel | 23-Jan-06 | 11-Nov-05 | 28-Feb-06 | Delayed (See #1) |
| Complete Pre-Operations of SCT Inside ID (UCSC) | 10-May-06 | -- | 28-Feb-06 | Delayed (See #2) |
| Start Installation of ID Barrel into UX15 (UCSC) | 11-May-06 | 1-Apr-06 | 11-May-06 | Delayed (See #3) |

Note #1  The schedule for pre-operations testing at CERN is running well. All four barrels have been delivered to CERN but they were delayed relative to the original schedule. The four barrels have also been assembled together, however, with the slip in delivery schedule of barrels, the testing of all four barrels together has been dropped until after integration with the TRT.

Note #2  Integration of the SCT barrel with the TRT has been delayed due to leaks in the TRT gas lines. Integration is now expected for Jan-06. Operations of barrel SCT and barrel TRT should be well underway by end of Feb-06. This is still consistent with the schedule for installation in UX15.

Note #3  This is the new ATLAS schedule for installation of the ID barrel into UX15

Alex Grillo (UCSC)

The integration of all four barrels was completed in October. Cooling services were connected to the pipes on each barrel and two small leaks were found at the connection points. These were fixed with epoxy. The four-barrel assembly is now ready for insertion into the TRT barrel, however, this has been delayed until Jan-06 due to leaks in the TRT gas manifolds, which are now being re-built.

Preparations are underway for cosmic rays tests with the combined SCT and TRT barrel as soon as the integration of the two systems is complete. Sofia is taking an active role in this work.

Sofia and Forest continue to share in the work of testing of power cables. This activity is expected to continue well into the spring. Sandra Ciocio from LBNL is supervising the entire cable testing and installation work at CERN. Cable assembly (i.e. cutting cables to length and mounting connectors) continues to be a problem. The latest is beaks in the insulation of the large conductors at the point where they are bent to fit into the connector hoods. This is being investigated by a group from CERN, Prague and the US. It is clear that there is a manufacturing problem with cable but replacing the faulty cable is not consistent with the installation schedule. Other possible solutions are being investigated, but even this is delaying the installation schedule.

Melbourne and Krakow sent technical staff and students to complete testing of the power supply backplanes. Sofia had modified the PVSS software and dummy load boards so that this testing could be accomplished efficiently. She helped with the testing, which was completed for all backplanes except the ones being used at Liverpool and NIKHEF for disk assembly testing. These nine backplanes will have to be tested later once they are returned to CERN. Fortunately, the rather high failure rate we had seen on the few backplanes tested earlier in the year, did not continue and only one new failure was found.

Ned evaluated the connectivity of the metal shielding of barrel Outer Thermal Enclosure to the Heat Spreader Plates and PP1 support plates and found the construction adequate. Also, modifications were made to the end-cap PP1 assembly design.

3.1.3 RODs

Abraham Seiden (UCSC)

The spare RODs have been fabricated and testing has started. The B-layer crates for Pixel have ordered.

3.1.3.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Pre-Operations for RODs with Pixel System | 1-Oct-05 | -- | 1-Dec-05 | Completed |
| Spare RODs Completed | 1-May-06 | -- | 1-May-06 | On Schedule |

## 3.2 M&O TRT

3.2 Subsystem Manager's Summary

Harold Ogren (Indiana University)

During this period of the research program we focused on electronics testing and cosmic ray testing and the preparation of the TRT barrel for integration with the SCT. We also redesigned large parts of the cooling and active gas system due to a number of leaks that were found after the initial mounting of the services.

Services Manifolds:

The distribution system for the cooling liquid (Fluorinert) was made of brazed stainless steel. This was used because it gave us a strong, selfsupporting system that was thought to be durable for the life time of the experiment. This stainless steel distribution system then connected to the modules with Peek tubes. After passing many pressure tests, and after mounting the system, several of the brazed joints began to leak. It is thought that this had to do with the slow removal of brazing flux during the cleaning and testing process that exposed gaps in the brazing. After removing and examining all the manifolds, we decided to replace the stainless steel with Peek for the entire manifold. The new "spines" were redesigned by groups at CERN and Indiana University, and by the end of December all Peek parts were completed and a complete prototype of a spine had been attached to the TRT barrel and successfully tested.

Electronics testing- Cosmic ray testing:

During this period we reverified all the barrel electronics and set up to run cosmic events through the top six modules and three of the lower modules. These events have been used to tune the on-line monitoring tools, measure cross-talk and other instrumental effects. Completing the "byte stream converter" for this task proved much more time consuming than originally estimated because of the complexity of the barrel straw mapping.

3.2.1 TRT-Subsystem

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT Installed in TRT | 23-Jan-06 | [New] | 11-Feb-06 | Delayed (See #1) |
| SCT-TRT Joint Test Complete | 10-May-06 | [New] | 10-Jun-06 | Delayed (See #2) |
| Barrel and SCT Install in ATLAS | 11-May-06 | [New] | 11-Jul-06 | Delayed (See #3) |

Note #1  Will be installed in February

Note #2  This will dragout until the ID is ready to go into the pit.

Note #3  Estimates vary when the services will be ready for us.

3.2.1.1 TRT Pre-Operations

3.2.1.1.4 TRT-6 mod-check

Rick Van Berg (University of Pennsylvania)

During this period Ben LeGeyt and Mike Hance reverified all the barrel electronics (finding a few fuse problems and one not so minor plumbing leak) and set up to run cosmic events through the top six modules and three of the lower modules. These events have been used to tune the on-line monitoring tools, measure cross-talk and other instrumental effects, and make lots of really pretty pictures for the group as a whole. The downside of this effort was that many people looking at off-line tools began demanding this data in the standard off-line format. Completing the "byte stream converter" for this task proved much more time consuming than originally estimated because of the interesting complexity of the barrel straw mapping. It is clear that the off-line troops really did want the data as off-line displays of SR cosmics appeared within six hours of Paul Keener's release of the completed byte stream converter.

Harold Ogren (Indiana University)

The TRT was being made ready for the joining of the SCT during this period. Kirill Egorov was working fulltime on repairing the cooling and active gas manifold to make it ready for the joining of the two in February, 2006. This consisted of testing the Peek manifolds for gas and liquid leaks, and constructing the newly designed units.

3.2.1.1.5 TRT-SCT in SR

Harold Ogren (Indiana University)

During this period we redesigned the services manifolds for the active gas and the cooling. Curt Baxter redrew the layout for the new Peek manifolds, and the Indiana machine shop machined the templates for bending the new Peek distribution lines. Bryan Martin completed the production of Peek components for the 16 Spine manifolds for each side of the detector. Work was completed on Jan 2, 2006.

3.2.2 Common TRT/ID

## 3.3 M&O Argon

Ryszard Stroynowski (Southern Methodist University)

All barrel Front End Boards are produced, tested and shipped to CERN. Most of them have been installed into the crates on the barrel cryostat. The commissioning of the crates started in Summer 2005 and is proceeding very slowly. The crates power supplies and cooling have not been connected, thus temporary, portable cooling system and temporary power supplies have to be used. At the end of December only 10 crates have been fully commissioned.

About 15% of the Front End Boards have some sort of problem. These boards are pulled out and replacement boards are put in, so the commissioned crate has a complete set of boards with all channels fully functional. The problem boards are collected and will be repaired in Spring 2006. The problems range from warped PCB boards due to uneven stress of the mounted cooling plates, to malfunctioning preamps, shapers or other components.

The commissioning is further slowed down by cabling campaigns limiting access to the detector. In November a badly inserted screw for mounting of the inner detector services generated loss of independent groundings between barrel and tile cryostats. Since the performance of electronics (noise) depends on this ground, all commissioning and installation work was stopped for several weeks until the culprit was found and repaired in December.

The precommissioning of the low voltage power supplies encountered several problems and uncovered a design flaw that has to be fixed before mounting of the units on the detector. The symptoms included cracking of the capacitors and breakdown of the inductors on some of the boards inside the power supply. Extensive design reviews and tests performed at BNL traced the problem to excessive heat generated on the boards. Design changes have been suggested and the negotiations with MDI company for repairs of all the units (including those that are already mounted on the cryostat) have been initiated. Power supplies are now on the critical path for the completion of the LAr detector commissioning. The repairs are expected to be completed by June 2006.

The analysis of the FCal test data showed several surprises, described in the accompanying text. Endcap C has been lowered down to the pit and its integration with extended tile barrel has started. Endcap A is transported to the Point 1 and will be lowered down to the pit in March.

Most of the cryogenics work was concentrated on the installation of cryo lines on the detector and connections of these lines to the refrigerators and pumping stations. The transition to the UNICOS software is schedule for February.

The preparations for the high intensity beam test to check the performance of the Liquid Argon calorimeter in very intense radiation (FCal region) have started in Arizona. Technical run is scheduled for summer 2006 at CERN and full intensity beam test will take place in November 2006 at Protvino.

3.3.1 Mechanical Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commission Cryogenic Connection Lines to the Barrel at z=0 | 10-Jan-06 | -- | 10-Jan-06 | On Schedule |
| Commission Vacuum Pumps, Monitoring etc. for Barrel | 30-Jan-06 | -- | 30-Jan-06 | On Schedule |
| Phase !&@ (Arizona) - Endcap (A+C) cold test in the pit | 15-Jun-06 | [New] | 15-Jun-06 | On Schedule |

3.3.1.1 Pre-Operations and Commissioning

John Rutherford (University of Arizona)

In June of 2005 Rutherford and undergraduate student Brokk Toggerson set up and ran tests on the FCal warm electronics in the EMF at Point 1. This was the same warm electronics used in part of the FCalC cold commissioning in Building 180 in March. Critical help came from Stefan Simion, Henrik Wilkens, Luis Hervas, John Parsons, and, in separate tests of the level 1 trigger path, from Vittorio Paoloni and Bill Cleland. Our run plan was developed in collaboration with Alexandre Savine. One goal was to determine the input impedance of the preamps by plugging precision resistor banks into the baseplane connectors where the pedestal cables normally go. The pigtails have characteristic impedance of 25 Ohms so looking backwards from the preamp input, one should see approximately 25 Ohms. We used resistor banks of 15 Ohms, 25 Ohms, and 62 Ohms and took calibration data, watching how the preamp output (through the shaper) changed with these precision resistors at the input. Preliminary results show that the preamp input impedance tends to be larger than 25 Ohms, some as high as 27 to 28 Ohms. Coupled with earlier measurements of the pigtail impedance via the TDR which showed some pigtails with characteristic impedance well below 25 Ohms there is the potential for rather large impedance mismatch, of order 4 to 5 Ohms. We observed rather large reflections in the region of the feedthrough during our FCal Calibration test beam run in 2003 and during the Combined EMEC/HEC/FCal test beam run in 2004 and this easily explains the cause. For that 2003 test beam run we were short one pigtail (of 64 coax lines) so Victoria gave us an extra. It is comforting that this pigtail had characteristic impedance quite close to the nominal 25 Ohms. So we hope the impedance mismatch in ATLAS will be smaller than in this test beam run where the rest of the pigtails were purchased by Arizona from batches produced by Axon before the production run.

A number of problems showed up during the EMF tests. We thought the earlier problems with the calibration pulser had been fixed. (The calibration pulse rise time was so sharp that slew-rate limitations in the preamp led to non-linearities. We thought these were fixed when we attached 150 pF capacitors across the 50 Ohm output resistor on the pulser to slow the rise-time.) But non-linearities, at least as bad as we had seen earlier, showed up again in the data we took in the EMF. After the June tests we sent the calibration pulser board back to Orsay along with the FCal baseplane. There it was discovered that all the pulsers, not just the FCal pulser, were subject to an instability. A work-around was found for this instability using a feature on the mother boards introduced for the FCal and Orsay now believes the pulsers, including the FCal ones, will work fine. Our next opportunity to test this is in the cavern when the final warm electronics is installed.

Further analysis of the EMF data at Arizona showed up another surprise. The rad-hard ADCs on the FEB, first used on the production boards, have a large differential non-linearity. We see spikes in the noise and calibration spectra which, only after a lot of effort, we were able to trace to the ADCs. Some ADC bins are half as wide as the nominal and others 40% wider than the nominal. We even traced down which bins were the bad ones and the patterns make sense when the technology of the ADC is taken into account. While it is discomforting to see spikes and narrow valleys in the noise spectra, this differential non-linearity probably has negligible effect on any measurement of concern to us. We have spent some time to see if there are diabolical cases where this could be a problem and haven’t found any so far.

The cold commissioning of the FCalA took place in Building 180 in September and the results were analyzed in this quarter. We found a few of the usual problems at the expected low level. But one big problem showed up as well. While filling the EndCap A cryostat with liquid argon a short developed on one of the FCal3A summing boards which took down an entire HV channel feeding about 57 readout channels. In the design of the summing boards we had foreseen a possibility that we would lose an HV channel so we distributed the HV in such a way that the affected readout channels are not clustered together. In this particular case one quarter of the readout channels in one quadrant of FCal3A are dead as a result of this HV short. None of these channels are adjacent and are rather uniformly distributed in a checkerboard pattern throughout the quadrant. So a software correction should be quite effective. Nevertheless we are hoping to fix the problem. First we expected that whatever created the short might float away when the liquid argon was emptied after the cold commissioning. But it didn’t. Next we hope that the supposed debris might fall away in the jostling during transport from Building 180 to Point 1. This transport happened late in January and testing is scheduled for early February. So we don’t know the answer yet. But we have prepared for the worst. We have constructed a device to introduce short electrical pulses down the HV lines in hopes of burning the debris off the board. And we have done extensive testing using a spare summing board to determine the limits where we might do permanent damage to the summing board itself. It is certainly possible that the debris is so robust that it can carry the current in our pulse without evaporating. In that event we will be stuck with this failure and will be forced to implement software corrections.

There is good progress on the test bench for the FCal electronics chain. Four readout channels, each with three gains, are being constructed. The part of the warm electronics which takes the ADC data into a digital pipeline and then reads it out to the online computer has been completed. Also a test board which outputs patterns to simulate the ADC output has been produced. Testing should start in January. It is hoped to have the analog parts finished and ready for testing in early Spring. It is possible that others in the liquid argon community will find our scheme useful for small-scale tests and that we will be providing this warm electronics to other groups once it’s utility proven.

In summer 2005 it was discovered that there was a problem with the geometry description of the FCal1 in the simulation, and perhaps in the analysis code. We have had several rounds of discussion within a fairly wide community and, as a result, several other problems and inconsistencies in the geometry were discovered and fixed. (None of these problems are in the hardware or in our description of the hardware, but in the descriptions in the standard ATLAS software.) But some problems or disagreements still remain. We take this as very productive because we expect that, when the dust settles, we will have enhanced confidence in the mapping of the FCal channels from the physical electrodes to deep within the ATHENA code.

3.3.1.2 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commissioning of EndcapC in the Pit Complete | 1-Feb-06 | 1-Feb-06 | 1-Jun-06 | Delayed (See #1) |
| Commissioning of Pit Cryogenics Complete | 1-Mar-06 | -- | 1-Mar-06 | On Schedule |
| Re-commissioning Underground Complete | 1-Mar-06 | -- | 1-Mar-06 | On Schedule |

Note #1  Schedule change put higher priority on cryogenics for toroid and solenoid than for the endcaps.

John Sondericker (Brookhaven National Laboratory)

Barrel Cryostat Operations and Cryogenic Operations

During the last three months of the reporting quarter year the Barrel Cryostat was moved to its final, center position on the ATLAS detector rails.

Work continues to connect cryogenic transfer lines and remote controls in preparation for cool down and fill of the Barrel Cryostat in the beginning of February as the schedule now stands.

3.3.1.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Barrel HV Operations (SB) | 1-Feb-06 | -- | 1-Feb-06 | On Schedule |

John Sondericker (Brookhaven National Laboratory)

Cryogenic Maintenance

Work to tune up and recalibrate the Quality Meters in the last quarter of the year never came to pass because all hands were mustered to complete Barrel Cryostat installation work in time for the scheduled cold testing. Word was left with CERN Experimental Cryogenics group that they should notify us at BNL when they have time to allow us to recalibrate the Quality Meters.

3.3.2 Electronic Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of the First Full Crate on the Truck Linked to USA15 | 30-Dec-05 | -- | 30-Dec-05 | On Schedule |
| Complete Commissioning of Barrel Optical Links (SMU) | 1-Mar-06 | -- | 1-Mar-06 | On Schedule |
| Complete Commissioning of EndcapC Optical Links (SMU) | 1-Mar-06 | 1-Mar-06 | 1-Jun-06 | Delayed (See #1) |
| Operation of all Crates on the Truck | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |
| Operation of all Crates on the Truck stand alone | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |
| Commissioning of Low Voltage Power Supplies on the Barrel Complete | 1-Jun-06 | [New] | 1-Jun-06 | On Schedule |

Note #1  Schedule change postponed the installation of electronics on the endcaps for after the magnet tests are complete.

3.3.2.1 Pre-Operations and Commissioning

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Commissioning of Barrel Receiver System (Pitt) | 15-Nov-05 | 15-Nov-05 | 15-Apr-06 | Delayed (See #1) |
| Completion of Documentation of Level 1 Trigger Interface for Liquid Argon and Tile Calorimeters (Pitt) | 1-Dec-05 | 1-Dec-05 | 1-Mar-06 | Delayed (See #2) |
| Complete Commissioning of Barrel Receiver System (Pitt) | 31-Dec-05 | 31-Dec-05 | 31-May-06 | Delayed (See #3) |
| Maintenance Procedures for Receiver Modules Complete (Pitt) | 31-Dec-05 | 31-Dec-05 | 15-Apr-06 | Delayed (See #4) |
| Start commissioning of EndcapC Receiver System (Pitt) | 1-Jan-06 | 1-Jan-06 | 15-May-06 | Delayed (See #5) |
| Complete Commissioning of EndcapC Receiver System (Pitt) | 1-Mar-06 | 1-Mar-06 | 15-Jun-06 | Delayed (See #6) |
| Start Commissioning of EndcapA Receiver System (Pitt) | 1-May-06 | 1-May-06 | 30-May-06 | Delayed (See #7) |
| Complete Commissioning of EndcapA Receiver System (Pitt) | 30-Jun-06 | -- | 30-Jun-06 | Delayed (See #8) |

Note #1  Need all FEC crates commissioned

Note #2  Documentation almost complete. Documents need to be updated with final versions of hardware.

Note #3  Need all FEC crates commissioned

Note #4  Need all FEC crates commissioned to finalize procedures

Note #5-8  Need all FEC crates commissioned

John Parsons (Columbia University (Nevis Laboratory))

Half of the 32 crates on the EMBarrel have been pre-tested using the temporary DAQ system. The first FE crate to BE crate connection using the final cables has been performed, and will be used during the Expert Week in January.

Equipping and testing of the 54 HEC FEBs is proceeding smoothly.

The setup at Nevis of the test system and environmental chamber to be used for FEB lifetime testing was completed. This test will get underway in spring, after the pre-production FEBs to be used are shipped back from CERN.

Francesco Lanni (Brookhaven National Laboratory)

Final commissioning of the receiver system require the installation of the FEC's and the final trigger cables completed and connected. Presently testing of the trigger paths are done with the same set of receivers and completed trigger cables.

All receivers are shipped to CERN and installed in their crates.

A problem was found in the transition boards for all detectors other than the barrel. The trigger cable ground for one input cable for the receiver (4 trigger cables/per receiver are installed) has been found to be connected to the receiver ground. A possible solution has been determined and will be done at CERN (i.e. no need to ship these transition boards back to Pittsburgh).

Approximately half of the 32 crates of EMBarrel readout electronics have been pre-commissioned using a standalone test setup. Work has re-started after a break of several weeks during the move of the cryostat to its final position around the IP. The first of the final connections from Frontend to Backend electronics is being made, in anticipation of an Expert Week planned for late January.

The HEC FEBs underwent testing and pre-ops using a dedicated setup in B180 developed for this purpose.

In parallel, work continues at Nevis to set up the environmental chamber and test system that will be used to perform the longterm lifetime test of the FEB.

Pre-commissioning of 8 LVPS installed on the EMBarrel completed. It was decided to install and temporarily commissioning 8 LVPS to allow for a smooth installation of the Front-End readout electronics while awaiting retro-fitting the LVPS in production.

Installation and phase-1 commissioning of the Crate Monitoring system (FEC-DCS) completed. DCS software development and integration in Atlas DCS in progress (D. Damazio).

Commissioning of standalone minimal cooling system at CERN completed.

3.3.2.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Long Term Burn-in of FEBs at BNL Complete | 1-Jun-06 | -- | 1-Jun-06 | On Schedule |

3.3.3 Beam Test

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of the first production FEB in a System Crate | 30-May-06 | -- | 30-May-06 | On Schedule |

3.3.3.1 FCal Hadronic Tail Measurement

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FCal Electrical Test Bench Completed (Ariz) | 20-Apr-06 | 20-Dec-05 | 20-Apr-06 | Delayed (See #1) |

Note #1  This project is moving along nicely but there are some aspects and extensions which will make it hard to determine the end. We hope to have a version available for preliminary tests in April 2006.

John Rutherford (University of Arizona)

In the design phase of the liquid argon calorimeters each of the sub-systems conducted radiation testing on the components to certify that they would survive 10+ years of exposure and would not poison the liquid argon. But for the FCal it wasn’t possible to find a facility which could provide the equivalent of 10 years of exposure because the FCal is in such an extreme radiation environment compared to the other calorimeter systems. During early LHC upgrade meetings it was proposed to conduct a test at Protvino on their 70 GeV proton accelerator. Arizona realized that this would be an opportunity to conduct definitive tests on the FCal for the full luminosity of the nominal LHC as well as the upgraded LHC. For this Protvino test we have designed a small version of the FCal1 module dubbed the FCalchik. The Russian suffix implies the diminutive. Half of the module has the conventional electrodes and the other half beside it has 100 micron gaps (2.5 times smaller than the nominal). So by moving the cryostat sideways we can direct the beam onto either the model of the existing FCal1 or onto a version better suited to the upgraded LHC. It is planned to have a technical run at CERN in the summer of 2006 and a first run at Protvino in November 2006, if the accelerator schedule allows. At Protvino, two types of tests are foreseen separately on the model of the EMEC, the HEC, and the FCal. The first test would run the beam at an intensity to match what will be seen in the worst position in the module at the upgraded LHC. The second type of test would be to run the beam at such a high intensity that we could match the integrated exposure seen in 5 years of running at the upgraded LHC in one week at Protvino. This latter type of test presents a number of severe challenges, particularly for the FCal. Foremost among these is cooling. The heat deposited in the FCalchik will be so large that special cooling features will be required. We have designed cooling channels into the FCalchik through which we intend to flow liquid nitrogen. This then confounds the usual methods used to regulate the temperature inside the cryostat so we will have to pioneer modified techniques. We plan tests at Arizona to develop a stable method for this regulation. Another severe challenge is to provide the HV current to the electrodes. This seems so far removed from the realm of reason (several amps) that our fall back position is to turn the HV down so far that currents in the range of tens of milliamps are drawn. So the interpretation of the long-term testing of the FCalchik will be compromised by this limitation. A few lesser challenges can probably be overcome. It is worth pointing out that this test will be pushing the limits of liquid argon calorimetry in a direction that could prove useful at future hadron colliders, should we succeed. We also hope to test some of the predictions of the positive ion buildup calculations.

We have started a big push to get out publications on past test beam runs. A long paper on our 1998 tests of our engineering prototype is nearly ready for review within the FCal community. And we have organized a month-long workshop at Arizona in March 2006 where we hope to finish off some of the analyses of the 2003 Calibration test beam run of the FCalC modules. In preparation for this workshop we are conducting bi-weekly conference calls during which we have been defining acceptable analysis procedures.

3.3.4 CERN Living Expenses

3.3.5 CERN Common Costs

## 3.4 M&O Tile

3.4 Subsystem Manager's Summary 	Larry Price (Argonne National Laboratory)

This period saw the completion of stand-alone (Mobi-Dick) certification of drawers before the start of certification by sectors of eight modules.  Sector certification was started in late November, discovering some additional individual faults in drawers, necessitating repairs, but also revealing problems in the operation of the low voltage power supply that needs further investigation.  In addition, it remains the case that electrical noise from the low voltage power supplies is compromising the performance of the TileCal readout. Work is in progress to understand and remove this noise but production is continuing with the present performance. The DAQ software for the drawer at Chicago was updated to make its maintenance easier and functioning more effective. A set of 45 repaired 3in1 cards was tested with the revised system and shipped to CERN.  Much work was done on testing and validation of cables and fibers both before and after installation by Technical Coordination.  The cryostat and MBTS (Minimum Bias Trigger Scintillator) counters were fabricated, tested and shipped to CERN for installation. Numerous tests were conducted on the MBTS prototypes and the design was altered in order to increase the light yield. A detailed plan was developed for the installation effort for all of the scintillation counters in 2006. The forward moderator plates (boronated polyethylene) were machined and shipped to CERN for installation in 2006.  Data were entered in the CERN MTF (Material Tracking Folders) system documenting the Tilecal components installed underground.  Database software was prepared for the onset of module by module commissioning toward the end of the period. ITC pre-installation work is completed. Post-installation work will take place in the next quarter.  Progress was made in planning ITC scintillator calibration.

3.4.1 TileCal - Specific Costs

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Module-by-Module Commissioning of Barrel | 1-Dec-05 | [New] | 1-Dec-05 | On Schedule |
| Complete Module-by-Module Commissioning of Barrel | 30-Apr-06 | [New] | 30-Apr-06 | On Schedule |
| Complete Initial Calibration of Barrel | 31-May-06 | [New] | 31-May-06 | On Schedule |
| Begin Module-by-Module Commissioning of Extended Barrels | 15-Jun-06 | [New] | 15-Jun-06 | On Schedule |

3.4.1.1 Pre-Operations 	Joey Huston (Michigan State University)

Work on ATLAS M&O proceeded at both Michigan State University and at CERN for the period of October 2005 through December 2005. The technical staff involved were Mike Nila (senior technician) and Ron Richards (engineer/designer) and the physicists were Joey Huston and Bob Miller. Ron Richards made 2 trips to CERN during this time period with each trip lasting 2-3 weeks. While at CERN, Ron installed light covers for the TileCal modules and installed vapor liners (fabricated at MSU) between the barrel and forward liquid Argon calorimeters and the TileCal calorimeters. He also drilled and tapped mounting holes for the cryostat scintillators as well as preparing EBA and EBC for their transport into the pit.

At MSU, the cryostat and MBTS (Minimum Bias Trigger Scintillator) counters were fabricated, tested and shipped to CERN for installation. Numerous tests were conducted on the MBTS prototypes and the design was altered in order to increase the light yield. A detailed plan was developed for the installation effort for all of the scintillation counters in 2006. The forward moderator plates (boronated polyethylene) were machined and shipped to CERN for installation in 2006.

Larry Price (Argonne National Laboratory)

Data were entered in the CERN MTF (Material Tracking Folders) system documenting the Tilecal components installed underground.  Database software was prepared for the onset of module by module commissioning toward the end of the period.

Module by module commissioning began in the latter part of November.  Faults were found in about 15% of the drawers tested.  Leon Reed from Argonne was joined the Clermont group on the team making repairs to drawers.  Detailed diagnosis was made with the portable DAQ system (Mobi-Dick), which was also used to determine drawer performance after repairs were made and before repeating the official commissioning process. Difficulties were discovered in the operation of the low voltage power supplies during the initial steps in commissioning and these are being investigated.  Use of COOL and other databases was exercised during the early commissioning runs.  The chain of programs was further exercised by using performance monitoring code in Athena.

Technicians commuting from Argonne worked on testing and validation of cables both before and after installation by Technical Coordination.  Samples of new trigger cables were received and tested.  Two expert weeks were held during this period to advance specific aspects of readiness for commissioning.

Steve Errede (University of Illinois, Urbana-Champaign)

Dave Forshier - one of our UIUC technicians continued to work full-time at CERN along with other TileCal technicians on installation & the cabling up & testing of ATLAS TileCal, under the daily supervision of Bob Stanek & Irene Vichou. He came back to the U.S. in mid-November, after working at CERN for 3 months.

Irene continued with her work at CERN, as the coordinator of the Services Installation and testing.  She is responsible for the generation and up-to-date maintenance  of the cabling database for TileCal (Oracle application interfaced through Excel tables) so that the installation crew/ supervisors have the necessary information to locate any/all cables/pipes etc. and the possibility to store the results of controls/checks before giving the final OK for operation.

James Pilcher (University of Chicago)

(a) Repair and Maintenance of FE Electronics

We maintain an electronics drawer at Chicago for testing and diagnosing the various PCBs in the drawer. During this quarter the DAQ software for this drawer was updated to make it’s maintenance easier and functioning more effective. A set of 45 repaired 3in1 cards was tested with the revised system and shipped to CERN.

New low voltage power supplies, prepared by the Prague group, are being installed in the calorimeter modules as part of the commissioning process. During the commissioning campaign in December, front-end electronics in 4 drawers was damaged by over-voltage from the supplies. This will require substantial repair work in the months ahead.

(b) Commissioning and Integration work

In an earlier calendar quarter transition boards were built at Chicago to connect the Tile Calorimeter trigger cables to the coincidence boards for the cosmic ray trigger. Now the Level 1 receiver boards start to become available and the trigger cables will be connected to them.

During the present quarter 8 additional transition boards were built at Chicago to connect outputs from the receiver boards to the trigger boards. This requires different connectors and different signal routing. During the months ahead the full number of receiver boards should be installed and the new transition boards will allow us to work directly with their outputs and to leave the input trigger cables untouched.

Work was also done to upgrade the firmware in the trigger boards to facilitate non-back-to-back triggers. This capability is needed to provide a cosmic ray trigger useful for the endcap calorimeters.

A set of flow meters and a readout panel were prepared at Chicago and sent to CERN for use with the cooling water for the drawer electronics.

A team of 5 Chicago people continue in full time residence at CERN working on commissioning and integration. This team consists of one postdoc, one graduate student, two BSc technical assistants, and one full time electronics technician. They were supplemented by periodic visits of faculty members and research personnel based in Chicago.

In November 2005 the barrel calorimeter was moved to its final location, centered on the interaction point. Work is underway to connect calorimeter modules to the off-detector services in USA15. This will continue for many months. David Miller, a Chicago BSc technical assistant is in charge of a team responsible for making the connections to the calorimeter modules. As of late December 2005, the first full sector of 8 modules had been connected to services on the C side.

It remains the case that electrical noise from the low voltage power supplies is compromising the performance of the TileCal readout. Work is in progress to understand and remove this noise but production is continuing with the present performance. The supplies are needed for commissioning the rest of the system.

(c) Calibration and Monitoring

Calibration and monitoring is an integral part of the commissioning process. Martina Hurwitz, a Chicago graduate student, is co-leader of a team responsible for processing and reviewing the calibration data taken after a calorimeter module is connected to services in USA15. She has set up monitoring histograms and reviewed all the calibration data collected to date.

Kaushik De (University of Texas at Arlington)

ITC pre-installation work is completed. Post-installation work will take place in the next quarter. UTA graduate student, Hyeonjin Kim arrived at CERN and is permanently based here. She will work on ITC related pre-operations tasks. She is getting trained and learning TileCal operations with the Barrel groups.

3.4.2 Calibration & Monitoring

3.4.2.1 Pre-Operations 	Kaushik De (University of Texas at Arlington)

Some progress was made in planning ITC scintillator calibration. Armen Vartapetian is looking at CTB data to understand performance. He is also studying QC issues for TileCal. We are also getting involved in commissioning database issues.

3.4.3 Tilecal System Common Costs

## 3.5 M&O Muon

3.5 Subsystem Manager's Summary

Frank Taylor (MIT)

Installation and Phase II commissioning of chambers for the BW-Side C and the EIL4 stations continued in B180 at CERN. At the end of December 05, the mechanical integration of four BW sectors was completed. In addition, two EIL4 stations (EIL4A13 and EIL4C13) were completed and one (EIL4A13) was installed in the ATLAS cavern.

The US group is organized with specific responsibilities assigned and is working well together and with the CERN and Pakistani teams.

The Michigan group continued to lead the electrical testing of completed sectors and stations (Phase II Commissioning). Three DAQ stations are employed to commission the EIL4 stations, the chambers in the current BW small and BW large sectors. Data collected are ported to the commissioning database. The UoW team is responsible for the mechanical integration of the EIL4 stations and the B-sensors for all the chambers. The commissioning of alignment components is covered by the Brandeis and CERN alignment group, who also oversee the photogrammetry of chambers and sectors. All members (including Harvard and MIT) contribute to the preparation of chambers for installation and their installation on the support structures.

A very fruitful workshop on the calibration and monitoring of MDT EC chambers was held in early November at the University of Michigan with broad participation of the US ATLAS Muon Group. It was decided at the workshop to have the UoM group organize the calibration and monitoring of the detector during data taking. The BMC group and others will also participate and various specifics of collaboration were discussed.

3.5.1 MDT Pre-operations, Operations & Maintenance

3.5.1.1 MDT Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete all 16 EIL4 MDT-TGC Assemblies | 14-Mar-06 | 14-Mar-06 | 14-Apr-06 | Delayed (See #1) |
| Start SW Side C Assembly in B191 | 1-May-06 | 1-May-06 | 1-Oct-06 | Delayed (See #2) |
| Complete all 16 Sectors BW-C | 30-Jun-06 | -- | 30-Jun-06 | On Schedule (See #3) |
| Start of Phase 3 Commissioning in UX15 | 1-Aug-06 | -- | 1-Aug-06 | On Schedule (See #4) |
| Complete 12 Sectors BW-A | 30-Sep-06 | -- | 30-Sep-06 | On Schedule (See #5) |
| Pre-operations of MDT Chambers - Phase 2 (Boston) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| Pre-operations of MDT Chambers - Phase 2 (MIT) | 30-Sep-06 | -- | 30-Sep-06 | On Schedule |
| Complete all 16 Sectors BW-A (Additional 4) | 15-Jan-07 | -- | 15-Jan-07 | On Schedule (See #6) |

Note #1  Delayed. Two EIL4 stations (EIL4A13, EIL4C13) are now installed in UX15, two are ready for installation (EIL4A05, EIL4C05) and four are being prepared for installation

Note #2  The SW is significantly delayed - primarily due to the delays of integrating the ECTs. The plan for the SW construction is to start the tooling construction and commissioning in B191 after ECTA exits for its 80-degree cold test in Jun-06. Following the completion of ECTC in late summer 06 the SW team will start installation of chambers in the first SW.

Note #3  The progress-to-date extrapolates to this completion date. The top watched item is the completion of the delivery of the last small wheel sector.

Note #4  Scheduled date is the best estimate at this time. However, the TGC1 C-side wheel has to be installed first and many items of tooling need to be designed, constructed and commissioned. Discussions have started with the ATLAS commissioners and within the US community on how to organize this task.

Note #5  A plan has been made and is being closely watched that has the completion of Side A at the end of Sep-06. In order to succeed the timely delivery of aluminum for the sectors is needed as well as additional storage space in B180.

Note #6  Schedule believed to be possible, but means are being taken to accelerate the completion date to 30-Sep-06 in order to clear space for another TGC wheel assembly station.

Edward Diehl (University of Michigan)

Three DAQ stations are in use in B180 - one each for small sector, large sectors, and EIL4. Electronics tests are done using standard scripts to drive the DAQ. A operator's manual has been written. We also installed PVSS software on all DAQ carts to permit readout of temperature sensors and other DCS data (with the help of Joe Rothberg of Seattle). A 4th station is being set up as a spare.

o UM personnel at CERN continued work on MDT sector construction and testing along with personnel from other US ATLAS institutions. Resident at CERN are Jay Chapman, Dan Levin, Claudio Ferretti, Manuela Cirilli, and Andrew Eppig. In December, Tiesheng Dai joined them. Bing Zhou, Curtis Weaverdyck, and Edward Diehl did some short trips to contribute to sector commissioning. Jay Chapman and Teisheng Dai are focused on electronics installation and testing, and Dan Levin is focused on gas system installation and testing. Jay has coordinated the sector cable fabrication, testing, labeling, and cataloging for the DB. The cables required for each sector are 5 HV, 5 LV, 5 pairs of CANbus cables, and 5 optical fiber cables.

o Our group helped with the installation of the small sector test stand, setting up the required supply of chamber gas, and electrical power. In the Oct-Dec period 2 large sectors (C09, C03), and 2 small sectors (C04, C02) were assembled and tested. They had to deal with a few problems found on chambers, such as a some gas leaks and hot channels. In most cases these were repaired, though a few hot channels had to be disabled by cutting the HV connection to the tube.

o Completed sectors are tested in a variety of ways:

- leak check

- HV check

- many tests of electronics functionality

- long-term electronics burn-in test

- spacer frame tension rods are adjusted as needed to remove chamber bow

- mechanical measurements (mainly done by other groups, but included for completeness).

o Jay Chapman and Claudio Ferretti worked on the design and implementation of the phase II database to store information on sector parts and tests mentioned above. See Ferretti talk in http://agenda.cern.ch/fullAgenda.php?ida=a057827 for more details on the phase II DB.

o We began the process of moving our chamber and commissioning data to CERN databases. There are 2 databases at CERN: MTF for part IDs of all hardware which is sent to the pit and Oracle for all other chamber info. Edward Diehl, Manuela Cirilli, and Claudio Ferretti are working various aspects of this project. Edward Diehl has supplied all the chamber parts IDs for the MTF database. Manuela is coordinating the transfer of other chamber data to the CERN Oracle database as well as working on the COOL database interface, by which the Athena analysis program interacts with the Oracle DB. Claudio Ferretti is supplying the chamber commissioning test data for the DB. This work will continue over a period of time as more chambers complete the final commissioning process at CERN.

o Michigan hosted a very successful US Calibration workshop on Nov 4-5, 2005 with 50 participants from 11 ATLAS institutions. The agenda and talks for this meeting can be seen at http://agenda.cern.ch/fullAgenda.php?ida=a056852. The meeting covered the full range of muon system calibration: CSCs, MDTS, alignment, magnetic field, as well as calibration software and computing issues.

A consensus was reached at this meeting that Michigan should spearhead a US MDT calibration center. This center would calibrate muon data on a daily basis using a special calibration data stream from CERN. Michigan would utilize both local computing resources, and also those at the Tier-II center at Boston for this work. A follow-up meeting is planned in 6 months.

3.5.2 CSC Pre-Operations, Operations & Maintenance

3.5.2.1 CSC Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Installation & Phase 11 Commissioning on SW in Bldg 191 | 1-Jun-06 | -- | 1-Jun-06 | On Schedule |

3.5.3 Alignment System Pre-Oper.'s, Operations & Maintenance

3.5.4 Muon Endcap Common Costs

3.5.4.2 Muon Endcap Common Costs Operations

Frank Taylor (MIT)

A model has been developed to estimate the cost of gas needed to commissioning BW sectors and EIL4 stations. At the beginning of March 06 the consumption of gas is about 20% of the model.

3.5.5 Monitoring & Calibration

## 3.6 M&O Trigger

3.6 Subsystem Manager's Summary

Andrew Lankford (University of California, Irvine)

The Pre-series system was used for commissioning of the pre-series Region-of-Interest (RoI) Builder, of TDAQ software, and of the Tile Calorimeter. Software commissioning included Monitoring, Event Filter Dataflow, and High Level Trigger (HLT) algorithms. In addition to support for TileCal commissioning, detector support activities included Monitoring and support for new single-board computers. Software maintenance involved improvements or updates to a number of software components, including the Readout Subsystem (ROS), Configuration, Monitoring services and HLT Steering. Operations activities included operation of the Pre-series system, and system and network administration.

3.6.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Operations Supervisor RoI Builder Support | 1-Mar-06 | -- | 1-Mar-06 | On Schedule |

Bernard Pope (Michigan State University)

Comune took part to the final review for the HLT Steering requirements at the TDAQ week in Mainz. The review document has now been approved and Comune has started looking into the implementation of those new requirements in view of the milestones set by release 12.0.0 (DC3). In particular, he has been developing new features in the PESA Core Software to support physics analyses off AODs. These data for the first time, thanks to these new features, will include trigger information and will deliver the trigger decision to the physics analyses. Other features pinpointed by the summer 2005 "Steering Review" include the changes in the persistency mechanism in the Steering, needed for release 11.0.x (which is used as the validation release) and will go into release 12.0.0 (due at the end of February 2006). This release is going to be used for the DC3 production where the new features are needed to perform combined Physics/Trigger studies.

At the same time Comune has kept providing support for the PESA software commissioning at point 1. It is now possible to run Tile algorithms on a subset of the real Tile detector installed in the ATLAS pit using the PESA software coming with release 11.0.0.

Werner Wiedenmann (University of Wisconsin, Madison)

Software Commissioning:

For commissioning and exploitation of the Pre-series system at Point 1 with HLT algorithms, a setup was run on the preseries machines using eight ROS Emulators, one Level-2 Supervisor, and one Level-2 Processing Unit. An installation based on offline release 10.0.6 was used together with preloaded bytestream data containing Level-1 preselected single muons, single electrons and jets. The algorithm setup contained electron (T2Calo), muon (muFast), and inner detector (IdScan, TrigSiTrack, TRTxK) selection algorithms which were run together in a common selection menu. Instrumentation data were taken for different configurations to evaluate framework overheads, network transfer times, and algorithm processing times.

TDAQ Support:

Together with developers from the TileCal group a HLT Level-2 TileCal selection algorithm (TrigTileMuId) was prepared for readout tests in Point 1 (P1) in 2006. The setup is based on offline release 11 and was tested on preloaded real data taken in an earlier TileCal commissioning run.

Robert Blair (ANL)

Hardware Commissioning:

Jim Schlereth has been in consultation with G. Unel and P. Werner as they begin to set up the RoIB system at Point 1. Some minor software patches were needed to repair bugs that became evident and advice on abnormal conditions was offered. Updated boards which fix some problems that were encountered during testing at ANL have been shipped to CERN. The old, unimproved, boards have been returned to ANL for updates.

3.6.1.3 Programming Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of a multi-node test bed for integ/testing/debug & performance Optimization of HLT code (Wisc) | 30-Sep-06 | [New] | 30-Sep-06 | On Schedule |
| Support of HLT SW installation in point 1(HLT installation image) (Wisc) | 30-Sep-06 | [New] | 30-Sep-06 | On Schedule |

Andrew Lankford (University of California, Irvine)

Pre-Ops Software Commissioning

Unel and Stancu, with the Measurement Analysis Group, continued investigating the performance of the Pre-series system and Dataflow software, including studies of fault tolerance and the impact of monitoring. Many other software components were also tested on the Pre-series system. Kolos organized and coordinated tests for Monitoring software. Results are being analyzed, including studying the impact of Monitoring on the main data flow. Negri studied the Event Filter Dataflow. Wheeler studied the efficiency of the protocols into and out of the Event Filter for very small events (as will be present during detector commissioning).

Pre-ops Detector Support

Kolos continued to lead the Monitoring group. He reported Online Monitoring plans at numerous ATLAS meetings and reviews.

Unel connected the TileCal barrel section to the Pre-series TDAQ system. Data was taken with sixteen Readout Links using the RoI Builder. The TDAQ system was able to take data as fast as the TileCal RODs would allow.

Unel adapted the diskless booting scheme to the newest single-board computers used by the detector systems.

Pre-Ops TDAQ Support

Stancu fixed a bug in the implementation of the UDP message passing software which prevented the development of the ROBIN network interface based on UDP.

Wheeler configured the HLT software for use on the performance testbed in Bldg. 32.

Pre-ops Operations

Unel coordinated operation of the Pre-series system. Stancu participated in network operations of the Pre-series system.

Pre-ops Hardware Maintenance

Stancu worked on the frequency of internal updates of SNMP counters in HP switches

3.6.2 Operations

Bernard Pope (Michigan State University)

New RoIB cards and a new version of the EPROMs were received from Argonne and installed in the USA15 counting room. The old RoIB cards were shipped back to ANL. A new 9U VME crate for the RoIB setup at Argonne were received from WIENER and sent to ANL. The stand-alone tests of the RoIB and L2SV were run both from ANL and from CERN. Ermoline has obtained an account on the Point 1 computers and is setting up an environment in order to test the RoIB. The RoIB is equipped with a second output HOLA card on the RoIB Builder card and the second L2 Supervisor with one more FILAR input card. This gives the possibility of running the ROIB with two L2 Supervisors. Ermoline participated in the RoIB FDR/PRR (Final Design Review / Product Readiness Review). The RoIB has been prepared for integration with MUCTPI of the L1 trigger. The ODIN LDC card was installed on the RoIB Input card and connected to the output of the MUCTPI. Ermoline reported on the status of rack DCS during the DAQ/HLT-I Coordination meeting. The rack DCS installation in SDX1 is now planned for January 2006, when the CANbus power crate will be delivered.

3.6.2.3 Programming Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support event read out library for detector commissioning & Cosmic Run (Wisc) | 30-Sep-06 | [New] | 30-Sep-06 | On Schedule |
| Support for HLT Application Framework for detector commissioning & Cosmic Run (Wisc) | 30-Sep-06 | [New] | 30-Sep-06 | On Schedule |
| Support of Level 2 Framework for detector commissioning & Cosmic Run (PSC) (Wisc) | 30-Sep-06 | [New] | 30-Sep-06 | On Schedule |

Andrew Lankford (University of California, Irvine)

Ops – Software Maintenance

Kolos developed a new implementation of the Error Reporting Software (ERS) component, incorporating more information on errors. He incorporated advanced facilities for information definition in the Information Services (IS) component and updated the IS documentation. He also improved the performance of the Histogramming components.

Unel began adapting both Readout Subsystem and Configuration software, for both 32-bit and 64-bit CPUs, to a new C/C++ compiler. He modified the database generation scripts and added functionality for TDAQ operations with multiple concurrent partitions.

Ops - Operations

Unel coordinated system administration activities at Point 1 and in TDAQ test labs.

3.10 M&O Technical Coordination

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commission First Mini-van used for Calorimeter Installation | 30-Apr-05 | -- | 30-Apr-05 | Completed |
| Commission Round Special Scaffolding used for Calorimeter installation | 30-Jun-05 | -- | 30-Jul-06 | Delayed (See #1) |
| Commission Minivans used for ID Installation | 30-Sep-05 | -- | 30-Sep-05 | Completed |
| Commission Round Scaffolding on the Tile Front Face | 30-Sep-05 | -- | 30-Jul-06 | Delayed (See #2) |
| Finish Mechanical Assembly of the Barrel Toroid | 30-Sep-05 | -- | 30-Sep-05 | Completed |
| Installation of the BCAM System, on the Barrel Calorimeter | 30-Sep-05 | -- | 30-Sep-05 | Completed |
| 30% Barrel Muon Installed | 30-Mar-06 | -- | 30-Mar-06 | On Schedule |
| Finish Round Scaffolding Production | 30-Mar-06 | -- | 30-Mar-06 | On Schedule |
| Complete EC-C Mechanical Assembly | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |
| Start Big Wheel Assembly Side C | 30-Apr-06 | -- | 30-Apr-06 | On Schedule |
| Barrel Toroid Field Test | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Complete EC-A Mechanical Assembly | 30-Jun-06 | -- | 30-Jun-06 | On Schedule |
| Solenoid Field test | 31-Jul-06 | -- | 31-Jul-06 | On Schedule |
| Install Barrel Part of Inner Detector | 30-Aug-06 | -- | 30-Aug-06 | On Schedule |
| 100% Barrel Muon Chambers Installed | 31-Oct-06 | -- | 31-Oct-06 | On Schedule |

Note #1  Prototype was tested. Currently in production. Will need the EC to commission them.

Note #2  Prototype was tested. Currently in production. Will need the EC to commission them.

David Lissauer (Brookhaven National Laboratory)

End-cap Toroid:  The problem with the helium cooling tubes which had been discovered in November 2005 was investigated. Unfortunately the situation with the cooling tubes was serious and they will have to be replaced.  The cooling tubes are square on the outside and a small diameter cavity on the inside. They were made of 6 meter long sections and that were joined together to make the full length of pipes that are up to 40 meter long. The pipes were tested and were found to be good after they were joined together.  At that point they were welded onto the EC Toroid heat shield.  At that stage is seems that too much heat was applied and the tubes were damaged. Lots of small cracks appeared and the tubes cannot hold the pressure. The operation will start in January 2006 and the estimated delay is in the order of two months.

End-cap Calorimeter Installation:  The EC calorimeter has been placed on the 22 EC tile modules. The placement in X,Y seem to have gone well. The Z position of the LAr relative to the tile had to be shifted by 9 mm (LAr further out in Z). The move is due to the fact that the LAr support that is attached to the tile could not be positioned well enough. Meetings took place with Technical Coordination (TC) engineers to understand the implications to the placement of other detectors. There are a few options that we are investigating. We can try to move the Tile in putting the LAr in nominal position or place the Tile in nominal position and the LAr will then be out in Z. The final solution will probably be somewhere between these two extreme options. Discussions took place to decide how we would like to install the EC-A. i.e. should we try to reproduce the same misalignment as on side C so that the experiment will be as symmetric as possible.

Muon Chamber Installation:  The BMS (Barrel Middle Small) chambers in six sectors have been installed and we still have to install the chambers in Sectors 4 and 6. In the mean time preparation for the installation of the barrel chambers has gone in to high gear with the arrival at the hall of the movable platform that will be used for the chamber installation. The movable platform will be assembled next week and the plan is to start the installation of the BOS (Barrel Outer Small) chambers before the end of 2005. The installation of the chambers will start at an increased rate early 2006.

The muon installation platform (20 meter long, 3 meter wide) made by ALIMAK was installed in the hall.  Meetings with the CERN safety group took place to discuss the operation mode of the platform and to obtain a European Certificate of Compliance.

Barrel Toroid Magnet:  During the fall of 2005 the magnet team reported on the results of the release of the jacks that supported the Barrel Toroid warm structure of the barrel Toroid magnet.  The expectation from the finite element calculation is that the structure will sag by 22mm.  The engineers recommended that we assemble the structure assuming 30 mm sag to take in to account a few additional mm expected due to expected imperfection in the shims.  The measured sag due to the barrel Toroid weight alone was 18mm.  We expect an additional 8-9 mm sag due to the weight of the muon chambers and services. We could see additional few mm sag due to creep.  So all in all this is a great achievement by the magnet team.

In late 2005 the committee was able to report that the work on connecting the Cryo-ring and on the last sector connection was moving forward.  The bus bar delivery is now on the critical path for performing the first magnet test.

Barrel Calorimeter Services:  Connections to the Barrel Calorimeter of the water supply and cables has started. The Inner Detector pipes are nearly done on the surface of the calorimeter.  Liquid Argon and Tile trigger cables are being connected all the way to the counting room. The rate is still low – but the plan is well defined now and at this stage is not in the critical path.  One worrying aspect that the LAr calorimeter that was supposed to be isolated from the tile and the ID seems to have a short at some point. A small team of experts is looking for the reason the grounding rule has been violated – but up to now the reason has not been found.

Rail and Barrel Calorimeter Positioning:  I gave a report to the TMB on the excellent results of the placement of the Barrel Calorimeter at Z=0. The survey team gave a report on their work during the move and the nice results obtained by the Hydrostatic system – it measured the floor movement of fraction of a millimeter during the move and slow sinking of the floor the following days at the rate at the level of microns.  We signed off on the calorimeter position and connections of the LAr services which have started. The solenoid magnet chimney is in position and the team from Japan (KEK/Toshiba) will come to make the connections between the solenoid/chimney and control dewar.

LHC Schedule:  Miikka Kotamaki presented an up-dated schedule.  The installation task force worked out this schedule in the last few months.  The schedule is aggressive especially regarding services installation.  From our experience to date it is clear that the largest uncertainty has to do with the time needed to install the large amount of cooling pipes, cables etc.  The large objects installation has gone quite well so far and the time estimate and resources needed has been quite accurate.  On the other hand, the time and resources needed to install the services and electronics in the pit has been vastly underestimated.

Access:  A. Gordeev from BNL was at CERN and a meeting took place with Michal Raymond to discuss the status of the access and installation tooling that he is designing at BNL. Michal Raymond is taking over from Tommi Nyman who has left for a new position in Finland – this has resulted in BNL having to take more responsibility than before for the assembly and operation of the equipment. We will have a similar problem with the movement control that we are doing in the US (ANL) and, I expect that here too we will have to fill in at least temporarily some of the functions that were covered by Tommi.

ATLAS Upgrade:  Discussions took place with engineers from ALICE experiment to understand some options for Carbon fiber structures that we can use for the ATLAS upgrade. We expect that A. Gordeev will follow up on this and conceptual design for the ATLAS upgrade will be developed.

With Marzio Nessi we started to develop the charge for the ATLAS Upgrade Project Office that will be charged with coordinating the execution of the ATLAS upgrade.  The main idea is that in the first phases of the upgrade activities will include the conceptual design, prototype and even construction work.   The Project Office function will be distributed among a few large Labs – CERN, Rutherford, Nikhef and possibly BNL.  While in the R&D stage the engineering will be at the outside Labs, and then during the installation stage most of the functions will be concentrated at CERN.  The aim will be to have a document ready for discussions in early 2006.

Safety Issues:  The unfortunate accident that happened in the LHC tunnel has had an impact on the work in the cavern. The enforcement of safety rules has intensified and all people involved in the installation are much more aware of the need to follow safety rules. This has slowed down the work on the access significantly as new reviews of the planned scaffolding took place and the requirements for example of safety rails have been intensified. All people working on the scaffolding have gone through special training for working at heights.

Magnetic Field Workshop:  A two-day workshop on the magnetic field in ATLAS took place. There is now a large effort to prepare for the magnetic field mapping of both the solenoid and the Toroid fields. We expect the solenoid and the Toroid tests to take place in the spring of ’06. Iuliu Stumer gave the results of his calculations for the Toroid field. The calculations now include a lot of the magnetic material that surround the Toroid.

Positioning Strategy:  I gave a presentation on the placement strategy and the plans for the placement of the next objects.  We have now gotten agreement on the placement “drivers” for each of the blocks being installed.  For example the barrel system that is assembled on the truck and consists of: Barrel Tile Hadronic calorimeter, Barrel Liquid Argon electromagnetic calorimeter, Solenoid magnet and warm Inner vessel (used later on the ID installation).  When we move to the final position all the above items would like to be aligned to the beam pipe but clearly we can align the whole system as one object.  Thus, it was decided after discussions and optimization that included physics, effects on magnetic field, etc. to align the system using the barrel solenoid.  Similar decisions have been taken and agreed for the EC system, EC Toroid and Muon system. Discussions with the software people have started to decide how best to translate the “as built” model being established by technical coordination in the model that exists in the simulation packages. (Geant 4)

4.1 Inner Detector Upgrade R&D

Abraham Seiden (UCSC)

Work on the inner detector R&D is continuing in all areas. Some highlights:

Several sensor types are in fab: #D pixels, stripixel detector. n-on-p detector layout is continuing.

The 6 module stave is nearly complete. This includes new hybrids, a new bus cable, and 4 of the 6 detectors bonded. The performance is good.

A 0.13 micron pixel chip has been irradiated to 70 Mrad. No problems observed to date, will continue with irradiation.

Three generations of SiGe from IBM (5HP, 7HP, 8HP) are in Ljubljana for neutron irradiation. These are expected back in April. A SiGe front end has also been submitted this month for fab.

Test setups and procedures are coming together for a number of data transmission tests among a number of groups (Oklahoma State, SMU, Ohio State).

4.1.1 Detectors

Hartmut Sadrozinski (UCSC)

4.1.1 Detectors

Fabrication of a group of wafers, mostly with full 3D, active edge sensors to match the ATLAS front end pixel readout chip was started. The run was carried past step 28 (of 107), mask step 2 (of 7) and page 26 (of

67) on the run sheets. This includes the growth of the field oxide, bonding to the backside support wafer, and the etching of the first set of electrode (N) holes, one of the slower steps, as the wafers must be etched one at a time.

Sensors with three n and three p electrodes in each ATLAS pixel, from an earlier run were irradiated in a reactor at Praha up to a fluence of 8.6 x 10e15 1 MeV neutrons / cm^2

UNM activities covered characterization of leakage current, depletion voltage, electrode capacitance, and charge collection speed on samples of 3D sensors of a pre-ATLAS design, both non-irradiated and irradiated to a fluence of 1015 55MeV protons. Two- and three-dimensional electrostatic calculations based on the geometry of the sensor electrodes were performed.

The work covers measurements of electrical parameters (interstrip isolation and capacitance) and breakdown behavior on novel p-type detectors, as built and after moderate gamma irradiation. The aim is to evaluate the differences between Float Zone (FZ) and Magnetic Czochralski bulk materials.

The test set-up for the ATLAS SCT is being modified for charge collection efficiency measurements using a source.

Work continues on the design and layout of new 3 cm long detectors to be manufactured on 6" wafers by a commercial manufacturer.

Work continues on the Short Strip/Stripixel Detector characterization station. Characterization of both n- and p-type stripixel detectors continues.

Design for a small 3 cm x 3 cm test stripixel detector submitted to RD50 for fabrication. This design features of variety of pixel designs that will permit an evaluation of how layout, pitch, and gaps will influence S/N.

Quotes for fabrication of short strip for stave development are sought from SINTEF and Hamamatsu.

4.1.1.1 Innermost Pixel Layer

Alex Grillo (UCSC)

University of New Mexico Activities reported for S. Seidel

UNM activities during the October to December 2005 period concerned characterisation of Leakage Current, Depletion Voltage, Electrode Capacitance, and Charge Collection speed on non-irradiated and irradiated samples 3D sensors of a pre-ATLAS design. The preliminary results were presented at the Inner Detector Upgrade Workshop at UCSC on November 10. The measurement of reverse bias leakage current on the non-irradiated n electrode confirms that the n electrodes are not fully isolated from each other due to the oxide surface charge. After irradiation to a fluence of 10^15 55MeVp the n electrodes are isolated and the leakage current for a single isolated n electrode is 400 nA (Tnorm = 20C) at 60 Vbias. The p electrode shows a leakage of 300 nA (Tnorm = 20C) at 60 Vbias. Depletion voltage was obtained from an LCR-meter based CV measurement and by reading out the signal response to a pulsed laser. The preliminary results were Vd = 10V for the non-irradiated sensor and Vd = 80V for the irradiated (10^15/cm2 55MeVp) sensor. These depletion voltage measurements were performed on the single isolated n and p electrodes. Electrode capacitance was measured directly using an LCR meter and indirectly by extracting it from the decay time measured with a Picoprobe and a pulsed laser. The results of the direct measurement are 68 fF for the non-irradiated nelectrode, 120 fF for the irradiated (10^15 /cm^2 55MeVp) n electrode, 32 fF for the non-irradiated p electrode, and 59 fF for the irradiated (10^15 /cm^2 55MeVp) p electrode. The results of the indirect method of measuring capacitance are 71 fF for the non-irradiated p electrode and 80 fF for the irradiated p electrode. Two- and three-dimensional electrostatic calculations based on the geometry of the sensor electrodes were performed and resulted in an electrode capacitance of 31 fF. The speed of the charge collection in the 3D sensor was measured by illuminating the area near the isolated p electrode with an IR laser pulsed as fast as possible and observing the rise time of the sensor response. With a pulsed laser duration of approximately 0.3 nS the p electrode output rise time was measured to be about 2 nS for both the non-irradiated and irradiated samples.

Sherwood Parker (University of Hawaii)

1. Fabrication of a group of wafers, mostly with full 3D, active edge sensors to match the ATLAS front end pixel readout chip was started. The run was carried past step 28 (of 107), mask step 2 (of 7) and page 26 (of 67) on the run sheets. This includes the growth of the field oxide, bonding to the backside support wafer, and the etching of the first set of electrode (N) holes, one of the slower steps, as the wafers must be etched one at a time.

2. Sensors with three n and three p electrodes in each ATLAS pixel, from an earlier run were irradiated in a reactor at Praha. The most heavily irradiated was exposed to 8.6 x 10e15 1 MeV equivalent neutrons per sq. cm., about triple the amount requested for the ATLAS B layer replacement and LHC upgrade. This work was done by Cinzia Da Via of Brunel U. and members of the S. Pospisil group at the Czech Technical University.

Note 1: A report for the next 3 months would show the fabrication run, is now at step 83, mask step 4, and page 51. At this point, just prior to metal deposition (with metal, overglass and dicing mask steps remaining), Chris diverted to depositing and etching a temporary metal pattern, covering enough pixels per probe point to allow a manual test for a preliminary value of the yield. One wafer, which could produce enough devices for all the solder bump bonds the group would need and could afford, had a preliminary yield of 80% (24 good, so far, of 30 measured).

Two other wafers had the metal to electrode contact problems seen earlier.

Spotting that at this early stage is now permitting tests that are starting to indicate the causes. These tests have also shown, during the last few days, that large edge leakage currents seen with the temporary metal, and never seen before, are removed by a normal later step, the forming gas anneal (step 89, page 55).

Note 2: A report for the next 3 months would show that charge signals (from an infrared laser microbeam) can be seen in the most heavily irradiated ATLAS-pitch test sensor from the earlier fabrication run.

4.1.1.2 Investigation of Strip Technology

Hartmut Sadrozinski (UCSC)

The work covers measurements of electrical parameters (interstrip isolation and capacitance) and breakdown behavior on novel p-type detectors, as built and after moderate gamma irradiation. The aim is to evaluate the differences between Float Zone (FZ) and Magnetic Czochralski bulk materials.

In addition, the test set-up of the ATLAS SCT is modified for charge collection efficiency measurements using a source.

Work continues on the design and layout of new 3 cm long detectors to be manufactured on 6" wafers by a commercial manufacturer.

4.1.1.3 Short Strips

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Purchase Order Released (SB) | 30-May-06 | [New] | 30-May-06 | On Schedule |
| Detector Received (SB) | 30-Nov-06 | [New] | 30-Nov-06 | On Schedule |
| Charaterization Complete (SB) | 30-Mar-07 | [New] | 30-Mar-07 | On Schedule |

David Lynn (Brookhaven National Laboratory)

Short Strip/Stripixel Detector Characterization Station

Detector motherboards, leakage current measurements boards, and capacitance measurement boards have been fabricated. Readout boards with low noise Viking chips have their preliminary layout completed (by Milano collaborators), with final layout to be completed within next few weeks. Fabrication to be done in Italy, assembly at BNL. Duplicate test stations exist at both BNL and Milano.

Stripixel Detectors

N and P type prototype stripixel detectors fabricated since a year. First N-type stripixel detector mounted on detector motherboard. Preliminary capacitance and leakage current measurements done at BNL. Detector has been taken to Milano for further testing. Initial results indicate abnormally low interstrip resistance. Awaiting fabrication of more motherboards to mount more detectors and test both at BNL and Milano.

Meanwhile, have begun manual probing of remaining N and P-type detectors to test a subset of strips to pre-select detectors prior to mounting on motherboards. Probing done at BNL by New York University personnel.

Measurements on subset of wirebonded stripixel detectors (one n-type, one p-type) also being done at UC Santa Cruz. Measurements are preliminary but will be reported soon.

RD50 Test Stripixel-like detector

Design for a small 3 cm x 3 cm test stripixel detector submitted to RD50 for fabrication. This design features of variety of pixel designs that will permit an evaluation of how layout, pitch, and gaps will influence S/N.

Short Strips for Stave development

Currently have quote from Sintef for fabrication of batch of short strip detectors. Am currently pursuing quote from Hamamatsu for comparison purposes. Need to agree on dimensions of detector.

4.1.2 Front-End Electronics

Alex Grillo (UCSC)

A pixel test chip in 0.13 micron technology has been irradiated at the 88” cyclotron to 70 Mrad with no observed degradation. More irradiations and SEU studies will follow.

Test structures of 3 SiGe technologies have been pre-radiation tested and sent to Ljubljana for neutron irradiation. The basic design of a SiGe demonstration chip is complete. Final layout details and cross-checks are in progress and on track for an April submission for fabrication.

4.1.2.1 Deep Sub Micron for Pixels

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

0.13um prototype test chip previously fabricated has been irradiated to 70MRad in 88" cyclotron. No degradation observed. More irradiations and SEU studies to follow.

4.1.2.2 SiGe for Strips

Alex Grillo (UCSC)

We have obtained test structure arrays from our collaborator at Georgia Tech for three generations of IBM SiGe technologies, 5HP, 7HP and 8HP. Testing of the first batch of these samples was completed and the parts were sent to Ljubljana for neutron irradiation, which will be performed in early January just after the holiday break. We anticipate having these parts returned to us in March or April after their activation has dropped to acceptable levels.

Work has started to automate the electrical testing. A “connector card” has been built which interfaces a standard SCSI cable to the small connector on the test card containing the test structure array. This SCSI cable then attaches to a switching matrix which can be controlled by a computer which also controls the parameter analyzer. In this way, a computer program can control the sequential measurements of all devices on one array in an automated fashion eliminating the need for probing the separate leads of each device. This should greatly reduce the time required for electrical testing.

Two more batches of test structure arrays have been received from Georgia Tech. These will be tested as soon as the automated test system is ready and then irradiated with gammas at BNL and protons at CERN this spring and summer.

The design of a demonstration IC using the IHP SG25H1 SiGe technology is progressing well. This technology is being radiation tested by our collaborators in Barcelona. We chose it for our demonstration IC because the cost of fabrication will be considerably less than for a comparable IBM process through MOSIS. We were unable to make the Jan-06 submission date because of M&O duties at CERN for the engineering staff but are on track for the mid-Apr-06 submission. The basic design is complete. Details of the layout and design rule checking are being worked out.

4.1.3 Optical Readout

4.1.3.1 Diode Receivers

Flera Rizatdinova (Oklahoma State)

The initial test setup (arrived from Ohio State U.) for measurements of the PiN diode arrays characteristics is in place. The training has been done using this setup. An additional equipment necessary for further tests is ordered.

Potential vendors of the PiN diode arrays are identified and currently we are in contact with these vendors

4.1.3.2 Fiber Drivers

Jingbo Ye (Southern Methodist University)

Test procedure and system level architecture for in-lab and in-radiation tests of the GOL chip have been defined. Schematics of testing circuits are designed and reviewed with people from Oxford UK and from the Micro Electronics Group at CERN. Test equipment has been identified.

K.K. Gan (Ohio State University)

One of the goals of the R&D program is to identify the PIN and VCSEL arrays that can survive in the intense SLHC radiation environment. We have performed a survey of the commercially available arrays and identified several potential candidate arrays. The next step is to purchase the arrays and package them so that they can be characterized.

4.1.3.4 Multiplexers and Interconnect Circuits

K.K. Gan (Ohio State University)

Another important goal of the R&D program is to measure the bandwidth of the infrastructure of the current pixel optical link. The two critical components in the infrastructure are: the micro twisted pair cables and fiber ribbons. The former transmits the LVDS signal between the optical components and the pixel modules. The latter transmits the optical signal between the optical components and the counting room. The ribbons consist of several meters of radiation-hard, low bandwidth SIMM fibers spliced to ~100 m of radiation tolerant, medium bandwidth GRIN fibers. At SLHC, we expect to transmit data at ~Gb/s.

We have constructed a prototype test system to measure the bandwidths. From the measurement of the rise and fall times and the “eye” diagrams, the preliminary conclusion is that the micro twisted pairs can transmit signals at up to 640 Mb/s and the fibers at up to 1 Gb/s. The current infrastructure therefore satisfies the needs of the SLHC. More detailed study is in progress.

4.1.4 Modules

4.1.4.1 Stave Structures

Carl Haber (Lawrence Berkeley Laboratory)

The effort here focuses on building and testing a 6 module stave. Each module consists of a single CDF Run2b surplus detector and a new ATLAS ABCD hybrid (see 4.1.4.1) developed for this project. To date we are part-way though fabricating and testing the first of these 6 module staves. We developed and fabricated a new bus cable and laminated 2 of these to carbon/foam/PEEK stave cores and cooling channels. We then mounted 6 hybrids (with no detectors) to this structure. It was fully bonded and tested with the existing ATLAS DAQ. A hybrids were seen to read out properly. We then started mounting and bonding hybrids to detectors. To date four have been mounted and 3 of these have been tested as individual units. They were seen to perform as expected for ATLAS electronics. Two of these have since been mounted and bonded to the stave itself. Their performance on the stave is as expected as well. We will continue to mount the remaining 4 to complete the stave.

A new DAQ system is under development to allow us to control and read large number of stave based modules in parallel. This system is based upon the National Instruments High Speed Digital I/O series of LVDS cards. These cards in in hand and code is being written to control them.

A new 3cm detector design is underway at BNL. Quotes have been solicited from 2 vendors.

4.1.4.2 Hybrids

Carl Haber (Lawrence Berkeley Laboratory)

The ATLAS hybrid for the stave was designed and fabricated last year. It performs as expected. About 60 were manufactured. About 20 of these have been built so far and performance is as expected. Four hybrids have been integrated with detectors, three of these have been tested and perform well.

4.1.4.3 Cooling Channels

Carl Haber (Lawrence Berkeley Laboratory)

Working in consultation with W.Miller studies of stave geometry and materials in terms of a 1 and 2 meter stave are underway. Thermal gradients and deformations, and gravitational sag have been studied. Iterations are underway particularly aimed at controlling gravitationalsag.

4.1.4.4 Powering Schemes

Carl Haber (Lawrence Berkeley Laboratory)

Design work continues at LBL on a DC-DC conversion scheme. The group at RAL is designing an interface card for serial powering which can go on our 6 module stave. We are redesigning the stave bus cable to connect to this card. A second 6 module stave with serial powering will be built using the RAL card, our hybrid, and this new bus cable. We aim to test all this in June 2006.

4.3 Liquid Argon Upgrade R&D

Francesco Lanni (Brookhaven National Laboratory)

The R&D activities for Liquid Argon in most of the WBS level 4 nodes have not been started yet pending also the availability of some of the funds. Some study has begun at SMU for the optical data link: radiation studies have been carried over for a laser driver chip on 0.5um SoS technology as well as the design of a test chip submitted in October at Peregrine and the test setup for measurements in-lab and for irradiation. Also some design studies of test structures for the PLL block has begun (always at SMU).

4.3.2.4 Optical Data Link

Francesco Lanni (Brookhaven National Laboratory)

The laser driver chip of 0.5 um SoS technology has been irradiated at MGH with 200 MeV proton up to 100 Mrad. Data analysis has been carried out and identified current leakage in SoS CMOS design. Solutions have been researched and proposed. A dedicated SoS technology test chip was then designed and fabricated with support from Peregrine. This chip was submitted in Oct. 2005. The in-lab and in-radiation test setup has been designed at system or architecture level. Schematics work has been started. Test equipment is been identified.

On the Link-on-Chip (LoC) front, preliminary studies have been carried out on the PLL block, the most critical part in the LoC design. A preliminary VCO and PLL together with PFD, dividers have been put on the SoS test chip.

# Financial Report (Chuck Butehorn, BNL)