Proposed Data Elements for PARS II

Revised: January 2, 2009 – Version 2.1

# Overview

The PARS II application will collect two major types of data from DOE Field Site and DOE Headquarters locations. The two types of data are called: (1) Oversight and Assessment Data and (2) Contractor Project Performance Data and are designed to provide information to support for the concepts and data elements represented by the DOE EVMS Gold Card. A reproduction the relevant section of the Gold Card appears to the right.

Overhead and Assessment Data, such as monthly assessments, contingency, profit/fees, other direct costs, performance baseline, milestone completion dates, contractor certification status, total project cost and other data elements will be collected from Federal Project Directors, Program Office Analysts and OECM Analysts using the PARS II Oversight and Assessment module. This type of data is often referred to as summary level data and is related to the items shown in the red-shaded portion the DOE EVMS Gold Card.

Contractor Project Performance Data, such as the management reserve, performance measurement baseline, contractor’s earned value data, schedule data, variance analysis reports and risk logs will be collected from the site contractor’s earned value management system using the PARS II Contractor Project Performance “project upload file function”. The contractor will use this functionality, on a monthly basis, to send (i.e., upload) files containing earned value data, schedule data, management reserve, variance reports and risk to the PARS II server at Headquarters  These types of data elements are related to the blue-shaded portion the DOE EVMS Gold Card.

PARS II will store both types of data in the database and will integrate them, for reporting purposes, using the Project ID as the common data element.

Please note that the names used to describe of database tables and data elements in this document are based on terms commonly used by Department of Energy federal and contractor personnel, and are based on the language found in relevant publications such as DOE Orders, Guides, Manuals and PARS 1 documentation.  PARS II will be implemented using the Dekker PMIS COTS product, which uses its own internal database table and data element naming conventions.  Therefore, when implemented, PARS II may not use many of the table names and data element names described below.  However, Dekker software will be modified to provide PARS II users with a “data aliasing” feature that translates Dekker terminology into DOE terminology.

Database Tables

The database for PARS II is being designed to store, for each project, oversight and assessment data and contractor project performance data. The database will contain many tables that can be categorized as either Reference Tables or Data Tables. The information stored in Reference Tables is static in nature (e.g., not updated very often) and contains data such as Contacts, Sites, Program Office Codes, Group Access Rights, etc.  Data elements in these Reference Tables will be used by PARS II for look-up or data validation purposes (e.g., using drop-down boxes). Information stored in Data Tables is dynamic in nature (e.g., is updated daily, weekly) and contains items such as the Projects Table, Narratives Table, Earned Value Table, Budget Profile Table, etc.

The sections below describe the information contained in the Reference Tables, the Data Tables and the entire list of data elements for PARS II. Please note that other tables and data elements may be added to this document as a result of information obtained from Discovery Sessions and feedback from stakeholders.

Reference Tables

The following list of Reference Tables will be included in the PARS II database.

|  | Reference Table Name | Description of Reference Table |
| --- | --- | --- |
|  | Calendar Table | An electronic calendar within PARS II to be used for calculating schedules, displaying months, days, years, selecting date range values on screens, etc. |
|  | Contract Types Table | The list of valid contracts types, such as Fixed Price, Cost Reimbursement. [to be implemented as a dropdown box on PARS screens] |
|  | Contractor EVMS Certification Status Codes Table | The list EV certification status codes that apply to the contractor, such as: Certified, Reviewed, Not Reviewed |
|  | Contractor Names Table | The list of prime contractor names [dropdown box] |
|  | Contractor Types Table | A brief list that identifies the type of contractor, such as: M&O, M&O Subcontractor [dropdown box] |
|  | FPD Certification Level Codes Table | The list of certification level codes that pertain to the FPD, such as: Level 4, Level 3, Level 2, Level 1 |
|  | FPD Certification Status Codes Table | The list of certification status codes that apply to the FPD, such as: Certified, Not Certified, Under Review |
|  | Managing Program Offices Table | The names and acronyms of all DOE Program Offices and Staff Offices, such as: EM, NNSA, NE, Science, MA, OCIO [dropdown box] |
|  | Milestone Types Table | The types of milestones to be placed in the Milestone Table, such as Regulatory Milestones, Key Milestones, EM Operations Funded Milestones, Other Milestones |
|  | Narrative Types Table | A list of the various types of narratives that to be written by the FPD, OECM, Program Office Analyst, such as: Status Assessment, Progress Assessment, Corrective Action Plan, Upcoming Events, Narrative to Achieve Green. [dropdown box] |
|  | Project Activity Codes Table | The list of codes that identify the current “activity status” of a project, such as: Active, Completed CD4, Financial Closeout, On-Hold. [dropdown box] |
|  | Project Category Codes Table | The list of categories for a project, such as: stand-alone project, discrete sub-project, sequential segment project [dropdown box] |
|  | Project Locations Table | The list of cities, states, and zip codes where the project is located. [dropdown box] |
|  | Project Sites Table | The list of valid DOE Site Codes and Site Descriptions where the project is located. [dropdown box] |
|  | Project Type Codes Table | The list of project types, such as: System, Facility Construction, Infrastructure Improvements, Restoration, Disposition, etc. [dropdown box] |
|  | User Access Rights Table | A table that lists the “access rights” available to groups of users (see User Groups) who will use PARS II. Examples of access rights include: READ ONLY, ADD, CHANGE, DELETE. Access rights within the Dekker COTS software extends to the data element level. [dropdown box] |
|  | User Groups Table | The list of valid user groups, such as OECM Analyst, FPD, Contractor Project Control, Contractor Project Manager, Program Office Project Manager and other groups. [dropdown box] |
|  | Users (Contacts) Table | The list of all users who may access PARS and contains information such as: user name, user title, user group, user location (building, city, state zip), user work phone number, user email address [dropdown box] |
|  | Color Status Indicators | A list of status indicators, to be used on screens and reports, indicating the health of the project. Color indicators are: Red, Yellow and Green and are also associated with control limit data elements. [dropdown box] |
|  | Project Upload File Types Table | Contains the list of the valid types of upload files to be sent from sites, such as: X12 EV, Time-Phased EV, Schedule, Variance, Management Reserve, Risk, Other |
|  | Other Tables | To be determined during discovery process. | Project Upload File Types Table | Contains a list of the various types of upload files to be received from sites, such as: X12 EV Type, Time-Phased EV Type, Schedule Type, Variance Type, Management Reserve Type, Risk Type, Other |

Data Tables

The table below lists and describes each the Data Table.

|  | Data Table Name | Description of Table |
| --- | --- | --- |
|  | Attachments Data | The electronic file or files “attached” by the operator during a data entry session, to include documents such as: assessments, safety documents, project approval documents, project plans, project design documents, etc. |
|  | Audit Log File Data | Log files, available to the PARS System Administrator, that show history transactions associated with data entry and internal workings of the system. With regard to all PARS data entry functions, log files must show who-changed-what-and-when. There will be several different types of audit log files. |
|  | Budget & Funding Profile Data | A table containing, for each fiscal year, the funding request and sources of funding to be used by the project. Data elements include the project’s Performance Baseline and funding sources from the DOE Integrated Priority List, OMB and Congress. The makeup of the Budget Profile table for PARS II is currently being discussed at OECM. |
|  | Contractor EVMS Certification Status Data | Contains information about each contractor’s EVMS certification status / level / date of certification. |
|  | FPD Certification Status Data | Contains current and historical information on the FPD’s certification process, showing current status, certification level and status dates (history). |
|  | KPP Data | A table that contains a list of all the KPPs for the project, including the KPP ID, KPP Description and KPP Narrative |
|  | Milestone Data | A table that contains data for the milestones and critical decisions to be associated with each project and includes the following data elements: Milestone ID, Milestone Name, Milestone Type (e.g., CD, Key, EM, Other), Milestone Narrative, Milestone Planned Date, Milestone Actual Date. |
|  | Narratives Data | This table contains written text for each type of narrative (see Narrative Types Table), as written by the FPD, Program Office Analyst, OECM Analyst. Each narrative must also be associated with the fiscal year, fiscal month and calendar date that the narrative was written. This table must also identify the Type of Narrative and name and title of the author who wrote the narrative. |
|  | Performance Baseline (PB) Change Data | A history file of changes made to the Performance Baseline, containing the Baseline Change Number, Baseline Change Title, Baseline Change Date, Approval Authority, Narrative, etc. The table also includes a snapshot of selected data elements that were a part of the PB, such as Contingency, Profit/Fee, Indirect Costs and the Contractor’s Baseline Budget. |
|  | Performance Measurement Baseline (PMB) Change Data | A history file of changes made to the contractor’s Performance Measurement Baseline, containing the Baseline Change Number, Baseline Change Title, Baseline Change Date, Approval Authority, Narrative, etc. The table also includes a snapshot of selected data elements that were a part of the PMB, such as Management Reserve, WBS-Level BCWP, ACWP, BAC and others. |
|  | Project Upload File Data | This table holds all of the various types of upload files that were received from contractors and identifies the type of upload file, the date received, and other information. Some upload files can be large in size (e.g., 100MB) |
|  | Projects Data | The master table containing all projects in the PARS II database. Each project record in the database will have data elements such as: Project ID, Project Description, Project Acronym, Project Site Code, Managing Office Code, Project Status, Project Location and will be linked to many other tables in the database. |
|  | Risk Log Data | This table contains the Risk Log data, for the project, that was collected from the contractor via the upload process. |
|  | Other Tables | To be determined during discovery process. |

Data Elements

The table in this section identifies the data elements that are proposed for use by the PARS II Overhead and Assessment and Contractor Project Performance modules.

For familiarity, the table makes use of the format used by the “PARS Data Input Requirements Document” (published by Project Performance Corporation, March 25, 2006).  The table shows how and data elements will be entered during the life cycle of the project. Cells in the table are color coded to identify the conditions for update, such as “required monthly, required annually, required at special event. The column headings and rows listed in the Proposed Data Elements for PARS II Table are arranged in the following manner:

- Column 01 – Row: contains the row number for the table;

- Column 02 – Ref: contains the name of the system or document from which the data element was sourced. Reference codes are: ART (from the ART database), PDIR (PARS Data Input Requirements document), NEW (from discussions with Dekker, John Makepeace, others), PMET (Performance Metrics defined by OECM in March 2007;

- Column 03 – Data Group: contains the data group or data classification code for the data element;

- Column 04 – Table Name: contains the name of the PARS II database table to which the data element belongs;

- Column 05 – Data Element Name: contains the name of the data element, along with examples of data to be used (for some data elements);

- Column 06 – Data Dictionary Description: contains the commonly used definition for the data element;

- Column 07 – Data Type: describes the data elements type, such as alphanumeric, numeric, date;

- Column 08 – Data Length: defines the data element‘s field length, in characters;

- Column 09 – List of Values: shows the list of data items (e.g., data values) that belong to the data element;

- Column 09 – List of Values: shows the

- Column 10 – Comment: contains a brief comment that can be used for multiple purposes;

- Column 11 – Responsible: contains the name of the group responsible for entering values into this data element.  Group codes names are: PO (Program Office),  FPD (Federal Project Director), OECM (OECM Analyst), CONTR (Contractor);

- Column 12 – contains instructions on how the data should be entered as the project is approved at CD-0;

- Column 13 – contains instructions on how the data should be entered as the project moves from CD-0 to approval at CD-1;

- Column 14 – contains instructions on how the data should be entered as the project moves from CD-1 to approval at CD-2;

- Column 15 – contains instructions on how the data should be entered as the project moves from CD-2 to approval at CD-3;

- Column 16 – contains instructions on how the data should be entered as the project moves from CD-3 to approval at CD-4;

- Column 17 – contains instructions on how the data should be entered as the project moves from CD-4 to approval at Close-out.

Use the legend (below) to interpret the symbols and information in color-coded cells found in the Proposed Data Elements for PARS II Table.

Legend for Table “Proposed Data Elements for PARS II”

| Legend for Understanding How Data Elements Should Be Processed |
| --- |
| Required (Special Event) | An update to this data element is required when the Special Event indicated occurs |
| Required (Annually) | An update to this data element is required at the end of each fiscal year. |
| Required (Monthly) | A monthly update is required (during the 3rd, 4th week of the following month). |
| Required | Input is required when the Critical Decision has been approved. |
| Update Required | An update is required when the Critical Decision has been approved. |
| As Needed | Update this data element at any time in the project life cycle (as needed). |
| When Condition Occurs | An update to this data element is required when a change occurs to a related data item, such as activity status. |
| ** | Double asterisk (**) Life Cycle Costs for EM Operations funded projects |
| *** | Triple Asterisk (***) Not required for EM Operations funded projects |
| PMB | Data elements flagged with the PMB superscript will be included in the Performance Measurement Baseline (PMB). |
| PB | Data elements flagged with the PB superscript will be included in the Performance Baseline (PB). |

Proposed Data Elements for PARS II

|  | Ref | Data Group | Table Name | Data Element Name | Data Dictionary Description | Data Type | Data Length | List of Values | Comments | Responsible | CD-0 | CD-1 | CD-2 | CD-3 | CD-4 | Closeout |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ART | Project Identity | Project | Project ID PB & PMB | The DOE Project Identification Code (e.g., 97-D-102) for construction and engineering design projects as reported in the OMB A-11 Exhibit 300 or the program budget submission. This field is used to identify the project record and to link the project record to other tables in the database. EM projects Project IDs may include PBS# and Project#. For tracking Category “2” projects that will be tracked as discrete subprojects add suffix #A, #B, etc. to the Project ID. For tracking Category “3” projects (For tracking performance of each Near-Term segment of EM projects) add suffix *1, *2, etc. to the Project ID. | A/N | 25 | N/A | Input once | PO | Required |  |  |  |  |  |
|  | ART | Project Identity | Project | Project Name PB & PMB | The official name of the project as approved by the Acquisition Executive. (e.g., National Ignition Facility). | A/N | 50 | N/A | Input once | PO | Required |  |  |  |  |  |
|  | PDIR | Project Identity | Project | Project Acronym | The acronym or abbreviated name for the project (e.g., NIF). | A/N | 15 | N/A | Input once | PO | Required |  |  |  |  |  |
|  | PDIR | Project Scope | Project | Project Description | A brief description of the project’s scope, schedule and budget. | A/N | 1000 | N/A | Input once | PO | Required |  |  |  |  |  |
|  | ART | Project Identity | Project | Project Type PB & PMB | This data element consists of two parts: The first part of the data element asks for the type of building, structure or device to be built, restored or decommissioned, such as System; Facility Construction; Infrastructure Improvements; Restoration; Disposition; Information Technology; Plant. The second part of the data element asks if the project is a: (1) Non-nuclear Facility (the default), (2) Nuclear Facility, or (3) Not applicable | A/N | 25 | System; Facility Construction; Infrastructure Improvements; Restoration; Disposition; Information Technology; Plant. | Input once | PO | Required |  |  |  |  |  |
|  | ART | Project Identity | Project | Project Size | The relative size of the project, as expressed in dollars, such as: - Major System = TPC > $750 million or EM Cleanup Project > $1 Billion) or Non-Major System = TPC < $750 million or EM Cleanup Project < $1 Billion) System of Interest – a special designation applied to the project by the Deputy Secretary | A/N | 50 | Major System = TPC > $750 million or EM Cleanup Project > $1 Billion), Non-Major System = TPC < $750 million or EM Cleanup Project < $1 Billion) System of Interest | Needed – JM? | PO | Required |  |  |  |  |  |
|  | ART | Project Identity | Project | Project Category PB & PMB | The internal designation of the project in the database, such as Stand Alone Project, Subproject, Project Segment, as defined below. 1. Stand-Alone Projects: Most of the projects fall into this category. The system will have one record for each such project. The project Critical Decisions may be phased or the project may initially be a Design Project that transitions to a Construction Project. 2. Projects with Discrete Sub-Projects: Projects with discrete sub-projects are managed in smaller sub-projects for status reporting and budget requests. CD-0 and CD-4 milestones are same for the entire project but the CD-1 through CD-3 dates could be independent. Further each sub-project could have its own CD-4 (4A, 4B etc). Project, Sub-Project A, Sub-Project B - PARS will have as many records in the system as the number of subprojects. - All subprojects will have the same Project ID but will have an additional subproject identifier with # suffix. As an example, if the main project had a project ID of 01-D-416, the sub-projects would have Ids such as 01-D-16#A, 01-D-16#B etc. - A Project can be subdivided into sub-projects at any time. When a project is subdivided, information prior to the breakup will be tracked as the first sub-project record. - Generally each sub-project will also have its own separate funding table in the Project Data Sheet. 3. Projects with Project Segments: This category of projects includes EM Operations Funded projects that may have multiple segments over time, based on new contracts that will be completed in sequential segments. Each contract-term is represented as a segment of the life-cycle baseline. - Eventually PARS will have as many records in the system as the number of Project Segments. - Each record will carry the cumulative EV data forward to the next segment. This will allow the tracking of life-cycle performance as well as measurement of each new contractor’s performance - All Project Segments will have the same project ID followed by an ‘*’ as a separator and a numeric segment identifier. (e.g. 2035: SR-0013* 1]. - Each Project Segment will have its own Critical Decisions 1 through 4. - Upon completion, each completed Project Segment will have its own Closeout details. | A/N | 25 | Stand Alone, Subproject, Project Segment | OECM Discussion Needed for Subprojects and Segments - JM | PO | Required |  |  |  |  |  |
|  | PDIR | Project Identity | Project | Project Activity Status | The current activity status of the project, to be selected from one of the following items: Active, Completed at CD-4, Financial Closeout, Cancelled, On-Hold, Other. If “On-Hold” or “Other” is selected, a brief narrative is required | A/N | 25 | Active, Completed CD-4, Financial Closeout, Cancelled, On-Hold, Other. |  | PO | Required | As Needed | As Needed | As Needed | As Needed | As Needed |
|  | PDIR | Project Identity | Project | Project Activity Status Narrative | A narrative that explains why the project was placed “On-Hold” or in the “Other” activity status. | A/N | 255 |  |  | PO | Required | When “Activity Status” Changes | When “Activity Status” Changes | When “Activity Status” Changes | When “Activity Status” Changes | When “Activity Status” Changes |
|  | ART | Project Resp. | Project | Managing Program Office PB & PMB | The alphanumeric code that represents the DOE Program Office responsible for providing oversight. | A/N | 25 | EM NNSA SC Others | Input once | PO | Required |  |  |  |  |  |
|  | ART | Project Cost | Project | TPC at CD-0 (low) ($K) ** | The low end of the total project cost range as approved at CD-0. | N | 12 |  | Input once | FPD | Required |  |  |  |  |  |
|  | ART | Project Cost | Project | TPC at CD-0 (high) ($K) ** | The high end of the total project cost range as approved at CD-0. | N | 12 |  | Input once | FPD | Required |  |  |  |  |  |
|  | PDIR | Project Schedule | Milestone | Milestone ID | The unique and sequential identification code for each milestone. This ID make is easier to track and sort milestones. Examples (1, 2, 3, Reg-1, Reg-2, etc) | A/N | 50 | N/A | Input once | FPD | Required |  |  |  |  |  |
|  | PDIR | Project Schedule | Milestone | Milestone Type | There are several types of milestones: 1. Critical Decision Milestones, 2. Regulatory Milestones, 3. Other Key Milestones, 4. EM Operations Funded Projects to Designate the Start Date of a New Near Term Project Segment Milestones | A/N | 50 | Critical Decision Milestones, Regulatory Milestones, Other Key Milestones, EM Operations Funded Projects Milestones. | DOE O 413.3A p.25 | FPD | Required |  |  |  |  |  |
|  | PDIR | Project Schedule | Milestone | Milestone Name | The official name or title of the milestone. If the Milestone Type was “1” then pick the Critical Decision from the pull-down menu and then input an extension (A, B) if the CD will occur in phases. For other types of milestones, enter the official milestone name. | A/N | 256 | N/A | DOE O 413.3A p.25 | FPD | Required |  |  |  |  |  |
|  | PDIR | Project Schedule | Milestone | Milestone Date Planned | The planned date in which the milestone or critical decision is expected to be met | Date | 10 | N/A | DOE O 413.3A p.25 | FPD | Required |  |  |  |  |  |
|  | PDIR | Project Scope | KPP | Key Performance Parameter ID PB | The unique sequential numeric identifier for each KPP. | N | 3 | N/A | Input once | OECM | Required | Upd Reqd | Upd Reqd |  |  |  |
|  | PDIR | Project Scope | KPP | Key Performance Parameter Description PB | Narrative that describes the characteristics, functions, requirements or design basis that, if changed, would have a major impact on the facility or system performance, schedule, cost and/or risk, or the ability of the interfacing project to meet its mission requirements. A KPP may be a performance, design, or interface requirement. Update KPPs as the project progresses through planning and design stages. | A/N | 4000 | N/A |  | OECM | Required | Upd Reqd | Upd Reqd |  |  |  |
|  | PDIR | Project Schedule | Milestone | Milestone Date Actual | The date that the milestone or critical decision was met. For projects initiated prior to DOE O 413.3 for which no formal CD- 0 was approved enter the date (2/1/yyyy) when first submitted in the President’s budget request. | Date | 10 | N/A |  | FPD | Required (when critical decision or milestone is achieved) |
|  | PDIR | Project Status | Milestone | Milestone Approved By | The name of the approving authority for the milestone or critical decision. | A/N | 50 | N/A |  | FPD | Required (when critical decision or milestone is achieved) |
|  | PDIR | Project Status | Milestone | Milestone Narrative | Narrative that describes key activities or deliverables related to the preparation for the milestone or critical decision. Include any current issues or actions. | A/N | 256 | N/A |  | FPD | Required (when critical decision or milestone is achieved) |
|  | PDIR | Project Status | Attachment | Project Attachment Title | The title of electronic document to be attached to the project. Examples include CD Approval, ESAAB Brief, etc) | A/N | 255 | N/A |  | FPD | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | PDIR | Project Status | Attachment | Project Attachment File Name | The computer filename of the attachment. Example: Project ABC123-4 CD Approval 20091021 | A/N | 50 | N/A |  | FPD | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | PDIR | Project Status | Attachment | Project Attachment URL | The hyperlink address of the attachment, once it has been stored on the PARS II or OECM Document Control Server. | A/N | 50 | N/A |  | OECM | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | ART | Project Cost | Project | Prior Year Work for EM-C ($k) | Prior year work, in dollars, for EM Construction projects. | N | 12 | N/A | Discussion Needed | OECM | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | ART | Project Cost | Project | Near Term Baseline Work for EM-C ($k) | Near term baseline work, in dollars, for EM construction projects. | N | 12 | Range of dollars??? | Discussion Needed | OECM | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | ART | Project Cost | Project | Out Year Planning Estimate Range for EM-C | Out year planning estimate range, in dollars for EM construction projects. | N | 12 | N/A | Discussion Needed | OECM | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | ART | Project Cost | Project | Life Cycle Cost for EM-C | Life cycle cost for EM construction project. | N | 12 | N/A | Discussion Needed | OECM | Required | Upd Reqd | Upd Reqd | Upd Reqd | Upd Reqd |  |
|  | ART | Project Resp. | Project | Federal Project Director Assigned to Project PB & PMB | The name of the federal project Director assigned to the project. | A/N | 50 | Dropdown from Contacts (FPDs only) |  | PO |  | Required |  |  |  |  |
|  | ART | Project Status | Assessments | Date of Project Status | The fiscal year (MM/YYYY) and calendar month for reporting status or writing assessments. This data element is updated by the author before writing or updating monthly status information. MM/YYYY | Date | 10 | N/A |  | FPD | Required (Monthly) |  |
|  | PDIR | Project Status | Assessments | FPD Status Assessment | A brief progress report on the current project status. Report on recent developments, comments, clarifications, or concerns relating to the project. Report any issues that need to be addressed at the Program and/or the Department level (e.g., risks encountered that will potentially require contingency held by DOE, assumptions in the project baseline that are not valid and could result in potential delays or cost overruns). | A/N | 4000 | N/A |  | FPD | Required (Monthly) |  |
|  | PDIR | Project Status | Assessments | FPD Status Assessment Indicator (R/Y/G)) | A color assigned to the red, yellow, green performance indicator that indicates the overall condition of the assessment. | Object | 1 | R, Y, G |  | FPD | Required (Monthly) |  |
|  | NEW | Project Status | Assessments | FPD Corrective Action Plan | A narrative from the FPD that describes the corrective action plan expected to bring the project back on schedule, cost or other parameter. | A/N | 4000 | N/A | Needed? – JM (DOE O 413.3A Attachment 2, P1) | FPD | Required (Monthly) |  |
|  | NEW | Project Status | Assessments | FPD Project Upcoming Events ID | A unique, sequential number that identifies the specific narrative, in order, for each of the upcoming events. | N | 3 | N/A | OK-JM | FPD | Required (Monthly) |  |
|  | NEW | Project Status | Assessments | FPD Project Upcoming Events Narrative | Brief narrative that describes an upcoming event that should be brought to the attention of senior DOE management. This narrative to be shown on the DepSec Report. | A/N | 4000 | N/A | OK-JM | FPD | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | FPD Forecasted Month to Achieve Green | The calendar year and month that the FPD believes that issues will be resolved and the project will return to a status of “green”. MM/YYYY | Date | 10 | N/A |  | FPD | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | FPD Forecasted Completion Date | The data that the FPD expects the project to be completed. mm/dd/yyyy | Date | 10 | N/A |  | FPD | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | FPD Forecasted Total Project Cost (TPC) ($K) | The FPD’s estimate for Total project Cost | N | 12 | N/A |  | FPD | Required (Monthly) |  |
|  | NEW | Project Status | Assessments | PO Status Assessment | A brief progress report on the current project status. Report on recent developments, comments, clarifications, or concerns relating to the project. Report any issues that need to be addressed at the Program and/or the Department level (e.g., risks encountered that will potentially require contingency held by DOE, assumptions in the project baseline that are not valid and could result in potential delays or cost overruns). | A/N | 4000 | N/A |  | PO | Required (Monthly) |  |
|  | NEW | Project Status | Assessments | PO Status Assessment Indicator (R/Y/G)) | A color assigned to the red, yellow, green performance indicator that indicates the overall condition of the assessment. | Object | 1 | R,Y,G |  | PO | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | OECM Status Assessment | A brief narrative that documents the current OECM assessment. OEC will use this data element to explain the color-coded assessments (Red, Yellow, Green) and other information as shown on the Monthly Report to the Deputy Secretary,. | A/N | 4000 | N/A |  | OECM | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | OECM Status Assessment Indicator (R/Y/G)) | A color assigned to the red, yellow, green performance indicator that indicates the overall condition of the assessment. | Object | 1 | R,Y,G |  | OECM | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | OECM Progress Assessment | Narrative from the OECM identifying progress made towards Green. | A/N | 4000 | N/A | Needed? – JM | OECM | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | OECM Progress Assessment Indicator (R/Y/G)) | A color assigned to the red, yellow, green performance indicator that indicates the overall condition of the assessment. | Object | 1 | R,Y,G | Needed? - JM | OECM | Required (Monthly) |  |
|  | ART | Project Status | Assessments | OECM Overall Assessment | A narrative of the OECM’s final and overall assessment of the project for the reporting period. This narrative goes on the DepSec Report. | A/N | 4000 | N/A |  | OECM | Required (Monthly) |  |
|  | ART | Project Status | Assessments | OECM Forecasted Month to Achieve Green | The calendar year and month that the OECM believes that issues will be resolved and the project will return to a status of “green”. MM/YYYY | Date | 10 | N/A |  | OECM | Required (Monthly) |  |
|  | ART | Project Status | Assessments | OECM Forecasted TPC ($k) | The OECM Analyst’s estimate for Total Project Cost | N | 12 | N/A |  | OECM | Required (Monthly) |  |
|  | PMET | Project Status | Assessments | OECM Forecasted Construction Completion Date at CD-4 | The OECM Analyst’s estimate for construction completion date at CD-4. MM/DD/YYYY | Date | 12 | N/A |  | OECM | Required (Monthly) |  |
|  | ART | Project Status | Assessments | OECM Analyst Detailed Comments | A detailed narrative, kept by the OECM Analyst that contains ongoing narrative about the project. This data should not be made available for reporting. | A/N | 4000 | N/A |  | OECM | Required (Monthly) |  |
|  | ART | Project Identity | Sites | Project Site Code PB & PMB | The alphanumeric abbreviation for Project Site (e.g., LLNL for Lawrence Livermore National Laboratory). Please note that sites have only been set up for DOE facilities where projects are located. Field and Operation offices are not considered "physical sites." The site code table also contains a description for the site (Lawrence Livermore National Laboratory). If a project has multiple sites, chose “Multiple” and include the site names in the project description. | A/N | 15 | Dropdown | Input once | FPD |  | Required |  |  |  |  |
|  | ART | Project Identity | Locations | Project Location PB & PMB | The project location data element consists of four separate data elements: area, city, state and zipcode. Enter Local area description, and the City, State, and Zip Code where project is located. Local area description is the location within a site (e.g., TA3 at Los Alamos, H Area at SRS). The data will be entered in four fields. | A/N | 256 | N/A | Input once | FPD |  | Required |  |  |  |  |
|  | ART | Project Resp. | Contractors | Prime Contractor Name PB & PMB | The name of the prime contractor responsible for overall management of the project when selected after CD-1. Select the dropdown value “Unknown” if contractor has not been selected. | A/N | 50 | Dropdown Name Name Name Unknown |  | FPD |  | Required |  |  |  |  |
|  | PMET | Project Resp. | FPD Certification | FPD Certification Current Status | The current EVMS certification status of the FPD. See dropdown. | A/N | 25 | Certified, not certified, under review |  | OECM |  | Required | As Needed | As Needed | As Needed | As Needed |
|  | PMET | Project Resp. | FPD Certification | FPD Certification Level | The current EVMS certification level of the FPD. See Dropdown | A/N | 100 | Level 4: TPC exceeding $400 million (M) • Level 3: TPC greater than $100M and equal to or less than $400M • Level 2: TPC greater than $20M and equal to or less than $100M • Level 1: TPC greater than $5M and equal to or less than $20M [A history file that shows the certification level number and the date in which it was achieved]. |  | OECM |  | Required | As Needed | As Needed | As Needed | As Needed |
|  | PMET | Project Resp. | FPD Certification | FPD Certification Dates and Levels (History File) | A list of historical records that shows one record for each certification event for the FPD; identifying the certification level and the date of the certification. | A/N | 4000 | N/A |  | OECM |  | Required | As Needed | As Needed | As Needed | As Needed |
|  | ART | Project Resp. | Contractor Certification | Contractor EVMS Certification Status | The contractor’s EVMS certification status. | A/N | 25 | Certified, Reviewed, Not reviewed |  | OECM |  | Required |  |  |  |  |
|  | ART | Project Resp. | Contractor Certification | Contractor EVMS Certification Date | The date that the contractor was certified. | Date | 10 | N/A |  | OECM |  | Required |  |  |  |  |
|  | ART | Project Cost | Project | TPC at CD-1 (low) ($K) ** | An estimate, at the low side of the range in dollars, of the Total Project Cost at CD-1 | N | 12 | N/A |  | FPD |  | Required |  |  |  |  |
|  | ART | Project Cost | Project | TPC at CD-1 (high) ($K) ** | An estimate, at the high side of the range in dollars, of the Total Project Cost at CD-1 | N | 12 | N/A |  | FPD |  | Required |  |  |  |  |
|  | ART | Project Schedule | Project | Estimated Completion Date at CD-1 (high) | The FPD’s estimate, expressed as a date on the high side of the range, for project completion date, taken at CD-1 approval. | Date | 10 | N/A |  | FPD |  | Required |  |  |  |  |
|  | PDIR | Budget Request | Budget | Budget Fiscal Year | The fiscal year of the President’s Congressional Budget request (CRB). (YYYY) | Date | 4 | N/A | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  | Required (Annually) After Budget Submission to Congress) |  |
|  | PDIR | Budget Request | Budget | Budget Source | The source of data for the budget profile, such as the DOE Integrated Priority List, OMB, Congress, or the Performance Baseline . | A/N | 256 | Dropdown List of Values: DOE Integrated Priority List, OMB, Congress, Performance Baseline | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Budget Request | Budget | TEC (Design) ($K) *** | The total Preliminary Engineering Design funding in the Budget Request. | N | 12 |  | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Budget Request | Budget | TEC (Long Lead Items) ($K) *** | Total funding requested for long lead time items. | N | 12 |  | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Budget Request | Budget | TEC (Construction) ($K) *** | Enter the Total Estimated Construction cost estimated for the project. (Note: this will be inclusive of any LLI funds). | N | 12 |  | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Budget Request | Budget | OPC Excluding D&D ($K) | Enter total Other Project Costs (e.g. Pre-Conceptual Design and Start-up). | N | 12 |  | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Budget Request | Budget | D&D Costs ($K) | Enter the total cost for D&D associated with the construction project | N | 12 |  | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Budget Request | Budget | Operations ($K) | If the project includes operations, enter the total life cycle Operations Cost. Operations costs are for plant operations and are not to be confused with operations funds required as “OPCs” for line-item projects. (Many EM clean-up projects will only have Operations costs). This does not include operations costs after CD-4. | N | 12 |  | Discuss redesign with Cindy Seiter and Jim Fountain | OECM |  |  |  |
|  | PDIR | Project Cost | Project | TPC at CD-2 (LCC for EM) ($K) ** | The approved TPC at CD-2. For EM operations funded project this will be the total life-cycle cost of the project. | N | 12 |  | Discuss with Mel Frank - JM | OECM |  |  | Required |  |  |  |
|  | PDIR | Project Cost | Project | TPC Near-Term (EM PBSs Only) ($K) ** | The approved Near-Term TPC based on the Contract Performance Baseline for EM operations funded projects. | N | 12 |  | Discuss with Mel Frank - JM | OECM |  |  | Required (whenever new contract is awarded) |  |  |
|  | ART | Project Schedule | Project | Estimated Completion Date at CD-2 (high) | The FPD’s estimate for project completion date, expressed as a date on the high side of the range, at CD-2 approval | Date | 10 | N/A |  | FPD |  |  | Required |  |  |  |
|  | ART | Earned Value | Project | Original Contractor Management Reserve ($K) | The initial or original amount of Management Reserve set aside for the project by DOE. Enter if the contractor has a management reserve. For EM operations funded projects the MR will be for the current Near-Term project segment. | N | 12 | N/A |  | CONTR |  |  | Required |  |  |  |
|  | ART | Earned Value | Project | Original DOE Cost Contingency ($K) | The initial or original amount set aside by DOE for Cost Contingency. DOE Cost Contingency is the reserve budget held by DOE. For EM operations funded projects this contingency will be for the entire PBS and consistent with the project baseline validated at CD-2. | N | 12 | N/A |  | FPD |  |  | Required |  |  |  |
|  | PDIR | Earned Value | Project | Original DOE Schedule Contingency | The original amount of schedule contingency, expressed in days, set aside for the project by DOE. Schedule Contingency is the total float in calendar days planned for this project. For EM operations funded projects schedule contingency will be for the entire PBS and Will be consistent with the project baseline validated at CD-2. | N | 4 | N/A |  | FPD |  |  | Required |  |  |  |
|  | NEW | Earned Value | Project | Original Contractor Fee/Profit ($k) | The initial or original amount of Fee or Profit, expressed in dollars, set aside by DOE for the project. | N | 12 | N/A | Discuss – JM | FPD |  |  | Required |  |  |  |
|  | PMET | Project Schedule | Project | Actual Construction / Execution Start Date | The date that construction started for the project. | D | 10 | N/A | Requested by Paul Bosco 2007 | FPD |  |  |  | Required |  |  |
|  | ART | Project Cost | Project | TPC at CD-3 (LCC for EM) ($K) ** | The FPD’s estimate for Total Project Cost, expressed in dollars, at CD-3 approval. | N | 12 | N/A | Discuss EM – JM | FPD |  |  |  | Required |  |  |
|  | ART | Project Schedule | Project | Estimated Completion Date at CD-3 (high) | The FPD’s estimate for project completion date, as expressed as a date on the high side of the range, at CD-3 approval. | Date | 10 | N/A |  | FPD |  |  |  | Required |  |  |
|  | ART | Earned Value | Project | ETC – Bottoms Up ($K) PMB | The bottoms up estimate to complete the project, as expressed in dollars. ETC is the latest bottoms-up estimate of the remaining work. ETC includes remaining contingency and management reserve but does not include profit or fee. For EM projects ETC will be for the contract period and will not include DOE held contingency. | N | 12 | N/A | Discuss – JM | CONTR |  |  | Required (Annually) |  |
|  | ART | Earned Value | Project | ETC - Bottoms U – Date PMB | The date that the bottoms up estimate to complete exercise was made. | Date | 10 | N/A | Discuss – JM | CONTR |  |  |  |  |
|  | ART | Earned Value | Upload File | BCWS Profile ($K) PMB | Budgeted Cost of Work Scheduled (BCWS) or Planned Value (PV) is the budget for the planned scope that is scheduled to be accomplished during the month. Enter monthly BCWS through project completion. BCWS must flow from the approved baseline at CD-2. | N | 12 | N/A |  | CONTR |  |  | Required |  |  |  |
|  | NEW | Earned Value | Upload File | BAC ($K) PMB | Enter the Budget at Completion (BAC), expressed in dollars, The BAC must equal the total of all BCWS Profile entries for the entire life cycle of the project, BAC can be calculated or can be entered manually to validate the integrity of the BCWS profile. | N | 12 | N/A | Discuss - NCA | OECM or Calculated |  |  | Required |  |  |  |
|  | New | Earned Value | Upload File | WBS Level Number PMB | The alphanumeric code that identifies the level of activity within the Contractor’s WBS at which EVMS is calculated. | A/N | 25 | N/A | Discuss NCA | Automatic |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Upload File | Monthly BCWP ($K) PMB | The Budgeted Cost of Work Performed (BCWP) or the Earned Value (EV) for the indicated period. This is the total budget for the scope that was actually accomplished during the month. | N | 12 | N/A |  | CONTR |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Upload File | Cumulative BCWP ($K) PMB | The BCWP amount, expressed in dollars for the cumulative reporting period, summarized from the contractor’s WBS. | N | 12 | N/A |  | Calculated |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Upload File | Monthly ACWP ($K) PMB | Cost (AC) for the indicated period. ACWP is the cost actually incurred for the work accomplished during the month and is based on actual expenses accrued and not from financial reports. | N | 12 | N/A |  | CONTR |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Upload File | Cumulative ACWP (K) PMB | The ACWP amount, expressed in dollars for the cumulative reporting period, summarized from the contractor’s WBS. | N | 12 | N/A |  | Calculated |  |  | Required (Monthly) |  |
|  | NEW | Earned Value | Upload File | Contractor Indirect Costs ($K) PMB | All monthly indirect costs allocated to the contract. | N | 12 | N/A | Discuss – NCA DOE M 413.3-1 P.12-8 | CONTR |  |  | Required (Monthly) |  |
|  | NEW | Earned Value | Upload File | Cost Variance Narrative | The contractor’s written narrative of cost variance, as sourced from the control account level of the contractor’s WBS. Give specific and most significant causes of variances, corrective actions being implemented, and recovery times. The narrative explanation must be clear, brief to the point and written to be understood by senior management – No abbreviations or acronyms are to be used. If the previously entered BCWS profile was changed for any reason an explanation must be provided in this narrative. | A/N | 4000 | N/A |  | CONTR |  |  | Required (Monthly) |  |
|  | NEW | Earned Value | Upload File | Schedule Variance Narrative | The contractor’s written narrative of schedule, as sourced from the control account level of the contractor’s WBS. Give specific and most significant causes of variances, corrective actions being implemented, and recovery times. The narrative explanation must be clear, brief to the point and written to be understood by senior management – No abbreviations or acronyms are to be used. If the previously entered BCWS profile was changed for any reason an explanation must be provided in this narrative. | A/N | 4000 | N/A |  | CONTR |  |  | Required (Monthly) |  |
|  | NEW | Earned Value | Upload File | Earned Value Narrative | The contractor’s written narrative of earned value, as sourced from the control account level of the contractor’s WBS. Give specific and most significant causes of variances, corrective actions being implemented, and recovery times. The narrative explanation must be clear, brief to the point and written to be understood by senior management – No abbreviations or acronyms are to be used. If the previously entered BCWS profile was changed for any reason an explanation must be provided in this narrative. | A/N | 4000 | N/A |  | CONTR |  |  | Required (Monthly) |  |
|  | NEW | Earned Value | Upload File | Risk Register Log | The contractor’s risk log, as sourced from the contractor’s scheduling system. | A/N | 4000 | N/A |  | CONTR |  |  |  |  |
|  | ART | Earned Value | Upload File | Contractor Management Reserve Used This Period ($K) | The amount of Management Reserve, expressed in dollars, used this period. | N | 12 | N/A |  | CONTR |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Project | Remaining Contractor Management Reserve ($K) PMB | The remaining amount of Management Reserve, expressed in dollars. | N | 12 | N/A |  | Calculated |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Project | DOE Cost Contingency Used This Period ($K) | The amount of Cost Contingency, expressed in dollars, used this period | N | 12 | N/A |  | FPD |  |  | Required (Monthly) |  |
|  | ART | Earned Value | Project | Remaining DOE Cost Contingency ($K) PB | The remaining amount of Cost Contingency, expressed in dollars. | N | 12 | N/A |  | Calculated |  |  | Required (Monthly) |  |
|  | PDIR | Earned Value | Project | DOE Schedule Contingency Used This Period (in days) | Enter if Schedule Contingency (the total float in days planned for this project) was used. | N | 4 | N/A |  | FPD |  |  | Required (Monthly) |  |
|  | PDIR | Earned Value | Project | Remaining DOE Schedule Contingency (days) PB | The remaining number of days of Schedule Contingency. | N | 4 | N/A |  | Calculated |  |  | Required (Monthly) |  |
|  | New | Earned Value | Project | Contractor Fee/Profit Used This Period ($K) | The amount of Contractor Fee/Profit, expressed in dollars, used this period | N | 12 | N/A | Discuss – JM | FPD |  |  | Required (Monthly) |  |
|  | New | Earned Value | Project | Remaining Contractor Fee/Profit ($K) PB | The remaining Contractor Fee/Profit. | N | 12 | N/A | Discuss – JM | Calculated |  |  | Required (Monthly) |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Version Number PB | The baseline change number from the change control log. This number is designed to make it easier to track and sort baseline changes. | N | 2 | N/A |  | CONTR |  |  | Required whenever a change to the Performance Baseline is approved. |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Title PB | The title given to the baseline change, such as Congressional Baseline. | A/N | 50 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Approval Date PB | The date that the PB was approved by the approving official. MM/DD/YYYY | Date | 12 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Approving Official Name PB | The name of the approving official that approved the PB. | A/N | 50 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Change Submission Date PB | The date that the request for the change to the PB was made. mm/dd/yyyy | Date | 12 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Change Directed? (Y/N) PB | A flag (Yes/No) that indicates if the change to the PB was directed by DOE. | Y/N | 1 | Yes No |  | CONTR |  |  |  |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Change in Cost ($K) PB | If the baseline change accompanies a change in cost, enter the dollar value of the approved change (positive or negative) | N | 12 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PB Baseline Change | PB Change | Performance Baseline Change in Schedule PB | If the baseline change accompanies a change in schedule, enter the calendar days of approved change (positive or negative) that the schedule will be extended or reduced. | N | 6 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Version Number PMB | The baseline change number from the change control log. This number is designed to make it easier to track and sort baseline changes. | N | 2 | N/A |  | CONTR |  |  | Required whenever a change to the Performance Baseline is approved. |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Title PMB | The title given to the baseline change, such as Congressional Baseline. | A/N | 50 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Approval Date PMB | The date that the PMB was approved by the approving official. MM/DD/YYYY | Date | 12 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Approving Official Name PMB | The name of the approving official that approved the PMB. | A/N | 50 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Change Submission Date PMB | The date that the request for the change to the PMB was made. mm/dd/yyyy | Date | 12 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Change Directed? (Y/N) PMB | A flag (Yes/No) that indicates if the change to the PMB was directed by DOE. | Y/N | 1 | Yes No |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Change in Cost ($K) PMB | If the baseline change accompanies a change in cost, enter the dollar value of the approved change (positive or negative) | N | 12 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | PMB Baseline Change | PMB Change | Performance Measurement Baseline Change in Schedule PMB | If the baseline change accompanies a change in schedule, enter the calendar days of approved change (positive or negative) that the schedule will be extended or reduced. | N | 6 | N/A |  | CONTR |  |  |  |  |
|  | PDIR | Project Scope | KPP | KPP Scope Narrative at Completion PB | A brief narrative done at the completion of the project that verifies the completed scope against the approved scope. KPPs at CD-4 must equal KPP’s at CD-2. | A/N | 4000 | N/A |  | FPD |  |  |  |  | Required |  |
|  | ART | Project Cost | Project | Actual Cost at Financial Close-out ($K) PB | Enter the final cost of the project when final financial closure is obtained. | N | 12 | N/A |  | FPD |  |  |  |  |  | Required |

# Footnotes

DOE Guide 413.3-10, Appendix B-1, May 6, 2008

Project attachments at CD-0 include the Pre-Conceptual Planning documents, Mission Needs Statement, Tailoring Strategy document, Mission Validation Independent Project Review document, Program Requirements document (required for NNSA only).

Project attachments at CD-1include the Conceptual Design Report, Acquisition Strategy, Preliminary Project Execution Plan, Project Data Sheet, Environmental documents, High Performance Sustainable Building Consideration documents, Preliminary Security Vulnerability Assessment, Cyber Security Plan (for IT projects),  Conceptual Safety Design Report, Preliminary Hazard Analysis Report, Preliminary Safety Validation Report.

Project attachments at CD-2include the Performance Baseline document, the revised Project Execution Plan, Performance Baseline Validation Independent Review document, Independent Cost Estimate, Preliminary Design document, Project Data Sheet, Preliminary Safety Design Report, Hazard Analysis Report, Preliminary Security Vulnerability Assessment Report, Preliminary Safety Validation Report, national Environmental Policy Act documentation.

Project attachments at CD-3include the revised Project Execution Plan, revised Performance Baseline, and revised Project Data Sheet, Independent Review for Construction or Execution Readiness, Preliminary Safety Analysis Report, the revised Hazard Analysis Report, Preliminary Security Vulnerability Assessment Report, Safety Evaluation Report.

Project attachments at CD-4 include the Checkout, Testing and Commissioning Plan, the Project Transition to Operations Plan, the revised Quality Assurance Plan, Safety Analysis Report, Construction Project Safety and Health Plan, Hazard Analysis Report, Security Vulnerability Assessment Report, Cyber Security Plan (for IT projects), Safety Evaluation Report, Final Project Closeout Report, Lessons Learned Report, Operational documentation, Key Performance Parameters Verification Report.

Projects with a Total Project Cost (TPC) greater than or equal to $20 million requires entry of Earned Value data elements