# MODEL STRUCTURE

# FEASIBILITY PHASE PROJECT MANAGEMENT PLAN

#### USE OF THIS MODEL

1.  BACKGROUND:

This model for a Project Management Plan (PMP) for the feasibility phase (formally referred to as a Project Study Plan (PSP) was developed in response to needs originally expressed at the South Pacific Division's annual planning conferences.  This need became more critical with the implementation of the expedited reconnaissance phase process which requires a much more efficient preparation of the project management plan, and even more critical with the implementation of the Program and Project Management Business Process.

2.  OBJECTIVES

This model strives to provide supplementary assistance for the development of PMPs.  It provides a model structure for the preparation of the Section 905(b) Analysis, which is both the basis and an integral part of the PMP, and it also provides a model of how to meet the PMP requirements for management of the study.  Through the structure it defines the process that is necessary to develop the PMP.  It also provides a structure for the implementation of the proposed South Pacific Division’s Regional Project Management Business Process, dated February 2000.

3.  CONTENT AND USE

The model structure provides an outline for the PMP and includes table formats and standard text that can be adapted to any study.  The text is also annotated in selected places to describe additional study specific information that would be required.  This model may be used as a reference and basis for preparing individual PMPs.  Although the structure that is presented in this model may not exactly fit a PMP that is under preparation, it does demonstrate the content that is required to properly develop a PMP.  The complexity, size and duration of any particular feasibility study will dictate the size and complexity of its PMP.  Thus, the intent of this model is to provide a foundation that can be adapted for a particular study.

4.  FILE TYPES

The Model PMP is a Microsoft Word document with embedded Microsoft Excel spreadsheets.  Enclosure C to the PMP, which contains the detailed scopes of work for individual tasks, is a Microsoft Excel document with embedded text descriptions in Microsoft Word.

## AUTHORIZED NAME OF STUDY

### COUNTY, STATE

FEASIBILITY PHASE

PROJECT MANAGEMENT PLAN

# Name District

Name Division

## Date:

CONCURRENCE PAGE

As members of the Name  District Project Review Board, we the undersigned, concur in the project management plan dated date       for the study name       .  We understand that the project management plan is a living management document that will be updated throughout the course of the study.

Name			Title			Signature			Date

NAME OF STUDY

FEASIBILITY PHASE

PROJECT MANAGEMENT PLAN

##### TABLE OF CONTENTS

Chapter 1- Purpose and Scope								1-1

Chapter 2 - Section 905(b)(WRDA) Analysis						2-1

Chapter 3 - Work Breakdown Structure							3-1

Chapter 4 - Scopes of Work								4-1

Chapter 5 - Responsibility Assignment							5-1

Chapter 6 – Feasibility Study Schedule							6-1

Chapter 7 - Feasibility Cost Estimate							7-1

Chapter 8 - Quality Control Plan								8-1

Chapter 9 - Identification of Procedures and Criteria						9-1

Chapter 10 - Coordination Mechanisms						 	10-1

##### ENCLOSURES

Enclosure A - Project Area Map								A-1

Enclosure B - CESPD Milestone System – Feasibility Phase					B-1

Enclosure C - Detailed Scopes of Work							C-1

Enclosure D - PMP Quality Certification							D-1

Enclosure E - List of Acronyms								E-1

NAME OF STUDY

FEASIBILTY PHASE

PROJECT MANAGEMENT PLAN

# CHAPTER I – PURPOSE AND SCOPE

1.  DEFINITION OF A PROJECT MANAGEMENT PLAN:

a.  The project management plan for the feasibility phase, herein after referred to as the PMP, is an attachment to the Feasibility Cost Sharing Agreement (FCSA), which defines the planning approach, activities to be accomplished, schedule, and associated costs that the Federal Government and the local sponsor(s) will be supporting financially.  The PMP, therefore defines a contract between the Corps and the local Sponsor(s), and reflects a "buy in" on the part of the financial backers, as well as those who will be performing, and reviewing, the activities involved in the feasibility study.  The PMP describes the initial tasks of the feasibility phase, continues through the preparation of the final feasibility report, the project management plan for project implementation and design agreement, and concludes with support during the Washington-level review of the final feasibility report.

b.  The PMP is a basis for change.  Because planning is an iterative process without a predetermined outcome, more or less costs and time may be required to accomplish reformulation and evaluations of the alternatives.  Changes in scope will occur as the technical picture unfolds.  With clear descriptions of the scopes and assumptions outlined in the PMP, deviations are easier to identify.  The impact in either time or money is easily assessed and decisions can be made on how to proceed.  The PMP provides a basis for change.

c.  The PMP is a basis for the review and evaluation of the feasibility report.  Since the PMP represents a contract among study participants, it will be used as the basis to determine if the draft feasibility report has been developed in accordance with established procedures and previous agreements.   The PMP reflects mutual agreements of the district, division, sponsor and HQUSACE into the scope, critical assumptions, methodologies, and level of detail for the studies that are to be conducted during the feasibility study.  Review of the draft report will be to insure that the study has been developed consistent with these agreements.  The objective is to provide early assurance that the project is developed in a way that can be supported by higher headquarters.

d.  The PMP is a study management tool.  It includes scopes of work that are used for funds allocation by the project manager.  It forms the basis for identifying commitments to the non-Federal sponsor and serves as a basis for performance measurement.

2.  SUMMARY OF PROJECT MANAGEMENT PLAN CONTENTS:

This PMP is comprised of the following chapters:

- Chapter 1 - Purpose and Scope.  This chapter includes the definition of the PMP and a summary of the PMP requirements.

- Chapter 2 - Section 905(b) Analysis.  This chapter includes the approved Section 905(b) Analysis that includes an overview of the reconnaissance study findings, the plan formulation rationale and proposed streamlining initiatives.  This chapter also documents any deviations from the approved Section 905(b) Analysis that have occurred during the negotiations of the FCSA.

- Chapter 3 - Work Breakdown Structure.  A product based Work Breakdown Structure (WBS) defines the project, sub-projects, parent tasks and tasks that will be accomplished through the study.

- Chapter 4 - Scopes of Work. A detailed scope of the tasks and activities that describe the work to be accomplished, in narrative form, that answers the questions: "what, how, and how much".  This chapter provides a reference to the detailed scopes of work that are included as Enclosure C to the PMP.

- Chapter 5 - Responsibility Assignment.  An Organizational Breakdown Structure (OBS) will define "who" will perform work on the study.  This allows the identification of the functional organization that will perform each of the tasks in a Responsibility Assignment Matrix (RAM).

- Chapter 6 – Feasibility Study Schedule. The schedule will define "when" key decision points,  CESPD milestone conferences and mandatory HQUSACE milestones will be accomplished.

- Chapter 7 - Feasibility Cost Estimate.  This is the baseline estimate for the feasibility phase of the study.

- Chapter 8 - Quality Management Plan: This chapter supplements the district’s Quality Management Plan.  It highlights any deviations to the district’s plan and lists the members of the study team and the independent review team.

- Chapter 9 - Identification of Procedures and Criteria: This chapter identifies references to the regulations and other guidance that covers the planning process and reporting procedures.

- Chapter 10 - Coordination Mechanisms: This chapter describes the study’s public involvement program.

# CHAPTER II

# NAME OF STUDY

# SECTION 905(b) (WRDA 86) ANALYSIS

(INSERT COPY OF APPROVED 905(B) ANALYSIS HERE)

15.  CHANGES TO THE APPROVED SECTION 905(b) ANALYSIS.

a.  The Section 905(b) Analysis was approved by Corps Headquarters on indicate date.  This approval was conditioned on the following revisions:

1) Indicate any revisions made as result of the coordination with HQUSACE.

2) …. …

b.  The following revisions to the cost, schedule or scope have been made from the approved Section 905(b) Analysis as a result of final negotiations of the PMP and FCSA:

1) Indicate any revisions made as a result of coordination with the non-Federal sponsor.

2)  … …

# CHAPTER III – WORK BREAKDOWN STRUCTURE

1.  LEVELS OF THE WORK BREAKDOWN STRUCTURE

The work breakdown structure is divided into the following four levels.

a.  Level 1: The Project

b.  Level 2: The Subprojects are established by the phase that is appropriated by Congress – in this case the feasibility phase of the study.  This level includes the major products generated in the feasibility phase: the Feasibility Report, the Project Management Plan and the PED Agreement, which are identified in the first character of the work breakdown structure code.

b.  Level 3: The Parent Tasks are generally identified as separate products that go into the final feasibility phase documentation.  Examples of these subprojects include such items as the real estate report, the H&H report, etc.  These parent tasks are normally identified with the responsibility of a particular functional organization.   This level is generally identified in the second and third characters of the work breakdown structure code.

c.  Level 4: The Tasks are major separable elements of the subprojects that are keyed to separately identifiable products that are developed for the major feasibility study milestones.  These tasks are elements of work resulting in a deliverable product which have a beginning and an end, may be accomplished within one functional organization, can be described at a work order of detail and are the lowest level that will be specifically tracked with respect to cost and schedule.  As an example, the cost estimates for the draft feasibility report would be an example of a task.  Tasks can be described as the summation of activities that would be accomplished by a particular functional organizational between two of the milestone events.  The milestones are defined in Enclosure B.  The following durations between milestones are generally used for the establishment of tasks.

1) – Between Milestone F1 and F3

2) – Between Milestone F3 and F4

3) – Between Milestone F4 and F4A

4) – Between Milestone F4A and F5

5) – Between Milestone F5 and F8

6) – Between Milestone F8 and F9

d.  Level 5: The Activities are separate elements of work that are managed by the functional managers to whom the tasks are assigned and which may not necessary result in a deliverable work product to another organization.  These activities are not tracked separately in terms of cost and schedule but are described in the scopes of work to the extent required to provide a clear understanding of the work required.

Note:  A task has not been defined very well in the guidance and the expectations of reviewers have not been consistent.  Because of this lack of definition, it is often defined differently.  At the extremes, a task could be defined as the preparation of a feasibility study, in which case there would be very few tasks described in a PMP.  At the other extreme, it could also be defined as the measurement of a single first floor elevation as input to the flood damage portion of an economic analysis, which would mean that the PMP would require the description of many thousands of tasks

2.  LISTING OF TASKS - WORK BREAKDOWN STRUCTURE

In accordance with the levels above, the following work breakdown structure indicates subprojects and parent tasks in bold type, followed by the subordinate tasks.

2.  LISTING OF TASKS - WORK BREAKDOWN STRUCTURE  (Continued)

2.  LISTING OF TASKS - WORK BREAKDOWN STRUCTURE  (Continued)

#### CHAPTER IV – SCOPES OF WORK

1.  DETAILED SCOPES OF WORK

For each task that is included in the work breakdown structure, a scope of work is developed that describes the work that is to be performed.  For each task, the scope describes the work, including specific activities, to be accomplished in narrative form.  The scopes of work have been developed by the study team, which includes representatives of the non-Federal sponsor.  The scopes also reflect the policy exceptions and streamlining initiatives that have been approved in the Section 905(b) Analysis.  The detailed scopes of work for the feasibility study are organized by parent task in Enclosure C.

2.  DURANTIONS OF TASKS

The durations for the tasks are entered into the project’s network analysis system (NAS) to develop the schedule that is included in Chapter VI – Schedule.  The durations are based on negotiations between the Project Manager and the chiefs of the responsible organizations, as identified in Chapter V, Responsibility Assignment.

3.  COSTS OF TASKS

Lastly, the scopes of work for the tasks are grouped by the parent tasks that they support.  The total estimates for the parent tasks are then combined in the Feasibility Cost Estimate, Chapter VII.  The cost estimates for the tasks are also based on negotiations between the Project Manager and the chiefs of the responsible organizations.

CHAPTER V – RESPONSIBILITY ASSIGNMENT

1.  ORGANIZATIONAL BREAKDOWN STRUCTURE

The scopes of work represent agreements between the Project Manager and first line supervisors of functional organizations.  The functions of these organizations in support of the project are defined by the work that is assigned.  All organizations responsible for tasks, including the local sponsor and other agencies, are included with their organization codes in the following Organizational Breakdown Structure (OBS).

2.  RESPONSIBILITY ASSIGNMENT MATRIX

The scopes for each task are grouped by the parent task that they support and the primary responsible organization for each parent task is identified by the organization codes in the following Responsibility Assignment Matrix (RAM).

#### CHAPTER VI – FEASIBILITY STUDY SCHEDULE

1.  SCHEDULE DEVELOPMENT

All schedules are developed using a Network Analysis System (NAS).  The network is based upon the tasks that are listed in Chapter III, Work Breakdown Structure and the durations that are included in the detailed scopes of work in Chapter IV, Scope of Studies.  Major milestones that are defined in Enclosure B, CESPD Milestone System, are also included in the schedules.

2.  FUNDING CONSTRAINTS

Funding for the first Fiscal Year of the feasibility study is normally limited because of the uncertainty in the initiation of the feasibility phase.  This constraint has been reflected in the development of the study schedule.  Following the first year, an optimum schedule based upon unconstrained funding has been assumed for subsequent Fiscal Years.

3.  LOCAL SPONSOR COMMITMENTS

Milestones become commitments when the project manager meets with the local sponsor(s) at the beginning of each Fiscal Year and identifies two to five tasks that are important for the district to complete during the Fiscal Year.  These commitments would be flagged in the PROMIS database and monitored and reported on accordingly.

4.  UNCERTAINTIES IN THE SCHEDULE

Because of the limited evaluations in the reconnaissance phase, the schedule must make appropriate allowances for uncertainty.  Describe allowances such as additional time for resolving comments on the draft report.

5.  MILESTONE SCHEDULE

The schedule for the milestones in the CESPD Milestone System is as follows:

CHAPTER VII – FEASIBILITY COST ESTIMATE

1.  BASIS FOR THE COST ESTIMATE

a.  The feasibility cost estimate is based upon a summation of the costs that were identified for the individual tasks in detailed scopes of work that are included in Enclosure C, Detailed Scopes of Work.  Study cost estimates include allowances for inflation so that the non-Federal sponsor is fully aware of its financial commitment.

b.  Appropriate contingencies and contingency management are included to adequately deal with the uncertainty in the elements of the study.  Experience has shown that approximately 20 percent of the study costs should be reserved for activities after the release of the draft report.  Contingencies in the amount required to raise the costs of activities after the draft report this amount have been added to the cost estimate.

2.  COSTS FOR FEDERAL AND NON-FEDERAL ACTIVITIES

The non-Federal sponsor must contribute 50 percent of the cost of the study during the period of the study.  Not more than one-half of the non-Federal share may be made by the provision of services, materials, supplies or other in-kind services necessary to prepare the feasibility report.  The feasibility cost estimate below includes credit for work that is to be accomplished by the non-Federal sponsor.

#### CHAPTER VIII – QUALITY CONTROL PLAN

1.  QUALTIY CONTROL PLAN OBJECTIVE

The quality control objective is to achieve feasibility phase documents and services that meet or exceed customer requirements, and are consistent with Corps policies and regulations.

2.  GUIDELINES FOLLOWED FOR TECHNICAL REVIEW

The guidelines for independent technical review are set forth in the South Pacific Division Quality Management Plan, CESPD R 1110-1-8, and in the corresponding District Quality Management Plan, _______.

3.  ROSTER OF THE PROJECT STUDY TEAM

4.  ROSTER OF THE TECHNICAL REVIEW TEAM

5.  DOCUMENTS TO BE REVIEWED AND SCHEDULE FOR REVIEW ACTIVITES

a.  All of the products of the tasks listed in the detailed scopes of work in Chapter IV, Scope of Studies, will be subject to independent technical review.  Seamless Single Discipline Review will be accomplished prior to the release of materials to other members of the study team or integrated into the overall study.  Section chiefs shall be responsible for accuracy of the computations through design checks and other internal procedures, prior to the independent technical review.

b.  Independent product review will occur prior to major decision points in the planning process at the CESPD milestones so that the technical results can be relied upon in setting the course for further study.  These products would include documentation for the CESPD mandatory milestone conferences (F3 & F4), HQUSACE issue resolution conferences (AFB &FRC) and the draft and final reports.  These products shall be essentially complete before review is undertaken.  Since this quality control will have occurred prior to each milestone conference, the conference is free to address critical outstanding issues and set direction for the next step of the study, since a firm technical basis for making decisions will have already been established.  In general, the independent technical review will be initiated at least two week prior to a CESPD mandatory milestone conference and at least two weeks prior to the submission of documentation for a HQUSACE issue resolution conference.

c.  For products that are developed under contract, the contractor will be responsible for quality control through an independent technical review.  Quality assurance of the contractor’s quality control will be the responsibility of the district.

6.  DEVIATIONS FROM THE APPROVED QUALITY MANGEMENT PLAN

The South Pacific Division has approved the following deviations to the approved quality management plan:

- List deviations

7.  COST ESTIMATE FOR QUALITY MANAGEMENT

The costs for conducting independent technical review are included in the individual scopes of work that are included in Chapter IV, Scope of Studies.  Quality management activities of Branch and Division Chiefs are included in Supervision and Administration.  The total cost for quality management is approximately $             , which is approximately __% of the study cost estimate.  Of this amount, $______ is included in parent task JLD00 and $______ is included in other parent tasks.

#### 8.  PMP QUALITY CERTICATION

The Chief, Planning Division has certified that 1) the independent technical review process for this PMP has been completed, 2) all issues have been addressed, 3) the streamlining initiatives proposed in this PMP will result in a technically adequate product, and 4) appropriate quality control plan requirements have been adequately incorporated into this PMP.  The signed certification is included as Enclosure D.

9.  FEASIBILITY PHASE CERTIFICATION

The documentation of the independent technical review shall be included with the submission of the reports to CESPD.  Documentation of the independent technical review shall be accompanied by a certification, indicating that the independent technical review process has been completed and that all technical issues have been resolved.   The certification requirement applies to all documentation that will be forwarded to either CESPD or HQUSACE for review or approval.  The Chief, Planning Division will certify the pre-conference documentation for the HQUSACE issue resolution conferences and the draft feasibility report.  The District Commander will certify the final feasibility report, which includes the signed recommendation of the District Commander.  This certification will follow the example that is included as Appendix H of the CESPD Quality Management Plan and will be signed by the Chief, Planning Division and the District Commander.

#### CHAPTER IX IDENTIFICATON OF PROCEDURES AND CRITERIA

1.  EVOLUTION OF THE PMP

The PMP describes all activities from the initial tasks of the feasibility phase through the preparation of the final feasibility report, the project management plan for project implementation and design agreement, and conclude with the district's support during the Washington-level review.  As the PMP is based primarily on existing information, it will be subject to scope changes as the technical picture unfolds.  While this PMP includes tasks through the completion of the feasibility study, the level of detail in the scopes of work are greater for those tasks that occur prior to the first milestone conference.  This plan will be reviewed at the first milestone conference and additional detail will be added to the scopes of work for the subsequent tasks.   During the feasibility phase of the study, the current PMP, including the documentation of agreements on changes to the conduct of the study, will be addressed at each of the CESPD milestone conferences and at the formal issue resolution conferences with HQUSACE, including the AFB and FRC.

2.  THE PLANNING PROCESS

The Water Resource Council's Principles and Guidelines (P&G) is the basic planning guidance, which establishes a six-step planning process.  This process is a conceptual planning sequence for developing solutions to water resource problems and opportunities.  The Planning Manual and Planning Primer, both published by IWR provide excellent coverage of the planning process.  The South Pacific Division also provides training in the six- step process.

3.  POLICY

The policies that govern the development of projects are contained in the DIGEST OF WATER REOURCES POLICIES AND AUTHORITIES, EP 1165-2-1.

4.  CORPS REGULATIONS

All of the Corps’ current regulations are included on the HQUSACE homepage.  The most important of these regulations is ER 1105-2-100, PLANNING GUIDANCE NOTEBOOK.  Policy compliance review is addressed in EC 1165-2-203, TECHNICAL AND POLICY COMPLIANCE REVIEW.  And, quality control is covered in the CESPD Quality Management Plan, CESPD R 1110-1-8.  The review of the products will be accomplished with the review checklist that is provided in EC 1165-2-203 as Appendix B, POLICY COMPLIANCE REIVEW CONSIDERATIONS.

6.  PROCESSING REQUIREMENTS

# In addition to ER 1105-2-100, the South Pacific Division has provided additional guidance on the processing requirements for each of the milestone submittals.  This guidance is contained in CESPD-ET-P memorandum, dated 30 March 2000, subject: Processing of Planning Reports in the South Pacific Division.

CHAPTER X – COORDINATION MECHANISMS

1.  CESPD MILESTONES

Two of the milestones in the CESPD milestone system have been established specifically for the purpose of providing a public forum to receive public input.  The first of these is the initial public workshop.  This workshop is an opportunity to present the study to the public, obtain input and public opinions, and fulfill the NEPA scoping meeting requirements.  The second milestone in the system is the final public meeting.  This meeting is after the release of the draft report for public review and is an opportunity to present the findings of the draft report to the public and receive public comment.

2.  STUDY SPECIFIC PUBLIC INVOLVEMENT ACTIVITIES

Provide a description of the study’s public involvement program.

#### ENCLOSURE B

CESPD Milestone System

# FEASIBILITY PHASE

# MIL(	MILESTONE NAME		DESCRIPTION

100	Initiate Feasibility Phase 		SPD Milestone F1( - This is the date the district receives 						Federal feasibility phase study funds.

101	Feas Study Pub Wkshp (F2)	SPD Milestone F2 – This is a Public Meeting/Workshop to 						inform the public and obtain input, public opinions and fulfill 						scoping requirements for NEPA purposes.

102 	Feas Study Conf #1 (F3)		SPD Milestone F3 – The Feasibility Scoping Meeting is						with HQUSACE to address potential changes in the PMP.  It 						will establish without project conditions and screen 							preliminary plans.

103	Feas Study Conf #2 (F4)		SPD Milestone F4 – The Alternative Review Conference will   					evaluate the final plans, reach a consensus that the evaluations 						are adequate to select a plan and prepare AFB issues.

124	Date of AFB			SPD Milestone F4A - Alternative Formulation Briefing 						(AFB) is for policy compliance review of the proposed plan 						with HQUSACE to identify actions required to prepare and 						release the draft report.

145	Public Review of Draft Report	SPD Milestone F5 - Initiation of field level coordination of 						the draft report with concurrent submittal to HQUSACE 						through	SPD for policy compliance review.

162	Final Public Meeting		SPD Milestone F6 - Date of the final public meeting.

130 	Feasibility Review Conference	SPD Milestone F7 - Policy compliance review of the draft 						report with HQUSACE to identify actions that are required to 						complete the final report.

165	Feasibility Report w\NEPA	SPD Milestone F8 - Date of submittal of final report package 						to CESPD-ET-P, 	including technical and legal certifications, 						compliance memorandum and other required documentation.

170 	MSC Commander’s Public Notice  SPD Milestone F9 - Date of issue of the Division 						Commander’s Public Notice.  Congressional notification 					would occur two days prior.  The report and supporting

MIL(	MILESTONE NAME		DESCRIPTION

documentation would be forwarded to HQUSACE.  This 					milestone is used as the completion of the feasibility report in 					the CMR.

310	Filing of Final EIS/EA		Date that the notice appears in the Federal Register.  Letters 							for filing would be furnished by HQUSACE.

330	Chief’s Report to ASA (CW) 	Date of the signed report of the Chief of Engineers.

320	ROD Signed or FONSI Signed	Date that the ROD is signed by the ASA(CW) when 							forwarded for authorization.

350	President Signs Authorization	Date President signs authorizing legislation.

ENCLOSURE D

#### QUALITY CONTROL CERITIFICATION

COMPLETION OF QUALITY CONTROL ACTIVITIES

The District has completed the Project management plan for the Name of Study.  All quality control activities defined in the generic quality control plan for reconnaissance phase products have been completed.  Compliance with clearly established policy principles and procedures, utilizing justified and valid assumptions, has been verified, including whether the PMP meets the non-Federal sponsors needs and is consistent with law and existing Corps policy.  All issues and concerns resulting from the independent technical review of the PMP have been resolved.

CERTIFICATION

Certification is hereby given that 1) the independent technical review process for this PMP has been completed, 2) all issues have been addressed, 3) the streamlining initiatives proposed in this PMP will result in a technically adequate product, and 4) appropriate quality control plan requirements have been adequately incorporated into this PMP.  In summary, the study may proceed into the feasibility phase in accordance with this PMP.

______________                       		____________________________

Date			                       Chief, Planning Division

ENCLOSURE E

#### LIST OF ACRONYMS

AFB		Alternative Formulation Briefing

ASA (CW)	Assistant Secretary of the Army for Civil Works

CESPD		South Pacific Division (also SPD)

DE		Division Engineer (Division Commander)

EA		Environmental Assessment

EC		Engineering Circular

EIS		Environmental Impact Statement

EP		Engineering Pamphlet

ER		Engineering Regulation

FCSA		Feasibility Cost Sharing Agreement

FONSI		Finding of No Significant Impact

FRC		Feasibility Review Conference

H&H		Hydrology and Hydraulics

HQUSACE	Headquarters, U.S. Army Corps of Engineers

HTRW		Hazardous, Toxic and Radioactive Waste

MSC		Major Subordinate Command

NAS		Network Analysis System

NED		National Economic Development

NEPA		National Environmental Policy Act

OBS		Organizational Breakdown Structure

P&G		Water Resources Council’s Principles and Guidelines

PED		Preconstruction Engineering and Design

PMP		Project Management Plan

PPMD		Programs and Project Management Division

PROMIS	Project Management Information System

PSP		Project study plan (now referred to as a PMP)

RAM 		Responsibility Assignment Matrix

ROD		Record of Decision

S&A		Supervision and Administration

SPD		South Pacific Division (CESPD)

USF&WL	U.S. Fish and Wildlife Service

WBS		Work Breakdown Structure

WRDA		Water Resources Development Act

# Footnotes

( MIL – Milestone number used in the PROMIS database.

2 F1 through F9 are the historical designations for the SPD Milestones.

( MIL – Milestone number used in the PROMIS database.