## Attachment A
Indian Health Service
Federally Administered Program
| 1 | Recommendation | Completion Date | On Track? (Y/N) | Comments on Status
IHS-35 |  | Develop a long-term performance goal to decrease obesity rates in the AI/AN population. | FY 2008 | Y | IHS is on track for developing a long term goal. However, expanding the focus of obesity treatment and prevention to include adults is dependent on the infrastructure developed and lessons learned in dealing with childhood obesity over the next five years. The results to date from the Diabetes Prevention Project, an NIH study, indicate that a significant amount of resources will be necessary to decrease obesity rates by even a slight amount.
|  | Next Milestone | Next Milestone Date | Lead Organization | Lead Official
|  | Provide proposed measures to OMB for review. | 2006-09-30 | Division of Clinical and Preventive Services | Jean Charles-Azure
| 2 | Recommendation | Completion Date | On Track? (Y/N) | Comments on Status
|  | Develop an annual target for decreasing obesity in AI/AN children. | 2006-09-30 | Y | IHS is on track for establishing a baseline for setting an annual performance target. However, setting annual targets is dependent on the diffusion of effective pilot technologies to the larger Indian health system.
|  | Next Milestone | Next Milestone Date | Lead Organization | Lead Official
|  | Baseline developed. | 2004-09-30 | Division of Clinical and Preventive Services | Jean Charles-Azure
IHS-36