## CURRENT YEAR
Code S -- UPN(s) | XXX | [15 empty] | Mission E
Launch Date | 2002-07-01 | [15 empty] | ELV Milestone Schedule, NOA and Cost Requirements
Launch Site | CCAFS | [15 empty] | Comparison of FY01 Phased Cost Plan to Actual
Configuration | 7X26-9.5
| Ref. | 2000-10-01 |  | 2000-11-01 |  | 2000-12-01 |  | 2001-01-01 |  | 2001-02-01 |  | 2001-03-01 |  | 2001-04-01 |  | 2001-05-01 |  | 2001-06-01 |  | 2001-07-01 |  | 2001-08-01 |  | 2001-09-01 |  | FY-02 |  |  |  | FY-03 |  | FY-04 | FY-05 | BTC
Milestone Schedule
ATP; long-lead H/W auth | 2000-01-01
Mission integration activities initiated | 2000-04-01
H/W matl, fab, & assemb auth for prod; Mssn Spec submitted | 2000-07-01
Subcontractors authorized | 2000-10-01 | * | 2000-10-01
PAF & fairing matl, fab, & assemb auth for prod | 2001-01-01 | [6 empty] | * | 2001-01-01
Mssn-peculiar H/W auth for prod | L-15 | [12 empty] | * | 2001-04-01
Preliminary Mssn Analysis Initiated; Flight Segment Wiring Diagram Submitted | L-12 | [18 empty] | * | 2001-07-01
Critical subassemblies complete | L-9 | [24 empty] | * | 2001-10-01
Completion of selective mssn-peculiar H/W | L-6 | [25 empty] | * | 2002-01-01
Selective major end items & Final Mssn Analysis complete | L-3 | [26 empty] | * | 2002-04-01
Measurement List complete; Launch; P3 Support | Launch | [27 empty] | * | 2002-07-01
Certify Mission Success | L+3 | [28 empty] | * | 2002-10-01
Mission Peculiars
Payload Processing
Variance Explanation/Comments:
Later than planned utilization of
mission unique funds.
| Pr Yrs | 2000-10-01 |  | 2000-11-01 |  | 2000-12-01 |  | 2001-01-01 |  | 2001-02-01 |  | 2001-03-01 |  | 2001-04-01 |  | 2001-05-01 |  | 2001-06-01 |  | 2001-07-01 |  | 2001-08-01 |  | 2001-09-01 |  | FY-02 |  |  |  | FY-03 |  | FY-04 | FY-05 | BTC | Total
NOA | 18.7 |  |  |  | 7.9 |  | 7.9 |  | 7.9 |  | 7.9 |  | 19.6 |  | 19.6 |  | 21.4 |  | 21.4 |  | 21.4 |  | 21.4 |  | 21.4 | 20.8 | [8 empty] | 60.9
Cum POP Plan | 13.2 |  | 1.4 | 2.1 | 2.8 | 3.45 | 4.1 | 4.8 | 5.5 | 6.2 | 6.9 | 7.6 | 8.3 | 9.2 | 10.1 | 12 | 13.9 | 14.75 | 15.6 | 16.45 | 17.3 | 18.75 | 20.2 | 20.7 | 21.2 | 26.5 | [8 empty] | 60.9
Cum Rev Plan | 13.2 |  | 1.4 | 2.1 | 2.8 | 3.4 | 4 | 4.5 | 5 | 5.6 | 6.2 | 6.8 | 7.4 | 8.25 | 9.1 | 10.35 | 11.6 | 12.5 | 13.4 | 14.6 | 15.8 | 16.3 | 16.8 | 18 | 19.2 | 28.5 | [8 empty] | 60.9
Cum Actual | 13.2 |  | 1.4 | 2.1 | 2.8 | 3.4 | 4 | 4.5 | 5 | 5.6 | 6.2 | 6.8 | 7.4 | 8.226 | 9.052 | 9.8063 |  | 0 |  | 0 |  | 0 |  | 0
Cost Variance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -0.048
Mo. POP Plan |  |  | 1.4 |  | 1.4 |  | 1.3 |  | 1.4 |  | 1.4 |  | 1.4 |  | 1.8 |  | 3.8 |  | 1.7 |  | 1.7 |  | 2.9 |  | 1
Mo. Rev Plan |  |  | 1.4 |  | 1.4 |  | 1.2 |  | 1 |  | 1.2 |  | 1.2 |  | 1.7 |  | 2.5 |  | 1.8 |  | 2.4 |  | 1 |  | 2.4
Mo. Actual |  |  | 1.4 |  | 1.4 |  | 1.2 |  | 1 |  | 1.2 |  | 1.2 |  | 1.652 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Note on C5: Grace Bell: Put the same "day" of October as you put in the launch date (ie. 4/8/03 launch = 10/8/00.
Note on A1: OAO: Input Enterprise
Note on R1: OAO: Input Mission Name
Note on B7: OAO: Input mos to launch on MS Calc Sheet
Feb-Jul
Mission Peculiars
Duration of Mission
plp
Mission Peculiars
plp
Current Period

## MS Calc
Milestone calculations (based on launch date)
Launch Date | 2002-07-01
[25 empty] | Q1 Calc |  |  |  | Q2 Calc |  |  |  | Q3 Calc |  |  |  | Q4 Calc |  |  |  | Q1 Calc |  |  |  | Q2 Calc |  |  |  | Q3 Calc |  |  |  | Q4 Calc |  |  |  | Q1 Calc |  |  |  | Q2 Calc |  |  |  | Q3 Calc |  |  |  | Q4 Calc |  |  |  | Q1 Calc |  |  |  | Q2 Calc |  |  |  | Q3 Calc |  |  |  | Q4 Calc |  |  |  | Q1 Calc |  |  |  | Q2 Calc |  |  |  | Q3 Calc |  |  |  | Q4 Calc
| Mos to Launch | M/S Date | 2000-10-01 | 2000-11-01 | 2000-12-01 | 2001-01-01 |  | 2001-02-01 |  | 2001-03-01 |  | 2001-04-01 |  | 2001-05-01 |  | 2001-06-01 |  | 2001-07-01 |  | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01 | M/S | 2002-01-01 | 2002-02-01 | 2002-03-01 | M/S | 2002-04-01 | 2002-05-01 | 2002-06-01 | M/S | 2002-07-01 | 2002-08-01 | 2002-09-01 | M/S | 2002-10-01 | 2002-11-01 | 2002-12-01 | M/S | 2003-01-01 | 2003-02-01 | 2003-03-01 | M/S | 2003-04-01 | 2003-05-01 | 2003-06-01 | M/S | 2003-07-01 | 2003-08-01 | 2003-09-01 | M/S | 2003-10-01 | 2003-11-01 | 2003-12-01 | M/S | 2004-01-01 | 2004-02-01 | 2004-03-01 | M/S | 2004-04-01 | 2004-05-01 | 2004-06-01 | M/S | 2004-07-01 | 2004-08-01 | 2004-09-01 | M/S | 2004-10-01 | 2004-11-01 | 2004-12-01 | M/S | 2005-01-01 | 2005-02-01 | 2005-03-01 | M/S | 2005-04-01 | 2005-05-01 | 2005-06-01 | M/S | 2005-07-01 | 2005-08-01 | 2005-09-01 | M/S | 2005-10-01 | 2005-11-01 | 2005-12-01 | M/S | 2006-01-01 | 2006-02-01 | 2006-03-01 | M/S | 2006-04-01 | 2006-05-01 | 2006-06-01 | M/S | 2006-07-01 | 2006-08-01 | 2006-09-01 | M/S
Milestone Schedule | L
ATP; long-lead H/W auth | -30 | 2000-01-01
Mission integration activities initiated | -27 | 2000-04-01
H/W matl, fab, & assemb auth for prod; Mssn Spec submitted | -24 | 2000-07-01
Subcontractors authorized | -21 | 2000-10-01 | 1
PAF & fairing matl, fab, & assemb auth for prod | -18 | 2001-01-01 |  |  |  | 1
Mssn-peculiar H/W auth for prod | -15 | 2001-04-01 | [9 empty] | 1
Preliminary Mssn Analysis Initiated; Flight Segment Wiring Diagram Submitted | -12 | 2001-07-01 | [15 empty] | 1
Critical subassemblies complete | -9 | 2001-10-01 | [19 empty] | 1 |  |  | 2001-10-01
Completion of selective mssn-peculiar H/W | -6 | 2002-01-01 | [23 empty] | 1 |  |  | 2002-01-01
Selective major end items & Final Mssn Analysis complete | -3 | 2002-04-01 | [27 empty] | 1 |  |  | 2002-04-01
Measurement List complete; Launch; P3 Support | 0 | 2002-07-01 | [31 empty] | 1 |  |  | 2002-07-01
Certify Mission Success | 3 | 2002-10-01 | [35 empty] | 1 |  |  | 2002-10-01
[5 empty] | Dec | Jan | Feb | feb |  | mar |  | apr |  | may |  | jun |  | jul |  | aug | sep
[5 empty] | 3669 | 4892 |  | 6115 |  | 7338 |  | 8968 |  | 10598 |  | 12228 |  | 13858 |  | 15488 | 17118 |  | 17118
[5 empty] | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 314 |  | 350 |  | 350 |  | 350 | 400
[5 empty] | 3983 | 5206 | 314 | 6429 | 314 | 7652 | 314 | 9282 | 314 | 10912 | 0 | 12578 | 0 | 14208 | 0 | 15838 | 17518