## Sheet1
Aspect or Impact | Objective | Target | Action Plan Steps |  | Responsibility | Milestone Dates | Status | % Impact on Goal | % Impact on total energy | Last Updated 01/10/04 | Committee To Do List |  | Responsibility | Milestone Dates | Status
[11 empty] | 1 | LN2 chambers heating elements | Madden | 2004-03-01
Natural Resources | Reduce Energy Usage at Melbourne Campus | Reduce FY04 energy usage by 1% ( with a stretch goal of 0.25%) | 1 | New roof installed on bldg 311 | Dave Roberts | 2004-01-01 | Completed | 25 | 0.25 |  | 2 | Determine method of capturing office equipment purchases to ensure they are energy-efficient and use recycled material if possible. Identify and heighten employee awareness of energy star equipment | Villiard | 2004-05-01
|  |  | 2 | Shutting Off unused production Equipment | Osborne | 2004-08-15 |  | 6 | 0.06 |  | 3 | FootLamp Readings in Parking lot.
[9 empty] | 0 |  |  | New wiring in Building for parking lot lighting
|  |  | 3 | Shutting Down un-used test equipment | G Goodnight, E. Stern, C. Deyo | 2004-02-23 | Completed | 25 | 0.25 |  | 4
|  |  | 4 | 9/80 Work Schedule | S Watson | 2004-05-02 | Completed | 50 | 0.5
|  |  | 5 | Purchase new ultrasound leak detection equipment. | K Mccarty / Roberts | 2004-09-01 | If a Capital expense will not be implemented until FY 05 | 5 | 0.05
|  |  | 6 | Replace DX system with Chilled water system | D Roberts | 2004-12-31 | Completed FY04 Changed DX unit in clean room in FY 04, Anther unit is scheduled for change in FY 05. | 5 | 0.05
|  |  | 7 | Verify and repair all HVAC equipment to ensure desired tempatures are maintained. | D Roberts | 2004-05-30 |  | 10 | 0.1
8
9
0.05
Completed To Do Items
[12 empty] | Determine how energy reduction target is measured. | Zerwek | 2003-09-15 | Completed 8/18/2003
[12 empty] | Determine energy usage for FY01, FY02, and FY03 | Costanza | 2003-08-18 | Completed 8/18/2003
[12 empty] | Determine if Energy reduction target is measured against FY03, average of prior 3 years, or normalized with units to finished goods | Yonts, Zerwek | 2003-09-15 | Completed 9/19/2003 Baseline will consist of FY 2003 KwH usage plus Additional Parking lot lighting
[12 empty] | Gather pertinent information | Zerwek | 2003-08-18 | Compete 9/19/2003
[12 empty] | Energy survey from FPL | Costanza | 2003-08-18 | Not at commercial level. Completed 8/18/2003
[12 empty] | Energy usage by building | Costanza | 2003-08-18 | Compete 9/19/2003
[12 empty] | Possible breakdown by building/area | Costanza | 2003-08-18 | Compete 9/19/2003
[12 empty] | Info on new exterior lighting | Villard | 2003-08-18 | Compete 9/19/2003
[12 empty] | Confer with Electrical Lead on Heavy usage items | Yonts, Zerwek | 2003-09-15 | Compete 9/19/2003
[11 empty] | 1 | Compare energy usage in Bldg 310 before and after new roof was put on. | Osborne | 2004-01-11 | Completed
[11 empty] | 2 | Determine office and production equipment being left on in BLdg 311 and 308 | Costanza / Joslin | 2004-01-11 | CompletedCarol Walk through( Brady Printers= 3 left on, Ionizer,1Small Oven, 3 halo lamps, 1 soldering iron, 1 personal fan, 6 calculators)= total 450 watt hours .45 KwH
[11 empty] | 2a | Cost in KwH of the log off leave on policy | Madden | 2004-01-26 | completed
[11 empty] | 3 | schedule a meeting with John Alives, Ed Snyder and Dave Mager regarding what test equipment can be shut down after hours/and or on weekends. | Madden/ Zerwek/ Joslin / Yonts | 2004-01-23 | Completed / Begin measuring for comparison 2/9/04
[11 empty] | 4 | check into reducing parking lot lighting in the outer perimeter areas and reducing the length of time the lights are on in the parking lot. | Yonts Zerwek | 2004-01-23 | Completed / rejected by security will re-evaluate in 6 months
[11 empty] | 5 | Work with Mike Benson to evaluate compressed air lines | Zerwek, Joslin, Osborne | 2004-06-30 | Jim P said Mike B would be the person to talk to we would have to contract the testing out. We need to determine price to test vs. hours run time saved and KWH saved by completing test and what is the payback. Spoke with Mike B and the last compressed air leak survey was done in 2000. We had 53 leaks with a annual cost of $2000.00. MIke took 2 action items. One to find out the cost of a leak dector and the second to find out the cost of having a leak survey done. Action items to be completed by 01/19/2004. Mike also stated the we are currently only using 3/4 of the capacity of the 50hp compressor during peak periods and do not use the 40hp or the 75hp compressors. Decision was made to purchase equipment. Maintenance and EH&S will work out the cost.
[11 empty] | 6 | Work With John Woods to see where applicable | Madden /Yonts / Zerwek | 2004-01-19 | Completed : All are at minimum requirments except for 3 units that are not on frequency drives(not contolable)(1 unit will be replaced next year if approved). If we went 74 deg across the board throughout the complex excluding clean rooms. It would reduce energy usage by 1%, but then we would run into employee morale problems which would translate into production problems.
[11 empty] | 7 | Work With John Woods to see where applicable | Madden /Yonts / Zerwek | 2004-01-20 | Completed: Per John can not be done because of Humidity vs Tempatures. Within the state of Florida Uses outside air for cooling purposes.
[11 empty] | 8 | Work With John Woods to see where applicable | Madden /Yonts / Zerwek | 2004-01-21 | Completed: Undermanned to have someone spend all day adjusting controls. (see above across the board temp)
[11 empty] | 9 | Work With John Woods to see where applicable and research ovens and timers. | Madden /Yonts / Zerwek | 2004-01-22 | Completed: Chiller area use condensing water to heat chemical and chiller room, All Bldgs have VAV boxes have heat. (only perimiter) 310 and 308 throughout the building. Use of boilers would not be cost effective.
[11 empty] | 10 | Work With John Woods to see where applicable | Madden /Yonts / Zerwek | 2004-01-19 | Completed
[11 empty] | 11 | Work with John Alives, Ed Snyder, and Dave Mager to evaluate test equipment and determine what equipment can be shut down after hours/on weekends. | Madden /Yonts / Zerwek | 2004-01-23 | Completed / Begin measuring for comparison 2/9/04
[11 empty] | 18 | Evaluate use of window tinting | Villiard | 2004-01-31 | Completed / Storm damage protection and tint
[11 empty] | 19 | Evaluate use of hot water heaters | Costanza | 2004-01-31 | Completed
[11 empty] | 20 | Evaluate use of instant-on hot water | Costanza | 2004-01-31 | Spoke with Jim Philpott and he said we have tried to use instant hot in the past. He stated it was an maintenance nightmare and the units have a short life span with frequent need of replacing.
[11 empty] | 21 | Investigate impact on water heater usage | Costanza | 2004-01-31 | Completed
[11 empty] | 22 | Investigate new water heater for cafeteria | Costanza | 2004-01-31 | Completed
[11 empty] | 23 | Check hot water heater temperatures in all buildings | Costanza | 2004-01-31 | Completed / On Average 135 degrees F
[11 empty] | 24 | Work with IT to determine whether re-deployed computers are energy-compliant | Yonts | 2004-01-31 | Completed / all re-deployed equipment is energy compliant.
[11 empty] | 25 | Evaluate vending machines to determine energy-compliance | Zerwek | 2003-12-08 | Completed / Mike Z will check with Pepsi and Coke to see if we are using energy star vending machines. The snack machines are currently using flourecent lighting.
[11 empty] | 26 | Work with maintenance to evaluate weather stripping at the facility | Zerwek, Joslin, Osborne | 2004-06-30 | Completed / The only areas that are weather stripped according to Jim Philpott are around doors and over head doors. They have weather stripping
[11 empty] | 27 | Work with Capital Analyst to verify that all AR submissions have included consideration of energy impact. | Glynn | 2003-12-17 | Completed
"Energy by Popualtion Total"