## wbs 1
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
1 | 3 | 1 | Scintillator Extrusion | 2005-06-01 08:00 | 2007-05-07 17:00 | No |  |  | 97.4 wks | 223008 | 47001.6 | 159046 | 40474 |  | 382054 | 469529.6
2 | 116 | 1.1 | ID Bar (no co-Ex) Prototypes Available | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 613 | 0 | 0 | WBS Description: This material was already available at Fermilab....
3 | 183 | 1.2 | Procure Scintillator Consumables for Prototyping | 2005-06-01 08:00 | 2005-09-29 17:00 | No |  |  | 17 wks | 0 | 0 | 0 | 0 |  | 0 | 0
4 | 245 | 1.2.1 | Purchase ID Scintillator Development Consumables | 2005-06-01 08:00 | 2005-09-29 17:00 | Yes | Fermilab |  | 17 wks | 0 | 0 | 0 | 0 | 2 | 0 | 0 | WBS Description: This task covers the purchase of the polystyrene pellets, dopants, and nitrogen for the ID scintillator R&D work....
5 | 244 | 1.2.2 | Purchase OD Scintillator Development Consumables | 2005-06-01 08:00 | 2005-09-29 17:00 | Yes | Fermilab |  | 17 wks | 0 | 0 | 0 | 0 | 2 | 0 | 0 | WBS Description: This task covers the purchase of the polystyrene pellets, dopants, and nitrogen for the OD scintillator R&D work....
6 | 634 | 1.2.3 | Purchase Full Module Prototype materials | 2005-06-01 08:00 | 2005-09-29 17:00 | Yes | Fermilab |  | 17 wks | 0 | 0 | 0 | 0 | 2 | 0 | 0 | WBS Description: This task covers the purchase of the polystyrene pellets, dopants, and nitrogen for scintillator to construct 1 module prototype....
7 | 118 | 1.3 | Procure Co-Extrusion Equipment | 2005-06-01 08:00 | 2005-12-05 17:00 | No |  |  | 26 wks | 0 | 0 | 0 | 0 |  | 0 | 0
8 | 635 | 1.3.1 | Co-extruder Delivered To Fermilab | 2005-10-10 08:00 | 2005-10-10 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 2 | 0 | 0 | Milestone Description: Purchase of the co-extruder unit from the manufacturer and delivered to Fermilab. This unit will handle the melting and mixing of the reflective coating material....
9 | 636 | 1.3.2 | Purchase Co-extruder Die | 2005-06-01 08:00 | 2005-08-16 17:00 | Yes | Fermilab |  | 10.8 wks | 0 | 0 | 0 | 0 | 6SS | 0 | 0 | WBS Description: This task covers the purchase of the connector between the co-extruder and the existing extruder as well as the adaptor to the current die....
10 | 637 | 1.3.3 | Purchase OD Die | 2005-06-01 08:00 | 2005-12-05 17:00 | Yes | Fermilab |  | 26 wks | 0 | 0 | 0 | 0 | 6SS | 0 | 0 | WBS Description: This task covers the purchase of the sizing tooling and die section needed to make a square-shaped scintillator bar for the outer detector....
11 | 638 | 1.3.4 | Purchase Titanium Dioxide Pellets | 2005-08-17 08:00 | 2005-09-26 17:00 | Yes | Fermilab |  | 5.6 wks | 0 | 0 | 0 | 0 | 9 | 0 | 0 | WBS Description: This task covers the cost of the material to make the reflective coating. ...
12 | 119 | 1.4 | Installation of Co-Extruder | 2005-10-10 08:00 | 2005-11-04 17:00 | No |  |  | 4 wks | 24000 | 7200 | 16720 | 4476 |  | 40720 | 52396
13 | 221 | 1.4.1 | Install Co-extruder (FNAL) | 2005-10-10 08:00 | 2005-11-04 17:00 | Yes | Fermilab | MTF Sr[200%],MTF Coextruder,T&M ElectricialF[0%],MandS[5,920] | 4 wks | 24000 | 7200 | 5920 | 1776 | 8,9,11 | 29920 | 38896 | WBS Description: This task involves installation and testing of the co-extruder. Equipment mounts with a pedestal set-up and will need to be levelled, electrically connected and turned on....
14 | 222 | 1.4.2 | Install Co-extruder (NIU) | 2005-10-10 08:00 | 2005-11-04 17:00 | Yes | NIU | MandS[10,800],NIU Scint. Tech | 4 wks | 0 | 0 | 10800 | 2700 | 8,9,11 | 10800 | 13500 | WBS Description: This task involves NIU contribution to the initial set-up....
15 | 656 | 1.4.3 | Co-extruder Installation Complete | 2005-11-04 17:00 | 2005-11-04 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 13,14 | 0 | 0 | WBS Description: This milestone is for the successful completion of the Co-extruder installation work....
16 | 120 | 1.5 | Tune ID Die and prepare Scintillator prototype | 2005-11-07 08:00 | 2006-01-13 17:00 | No |  |  | 9 wks | 54000 | 10800 | 24430 | 6195 |  | 78430 | 95425
17 | 223 | 1.5.1 | Tune and prototype ID scintillator (FNAL) | 2005-11-07 08:00 | 2006-01-06 17:00 | Yes | Fermilab | MTF Sr[200%],MTF Coextruder | 8 wks | 54000 | 10800 | 0 | 0 | 15 | 54000 | 64800 | WBS Description: This task addresses the FNAL contribution to test the die for ID scintillator, producing scintillator to amtch the technical specifications, modifying the die as necessary, and prepare the strips for light yield tests....
18 | 224 | 1.5.2 | Tune and prototype ID scintillator (NIU) | 2005-11-07 08:00 | 2006-01-06 17:00 | Yes | NIU | MandS[22,680],NIU Scint. Tech | 8 wks | 0 | 0 | 22680 | 5670 | 17SS | 22680 | 28350 | WBS Description: This task addresses the NIU contribution to test the die for ID scintillator, producing scintillator to amtch the technical specifications, modifying the die as necessary, and prepare the strips for light yield tests....
19 | 640 | 1.5.3 | Inspect and modify ID die | 2005-11-07 08:00 | 2006-01-06 17:00 | Yes | Fermilab | MandS[1,750] | 8 wks | 0 | 0 | 1750 | 525 | 17SS | 1750 | 2275 | WBS Description: This task involves return and rework for the ID die if we discover defects or the final part is out of spec....
20 | 970 | 1.5.4 | Ship to Hampton and W&M | 2006-01-09 08:00 | 2006-01-13 17:00 | No | Fermilab |  | 1 wk | 0 | 0 | 0 | 0 | 19 | 0 | 0
21 | 57 | 1.6 | OD Die Tuning | 2006-01-24 08:00 | 2006-03-27 17:00 | No |  |  | 9 wks | 48000 | 9600 | 21910 | 5565 |  | 69910 | 85075
22 | 226 | 1.6.1 | Tune and prototype OD scintillator (FNAL) | 2006-01-24 08:00 | 2006-03-20 17:00 | Yes | Fermilab | MTF Sr[200%],MTF Coextruder | 8 wks | 48000 | 9600 | 0 | 0 | 17,18,19FS+2 wks,10 | 48000 | 57600 | WBS Description: This task addresses the FNAL contribution to test the die for OD scintillator, producing scintillator to amtch the technical specifications, modifying the die as necessary, and prepare the strips for light yield tests. ...
23 | 225 | 1.6.2 | Tune and prototype OD scintillator (NIU) | 2006-01-24 08:00 | 2006-03-20 17:00 | Yes | NIU | MandS[20,160],NIU Scint. Tech | 8 wks | 0 | 0 | 20160 | 5040 | 22SS | 20160 | 25200 | WBS Description: This task addresses the NIU contribution to test the die for OD scintillator, producing scintillator to amtch the technical specifications, modifying the die as necessary, and prepare the strips for light yield tests. ...
24 | 641 | 1.6.3 | Inspect and modify OD die | 2006-01-24 08:00 | 2006-03-20 17:00 | Yes | Fermilab | MandS[1,750] | 8 wks | 0 | 0 | 1750 | 525 | 22SS | 1750 | 2275 | WBS Description: This task covers the potential costs that might be incurred if we need to modify the die or sizing tooling to meet scintillator specifications. ...
25 | 971 | 1.6.4 | Ship to Hampton and W&M | 2006-03-21 08:00 | 2006-03-27 17:00 | No | Fermilab |  | 1 wk | 0 | 0 | 0 | 0 | 24 | 0 | 0
26 | 657 | 1.6.5 | Prototype Scintillator Work Complete | 2006-03-27 17:00 | 2006-03-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 25 | 0 | 0 | WBS Description: This milestone is for the successful completion of the prototype scintillator work and means that we are ready to move into the production phase....
27 | 71 | 1.7 | Procurement of Scintillator Consumables | 2006-10-02 08:00 | 2007-01-12 17:00 | No |  |  | 14 wks | 0 | 0 | 15110 | 5694 |  | 15110 | 20804
28 | 644 | 1.7.1 | Purchase ID Spare Production Tooling | 2006-10-02 08:00 | 2007-01-12 17:00 | No | Fermilab | MandS[1,750] | 14 wks | 0 | 0 | 1750 | 525 | 616 | 1750 | 2275 | WBS Description: This task covers the cost to purchase new sizing tooling or die section if necessary. ...
29 | 645 | 1.7.2 | Purchase OD Spare Production Tooling | 2006-10-02 08:00 | 2007-01-12 17:00 | No | Fermilab | MandS[1,750] | 14 wks | 0 | 0 | 1750 | 525 | 616 | 1750 | 2275 | WBS Description: This task covers the cost to purchase new sizing tooling or die section if necessary. ...
30 | 1288 | 1.7.3 | Purchase Construction Scintillator Consumables | 2006-10-02 08:00 | 2006-11-28 17:00 | No | Fermilab | MandS[11,610] | 8 wks | 0 | 0 | 11610 | 4644 | 616 | 11610 | 16254 | WBS Description: Covers the consumable materials necessary for the scintillator extrusion production runs....
31 | 58 | 1.8 | ID Scintillator Production | 2006-11-29 08:00 | 2007-02-19 17:00 | No |  |  | 11 wks | 60888 | 12177.6 | 29736 | 7434 |  | 90624 | 110235.6 | WBS Description: This section covers the Inner Detector Scintillator Production. ...
32 | 218 | 1.8.1 | Produce ID Scintillator (FNAL) | 2006-11-29 08:00 | 2007-02-19 17:00 | No | Fermilab | MTF Coextruder[200%],MTF Sr | 11 wks | 60888 | 12177.6 | 0 | 0 | 28SS,26,622,623,30 | 60888 | 73065.6 | WBS Description: This task involves the FNAL effort for extrusion of the ID scintillator bars....
33 | 217 | 1.8.2 | Produce ID Scintillator (NIU) | 2006-11-29 08:00 | 2007-02-19 17:00 | No | NIU | MandS[29,736],NIU Scint. Tech | 11 wks | 0 | 0 | 29736 | 7434 | 32SS | 29736 | 37170 | WBS Description: This task involves the NIU contribution to extrude the ID scintillator bars....
34 | 115 | 1.9 | OD Scintillator Production | 2007-02-20 08:00 | 2007-04-09 17:00 | No |  |  | 7 wks | 36120 | 7224 | 17640 | 4410 |  | 53760 | 65394 | WBS Description: This section covers the Outer Detector Scintillator Production. ...
35 | 220 | 1.9.1 | Produce OD Scintillator (FNAL) | 2007-02-20 08:00 | 2007-04-09 17:00 | No | Fermilab | MTF Coextruder[200%],MTF Sr | 7 wks | 36120 | 7224 | 0 | 0 | 33,32 | 36120 | 43344 | WBS Description: This task involves the FNAL effort for extrusion of the OD scintillator bars....
36 | 219 | 1.9.2 | Produce OD Scintillator (NIU) | 2007-02-20 08:00 | 2007-04-09 17:00 | No | NIU | MandS[17,640],NIU Scint. Tech | 7 wks | 0 | 0 | 17640 | 4410 | 35SS,33 | 17640 | 22050 | WBS Description: This task involves the NIU contribution to extrude the OD scintillator bars....
37 | 658 | 1.9.3 | Scintillator Production Complete | 2007-04-09 17:00 | 2007-04-09 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 36,28,29,35 | 0 | 0 | WBS Description: This milestone is for the successful completion of the scintillator production work and means that we are ready to ship the scintillator bars....
38 | 5 | 1.10 | Scintillator Prototype Shipping | 2005-11-07 08:00 | 2006-04-17 17:00 | No |  |  | 22 wks | 0 | 0 | 7600 | 1520 |  | 7600 | 9120
39 | 249 | 1.10.1 | ID Crates and Shipping | 2005-11-07 08:00 | 2006-04-17 17:00 | No |  |  | 22 wks | 0 | 0 | 3800 | 760 |  | 3800 | 4560
40 | 281 | 1.10.1.1 | Purchase ID Crate Materials | 2005-11-07 08:00 | 2005-11-18 17:00 | Yes | Fermilab | MandS[1,000] | 2 wks | 0 | 0 | 1000 | 200 | 15 | 1000 | 1200 | WBS Description: This task covers materials and suppplies to construct ID scintillator prototype shipping crates....
41 | 280 | 1.10.1.2 | Build ID prototype crates | 2005-11-21 08:00 | 2005-11-29 17:00 | Yes | Fermilab | MandS[1,800] | 1 wk | 0 | 0 | 1800 | 360 | 40 | 1800 | 2160 | WBS Description: This task covers labor to build shipping crates. This will be provided by a university and billed to Fermilab as an M&S cost. ...
42 | 624 | 1.10.1.3 | Ship ID prototype crates to HU/W&M | 2006-01-09 08:00 | 2006-04-17 17:00 | Yes | Fermilab | MandS[1,000] | 14 wks | 0 | 0 | 1000 | 200 | 41,18 | 1000 | 1200 | WBS Description: This task covers shipping costs for crates....
43 | 248 | 1.10.2 | OD Crates and Shipping | 2006-01-09 08:00 | 2006-04-17 17:00 | No |  |  | 14 wks | 0 | 0 | 3800 | 760 |  | 3800 | 4560
44 | 283 | 1.10.2.1 | Purchase OD Crate Materials | 2006-01-09 08:00 | 2006-01-23 17:00 | Yes | Fermilab | MandS[1,000] | 2 wks | 0 | 0 | 1000 | 200 | 17 | 1000 | 1200 | WBS Description: This task covers materials and suppplies to construct OD prototype scintillator shipping crates....
45 | 282 | 1.10.2.2 | Construct OD prototype crates | 2006-01-24 08:00 | 2006-01-30 17:00 | Yes | Fermilab | MandS[1,800] | 1 wk | 0 | 0 | 1800 | 360 | 44 | 1800 | 2160 | WBS Description: This task covers labor to build shipping crates. This will be provided by a university and billed to Fermilab as an M&S cost. ...
46 | 623 | 1.10.2.3 | Ship OD prototype crates to HU/W&M | 2006-03-21 08:00 | 2006-04-17 17:00 | Yes | Fermilab | MandS[1,000] | 4 wks | 0 | 0 | 1000 | 200 | 45,23,22 | 1000 | 1200 | WBS Description: This task covers shipping costs for crates....
47 | 647 | 1.11 | Scintillator Production Shipping | 2006-10-02 08:00 | 2007-05-07 17:00 | No |  |  | 30 wks | 0 | 0 | 25900 | 5180 |  | 25900 | 31080
48 | 648 | 1.11.1 | ID Crates and Shipping | 2006-10-02 08:00 | 2007-03-26 17:00 | No |  |  | 24 wks | 0 | 0 | 15200 | 3040 |  | 15200 | 18240
49 | 649 | 1.11.1.1 | Purchase ID Crate Materials | 2006-10-02 08:00 | 2006-10-13 17:00 | No | Fermilab | MandS[8,800] | 2 wks | 0 | 0 | 8800 | 1760 | 28SS | 8800 | 10560 | WBS Description: This task covers materials and suppplies to construct ID production scintillator shipping crates. ...
50 | 650 | 1.11.1.2 | Build ID production crates | 2006-10-16 08:00 | 2006-11-03 17:00 | No | Fermilab | MandS[4,200] | 3 wks | 0 | 0 | 4200 | 840 | 49 | 4200 | 5040 | WBS Description: This task covers labor to build shipping crates. This will be provided by a university and billed to Fermilab as an M&S cost. ...
51 | 651 | 1.11.1.3 | Ship ID production crates to HU/W&M | 2007-02-20 08:00 | 2007-03-26 17:00 | No | Fermilab | MandS[2,200] | 5 wks | 0 | 0 | 2200 | 440 | 33,50 | 2200 | 2640 | WBS Description: This task covers shipping costs for crates....
52 | 652 | 1.11.2 | OD Crates and Shipping | 2006-11-29 08:00 | 2007-05-07 17:00 | No |  |  | 22 wks | 0 | 0 | 10700 | 2140 |  | 10700 | 12840
53 | 653 | 1.11.2.1 | Purchase OD Crate Materials | 2006-11-29 08:00 | 2006-12-12 17:00 | No | Fermilab | MandS[5,000] | 2 wks | 0 | 0 | 5000 | 1000 | 33SS | 5000 | 6000 | WBS Description: This task covers materials and suppplies to construct OD production scintillator shipping crates. ...
54 | 654 | 1.11.2.2 | Construct OD production crates | 2006-12-13 08:00 | 2007-01-05 17:00 | No | Fermilab | MandS[3,500] | 3 wks | 0 | 0 | 3500 | 700 | 53 | 3500 | 4200 | WBS Description: This task covers labor to build shipping crates. This will be provided by a university and billed to Fermilab as an M&S cost. ...
55 | 655 | 1.11.2.3 | Ship OD production crates to HU/W&M | 2007-04-10 08:00 | 2007-05-07 17:00 | No | Fermilab | MandS[2,200] | 4 wks | 0 | 0 | 2200 | 440 | 36,54 | 2200 | 2640 | WBS Description: This task covers shipping costs for crates....
56 | 659 | 1.11.2.4 | Scintillator Shipping Complete | 2007-05-07 17:00 | 2007-05-07 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 55,37 | 0 | 0 | WBS Description: This milestone is for the successful completion of the scintillator production shipping and means that scintillator fabrication is complete....

## wbs 2
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
57 | 70 | 2 | WLS Fibers | 2005-08-12 08:00 | 2007-07-11 17:00 | No |  |  | 96.2 wks | 119080 | 47632 | 383230 | 116903 |  | 502310 | 666845
58 | 191 | 2.1 | WLS Fiber Purchase and Testing | 2005-08-12 08:00 | 2007-04-09 17:00 | No |  |  | 83.2 wks | 3760 | 1504 | 367790 | 110967 |  | 371550 | 484021
59 | 188 | 2.1.1 | WLS Fiber R&D Procurement | 2005-08-12 08:00 | 2005-10-21 17:00 | No |  |  | 10 wks | 3760 | 1504 | 5150 | 1415 |  | 8910 | 11829
60 | 738 | 2.1.1.1 | Purchase Y-11 fiber for R&D | 2005-08-12 08:00 | 2005-09-30 17:00 | Yes | Rochester | MandS[2,750] | 7 wks | 0 | 0 | 2750 | 825 |  | 2750 | 3575 | WBS Description: Purchase and evaluate Y-11 fiber for desired performance....
61 | 739 | 2.1.1.2 | Purchase Y-7 fiber for R&D | 2005-08-12 08:00 | 2005-09-30 17:00 | Yes | Rochester | MandS[1,750] | 7 wks | 0 | 0 | 1750 | 525 | 60SS | 1750 | 2275 | WBS Description: Purchase and evaluate Y-7 fiber for desired performance....
62 | 782 | 2.1.1.3 | Commission Lab 6 WLS Fiber QC device | 2005-10-03 08:00 | 2005-10-14 17:00 | Yes | Rochester | Roch Tech[0%],MandS[650] | 2 wks | 0 | 0 | 650 | 65 | 61 | 650 | 715 | WBS Description: Verification of the operating properties for the WLS FIber Tester at Lab 6....
63 | 783 | 2.1.1.4 | Test initial quality of mirrors | 2005-10-17 08:00 | 2005-10-21 17:00 | Yes | Fermilab | MTF,MTF Supervisor | 1 wk | 3760 | 1504 | 0 | 0 | 62 | 3760 | 5264 | WBS Description: This task involves checking the quality of the mirroring performed at Lab 7 on the fibers purchased for R&D work....
64 | 784 | 2.1.2 | WLS Fiber Prototype Procurement | 2006-01-27 08:00 | 2006-04-27 17:00 | No |  |  | 13 wks | 0 | 0 | 21520 | 6608 |  | 21520 | 28128
65 | 253 | 2.1.2.1 | WLS Fiber for Prototype Procurement | 2006-01-27 08:00 | 2006-04-20 17:00 | Yes | Fermilab | MandS[20,000] | 12 wks | 0 | 0 | 20000 | 6000 | 299 | 20000 | 26000 | WBS Description: Cost of the prototype purchase (roughly 3% of total order) of the WLS Fiber order from Kuraray (Japan). THIS QUOTE NEEDS TO BE REDONE BY HOWARD BUDD!...
66 | 785 | 2.1.2.2 | Prototype Purchase WLS Fiber QC | 2006-04-20 17:00 | 2006-04-27 17:00 | Yes | Rochester | Roch Tech[0%],MandS[1,520] | 1 wk | 0 | 0 | 1520 | 608 | 65 | 1520 | 2128 | WBS Description: This task addresses the quality control inspection of the WLS fibers. This will be done at Fermilab....
67 | 53 | 2.1.3 | WLS Fiber First Procurement | 2006-07-07 08:00 | 2007-01-12 17:00 | No |  |  | 26 wks | 0 | 0 | 170560 | 51472 |  | 170560 | 222032
68 | 798 | 2.1.3.1 | Submit purchase req for WLS bulk purchase | 2006-07-07 08:00 | 2006-09-29 17:00 | No | Fermilab |  | 12 wks | 0 | 0 | 0 | 0 | 616FS-12 wks | 0 | 0 | WBS Description: This task is for the submission of the purchase req for the first bulk WLS fiber order. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
69 | 1453 | 2.1.3.2 | First Bulk Order for Fiber Placed | 2006-09-29 17:00 | 2006-09-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 68 | 0 | 0
70 | 255 | 2.1.3.3 | WLS Fiber Bulk Procurement | 2006-10-02 08:00 | 2006-12-28 12:00 | No | Fermilab | MandS[167,520] | 12 wks | 0 | 0 | 167520 | 50256 | 616,69 | 167520 | 217776 | WBS Description: Cost of the first bulk purchase (roughly one half) of the WLS Fiber order from Kuraray (Japan). ...
71 | 779 | 2.1.3.4 | WLS Fiber QC | 2006-12-28 12:00 | 2007-01-12 17:00 | No | Rochester | Roch Tech[0%],MandS[3,040] | 2 wks | 0 | 0 | 3040 | 1216 | 70 | 3040 | 4256 | WBS Description: This task addresses the quality control inspection of the WLS fibers. This will be done at Fermilab....
72 | 1400 | 2.1.4 | WLS Fiber Second Procurement | 2006-10-02 08:00 | 2007-04-09 17:00 | No |  |  | 26 wks | 0 | 0 | 170560 | 51472 |  | 170560 | 222032
73 | 1401 | 2.1.4.1 | Submit purchase req for WLS bulk purchase | 2006-10-02 08:00 | 2006-12-28 12:00 | No | Fermilab |  | 12 wks | 0 | 0 | 0 | 0 | 616 | 0 | 0 | WBS Description: This task is for the submission of the purchase req for the first bulk WLS fiber order. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
74 | 1402 | 2.1.4.2 | WLS Fiber Bulk Procurement | 2006-12-28 13:00 | 2007-03-26 17:00 | No | Fermilab | MandS[167,520] | 12 wks | 0 | 0 | 167520 | 50256 | 73 | 167520 | 217776 | WBS Description: Cost of the first bulk purchase (roughly one half) of the WLS Fiber order from Kuraray (Japan). ...
75 | 1452 | 2.1.4.3 | Second Fiber Purchase Arrives at Fermilab | 2007-03-26 17:00 | 2007-03-26 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 74 | 0 | 0
76 | 1403 | 2.1.4.4 | WLS Fiber QC | 2007-03-26 17:00 | 2007-04-09 17:00 | No | Rochester | Roch Tech[0%],MandS[3,040] | 2 wks | 0 | 0 | 3040 | 1216 | 75 | 3040 | 4256 | WBS Description: This task addresses the quality control inspection of the WLS fibers. This will be done at Fermilab....
77 | 4 | 2.2 | WLS Fiber Mirroring | 2005-10-24 08:00 | 2007-06-26 17:00 | No |  |  | 84.2 wks | 115320 | 46128 | 600 | 0 |  | 115920 | 162048 | WBS Description: This section covers the WLS Fiber Preparation....
78 | 287 | 2.2.1 | Mirror R&D WLS Fiber | 2005-10-24 08:00 | 2005-10-25 17:00 | Yes | Fermilab | MTF Lab7,MandS[100],MTF Supervisor[40%],Eileen Hahn[40%] | 2 days | 918.4 | 367.36 | 100 | 0 | 63,60 | 1018.4 | 1385.76 | WBS Description: This task involves polishing, mirroring, and protecting (UV coating) of the R&D fibers. This includes some fibers for the Vertical Slice Test....
79 | 286 | 2.2.2 | Mirror Prototype WLS Fiber | 2006-04-28 08:00 | 2006-05-18 17:00 | Yes | Fermilab | MTF Lab7,MandS[500],MTF Supervisor[40%],Eileen Hahn[40%] | 3 wks | 6888 | 2755.2 | 500 | 0 | 66 | 7388 | 10143.2 | WBS Description: This task involves polishing, mirroring, and protecting (UV coating) of the prototype fibers....
80 | 590 | 2.2.3 | Mirror First Half Bulk WLS Fiber | 2007-01-15 08:00 | 2007-04-03 17:00 | No | Fermilab | MTF Lab7[200%],MTF Supervisor[85%],Eileen Hahn[85%],MTF Lab Assist Lab7 | 11.2 wks | 53756.8 | 21502.72 | 0 | 0 | 71 | 53756.8 | 75259.52 | WBS Description: This task involves polishing, mirroring, and protecting (UV coating) of the first bulk purchase of fibers....
81 | 591 | 2.2.4 | Mirror Second Half Bulk WLS Fiber | 2007-04-10 08:00 | 2007-06-26 17:00 | No | Fermilab | MTF Lab7[200%],MTF Supervisor[85%],MTF Lab Assist Lab7,Eileen Hahn[85%] | 11 wks | 53756.8 | 21502.72 | 0 | 0 | 80,76 | 53756.8 | 75259.52 | WBS Description: This task involves polishing, mirroring, and protecting (UV coating) of the second bulk purchase of fibers....
82 | 111 | 2.3 | Shipping WLS Fibers | 2005-10-26 08:00 | 2007-07-11 17:00 | No |  |  | 85.8 wks | 0 | 0 | 14840 | 5936 |  | 14840 | 20776
83 | 285 | 2.3.1 | Ship R&D fibers to Tufts and W&M | 2005-10-26 08:00 | 2005-11-01 17:00 | Yes | Fermilab | MandS[200] | 1 wk | 0 | 0 | 200 | 80 | 78 | 200 | 280 | WBS Description: Shipment of the R&D fibers to Tufts when they are ready....
84 | 284 | 2.3.2 | Ship prototype fibers to W&M | 2006-05-18 17:00 | 2006-05-25 17:00 | Yes | Fermilab | Roch Tech[0%],MandS[688] | 1 wk | 0 | 0 | 688 | 275.2 | 79 | 688 | 963.2 | WBS Description: Shipment of the prototype fibers to William & Mary when they are ready....
85 | 1454 | 2.3.3 | Prototype Fiber Shipped to W&M | 2006-05-25 17:00 | 2006-05-25 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 84 | 0 | 0
86 | 786 | 2.3.4 | Ship 1st Bulk set of fibers to W&M | 2007-04-03 17:00 | 2007-04-17 17:00 | No | Rutgers | MandS[6,976],Roch Tech[0%] | 2 wks | 0 | 0 | 6976 | 2790.4 | 80 | 6976 | 9766.4 | WBS Description: Shipment of fibers to William & Mary when they are ready....
87 | 787 | 2.3.5 | Ship 2nd Bulk set of fibers to W&M | 2007-06-26 17:00 | 2007-07-11 17:00 | No | Fermilab | Roch Tech[0%],MandS[6,976] | 2 wks | 0 | 0 | 6976 | 2790.4 | 81 | 6976 | 9766.4 | WBS Description: Shipment of fibers to William & Mary when they are ready....

## wbs 3
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
88 | 59 | 3 | Scintillator Plane Assembly | 2005-06-01 08:00 | 2008-05-13 17:00 | No |  |  | 148.6 wks | 783635.2 | 292515.76 | 445855 | 172487 |  | 1229490.2 | 1694492.96
89 | 7 | 3.1 | Plane Prototypes and Outfitting | 2005-06-01 08:00 | 2006-11-09 17:00 | No |  |  | 73.2 wks | 178206.4 | 77082.16 | 82821 | 30633.4 |  | 261027.4 | 368742.96
90 | 501 | 3.1.1 | Scintillator Assembly R&D Milestones | 2006-01-18 17:00 | 2006-07-20 17:00 | No |  |  | 25.8 wks | 0 | 0 | 0 | 0 |  | 0 | 0
91 | 505 | 3.1.1.1 | Complete ID Half Plane Prototype | 2006-03-27 17:00 | 2006-03-27 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 107,122 | 0 | 0 | WBS Description: This milestone is for the ...
92 | 504 | 3.1.1.2 | Complete ID Preliminary Design | 2006-03-27 17:00 | 2006-03-27 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 102,105,106,107,103,104,120,121 | 0 | 0 | WBS Description: This milestone is for the ...
93 | 577 | 3.1.1.3 | Complete ID 1 Plane Prototype | 2006-06-08 17:00 | 2006-06-08 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 139,143,91 | 0 | 0 | WBS Description: This milestone is for the ...
94 | 578 | 3.1.1.4 | Complete ID Module Prototype | 2006-07-20 17:00 | 2006-07-20 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 140,144,93 | 0 | 0 | WBS Description: This milestone is for the ...
95 | 579 | 3.1.1.5 | Complete OD Tower Prototype | 2006-02-08 17:00 | 2006-02-08 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 110,124 | 0 | 0 | WBS Description: This milestone is for the ...
96 | 576 | 3.1.1.6 | Complete OD Preliminary Design | 2006-01-18 17:00 | 2006-01-18 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 102,109,110,103,104,108,123 | 0 | 0 | WBS Description: This milestone is for the ...
97 | 581 | 3.1.1.7 | Complete OD 1 Frame Plane Prototype | 2006-02-20 17:00 | 2006-02-20 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 148,152 | 0 | 0 | WBS Description: This milestone is for the ...
98 | 582 | 3.1.1.8 | Complete OD Module Prototype | 2006-03-07 17:00 | 2006-03-07 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 149,153,97 | 0 | 0 | WBS Description: This milestone is for the ...
99 | 583 | 3.1.1.9 | Complete Scintillator Assembly Prototyping | 2006-03-07 17:00 | 2006-03-07 17:00 | No |  |  | 0 days | 0 | 0 | 0 | 0 | 95,98 | 0 | 0 | WBS Description: This milestone is for the ...
100 | 362 | 3.1.2 | Design & Engineering | 2005-06-01 08:00 | 2006-06-06 17:00 | No |  |  | 51.2 wks | 108964 | 49271.2 | 57465 | 20491 |  | 166429 | 236191.2
101 | 471 | 3.1.2.1 | W&M design and testing | 2005-06-01 08:00 | 2006-03-27 17:00 | No |  |  | 41.2 wks | 69854 | 33627.2 | 20500 | 6705 |  | 90354 | 130686.2
102 | 459 | 3.1.2.1.1 | Conceptual Design for readout integration | 2005-06-01 08:00 | 2005-08-10 17:00 | Yes | Rochester | Roch ME[25%] | 10 wks | 6700 | 3350 | 0 | 0 |  | 6700 | 10050 | WBS Description: This task involves the preliminary conceptual design for readout-end (green) fiber routing, light tightening, and connector placement, gap between ID scintillator and OD scintillator....
103 | 573 | 3.1.2.1.2 | Fiber Gluing Tests | 2005-11-18 08:00 | 2006-01-05 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[75%],W&M MandS[1,700] | 6 wks | 10604 | 5302 | 1500 | 300 | 113 | 12104 | 17706 | WBS Description: This task involves ...
104 | 574 | 3.1.2.1.3 | Connection Polishing Design and Prototyping | 2005-08-25 08:00 | 2005-10-20 17:00 | Yes | W&M | W&M Undergrad[25%],W&M Shop [50%],W&M MandS[5,000] | 8 wks | 5760 | 2880 | 5000 | 1000 |  | 10760 | 14640 | WBS Description: This task involves ...
105 | 463 | 3.1.2.1.4 | ID H-clip prototype and testing | 2005-11-14 08:00 | 2005-12-29 12:00 | Yes | W&M | W&M Undergrad[10%],W&M Shop [20%],W&M MandS[2,500] | 6 wks | 1728 | 864 | 2500 | 750 | 112 | 4228 | 5842 | WBS Description: This task involves ...
106 | 522 | 3.1.2.1.5 | W&M ID Routing design and mockup | 2005-06-29 08:00 | 2005-10-20 17:00 | Yes | W&M | W&M Tech[50%],W&M Undergrad[50%],W&M Shop [25%],W&M MandS[3,000] | 16 wks | 22400 | 11200 | 3000 | 1200 | 102SS+1 mon | 25400 | 37800 | WBS Description: This task involves ...
107 | 479 | 3.1.2.1.6 | W&M ID half plane PT | 2006-01-31 08:00 | 2006-03-27 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[50%],W&M MandS[5,000] | 8 wks | 8800 | 4400 | 5000 | 2500 | 115,120,106,121 | 13800 | 20700 | WBS Description: This task involves ...
108 | 575 | 3.1.2.1.7 | OD Mounting tab prototype and testing | 2005-08-11 08:00 | 2005-08-31 17:00 | Yes | W&M | W&M Undergrad[10%],W&M Shop [20%],W&M MandS[500] | 3 wks | 864 | 432 | 500 | 55 | 102 | 1364 | 1851 | WBS Description: This task involves ...
109 | 560 | 3.1.2.1.8 | W&M OD Routing design and mockup | 2005-06-29 08:00 | 2005-08-09 17:00 | Yes | W&M | W&M Tech[75%],W&M Undergrad[25%],W&M Shop [25%],W&M MandS[3,000] | 5.8 wks | 9918 | 3967.2 | 3000 | 900 | 102SS+1 mon | 12918 | 17785.2 | WBS Description: This task involves ...
110 | 561 | 3.1.2.1.9 | W&M OD One Tower PT | 2005-12-27 13:00 | 2006-01-18 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[50%] | 2.8 wks | 3080 | 1232 | 0 | 0 | 109,123,108,120 | 3080 | 4312 | WBS Description: This task involves ...
111 | 466 | 3.1.2.2 | Consulting Design Engineer Phase 1 | 2005-06-01 08:00 | 2006-01-30 17:00 | No |  |  | 33.2 wks | 0 | 0 | 12768 | 5107.2 |  | 12768 | 17875.2
112 | 468 | 3.1.2.2.1 | Design H-clip | 2005-10-03 08:00 | 2005-11-11 17:00 | Yes | W&M | W&M MandS[12,768] | 6 wks | 0 | 0 | 12768 | 5107.2 | 615 | 12768 | 17875.2 | WBS Description: This task involves ...
113 | 513 | 3.1.2.2.2 | Design Glue machine | 2005-06-01 08:00 | 2005-11-17 17:00 | Yes | W&M |  | 24 wks | 0 | 0 | 0 | 0 | 2 | 0 | 0 | WBS Description: This task involves ...
114 | 512 | 3.1.2.2.3 | Skin & Adhesive specifications | 2005-10-03 08:00 | 2005-10-21 17:00 | Yes | W&M |  | 3 wks | 0 | 0 | 0 | 0 | 615 | 0 | 0 | WBS Description: This task involves ...
115 | 481 | 3.1.2.2.4 | Edge and manifold part design | 2005-10-03 08:00 | 2006-01-30 17:00 | Yes | W&M |  | 16 wks | 0 | 0 | 0 | 0 | 615 | 0 | 0 | WBS Description: This task involves ...
116 | 370 | 3.1.2.3 | Consulting Design Engineer Phase 2 | 2006-03-28 08:00 | 2006-06-06 17:00 | No |  |  | 10 wks | 0 | 0 | 12768 | 5107.2 |  | 12768 | 17875.2
117 | 469 | 3.1.2.3.1 | Design H-clip production | 2006-03-28 08:00 | 2006-06-06 17:00 | Yes | W&M | W&M MandS[12,768] | 10 wks | 0 | 0 | 12768 | 5107.2 | 92 | 12768 | 17875.2 | WBS Description: This task involves ...
118 | 472 | 3.1.2.3.2 | Edge and manifold part production design | 2006-03-28 08:00 | 2006-06-06 17:00 | Yes | W&M |  | 10 wks | 0 | 0 | 0 | 0 | 92 | 0 | 0 | WBS Description: This task involves ...
119 | 373 | 3.1.2.4 | HU Design and Testing | 2005-06-29 08:00 | 2006-03-10 17:00 | No |  |  | 35 wks | 39110 | 15644 | 11429 | 3571.6 |  | 50539 | 69754.6
120 | 465 | 3.1.2.4.1 | Adhesives and Skins Design and specification | 2005-10-24 08:00 | 2005-12-27 12:00 | Yes | Hampton | HU Undergrad[67%],HU Tech[133%],HU MandS[5,000] | 8.6 wks | 19264 | 7705.6 | 5000 | 1000 | 114 | 24264 | 32969.6 | WBS Description: This task involves ...
121 | 525 | 3.1.2.4.2 | ID fiber routing, light sealing, and protection design and prototyping | 2005-06-29 08:00 | 2005-08-29 17:00 | Yes | Rochester | Roch ME[25%] | 8.6 wks | 5762 | 2304.8 | 0 | 0 | 106SS | 5762 | 8066.8 | WBS Description: This task involves ...
122 | 571 | 3.1.2.4.3 | HU ID half plane PT | 2006-01-31 08:00 | 2006-03-10 17:00 | Yes | Hampton | HU Shop[50%],HU Undergrad[50%],HU MandS[1,429] | 5.8 wks | 5568 | 2227.2 | 1429 | 571.6 | 107SS | 6997 | 9795.8 | WBS Description: This task involves ...
123 | 483 | 3.1.2.4.4 | OD fiber routing, light sealing, and protection design and prototyping | 2005-06-29 08:00 | 2005-07-29 17:00 | Yes | Rochester | Roch ME[25%],Roch MandS[3,571] | 4.4 wks | 2948 | 1179.2 | 3571 | 1428.4 | 109SS | 6519 | 9126.6 | WBS Description: This task involves ...
124 | 570 | 3.1.2.4.5 | HU OD One Tower PT | 2005-12-27 13:00 | 2006-02-08 17:00 | Yes | Hampton | HU Tech[50%],HU Undergrad[50%],HU MandS[1,429] | 5.8 wks | 5568 | 2227.2 | 1429 | 571.6 | 110SS | 6997 | 9795.8 | WBS Description: This task involves ...
125 | 440 | 3.1.3 | Outfitting | 2006-01-12 08:00 | 2006-11-09 17:00 | No |  |  | 42.4 wks | 23954.4 | 9581.76 | 8928 | 3571.2 |  | 32882.4 | 46035.36
126 | 441 | 3.1.3.1 | W&M Outfitting | 2006-01-12 08:00 | 2006-11-09 17:00 | No |  |  | 42.4 wks | 16228.8 | 6491.52 | 8928 | 3571.2 |  | 25156.8 | 35219.52
127 | 442 | 3.1.3.1.1 | W&M ID PT Outfitting | 2006-03-14 08:00 | 2006-06-01 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[50%],W&M MandS[3,571] | 11.4 wks | 12540 | 5016 | 3571 | 1428.4 | 107SS+1.5 mons | 16111 | 22555.4 | WBS Description: This task involves ...
128 | 444 | 3.1.3.1.2 | W&M OD PT Outfitting | 2006-01-12 08:00 | 2006-02-16 17:00 | Yes | W&M |  | 5 wks | 0 | 0 | 0 | 0 | 110SS+2 wks | 0 | 0 | WBS Description: This task involves ...
129 | 446 | 3.1.3.1.3 | W&M ID Outfitting | 2006-10-02 08:00 | 2006-11-09 17:00 | Yes | W&M | W&M Shop [53%],W&M MandS[5,357] | 5.8 wks | 3688.8 | 1475.52 | 5357 | 2142.8 | 616 | 9045.8 | 12664.12 | WBS Description: This task involves ...
130 | 448 | 3.1.3.1.4 | W&M OD Outfitting | 2006-10-02 08:00 | 2006-10-27 17:00 | Yes | W&M |  | 4 wks | 0 | 0 | 0 | 0 | 616 | 0 | 0 | WBS Description: This task involves ...
131 | 450 | 3.1.3.2 | HU Outfitting | 2006-01-12 08:00 | 2006-11-09 17:00 | No |  |  | 42.4 wks | 7725.6 | 3090.24 | 0 | 0 |  | 7725.6 | 10815.84
132 | 451 | 3.1.3.2.1 | HU ID PT Outfitting | 2006-03-14 08:00 | 2006-07-05 17:00 | Yes | Hampton |  | 16 wks | 0 | 0 | 0 | 0 | 107SS+1.5 mons | 0 | 0 | WBS Description: This task involves ...
133 | 453 | 3.1.3.2.2 | HU OD PT Outfitting | 2006-01-12 08:00 | 2006-02-16 17:00 | Yes | Hampton |  | 5 wks | 0 | 0 | 0 | 0 | 110SS+2 wks | 0 | 0 | WBS Description: This task involves ...
134 | 455 | 3.1.3.2.3 | HU ID Outfitting | 2006-10-02 08:00 | 2006-11-09 17:00 | Yes | Hampton | HU Shop[93%] | 5.8 wks | 7725.6 | 3090.24 | 0 | 0 | 616 | 7725.6 | 10815.84 | WBS Description: This task involves ...
135 | 457 | 3.1.3.2.4 | HU OD Outfitting | 2006-10-02 08:00 | 2006-10-20 17:00 | Yes | Hampton |  | 3 wks | 0 | 0 | 0 | 0 | 616 | 0 | 0 | WBS Description: This task involves ...
136 | 257 | 3.1.4 | ID Plane Prototype Development | 2006-04-18 08:00 | 2006-07-20 17:00 | No |  |  | 13.2 wks | 32240 | 12959.2 | 10001 | 4000.4 |  | 42241 | 59200.6
137 | 376 | 3.1.4.1 | W&M ID Plane Prototyping | 2006-04-18 08:00 | 2006-07-05 17:00 | No |  |  | 11 wks | 17552 | 7055.2 | 7143 | 2857.2 |  | 24695 | 34607.4
138 | 538 | 3.1.4.1.1 | W&M ID One Plane Prototype | 2006-04-18 08:00 | 2006-06-07 17:00 | Yes | W&M | W&M Undergrad[25%],W&M Tech[50%],W&M MandS[2,143] | 7.2 wks | 7056 | 2822.4 | 2143 | 857.2 | 92,42,46 | 9199 | 12878.6 | WBS Description: This task involves ...
139 | 539 | 3.1.4.1.2 | W&M ID 1PP Review | 2006-06-08 08:00 | 2006-06-08 17:00 | Yes | W&M | W&M Tech,W&M MandS[2,857] | 1 day | 344 | 172 | 2857 | 1142.8 | 138 | 3201 | 4515.8 | WBS Description: This task involves ...
140 | 540 | 3.1.4.1.3 | W&M ID Full Module Prototype | 2006-06-09 08:00 | 2006-07-05 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[150%],W&M MandS[2,143] | 3.6 wks | 10152 | 4060.8 | 2143 | 857.2 | 139,20 | 12295 | 17213 | WBS Description: This task involves ...
141 | 378 | 3.1.4.2 | HU ID Plane Prototyping | 2006-04-18 08:00 | 2006-07-20 17:00 | No |  |  | 13.2 wks | 14688 | 5904 | 2858 | 1143.2 |  | 17546 | 24593.2
142 | 548 | 3.1.4.2.1 | HU ID One Plane Prototype | 2006-04-18 08:00 | 2006-06-07 17:00 | Yes | Hampton | HU Tech[50%],HU Undergrad[25%],HU MandS[1,429] | 7.2 wks | 6048 | 2419.2 | 1429 | 571.6 | 92,42,46 | 7477 | 10467.8 | WBS Description: This task involves ...
143 | 549 | 3.1.4.2.2 | HU ID 1PP Review | 2006-06-08 08:00 | 2006-06-08 17:00 | Yes | Hampton | HU Tech | 1 day | 288 | 144 | 0 | 0 | 138,142 | 288 | 432 | WBS Description: This task involves ...
144 | 550 | 3.1.4.2.3 | HU ID Full Module Prototype | 2006-06-09 08:00 | 2006-07-20 17:00 | Yes | Hampton | HU Tech[50%],HU Undergrad[150%],HU MandS[1,429] | 5.8 wks | 8352 | 3340.8 | 1429 | 571.6 | 139 | 9781 | 13693.4 | WBS Description: This task involves ...
145 | 256 | 3.1.5 | OD Package Prototype Development | 2006-01-19 08:00 | 2006-03-07 17:00 | No |  |  | 6.8 wks | 13048 | 5270 | 6427 | 2570.8 |  | 19475 | 27315.8
146 | 387 | 3.1.5.1 | W&M OD Plane Prototyping | 2006-01-19 08:00 | 2006-03-07 17:00 | No |  |  | 6.8 wks | 6952 | 2802.8 | 4999 | 1999.6 |  | 11951 | 16753.4
147 | 567 | 3.1.5.1.1 | W&M OD One Frame Prototype | 2006-01-19 08:00 | 2006-02-17 17:00 | Yes | W&M | W&M Undergrad[25%],W&M Tech[50%],W&M MandS[1,071] | 4.4 wks | 4312 | 1724.8 | 1071 | 428.4 | 96 | 5383 | 7536.2 | WBS Description: This task involves ...
148 | 568 | 3.1.5.1.2 | W&M OD 1FP Review | 2006-02-20 08:00 | 2006-02-20 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[50%],W&M MandS[2,857] | 1 day | 220 | 110 | 2857 | 1142.8 | 147 | 3077 | 4329.8 | WBS Description: This task involves ...
149 | 569 | 3.1.5.1.3 | W&M OD Full Module Prototype | 2006-02-21 08:00 | 2006-03-07 17:00 | Yes | W&M | W&M Undergrad[50%],W&M Tech[50%],W&M MandS[1,071] | 2.2 wks | 2420 | 968 | 1071 | 428.4 | 148 | 3491 | 4887.4 | WBS Description: This task involves ...
150 | 386 | 3.1.5.2 | HU OD Plane Prototyping | 2006-01-19 08:00 | 2006-03-07 17:00 | No |  |  | 6.8 wks | 6096 | 2467.2 | 1428 | 571.2 |  | 7524 | 10562.4
151 | 563 | 3.1.5.2.1 | HU OD One Frame Prototype | 2006-01-19 08:00 | 2006-02-17 17:00 | Yes | Hampton | HU Undergrad[25%],HU Tech[50%],HU MandS[714] | 4.4 wks | 3696 | 1478.4 | 714 | 285.6 | 96 | 4410 | 6174 | WBS Description: This task involves ...
152 | 564 | 3.1.5.2.2 | HU OD 1FP Review | 2006-02-20 08:00 | 2006-02-20 17:00 | Yes | Hampton | HU Tech | 1 day | 288 | 144 | 0 | 0 | 147,151 | 288 | 432 | WBS Description: This task involves ...
153 | 565 | 3.1.5.2.3 | HU OD Full Module Prototype | 2006-02-21 08:00 | 2006-03-07 17:00 | Yes | Hampton | HU Tech[50%],HU Undergrad[50%],HU MandS[714] | 2.2 wks | 2112 | 844.8 | 714 | 285.6 | 148 | 2826 | 3956.4 | WBS Description: This task involves ...
154 | 75 | 3.2 | Scintillator Plane Components | 2006-10-02 08:00 | 2007-12-18 17:00 | No |  |  | 61.2 wks | 9360 | 2304 | 272292 | 105556.8 |  | 281652 | 389512.8
155 | 1409 | 3.2.1 | Financial Commitments by Universities | 2006-10-02 08:00 | 2007-10-19 17:00 | No |  |  | 53.2 wks | 0 | 0 | 0 | 0 |  | 0 | 0
156 | 610 | 3.2.1.1 | W&M FY07 Pre-award for plane components | 2006-10-02 08:00 | 2006-10-20 17:00 | Yes | W&M |  | 3 wks | 0 | 0 | 0 | 0 | 616 | 0 | 0 | WBS Description: This task involves ...
157 | 609 | 3.2.1.2 | Hampton FY07 Pre-award for plane components | 2006-10-02 08:00 | 2006-10-20 17:00 | Yes | Hampton |  | 3 wks | 0 | 0 | 0 | 0 | 156SS | 0 | 0 | WBS Description: This task involves ...
158 | 608 | 3.2.1.3 | W&M and Hampton FY07 Pre-awards Approved | 2006-10-20 17:00 | 2006-10-20 17:00 | Yes |  |  | 0 wks | 0 | 0 | 0 | 0 | 156,157 | 0 | 0 | WBS Description: This task involves ...
159 | 1314 | 3.2.1.4 | W&M FY08 Pre-award for plane components | 2007-10-01 08:00 | 2007-10-19 17:00 | No | W&M |  | 3 wks | 0 | 0 | 0 | 0 | 617 | 0 | 0
160 | 1313 | 3.2.1.5 | Hampton FY08 Pre-award for plane components | 2007-10-01 08:00 | 2007-10-19 17:00 | No | Hampton |  | 3 wks | 0 | 0 | 0 | 0 | 159SS | 0 | 0
161 | 1312 | 3.2.1.6 | W&M and Hampton FY08 Pre-awards Approved | 2007-10-19 17:00 | 2007-10-19 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 159,160 | 0 | 0
162 | 1339 | 3.2.2 | Acquire Inner Detector Plane Components | 2006-10-23 08:00 | 2007-12-18 17:00 | No |  |  | 58.2 wks | 4680 | 1152 | 136146 | 52778.4 |  | 140826 | 194756.4
163 | 399 | 3.2.2.1 | ID Plane Components 1 - 20 at William & Mary | 2006-10-23 08:00 | 2006-12-19 17:00 | No |  |  | 8 wks | 1560 | 384 | 43982 | 17592.8 |  | 45542 | 63518.8
164 | 398 | 3.2.2.1.1 | Procure components for ID Modules (1-20) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[41,589] | 6 wks | 0 | 0 | 41589 | 16635.6 | 158,94 | 41589 | 58224.6 | WBS Description: Acquisition of parts and materials needed to for the mirror end and sides of the ID scintillator planes ...
165 | 397 | 3.2.2.1.2 | Procure ID scintillator readout routing parts (1-20) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[993] | 6 wks | 0 | 0 | 993 | 397.2 | 158 | 993 | 1390.2 | WBS Description: Acquisition of parts and materials needed to routing the ID WLS fiber from the end of the scintillator strips to the surface for the frames....
166 | 401 | 3.2.2.1.3 | Machine ID scintillator readout routing parts (1-20) | 2006-12-06 08:00 | 2006-12-19 17:00 | No | W&M | W&M Shop [40%] | 2 wks | 960 | 384 | 0 | 0 | 165 | 960 | 1344 | WBS Description: This task involves ...
167 | 400 | 3.2.2.1.4 | Procure WLS fiber OD routing components (1-20) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[1,000] | 6 wks | 0 | 0 | 1000 | 400 | 165SS | 1000 | 1400 | WBS Description: Acquisition of parts and materials needed to route WLS fibers from the “S” bend at the inside of the steel frame to the optical connector boxes at edge of the frame...
168 | 395 | 3.2.2.1.5 | Procure routing supports & box mounts (1-20) | 2006-10-23 08:00 | 2006-11-03 17:00 | No | W&M | W&M MandS[400] | 2 wks | 0 | 0 | 400 | 160 | 167SS | 400 | 560 | WBS Description: This task involves ...
169 | 405 | 3.2.2.1.6 | Machine routing supports & box mounts (1-20) | 2006-11-06 08:00 | 2006-11-17 17:00 | No | W&M | W&M Shop [25%] | 2 wks | 600 | 0 | 0 | 0 | 168 | 600 | 600 | WBS Description: This task involves machining of the routing supports and connector box mounts (planes 1-20)...
170 | 407 | 3.2.2.2 | ID Plane Components 1 - 20 at Hampton | 2006-10-23 08:00 | 2006-12-19 17:00 | No |  |  | 8 wks | 0 | 0 | 1400 | 0 |  | 1400 | 1400
171 | 404 | 3.2.2.2.1 | Purchase ID package materials (1-20) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | Hampton | HU MandS[1,000] | 6 wks | 0 | 0 | 1000 | 0 | 158 | 1000 | 1000 | WBS Description: Purchase of materials required for planes 1 - 20 to be constructed at Hampton....
172 | 406 | 3.2.2.2.2 | Purchase scintillator detailing and curing components (1-20) | 2006-10-23 08:00 | 2006-11-17 17:00 | No | Hampton | HU MandS[400] | 4 wks | 0 | 0 | 400 | 0 | 171SS | 400 | 400 | WBS Description: This task involves ...
173 | 1315 | 3.2.2.2.3 | Module Parts Ready to Assemble Planes 1 - 20 | 2006-12-19 17:00 | 2006-12-19 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 171,166,164,169,172,167 | 0 | 0
174 | 1317 | 3.2.2.3 | ID Plane Components 21 - 100 at William & Mary | 2006-12-20 08:00 | 2007-02-19 17:00 | No |  |  | 8 wks | 1560 | 384 | 43982 | 17592.8 |  | 45542 | 63518.8
175 | 1318 | 3.2.2.3.1 | Procure components for ID Modules (21-100) | 2006-12-20 08:00 | 2007-02-05 17:00 | No | W&M | W&M MandS[41,589] | 6 wks | 0 | 0 | 41589 | 16635.6 | 173 | 41589 | 58224.6 | WBS Description: Acquisition of parts and materials needed to for the mirror end and sides of the ID scintillator planes ...
176 | 1319 | 3.2.2.3.2 | Procure ID scintillator readout routing parts (21-100) | 2006-12-20 08:00 | 2007-02-05 17:00 | No | W&M | W&M MandS[993] | 6 wks | 0 | 0 | 993 | 397.2 | 175SS | 993 | 1390.2 | WBS Description: Acquisition of parts and materials needed to routing the ID WLS fiber from the end of the scintillator strips to the surface for the frames....
177 | 1320 | 3.2.2.3.3 | Machine ID scintillator readout routing parts (21-100) | 2007-02-06 08:00 | 2007-02-19 17:00 | No | W&M | W&M Shop [40%] | 2 wks | 960 | 384 | 0 | 0 | 176 | 960 | 1344 | WBS Description: This task involves ...
178 | 1321 | 3.2.2.3.4 | Procure WLS fiber OD routing components (21-100) | 2006-12-20 08:00 | 2007-02-05 17:00 | No | W&M | W&M MandS[1,000] | 6 wks | 0 | 0 | 1000 | 400 | 176SS | 1000 | 1400 | WBS Description: Acquisition of parts and materials needed to route WLS fibers from the “S” bend at the inside of the steel frame to the optical connector boxes at edge of the frame...
179 | 1322 | 3.2.2.3.5 | Procure routing supports & box mounts (21-100) | 2006-12-20 08:00 | 2007-01-05 17:00 | No | W&M | W&M MandS[400] | 2 wks | 0 | 0 | 400 | 160 | 178SS | 400 | 560 | WBS Description: This task involves ...
180 | 1323 | 3.2.2.3.6 | Machine routing supports & box mounts (21-100) | 2007-01-08 08:00 | 2007-01-22 17:00 | No | W&M | W&M Shop [25%] | 2 wks | 600 | 0 | 0 | 0 | 179 | 600 | 600 | WBS Description: This task involves machining of the routing supports and connector box mounts (planes 1-20)...
181 | 1324 | 3.2.2.4 | ID Plane Components 21 - 100 at Hampton | 2006-12-20 08:00 | 2007-02-19 17:00 | No |  |  | 8 wks | 0 | 0 | 1400 | 0 |  | 1400 | 1400
182 | 1325 | 3.2.2.4.1 | Purchase ID package materials (21-100) | 2006-12-20 08:00 | 2007-02-05 17:00 | No | Hampton | HU MandS[1,000] | 6 wks | 0 | 0 | 1000 | 0 | 173 | 1000 | 1000 | WBS Description: Purchase of materials required for planes 1 - 20 to be constructed at Hampton....
183 | 1326 | 3.2.2.4.2 | Purchase scintillator detailing and curing components (21-100) | 2006-12-20 08:00 | 2007-01-22 17:00 | No | Hampton | HU MandS[400] | 4 wks | 0 | 0 | 400 | 0 | 182SS | 400 | 400 | WBS Description: This task involves ...
184 | 1327 | 3.2.2.4.3 | Module Parts Ready to Assemble Planes 21 - 100 | 2007-02-19 17:00 | 2007-02-19 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 182,175,177,180,183,178 | 0 | 0
185 | 1328 | 3.2.2.5 | ID Plane Components 101 - 208 at William & Mary | 2007-10-22 08:00 | 2007-12-18 17:00 | No |  |  | 8 wks | 1560 | 384 | 43982 | 17592.8 |  | 45542 | 63518.8
186 | 1329 | 3.2.2.5.1 | Procure components for ID Modules (101 - 208) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | W&M | W&M MandS[41,589] | 6 wks | 0 | 0 | 41589 | 16635.6 | 161 | 41589 | 58224.6 | WBS Description: Acquisition of parts and materials needed to for the mirror end and sides of the ID scintillator planes ...
187 | 1330 | 3.2.2.5.2 | Procure ID scintillator readout routing parts (101 - 208) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | W&M | W&M MandS[993] | 6 wks | 0 | 0 | 993 | 397.2 | 186SS | 993 | 1390.2 | WBS Description: Acquisition of parts and materials needed to routing the ID WLS fiber from the end of the scintillator strips to the surface for the frames....
188 | 1331 | 3.2.2.5.3 | Machine ID scintillator readout routing parts (101 - 208) | 2007-12-05 08:00 | 2007-12-18 17:00 | No | W&M | W&M Shop [40%] | 2 wks | 960 | 384 | 0 | 0 | 187 | 960 | 1344 | WBS Description: This task involves ...
189 | 1332 | 3.2.2.5.4 | Procure WLS fiber OD routing components (101 - 208) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | W&M | W&M MandS[1,000] | 6 wks | 0 | 0 | 1000 | 400 | 187SS | 1000 | 1400 | WBS Description: Acquisition of parts and materials needed to route WLS fibers from the “S” bend at the inside of the steel frame to the optical connector boxes at edge of the frame...
190 | 1333 | 3.2.2.5.5 | Procure routing supports & box mounts (101 - 208) | 2007-10-22 08:00 | 2007-11-02 17:00 | No | W&M | W&M MandS[400] | 2 wks | 0 | 0 | 400 | 160 | 189SS | 400 | 560 | WBS Description: This task involves ...
191 | 1334 | 3.2.2.5.6 | Machine routing supports & box mounts (101 - 208) | 2007-11-05 08:00 | 2007-11-16 17:00 | No | W&M | W&M Shop [25%] | 2 wks | 600 | 0 | 0 | 0 | 190 | 600 | 600 | WBS Description: This task involves machining of the routing supports and connector box mounts (planes 1-20)...
192 | 1335 | 3.2.2.6 | ID Plane Components 101 - 208 at Hampton | 2007-10-22 08:00 | 2007-12-18 17:00 | No |  |  | 8 wks | 0 | 0 | 1400 | 0 |  | 1400 | 1400
193 | 1336 | 3.2.2.6.1 | Purchase ID package materials (101 - 208) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | Hampton | HU MandS[1,000] | 6 wks | 0 | 0 | 1000 | 0 | 161 | 1000 | 1000 | WBS Description: Purchase of materials required for planes 1 - 20 to be constructed at Hampton....
194 | 1337 | 3.2.2.6.2 | Purchase scintillator detailing and curing components (101 - 208) | 2007-10-22 08:00 | 2007-11-16 17:00 | No | Hampton | HU MandS[400] | 4 wks | 0 | 0 | 400 | 0 | 193SS | 400 | 400 | WBS Description: This task involves ...
195 | 1338 | 3.2.2.6.3 | Module Parts Ready to Assemble Planes 101 - 208 | 2007-12-18 17:00 | 2007-12-18 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 193,186,194,188,189,191 | 0 | 0
196 | 1340 | 3.2.3 | Acquire Outer Detector Tower Components | 2006-10-23 08:00 | 2007-12-18 17:00 | No |  |  | 58.2 wks | 4680 | 1152 | 136146 | 52778.4 |  | 140826 | 194756.4
197 | 1341 | 3.2.3.1 | OD Tower Components 1 - 12 at William & Mary | 2006-10-23 08:00 | 2006-12-19 17:00 | No |  |  | 8 wks | 1560 | 384 | 43982 | 17592.8 |  | 45542 | 63518.8
198 | 1342 | 3.2.3.1.1 | Procure components for OD Modules (1-12) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[41,589] | 6 wks | 0 | 0 | 41589 | 16635.6 | 158 | 41589 | 58224.6 | WBS Description: Acquisition of parts and materials needed to for the mirror end and sides of the ID scintillator planes ...
199 | 1343 | 3.2.3.1.2 | Procure OD scintillator readout routing parts (1-12) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[993] | 6 wks | 0 | 0 | 993 | 397.2 | 198SS | 993 | 1390.2 | WBS Description: Acquisition of parts and materials needed to routing the ID WLS fiber from the end of the scintillator strips to the surface for the frames....
200 | 1344 | 3.2.3.1.3 | Machine OD scintillator readout routing parts (1-12) | 2006-12-06 08:00 | 2006-12-19 17:00 | No | W&M | W&M Shop [40%] | 2 wks | 960 | 384 | 0 | 0 | 199 | 960 | 1344 | WBS Description: This task involves ...
201 | 1345 | 3.2.3.1.4 | Procure WLS fiber OD routing components (1-12) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[1,000] | 6 wks | 0 | 0 | 1000 | 400 | 199SS | 1000 | 1400 | WBS Description: Acquisition of parts and materials needed to route WLS fibers from the “S” bend at the inside of the steel frame to the optical connector boxes at edge of the frame...
202 | 1346 | 3.2.3.1.5 | Procure routing supports & box mounts (1-12) | 2006-10-23 08:00 | 2006-11-03 17:00 | No | W&M | W&M MandS[400] | 2 wks | 0 | 0 | 400 | 160 | 201SS | 400 | 560 | WBS Description: This task involves ...
203 | 1347 | 3.2.3.1.6 | Machine routing supports & box mounts (1-12) | 2006-11-06 08:00 | 2006-11-17 17:00 | No | W&M | W&M Shop [25%] | 2 wks | 600 | 0 | 0 | 0 | 202 | 600 | 600 | WBS Description: This task involves machining of the routing supports and connector box mounts (planes 1-20)...
204 | 1348 | 3.2.3.2 | OD Tower Components 1 - 12 at Hampton | 2006-10-23 08:00 | 2006-12-19 17:00 | No |  |  | 8 wks | 0 | 0 | 1400 | 0 |  | 1400 | 1400
205 | 1349 | 3.2.3.2.1 | Purchase OD package materials (1-12) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | Hampton | HU MandS[1,000] | 6 wks | 0 | 0 | 1000 | 0 | 158 | 1000 | 1000 | WBS Description: Purchase of materials required for planes 1 - 20 to be constructed at Hampton....
206 | 1350 | 3.2.3.2.2 | Purchase scintillator detailing and curing components (1-12) | 2006-10-23 08:00 | 2006-11-17 17:00 | No | Hampton | HU MandS[400] | 4 wks | 0 | 0 | 400 | 0 | 205SS | 400 | 400 | WBS Description: This task involves ...
207 | 1351 | 3.2.3.2.3 | Module Parts Ready to Assemble Towers 1 - 12 | 2006-12-19 17:00 | 2006-12-19 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 198,200,205,203,206,201 | 0 | 0
208 | 1352 | 3.2.3.3 | OD Tower Components 13 - 50 at William & Mary | 2006-10-23 08:00 | 2006-12-19 17:00 | No |  |  | 8 wks | 1560 | 384 | 43982 | 17592.8 |  | 45542 | 63518.8
209 | 1353 | 3.2.3.3.1 | Procure components for OD Modules (13-50) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[41,589] | 6 wks | 0 | 0 | 41589 | 16635.6 | 158 | 41589 | 58224.6 | WBS Description: Acquisition of parts and materials needed to for the mirror end and sides of the ID scintillator planes ...
210 | 1354 | 3.2.3.3.2 | Procure OD scintillator readout routing parts (13-50) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[993] | 6 wks | 0 | 0 | 993 | 397.2 | 209SS | 993 | 1390.2 | WBS Description: Acquisition of parts and materials needed to routing the ID WLS fiber from the end of the scintillator strips to the surface for the frames....
211 | 1355 | 3.2.3.3.3 | Machine OD scintillator readout routing parts (13-50) | 2006-12-06 08:00 | 2006-12-19 17:00 | No | W&M | W&M Shop [40%] | 2 wks | 960 | 384 | 0 | 0 | 210 | 960 | 1344 | WBS Description: This task involves ...
212 | 1356 | 3.2.3.3.4 | Procure WLS fiber OD routing components (13-50) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | W&M | W&M MandS[1,000] | 6 wks | 0 | 0 | 1000 | 400 | 210SS | 1000 | 1400 | WBS Description: Acquisition of parts and materials needed to route WLS fibers from the “S” bend at the inside of the steel frame to the optical connector boxes at edge of the frame...
213 | 1357 | 3.2.3.3.5 | Procure routing supports & box mounts (13-50) | 2006-10-23 08:00 | 2006-11-03 17:00 | No | W&M | W&M MandS[400] | 2 wks | 0 | 0 | 400 | 160 | 212SS | 400 | 560 | WBS Description: This task involves ...
214 | 1358 | 3.2.3.3.6 | Machine routing supports & box mounts (13-50) | 2006-11-06 08:00 | 2006-11-17 17:00 | No | W&M | W&M Shop [25%] | 2 wks | 600 | 0 | 0 | 0 | 213 | 600 | 600 | WBS Description: This task involves machining of the routing supports and connector box mounts (planes 1-20)...
215 | 1359 | 3.2.3.4 | OD Tower Components 13 - 50 at Hampton | 2006-10-23 08:00 | 2006-12-19 17:00 | No |  |  | 8 wks | 0 | 0 | 1400 | 0 |  | 1400 | 1400
216 | 1360 | 3.2.3.4.1 | Purchase OD package materials (13-50) | 2006-10-23 08:00 | 2006-12-05 17:00 | No | Hampton | HU MandS[1,000] | 6 wks | 0 | 0 | 1000 | 0 | 158 | 1000 | 1000 | WBS Description: Purchase of materials required for planes 1 - 20 to be constructed at Hampton....
217 | 1361 | 3.2.3.4.2 | Purchase scintillator detailing and curing components (13-50) | 2006-10-23 08:00 | 2006-11-17 17:00 | No | Hampton | HU MandS[400] | 4 wks | 0 | 0 | 400 | 0 | 216SS | 400 | 400 | WBS Description: This task involves ...
218 | 1362 | 3.2.3.4.3 | Module Parts Ready to Assemble Towers 13 - 50 | 2006-12-19 17:00 | 2006-12-19 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 209,211,214,216,217,212 | 0 | 0
219 | 1363 | 3.2.3.5 | OD Tower Components 51 - 116 at William & Mary | 2007-10-22 08:00 | 2007-12-18 17:00 | No |  |  | 8 wks | 1560 | 384 | 43982 | 17592.8 |  | 45542 | 63518.8
220 | 1364 | 3.2.3.5.1 | Procure components for OD Modules (51-116) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | W&M | W&M MandS[41,589] | 6 wks | 0 | 0 | 41589 | 16635.6 | 161 | 41589 | 58224.6 | WBS Description: Acquisition of parts and materials needed to for the mirror end and sides of the ID scintillator planes ...
221 | 1365 | 3.2.3.5.2 | Procure OD scintillator readout routing parts (51-116) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | W&M | W&M MandS[993] | 6 wks | 0 | 0 | 993 | 397.2 | 220SS | 993 | 1390.2 | WBS Description: Acquisition of parts and materials needed to routing the ID WLS fiber from the end of the scintillator strips to the surface for the frames....
222 | 1366 | 3.2.3.5.3 | Machine OD scintillator readout routing parts (51-116) | 2007-12-05 08:00 | 2007-12-18 17:00 | No | W&M | W&M Shop [40%] | 2 wks | 960 | 384 | 0 | 0 | 221 | 960 | 1344 | WBS Description: This task involves ...
223 | 1367 | 3.2.3.5.4 | Procure WLS fiber OD routing components (51-116) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | W&M | W&M MandS[1,000] | 6 wks | 0 | 0 | 1000 | 400 | 221SS | 1000 | 1400 | WBS Description: Acquisition of parts and materials needed to route WLS fibers from the “S” bend at the inside of the steel frame to the optical connector boxes at edge of the frame...
224 | 1368 | 3.2.3.5.5 | Procure routing supports & box mounts (51-116) | 2007-10-22 08:00 | 2007-11-02 17:00 | No | W&M | W&M MandS[400] | 2 wks | 0 | 0 | 400 | 160 | 223SS | 400 | 560 | WBS Description: This task involves ...
225 | 1369 | 3.2.3.5.6 | Machine routing supports & box mounts (51-116) | 2007-11-05 08:00 | 2007-11-16 17:00 | No | W&M | W&M Shop [25%] | 2 wks | 600 | 0 | 0 | 0 | 224 | 600 | 600 | WBS Description: This task involves machining of the routing supports and connector box mounts (planes 1-20)...
226 | 1370 | 3.2.3.6 | OD Tower Components 51 - 116 at Hampton | 2007-10-22 08:00 | 2007-12-18 17:00 | No |  |  | 8 wks | 0 | 0 | 1400 | 0 |  | 1400 | 1400
227 | 1371 | 3.2.3.6.1 | Purchase OD package materials (51-116) | 2007-10-22 08:00 | 2007-12-04 17:00 | No | Hampton | HU MandS[1,000] | 6 wks | 0 | 0 | 1000 | 0 | 161 | 1000 | 1000 | WBS Description: Purchase of materials required for planes 1 - 20 to be constructed at Hampton....
228 | 1372 | 3.2.3.6.2 | Purchase scintillator detailing and curing components (51-116) | 2007-10-22 08:00 | 2007-11-16 17:00 | No | Hampton | HU MandS[400] | 4 wks | 0 | 0 | 400 | 0 | 227SS | 400 | 400 | WBS Description: This task involves ...
229 | 1373 | 3.2.3.6.3 | Module Parts Ready to Assemble Towers 51 - 116 | 2007-12-18 17:00 | 2007-12-18 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 220,222,223,225,227,228 | 0 | 0
230 | 60 | 3.3 | Plane Production | 2006-12-20 08:00 | 2008-04-29 17:00 | No |  |  | 68.2 wks | 596068.8 | 213129.6 | 0 | 0 |  | 596068.8 | 809198.4
231 | 611 | 3.3.1 | Plane Production Factory Start-ups | 2006-12-20 08:00 | 2007-03-08 17:00 | No |  |  | 10.6 wks | 136771.2 | 29410.56 | 0 | 0 |  | 136771.2 | 166181.76
232 | 613 | 3.3.1.1 | W&M Plane Production Factory Start-up | 2006-12-20 08:00 | 2007-03-08 17:00 | Yes | W&M | W&M Tech[340%],W&M Undergrad[200%] | 10.6 wks | 73526.4 | 29410.56 | 0 | 0 | 173,93,85 | 73526.4 | 102936.96 | WBS Description: This task covers the initial start-up of the factory at William & Mary for ID Plane production. Once the first 20 Planes have been produced (roughly 10 each at W&M and Hampton) the factory will begin full production....
233 | 612 | 3.3.1.2 | HU Plane Production Factory Start-up | 2006-12-20 08:00 | 2007-03-05 17:00 | Yes | Hampton | HU Tech[340%],HU Undergrad[200%] | 10 wks | 63244.8 | 0 | 0 | 0 | 173,93 | 63244.8 | 63244.8 | WBS Description: This task covers the initial start-up of the factory at Hampton University for ID Plane production. Once the first 20 Planes have been produced (roughly 10 each at W&M and Hampton) the factory will begin full production....
234 | 259 | 3.3.2 | ID Plane Production | 2007-04-18 08:00 | 2008-04-29 17:00 | No |  |  | 52 wks | 308505.6 | 123402.24 | 0 | 0 |  | 308505.6 | 431907.84
235 | 413 | 3.3.2.1 | Construct ID Planes 1 -50 at W&M | 2007-04-18 08:00 | 2007-06-07 17:00 | No | W&M | W&M Tech[240%],W&M Undergrad | 7.2 wks | 33177.6 | 13271.04 | 0 | 0 | 232,86,51,184 | 33177.6 | 46448.64 | WBS Description: This task involves ...
236 | 412 | 3.3.2.2 | Construct ID Planes 1 -50 at Hampton | 2007-04-18 08:00 | 2007-06-06 17:00 | No | Hampton | HU Tech[240%],HU Undergrad | 7 wks | 27552 | 11020.8 | 0 | 0 | 51,233,86 | 27552 | 38572.8 | WBS Description: This task involves ...
237 | 1374 | 3.3.2.3 | Construct ID Planes 51 -100 at W&M | 2007-06-08 08:00 | 2007-08-17 17:00 | No | W&M | W&M Tech[240%],W&M Undergrad | 10 wks | 46080 | 18432 | 0 | 0 | 235 | 46080 | 64512 | WBS Description: This task involves ...
238 | 1375 | 3.3.2.4 | Construct ID Planes 51 -100 at Hampton | 2007-06-07 08:00 | 2007-08-16 17:00 | No | Hampton | HU Tech[240%],HU Undergrad | 10 wks | 39360 | 15744 | 0 | 0 | 236 | 39360 | 55104 | WBS Description: This task involves ...
239 | 1377 | 3.3.2.5 | Construct ID Planes 101 -150 at W&M | 2007-12-19 08:00 | 2008-02-26 17:00 | No | W&M | W&M Tech[240%],W&M Undergrad | 9 wks | 46080 | 18432 | 0 | 0 | 237,195 | 46080 | 64512 | WBS Description: This task involves ...
240 | 1378 | 3.3.2.6 | Construct ID Planes 101 -150 at Hampton | 2007-12-19 08:00 | 2008-02-26 17:00 | No | Hampton | HU Tech[240%],HU Undergrad | 9 wks | 39360 | 15744 | 0 | 0 | 238,195 | 39360 | 55104 | WBS Description: This task involves ...
241 | 1379 | 3.3.2.7 | Construct ID Planes 151 -203 at W&M | 2008-02-27 08:00 | 2008-04-29 17:00 | No | W&M | W&M Tech[240%],W&M Undergrad | 9 wks | 41472 | 16588.8 | 0 | 0 | 239 | 41472 | 58060.8 | WBS Description: This task involves ...
242 | 1380 | 3.3.2.8 | Construct ID Planes 151 -203 at Hampton | 2008-02-27 08:00 | 2008-04-29 17:00 | No | Hampton | HU Tech[240%],HU Undergrad | 9 wks | 35424 | 14169.6 | 0 | 0 | 240 | 35424 | 49593.6 | WBS Description: This task involves ...
243 | 1385 | 3.3.2.9 | Inner Detector Plane Construction Complete | 2008-04-29 17:00 | 2008-04-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 241,242 | 0 | 0
244 | 258 | 3.3.3 | Outer Detector Tower Production | 2007-05-08 08:00 | 2008-04-24 17:00 | No |  |  | 48.6 wks | 150792 | 60316.8 | 0 | 0 |  | 150792 | 211108.8
245 | 415 | 3.3.3.1 | Construct OD Towers 1 -12 at W&M | 2007-07-12 08:00 | 2007-09-06 17:00 | No | W&M | W&M Tech,W&M Undergrad | 8.2 wks | 18040 | 7216 | 0 | 0 | 87,55,207 | 18040 | 25256 | WBS Description: This task involves ...
246 | 414 | 3.3.3.2 | Construct OD Towers 1 -12 at Hampton | 2007-05-08 08:00 | 2007-07-03 17:00 | No | Hampton | HU Tech,HU Undergrad | 8 wks | 15744 | 6297.6 | 0 | 0 | 55,218,207 | 15744 | 22041.6 | WBS Description: This task involves ...
247 | 1393 | 3.3.3.3 | Construct OD Towers 13 -50 at W&M | 2007-09-07 08:00 | 2007-11-16 17:00 | No | W&M | W&M Tech,W&M Undergrad | 10 wks | 22000 | 8800 | 0 | 0 | 245,218 | 22000 | 30800 | WBS Description: This task involves ...
248 | 1394 | 3.3.3.4 | Construct OD Towers 13 -50 at Hampton | 2007-07-04 08:00 | 2007-09-12 17:00 | No | Hampton | HU Tech,HU Undergrad | 9.8 wks | 19200 | 7680 | 0 | 0 | 246,218 | 19200 | 26880 | WBS Description: This task involves ...
249 | 1390 | 3.3.3.5 | Construct OD Towers 51 -112 at W&M | 2007-12-19 08:00 | 2008-04-24 17:00 | No | W&M | W&M Tech,W&M Undergrad | 17.4 wks | 40480 | 16192 | 0 | 0 | 247,229 | 40480 | 56672 | WBS Description: This task involves ...
250 | 1391 | 3.3.3.6 | Construct OD Towers 51 -112 at Hampton | 2007-12-19 08:00 | 2008-04-24 17:00 | No | Hampton | HU Tech,HU Undergrad | 17.4 wks | 35328 | 14131.2 | 0 | 0 | 248,229 | 35328 | 49459.2 | WBS Description: This task involves ...
251 | 1395 | 3.3.3.7 | Outer Detector Tower Construction Complete | 2008-04-24 17:00 | 2008-04-24 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 249,250 | 0 | 0
252 | 72 | 3.4 | Plane Shipping | 2006-03-08 08:00 | 2008-05-13 17:00 | No |  |  | 110.2 wks | 0 | 0 | 90742 | 36296.8 |  | 90742 | 127038.8
253 | 584 | 3.4.1 | Prototype Shipments | 2006-03-08 08:00 | 2006-04-18 17:00 | No |  |  | 6 wks | 0 | 0 | 8580 | 3432 |  | 8580 | 12012
254 | 473 | 3.4.1.1 | Purchase PT Shipping Box Materials | 2006-03-08 08:00 | 2006-03-21 17:00 | Yes | W&M | W&M MandS[714] | 2 wks | 0 | 0 | 714 | 285.6 | 99 | 714 | 999.6 | WBS Description: This task involves ...
255 | 474 | 3.4.1.2 | Build PT Shipping Box | 2006-03-22 08:00 | 2006-04-04 17:00 | Yes | W&M | W&M MandS[714] | 2 wks | 0 | 0 | 714 | 285.6 | 254 | 714 | 999.6 | WBS Description: This task involves ...
256 | 475 | 3.4.1.3 | Ship PT Boxes To Rochester?? | 2006-04-05 08:00 | 2006-04-18 17:00 | Yes | W&M | W&M MandS[7,152] | 2 wks | 0 | 0 | 7152 | 2860.8 | 255 | 7152 | 10012.8 | WBS Description: This task involves ...
257 | 585 | 3.4.2 | Inner Detector Plane Shipments | 2007-04-18 08:00 | 2008-05-13 17:00 | No |  |  | 54 wks | 0 | 0 | 46155 | 18462 |  | 46155 | 64617
258 | 418 | 3.4.2.1 | Purchase Shipping Box Materials | 2007-04-18 08:00 | 2007-04-24 17:00 | No | W&M | W&M MandS[8,785] | 1 wk | 0 | 0 | 8785 | 3514 | 235SS,236SS | 8785 | 12299 | WBS Description: This task involves ...
259 | 417 | 3.4.2.2 | Build Shipping Boxes for ID 1-20 | 2007-04-25 08:00 | 2007-05-15 17:00 | No | W&M | W&M MandS[5,074] | 3 wks | 0 | 0 | 5074 | 2029.6 | 258 | 5074 | 7103.6 | WBS Description: This task involves ...
260 | 1415 | 3.4.2.3 | Build Shipping Boxes for ID 21-50 | 2007-05-16 08:00 | 2007-06-13 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 259 | 5074 | 7103.6 | WBS Description: This task involves ...
261 | 1414 | 3.4.2.4 | Build Shipping Boxes for ID 51-100 | 2007-06-14 08:00 | 2007-07-12 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 260 | 5074 | 7103.6 | WBS Description: This task involves ...
262 | 1413 | 3.4.2.5 | Build Shipping Boxes for ID 101-150 | 2007-07-13 08:00 | 2007-08-09 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 261 | 5074 | 7103.6 | WBS Description: This task involves ...
263 | 1412 | 3.4.2.6 | Build Shipping Boxes for ID 151-203 | 2007-08-10 08:00 | 2007-09-06 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 262 | 5074 | 7103.6 | WBS Description: This task involves ...
264 | 416 | 3.4.2.7 | Ship ID Planes 1 - 50 to Fermilab | 2007-06-14 08:00 | 2007-06-27 17:00 | No | W&M | HU MandS[3,000] | 2 wks | 0 | 0 | 3000 | 1200 | 259,235,236,260 | 3000 | 4200 | WBS Description: This task involves ...
265 | 1388 | 3.4.2.8 | Ship ID Planes 51 - 100 to Fermilab | 2007-08-20 08:00 | 2007-08-31 17:00 | No | W&M | HU MandS[3,000] | 2 wks | 0 | 0 | 3000 | 1200 | 264,237,238,261 | 3000 | 4200 | WBS Description: This task involves ...
266 | 1387 | 3.4.2.9 | Ship ID Planes 101 - 150 to Fermilab | 2008-02-27 08:00 | 2008-03-11 17:00 | No | W&M | HU MandS[3,000] | 2 wks | 0 | 0 | 3000 | 1200 | 265,239,240,262 | 3000 | 4200 | WBS Description: This task involves ...
267 | 1386 | 3.4.2.10 | Ship ID Planes 150 - 203 to Fermilab | 2008-04-30 08:00 | 2008-05-13 17:00 | No | W&M | HU MandS[3,000] | 2 wks | 0 | 0 | 3000 | 1200 | 266,243,263 | 3000 | 4200 | WBS Description: This task involves ...
268 | 1398 | 3.4.2.11 | All Inner Detrector Planes Shipped To Fermilab | 2008-05-13 17:00 | 2008-05-13 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 267 | 0 | 0
269 | 1381 | 3.4.3 | Outer Detector Tower Shipments | 2007-07-12 08:00 | 2008-05-08 17:00 | No |  |  | 41.6 wks | 0 | 0 | 36007 | 14402.8 |  | 36007 | 50409.8
270 | 1382 | 3.4.3.1 | Purchase Shipping Box Materials | 2007-07-12 08:00 | 2007-07-18 17:00 | No | W&M | W&M MandS[8,785] | 1 wk | 0 | 0 | 8785 | 3514 | 245SS,246SS | 8785 | 12299 | WBS Description: This task involves ...
271 | 1383 | 3.4.3.2 | Build Shipping Box for OD 1-20 | 2007-07-19 08:00 | 2007-08-15 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 270 | 5074 | 7103.6 | WBS Description: This task involves ...
272 | 1417 | 3.4.3.3 | Build Shipping Box for OD 21-50 | 2007-09-07 08:00 | 2007-10-05 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 247SS | 5074 | 7103.6 | WBS Description: This task involves ...
273 | 1416 | 3.4.3.4 | Build Shipping Box for 51-112 | 2007-12-19 08:00 | 2008-01-22 17:00 | No | W&M | W&M MandS[5,074] | 4 wks | 0 | 0 | 5074 | 2029.6 | 249SS,250SS | 5074 | 7103.6 | WBS Description: This task involves ...
274 | 1384 | 3.4.3.5 | Ship OD Towers 1 - 50 to Fermilab | 2007-10-08 08:00 | 2007-10-19 17:00 | No | W&M | HU MandS[6,000] | 2 wks | 0 | 0 | 6000 | 2400 | 271,272 | 6000 | 8400 | WBS Description: This task involves ...
275 | 1397 | 3.4.3.6 | Ship OD Towers 51 - 112 to Fermilab | 2008-04-25 08:00 | 2008-05-08 17:00 | No | W&M | HU MandS[6,000] | 2 wks | 0 | 0 | 6000 | 2400 | 274,251,273 | 6000 | 8400 | WBS Description: This task involves ...
276 | 1399 | 3.4.3.7 | All Outer Detector Towers Shipped To Fermilab | 2008-05-08 17:00 | 2008-05-08 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 275 | 0 | 0

## wbs 4
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
277 | 8 | 4 | Clear Fiber Cables | 2005-06-01 08:00 | 2008-01-02 17:00 | No |  |  | 130 wks | 41774 | 0 | 704887 | 84070.1 |  | 746661 | 830731.1
278 | 192 | 4.1 | Clear Fiber R&D | 2005-06-01 08:00 | 2006-03-23 17:00 | No |  |  | 40.8 wks | 0 | 0 | 13585 | 4989 |  | 13585 | 18574
279 | 708 | 4.1.1 | Purchase Clear Fiber for R&D | 2005-06-01 08:00 | 2005-10-06 17:00 | Yes | Rochester | MandS[3,450] | 18 wks | 0 | 0 | 3450 | 1035 |  | 3450 | 4485 | WBS Description: Purchase clear fiber for R&D and prototyping work....
280 | 932 | 4.1.2 | Produce practice ODU's for Tufts | 2005-11-07 08:00 | 2005-12-22 17:00 | Yes | Rochester | MandS[250] | 6.4 wks | 0 | 0 | 250 | 0 |  | 250 | 250 | WBS Description: This task involves ...
281 | 146 | 4.1.3 | Setup Clear fiber QC bench | 2005-12-07 08:00 | 2006-01-06 17:00 | Yes | Rochester |  | 4 wks | 0 | 0 | 0 | 0 | 324 | 0 | 0 | WBS Description: This task covers the construction of the testing fixture required for the clear fiber testing. ...
282 | 195 | 4.1.4 | QC R&D Clear Fiber | 2006-02-24 08:00 | 2006-03-23 17:00 | Yes | Rochester | MandS[9,885] | 4 wks | 0 | 0 | 9885 | 3954 | 281,279,325 | 9885 | 13839 | WBS Description: This task addresses the quality control inspection of the Clear fibers. This will be done at Fermilab....
283 | 1418 | 4.1.5 | Qualified Clear Fiber | 2006-03-23 17:00 | 2006-03-23 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 282 | 0 | 0
284 | 790 | 4.2 | Prototype Clear Fiber | 2006-03-24 08:00 | 2006-06-23 17:00 | No |  |  | 13 wks | 0 | 0 | 17923 | 5217.3 |  | 17923 | 23140.3
285 | 789 | 4.2.1 | Submit Purchase Req - fiber for cable prototypes | 2006-03-24 08:00 | 2006-05-04 17:00 | Yes | Rochester |  | 6 wks | 0 | 0 | 0 | 0 | 299,283 | 0 | 0 | WBS Description: This task is for the submission of the purchase req for the cable prototype fibers. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
286 | 696 | 4.2.2 | Purchase clear fiber for cable prototypes | 2006-05-05 08:00 | 2006-06-16 17:00 | Yes | Rochester | MandS[17,391] | 6 wks | 0 | 0 | 17391 | 5217.3 | 285 | 17391 | 22608.3 | WBS Description: Cost of clear fiber purchase from Kuraray (Japan). ...
287 | 788 | 4.2.3 | QC prototype Clear Fibers | 2006-06-16 17:00 | 2006-06-23 17:00 | Yes | Rochester | Roch Tech[0%],Roch Physicist[15%],MandS[532] | 1 wk | 0 | 0 | 532 | 0 | 286 | 532 | 532 | WBS Description: This task addresses the quality control inspection of the Clear fibers. This will be done at Fermilab....
288 | 197 | 4.3 | Clear Fiber Bulk Procurement | 2006-11-13 08:00 | 2007-04-10 17:00 | No |  |  | 20.2 wks | 0 | 0 | 157776 | 45873.6 |  | 157776 | 203649.6
289 | 663 | 4.3.1 | Submit Purchase Req for bulk fiber | 2006-11-13 08:00 | 2006-12-28 12:00 | Yes | Rochester |  | 6 wks | 0 | 0 | 0 | 0 | 299,616FS-4 wks,283,303 | 0 | 0 | WBS Description: This task is for the submission of the purchase req for the bulk fiber order. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
290 | 263 | 4.3.2 | Clear Fiber Bulk Procurement | 2006-12-28 13:00 | 2007-03-12 17:00 | No | Rochester | MandS[152,912] | 10 wks | 0 | 0 | 152912 | 45873.6 | 289,281 | 152912 | 198785.6 | WBS Description: This task involves bulk purchase of ID and OD clear fibers....
291 | 737 | 4.3.3 | Polish cables for QC of production Clear fiber | 2007-03-13 08:00 | 2007-03-19 17:00 | Yes | Fermilab |  | 1 wk | 0 | 0 | 0 | 0 | 290 | 0 | 0 | WBS Description: This task involves ...
292 | 736 | 4.3.4 | QC production Clear fibers | 2007-03-19 17:00 | 2007-04-10 17:00 | No | Rochester | Roch Tech[0%],Roch Physicist[15%],MandS[4,864] | 3.2 wks | 0 | 0 | 4864 | 0 | 291,324 | 4864 | 4864 | WBS Description: This task addresses the quality control inspection of the Clear fibers. This will be done at Fermilab....
293 | 63 | 4.4 | Optical Connectors | 2005-09-15 08:00 | 2006-11-10 17:00 | No |  |  | 58.6 wks | 7920 | 0 | 93851 | 27240.2 |  | 101771 | 129011.2
294 | 791 | 4.4.1 | R&D Optical Connector | 2005-09-15 08:00 | 2006-01-26 17:00 | No |  |  | 18 wks | 5280 | 0 | 32500 | 9750 |  | 37780 | 47530
295 | 664 | 4.4.1.1 | Submit purchase req for R&D optical connector | 2005-09-15 08:00 | 2005-10-26 17:00 | Yes | Rochester |  | 6 wks | 0 | 0 | 0 | 0 | 613 | 0 | 0 | WBS Description: Submit purchase requisition to buy initial order of 200 connectors. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
296 | 145 | 4.4.1.2 | 400 R&D optical connector procurement | 2005-10-27 08:00 | 2005-12-27 12:00 | Yes | Rochester | MandS[32,500] | 8 wks | 0 | 0 | 32500 | 9750 | 295 | 32500 | 42250 | WBS Description: Purchase order from FNAL to buy initial order of 400 connectors....
297 | 1420 | 4.4.1.3 | Ship R&D optical connector to W&M | 2005-12-27 13:00 | 2006-01-11 17:00 | No |  |  | 2 wks | 0 | 0 | 0 | 0 | 296 | 0 | 0
298 | 144 | 4.4.1.4 | QC of optical connector | 2005-12-27 13:00 | 2006-01-26 17:00 | Yes | Fermilab | MTF | 4 wks | 5280 | 0 | 0 | 0 | 296,307,324 | 5280 | 5280 | WBS Description: Quality control check of intial connectors....
299 | 715 | 4.4.1.5 | Qualified Optical Connector | 2006-01-26 17:00 | 2006-01-26 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 298 | 0 | 0 | WBS Description: This milestone is for the ...
300 | 143 | 4.4.2 | Prototype and Production of Optical Connectors | 2006-01-27 08:00 | 2006-11-10 17:00 | No |  |  | 40.6 wks | 2640 | 0 | 61351 | 17490.2 |  | 63991 | 81481.2
301 | 614 | 4.4.2.1 | Purchase prototype cable optical connectors | 2006-01-27 08:00 | 2006-03-09 17:00 | Yes | Rochester | MandS[9,151] | 6 wks | 0 | 0 | 9151 | 1830.2 | 299 | 9151 | 10981.2 | WBS Description: Purchase a small number of connectors for R&D activities. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
302 | 265 | 4.4.2.2 | Procure production optical connectors | 2006-09-01 08:00 | 2006-10-27 17:00 | No | Rochester | MandS[52,200] | 8 wks | 0 | 0 | 52200 | 15660 | 299,616FS-4 wks,301 | 52200 | 67860 | WBS Description: Bulk purchase of the rest of the connectors needed for the project....
303 | 792 | 4.4.2.3 | QC of production connectors | 2006-10-30 08:00 | 2006-11-10 17:00 | No | Fermilab | MTF | 2 wks | 2640 | 0 | 0 | 0 | 302 | 2640 | 2640 | WBS Description: Quality control check of intial connectors....
304 | 10 | 4.5 | Cable Light-Tight Mold | 2005-06-01 08:00 | 2007-03-26 17:00 | No |  |  | 91.4 wks | 0 | 0 | 73684 | 0 |  | 73684 | 73684
305 | 62 | 4.5.1 | Design a single light tight mold | 2005-06-01 08:00 | 2005-08-10 17:00 | Yes | Rochester | Roch ME[0%],MandS[12,072] | 10 wks | 0 | 0 | 12072 | 0 | 613 | 12072 | 12072 | WBS Description: This task involves ...
306 | 666 | 4.5.2 | Fabricate R&D light tight mold | 2005-08-10 17:00 | 2005-08-24 17:00 | Yes | Rochester | MandS[3,500],Roch Tech[0%] | 2 wks | 0 | 0 | 3500 | 0 | 305 | 3500 | 3500 | WBS Description: This task involves ...
307 | 665 | 4.5.3 | Test R&D and redesign mold | 2005-08-24 17:00 | 2005-10-06 17:00 | Yes | Rochester | Roch ME[0%],MandS[3,168] | 6 wks | 0 | 0 | 3168 | 0 | 306 | 3168 | 3168 | WBS Description: This task involves ...
308 | 670 | 4.5.4 | Qualified Light-Tight Cable | 2005-10-06 17:00 | 2005-10-06 17:00 | Yes | Rochester |  | 0 wks | 0 | 0 | 0 | 0 | 307 | 0 | 0 | WBS Description: This task involves ...
309 | 61 | 4.5.5 | Produce production light tight molds | 2006-10-02 08:00 | 2007-03-26 17:00 | Yes | Rochester | Roch Machinist[0%],MandS[54,944] | 24 wks | 0 | 0 | 54944 | 0 | 308,616 | 54944 | 54944 | WBS Description: This task involves additional molds for production....
310 | 671 | 4.6 | Optical Connector Polishing R&D | 2005-07-11 08:00 | 2006-03-17 17:00 | No |  |  | 34.6 wks | 7238 | 0 | 13328 | 0 |  | 20566 | 20566
311 | 676 | 4.6.1 | Produce R&D pigtails for polish tests | 2005-12-22 17:00 | 2006-01-10 17:00 | Yes | Fermilab | Roch Lead Tech[0%],Dan Ruggiero[50%],MandS[2,288] | 2 wks | 0 | 0 | 2288 | 0 | 280 | 2288 | 2288 | WBS Description: This task involves ...
312 | 677 | 4.6.2 | Design connector polish holding fixture | 2005-07-11 08:00 | 2005-07-15 17:00 | Yes | Fermilab | MEF[50%] | 1 wk | 1420 | 0 | 0 | 0 |  | 1420 | 1420 | WBS Description: This task involves machining the polishing fixtures....
313 | 678 | 4.6.3 | Produce default connector polish holding fixture | 2005-07-25 08:00 | 2005-07-29 17:00 | Yes | Fermilab | MandS[3,900] | 1 wk | 0 | 0 | 3900 | 0 | 312 | 3900 | 3900 | WBS Description: This task involves testing the connector fixture....
314 | 672 | 4.6.4 | Produce MSU technique connector polish holding fixture | 2005-10-03 08:00 | 2005-10-07 17:00 | Yes | Fermilab | MEF[5%],MachinistF[10%],MandS[200],MTF Sr Lab7,Eileen Hahn | 1 wk | 2914 | 0 | 200 | 0 | 313,615 | 3114 | 3114 | WBS Description: This task involves understanding the transmission of polished connectors....
315 | 673 | 4.6.5 | Polish R&D Cables and Pigtails | 2006-01-11 17:00 | 2006-02-09 17:00 | Yes | Rochester | Roch Tech[0%],MandS[3,040] | 4 wks | 0 | 0 | 3040 | 0 | 313,311,314,323,340FF | 3040 | 3040 | WBS Description: This task involves understanding the transmissoin of polished connectors....
316 | 674 | 4.6.6 | Tests with R&D Cable and Pigtails | 2006-02-24 08:00 | 2006-03-10 17:00 | Yes | Fermilab | MTF | 2.2 wks | 2904 | 0 | 0 | 0 | 315,325 | 2904 | 2904 | WBS Description: Test the number of polishes that can be successfully achieved using the diamonds....
317 | 675 | 4.6.7 | Qualified ODU Fabrication Technique | 2006-03-10 17:00 | 2006-03-10 17:00 | Yes | Rochester |  | 0 wks | 0 | 0 | 0 | 0 | 316 | 0 | 0 | WBS Description: Test the number of polishes that can be successfully achieved using the diamonds....
318 | 679 | 4.6.8 | Produce second connector polish holding fixture | 2006-03-13 08:00 | 2006-03-17 17:00 | Yes | Rochester | MandS[3,900] | 1 wk | 0 | 0 | 3900 | 0 | 317 | 3900 | 3900 | WBS Description: This task involves ...
319 | 680 | 4.7 | Cable Tester and Optical Cable Mapper | 2005-10-03 08:00 | 2006-02-23 17:00 | No |  |  | 19.6 wks | 3544 | 0 | 27488 | 750 |  | 31032 | 31782
320 | 793 | 4.7.1 | Light Injector | 2005-10-03 08:00 | 2006-02-23 17:00 | No |  |  | 19.6 wks | 3200 | 0 | 6548 | 500 |  | 9748 | 10248
321 | 681 | 4.7.1.1 | Design Light Injector | 2005-10-03 08:00 | 2005-10-07 17:00 | Yes | Rochester | Roch Physicist | 1 wk | 0 | 0 | 0 | 0 | 615 | 0 | 0 | WBS Description: This task involves ...
322 | 683 | 4.7.1.2 | Purchase light injector parts | 2005-10-10 08:00 | 2005-11-18 17:00 | Yes | Rochester | MandS[2,500] | 6 wks | 0 | 0 | 2500 | 500 | 321 | 2500 | 3000 | WBS Description: This task covers purchase of the parts and materials needed for the light injector. ...
323 | 1419 | 4.7.1.3 | Produce Pigtails for cable testers | 2005-12-27 12:00 | 2006-01-11 17:00 | No |  | Roch Lead Tech[0%],Dan Ruggiero,MandS[4,048] | 2 wks | 0 | 0 | 4048 | 0 | 296,78,279 | 4048 | 4048 | WBS Description: This task covers ...
324 | 796 | 4.7.1.4 | Fabricate light injector parts (incl. electronics for readout box) | 2005-11-21 08:00 | 2005-12-06 17:00 | Yes | Fermilab | MTF Lab7[50%] | 2 wks | 1584 | 0 | 0 | 0 | 322 | 1584 | 1584 | WBS Description: This task involves ...
325 | 682 | 4.7.1.5 | Assemble Light Injector | 2006-02-10 08:00 | 2006-02-23 17:00 | Yes | Fermilab | ETF[10%],MTF[50%],Roch Physicist[20%] | 2 wks | 1616 | 0 | 0 | 0 | 324,323,315 | 1616 | 1616 | WBS Description: This task involves actual construction of the light injector....
326 | 1446 | 4.7.2 | Cable Tester readout | 2005-10-10 08:00 | 2005-12-20 17:00 | No |  |  | 10 wks | 0 | 0 | 16000 | 0 |  | 16000 | 16000
327 | 1447 | 4.7.2.1 | Design cable tester readout box | 2005-10-10 08:00 | 2005-10-21 17:00 | No |  | Roch Physicist | 2 wks | 0 | 0 | 0 | 0 | 321 | 0 | 0
328 | 1448 | 4.7.2.2 | Obtain and fabricate readout box parts | 2005-10-24 08:00 | 2005-11-04 17:00 | No |  |  | 2 wks | 0 | 0 | 0 | 0 | 327 | 0 | 0
329 | 1449 | 4.7.2.3 | Obtain readout electronics | 2005-10-24 08:00 | 2005-11-04 17:00 | No |  | MandS[16,000] | 2 wks | 0 | 0 | 16000 | 0 | 327 | 16000 | 16000
330 | 1450 | 4.7.2.4 | Assemble Readout Box | 2005-12-07 08:00 | 2005-12-20 17:00 | No |  |  | 2 wks | 0 | 0 | 0 | 0 | 324,328,329 | 0 | 0
331 | 794 | 4.7.3 | Optical Cable Mapper | 2005-10-03 08:00 | 2005-11-29 17:00 | No |  |  | 8 wks | 344 | 0 | 4940 | 250 |  | 5284 | 5534
332 | 687 | 4.7.3.1 | Design a Optical Cable Mapper (FNAL) | 2005-10-03 08:00 | 2005-10-14 17:00 | Yes | Rochester | DrafterF[10%] | 2 wks | 344 | 0 | 0 | 0 | 615 | 344 | 344 | WBS Description: This task involves ...
333 | 1451 | 4.7.3.2 | Design a Optical Cable Mapper (Rochester) | 2005-10-03 08:00 | 2005-10-14 17:00 | Yes | Rochester | Roch Physicist[10%],Roch ME[0%],MandS[1,320] | 2 wks | 0 | 0 | 1320 | 0 | 332SS | 1320 | 1320 | WBS Description: This task involves ...
334 | 688 | 4.7.3.3 | Machine parts for Optical Cable Mapper | 2005-10-14 17:00 | 2005-10-28 17:00 | Yes | Rochester | MandS[1,600],Roch Machinist[0%] | 2 wks | 0 | 0 | 1600 | 0 | 332,333 | 1600 | 1600 | WBS Description: This task involves ...
335 | 689 | 4.7.3.4 | Purchase parts for Optical Cable Mapper | 2005-10-31 08:00 | 2005-11-11 17:00 | Yes | Rochester | MandS[500] | 2 wks | 0 | 0 | 500 | 250 | 334 | 500 | 750 | WBS Description: This task involves ...
336 | 690 | 4.7.3.5 | Build Optical Cable Mapper | 2005-11-11 17:00 | 2005-11-29 17:00 | Yes | Rochester | Roch Tech[0%],MandS[1,520] | 2 wks | 0 | 0 | 1520 | 0 | 335 | 1520 | 1520 | WBS Description: This task involves ...
337 | 691 | 4.8 | Fabricate Cables and ODU's | 2005-11-07 08:00 | 2008-01-02 17:00 | No |  |  | 107.8 wks | 23072 | 0 | 307252 | 0 |  | 330324 | 330324
338 | 692 | 4.8.1 | Fabricate R&D Cables and ODUs | 2005-11-07 08:00 | 2006-03-03 17:00 | Yes | Rochester |  | 15.8 wks | 3008 | 0 | 12682 | 0 |  | 15690 | 15690 | WBS Description: This task covers the purchase of consumable materials and tooling for the ODU factory....
339 | 693 | 4.8.1.1 | Outfit Cable and ODU Factory | 2005-11-07 08:00 | 2005-11-29 17:00 | Yes | Rochester | MandS[3,440] | 3 wks | 0 | 0 | 3440 | 0 |  | 3440 | 3440 | WBS Description: This covers the cost of the consumable materials that are necessary for the ODU and some of the cable production....
340 | 694 | 4.8.1.2 | Fabicate ODUs and Cables for R&D | 2005-12-27 13:00 | 2006-01-20 17:00 | Yes | Rochester | MandS[9,242] | 3.2 wks | 0 | 0 | 9242 | 0 | 339,279,296 | 9242 | 9242 | WBS Description: This task involves ...
341 | 1290 | 4.8.1.3 | Ship subsample (24) ODUs to Tufts | 2006-02-10 08:00 | 2006-03-03 17:00 | Yes | Fermilab | MTF Lab7[25%],MTF Sr Lab7[25%] | 3.2 wks | 3008 | 0 | 0 | 0 | 340,315 | 3008 | 3008 | WBS Description: This task involves ...
342 | 711 | 4.8.2 | Fabricate Prototype Cables and ODUs | 2006-06-23 17:00 | 2006-12-07 17:00 | Yes | Rochester |  | 23 wks | 18048 | 0 | 69920 | 0 |  | 87968 | 87968 | WBS Description: This task involves ...
343 | 856 | 4.8.2.1 | Fabricate Prototype ODUs and Cables | 2006-06-23 17:00 | 2006-10-31 17:00 | Yes | Fermilab | Roch Tech[0%],MandS[69,920] | 18 wks | 0 | 0 | 69920 | 0 | 287,317,615,330,336 | 69920 | 69920 | WBS Description: This task involves ...
344 | 695 | 4.8.2.2 | Polish Prototype ODUs and Cables | 2006-07-11 08:00 | 2006-11-21 17:00 | No | Rochester | MTF Lab7[25%],MTF Sr Lab7[25%] | 19 wks | 18048 | 0 | 0 | 0 | 343SS+2 wks | 18048 | 18048 | WBS Description: This task involves moving to full production capacity....
345 | 730 | 4.8.2.3 | Ship Prototype ODUs to Tufts | 2006-11-22 08:00 | 2006-12-07 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 344 | 0 | 0 | WBS Description: This task involves ...
346 | 857 | 4.8.2.4 | Light-Tight Prototype Cables | 2006-11-22 08:00 | 2006-12-07 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 344,343 | 0 | 0 | WBS Description: This task involves ...
347 | 858 | 4.8.2.5 | Prototype ODUs and Cables Complete | 2006-12-07 17:00 | 2006-12-07 17:00 | No | Fermilab |  | 0 wks | 0 | 0 | 0 | 0 | 346 | 0 | 0 | WBS Description: This task involves ...
348 | 184 | 4.8.3 | Fabrication Production Cables and ODUs | 2007-04-11 08:00 | 2007-11-13 17:00 | No |  |  | 30.4 wks | 2016 | 0 | 224450 | 0 |  | 226466 | 226466
349 | 185 | 4.8.3.1 | Fabricate Production ODUs | 2007-04-11 08:00 | 2007-08-16 17:00 | No |  | MandS[68,840] | 18 wks | 0 | 0 | 68840 | 0 | 292,303,347,318 | 68840 | 68840 | WBS Description: This task is defined to be first 20% of cable production...
350 | 303 | 4.8.3.2 | Polish Production ODUs | 2007-04-25 08:00 | 2007-05-22 17:00 | Yes | Rochester | MandS[4,128] | 4 wks | 0 | 0 | 4128 | 0 | 349SS+2 wks | 4128 | 4128 | WBS Description: This task involves ...
351 | 713 | 4.8.3.3 | Ship production ODU's to Tufts | 2007-08-17 08:00 | 2007-09-03 17:00 | Yes | Rochester | Roch Tech[50%] | 2.4 wks | 2016 | 0 | 0 | 0 | 350,349 | 2016 | 2016 | This will produce a small number of cables.
352 | 304 | 4.8.3.4 | Ship production ODU's to Rutgers | 2007-05-23 08:00 | 2007-06-06 17:00 | No | Rochester | MandS[51,000] | 2 wks | 0 | 0 | 51000 | 0 | 350 | 51000 | 51000 | WBS Description: This covers the cost of the consumable materials that are necessary for the ODU and some of the cable production. (i.e. epoxies, glues, syringes, etc.)...
353 | 890 | 4.8.3.5 | ODU shipments complete | 2007-09-03 17:00 | 2007-09-03 17:00 | No | Rochester |  | 0 wks | 0 | 0 | 0 | 0 | 351,352 | 0 | 0
354 | 714 | 4.8.3.6 | Fabricate Production Cables | 2007-09-03 17:00 | 2007-10-16 17:00 | No |  | MandS[41,222],Roch Tech[0%] | 6 wks | 0 | 0 | 41222 | 0 | 292,303,347,353 | 41222 | 41222 | WBS Description: This section covers the work to bring the cable factory up to full production status....
355 | 731 | 4.8.3.7 | Polish Production Cables | 2007-09-18 17:00 | 2007-10-16 17:00 | No | Rochester | Roch Tech[0%],MandS[18,240] | 4 wks | 0 | 0 | 18240 | 0 | 354SS+2 wks | 18240 | 18240 | WBS Description: This task involves ...
356 | 733 | 4.8.3.8 | Light-Tight Production Cables | 2007-10-17 08:00 | 2007-11-13 17:00 | No | Fermilab | MandS[41,020] | 4 wks | 0 | 0 | 41020 | 0 | 355,309 | 41020 | 41020 | WBS Description: This task involves ...
357 | 892 | 4.8.3.9 | Cable production complete | 2007-11-13 17:00 | 2007-11-13 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 356,354 | 0 | 0 | WBS Description: This task involves ...
358 | 891 | 4.8.4 | Cable storage | 2007-11-14 08:00 | 2008-01-02 17:00 | No |  |  | 6 wks | 0 | 0 | 200 | 0 |  | 200 | 200
359 | 893 | 4.8.4.1 | Construct storage containers for cables | 2007-11-14 08:00 | 2007-12-13 17:00 | No | Rochester | MandS[200] | 4 wks | 0 | 0 | 200 | 0 | 357 | 200 | 200 | WBS Description: This task involves ...
360 | 894 | 4.8.4.2 | Cable containers stored until ready for use | 2007-12-14 08:00 | 2008-01-02 17:00 | No | Rochester |  | 2 wks | 0 | 0 | 0 | 0 | 359 | 0 | 0 | WBS Description: This task involves ...

## wbs 5
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
361 | 152 | 5 | PMT Boxes | 2005-07-28 08:00 | 2008-10-17 17:00 | No |  |  | 162.6 wks | 0 | 0 | 885549 | 366284.21 |  | 885549 | 1251833.21
362 | 13 | 5.1 | PMT Box Prototyping | 2005-07-28 08:00 | 2006-12-28 12:00 | No |  |  | 71.4 wks | 0 | 0 | 82720 | 19979 |  | 82720 | 102699
363 | 288 | 5.1.1 | Set up prototyping box factory shop at Tufts (FY05) | 2005-07-28 08:00 | 2005-09-30 17:00 | Yes | Tufts |  | 9.2 wks | 0 | 0 | 0 | 0 | 624FS-14 wks | 0 | 0 | WBS Description: Tufts will purchase tooling required to construct the prototypes. This task involves the work of technicians and a machinist are required to assist facultly researchers with the design and implement the four fabrication workstations ...
364 | 1310 | 5.1.2 | Set up prototyping box factory shop at Tufts (FY06) | 2005-10-03 08:00 | 2006-01-30 17:00 | No | Tufts | MandS[14,000] | 16 wks | 0 | 0 | 14000 | 3360 | 363 | 14000 | 17360 | WBS Description: Tufts will purchase tooling required to construct the prototypes. This task involves the work of facultly researchers to design and implement the four fabrication workstations which are required at each of the box factories at Tufts ...
365 | 716 | 5.1.3 | Tufts produces 100 alignment holders | 2006-01-31 08:00 | 2006-02-27 17:00 | Yes | Tufts | MandS[2,500] | 4 wks | 0 | 0 | 2500 | 500 | 83,364 | 2500 | 3000 | WBS Description: This is to produce the initial 100 alignment holders for JMU....
366 | 897 | 5.1.4 | Ship 100 alignment holders to JMU | 2006-02-14 08:00 | 2006-02-20 17:00 | Yes | Tufts | MandS[200] | 1 wk | 0 | 0 | 200 | 40 | 365FS-2 wks | 200 | 240 | WBS Description: This task involves shipment of the first 100 holders to JMU....
367 | 900 | 5.1.5 | Prepare fiber loaded cookies for JMU and Athens | 2006-03-28 08:00 | 2006-05-08 17:00 | Yes | Tufts | Tufts-Physicist[50%],Tufts-Assmbly Techs,MandS[7,920] | 6 wks | 0 | 0 | 7920 | 1584 | 393,280 | 7920 | 9504 | WBS Description: Receive ODU's from Fermi, cut ODU's, weave the fibre ends into the cookie, epoxy the fibers into the cookie and flycut the cookie. (6 cookies)...
368 | 901 | 5.1.6 | Ship fiber loaded cookies to JMU and Athens | 2006-05-09 08:00 | 2006-05-30 17:00 | Yes | Tufts | MandS[600] | 3 wks | 0 | 0 | 600 | 120 | 367 | 600 | 720 | WBS Description: This task covers shipment of fiber loaded cookies to JMU and Athens as needed....
369 | 902 | 5.1.7 | Set up Rutgers workstations - Part 1 | 2005-11-30 08:00 | 2006-05-01 17:00 | Yes | Rutgers | MandS[13,000] | 21 wks | 0 | 0 | 13000 | 3250 | 364SS+8 wks | 13000 | 16250 | WBS Description: This task involves ...
370 | 1294 | 5.1.8 | Set up Rutgers workstations - Part 2 | 2006-10-02 08:00 | 2006-12-28 12:00 | Yes | Rutgers | MandS[44,500] | 12 wks | 0 | 0 | 44500 | 11125 | 616,369,394SS | 44500 | 55625 | WBS Description: This task involves ...
371 | 290 | 5.2 | PMT Box Construction | 2006-05-31 08:00 | 2008-09-19 17:00 | No |  |  | 116.4 wks | 0 | 0 | 572229 | 184925.21 |  | 572229 | 757154.21 | WBS Description: This sub-section applies to the assembly of PMT boxes at Tufts and Rutgers....
372 | 615 | 5.2.1 | Produce rest of alignment holders | 2006-10-02 08:00 | 2007-02-19 17:00 | Yes | Tufts | Tufts-Machinist[50%],MandS[13,332] | 19 wks | 0 | 0 | 13332 | 3333 | 365,616 | 13332 | 16665 | WBS Description: This task involves ...
373 | 904 | 5.2.2 | Continue cookie production | 2007-02-20 08:00 | 2008-02-18 17:00 | No | Tufts | MandS[7,432],Tufts-Machinist[5%] | 50 wks | 0 | 0 | 7432 | 2452.56 | 367,372 | 7432 | 9884.56 | WBS Description: This task involves the completion of the cookie production. ...
374 | 712 | 5.2.3 | Exercise PMT Box Factory at Tufts | 2006-05-31 08:00 | 2006-10-19 17:00 | Yes | Tufts | MandS[10,000] | 20 wks | 0 | 0 | 10000 | 2500 | 368 | 10000 | 12500 | WBS Description: This task involves the initial test cycle for the box factory workstations....
375 | 14 | 5.2.4 | Manufacture first 10% of PMT boxes at Tufts | 2006-10-20 08:00 | 2007-03-21 17:00 | No | Tufts | MandS[39,984],Tufts-Assmbly Techs[85%],Tufts-Machinist[15%] | 20.6 wks | 0 | 0 | 39984 | 9996 | 616,374,364,425FS-3 wks | 39984 | 49980 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
376 | 1405 | 5.2.5 | Manufacture first 10% of PMT boxes at Rutgers | 2006-10-20 08:00 | 2007-03-21 17:00 | No | Rutgers | Rutgers-Tech[115%],Rutgers-Machinist[15%],MandS[48,379] | 20.6 wks | 0 | 0 | 48379 | 16932.65 | 375SS,426FS-3 wks | 48379 | 65311.65 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
377 | 1404 | 5.2.6 | Manufacture 11% to 50% of PMT boxes at Tufts | 2007-03-22 08:00 | 2008-01-17 17:00 | No | Tufts | Tufts-Assmbly Techs[85%],Tufts-Machinist[15%],MandS[104,500] | 41.4 wks | 0 | 0 | 104500 | 28215 | 375,427FS-3 wks | 104500 | 132715 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
378 | 360 | 5.2.7 | Manufacture 11% to 50% of PMT boxes at Rutgers | 2007-03-22 08:00 | 2008-01-17 17:00 | No | Rutgers | Rutgers-Tech[115%],Rutgers-Machinist[15%],MandS[121,445] | 41.4 wks | 0 | 0 | 121445 | 42505.75 | 370,376,428FS-4 wks,346 | 121445 | 163950.75 | WBS Description: This task is for the assembly of PMT boxes at Rutgers....
379 | 1407 | 5.2.8 | Manufacture 51% to 100% of PMT boxes at Tufts | 2008-01-30 08:00 | 2008-09-19 17:00 | No | Tufts | Tufts-Assmbly Techs[85%],Tufts-Machinist[15%],MandS[104,352] | 33 wks | 0 | 0 | 104352 | 36523.2 | 377,431 | 104352 | 140875.2 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
380 | 1406 | 5.2.9 | Manufacture 51% to 100% of PMT boxes at Rutgers | 2008-01-30 08:00 | 2008-09-19 17:00 | No | Rutgers | Rutgers-Tech[115%],Rutgers-Machinist[15%],MandS[117,658] | 33 wks | 0 | 0 | 117658 | 41180.3 | 378,431 | 117658 | 158838.3 | WBS Description: This task is for the assembly of PMT boxes at Rutgers....
381 | 15 | 5.2.10 | Install ODUs into Cookie | 2007-03-13 08:00 | 2008-04-07 17:00 | No | Tufts | MandS[5,147],Tufts-Assmbly Techs[7%] | 54 wks | 0 | 0 | 5147 | 1286.75 | 373SS+3 wks | 5147 | 6433.75 | WBS Description: This task involves fiber cookie loading...
382 | 77 | 5.3 | PMT Box Frame Construction (FY07) | 2006-10-02 08:00 | 2006-12-28 12:00 | No | Rochester | MandS[5,000] | 12 wks | 0 | 0 | 5000 | 2000 | 616,573,364 | 5000 | 7000 | WBS Description: This task involves construction of lattice-work mounting frames, totaling 42 sectioned pieces. Pieces include steel framework, aluminum standoff pieces, hinges, assorted joint pieces, nuts, bolts, screws and will be made at Rochest...
383 | 1408 | 5.4 | PMT Box Frame Construction (FY08) | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Rochester | MandS[5,000] | 12 wks | 0 | 0 | 5000 | 2000 | 617,382 | 5000 | 7000 | WBS Description: This task involves construction of lattice-work mounting frames, totaling 42 sectioned pieces. Pieces include steel framework, aluminum standoff pieces, hinges, assorted joint pieces, nuts, bolts, screws and will be made at Rochest...
384 | 1292 | 5.5 | Ship PMT frame to Fermilab | 2007-12-28 08:00 | 2008-01-29 17:00 | No | Rochester | MandS[1,000] | 4 wks | 0 | 0 | 1000 | 0 | 383 | 1000 | 1000
385 | 914 | 5.6 | Ship Completed PMT Boxes | 2007-03-22 08:00 | 2008-10-17 17:00 | No |  |  | 79.8 wks | 0 | 0 | 24600 | 7380 |  | 24600 | 31980
386 | 915 | 5.6.1 | Ship first 10% of PMT boxes from Tufts to Fermi | 2007-03-22 08:00 | 2007-04-18 17:00 | Yes | Tufts | MandS[1,600] | 4 wks | 0 | 0 | 1600 | 480 | 375 | 1600 | 2080 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
387 | 916 | 5.6.2 | Ship first 10% of PMT boxes from Rutgers to Fermi | 2007-03-22 08:00 | 2007-04-18 17:00 | Yes | Rutgers | MandS[1,600] | 4 wks | 0 | 0 | 1600 | 480 | 376 | 1600 | 2080 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
388 | 917 | 5.6.3 | Ship first bulk PMT boxes from Tufts to Fermi | 2008-01-18 08:00 | 2008-02-15 17:00 | No | Tufts | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 386,377 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
389 | 918 | 5.6.4 | Ship first bulk PMT boxes from Rutgers to Fermi | 2008-01-18 08:00 | 2008-02-15 17:00 | No | Rutgers | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 387,378 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
390 | 919 | 5.6.5 | Ship last bulk PMT boxes from Tufts to Fermi | 2008-09-22 08:00 | 2008-10-17 17:00 | No | Tufts | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 388,379 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
391 | 920 | 5.6.6 | Ship last bulk PMT boxes from Rutgers to Fermi | 2008-09-22 08:00 | 2008-10-17 17:00 | No | Rutgers | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 389,380 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
392 | 921 | 5.6.7 | All PMT Boxes Shipped to Fermilab | 2008-10-17 17:00 | 2008-10-17 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 390,391,381,373 | 0 | 0 | WBS Description: This milestone is for the ...
393 | 969 | 5.7 | Light Injection R&D | 2006-01-31 08:00 | 2006-03-27 17:00 | Yes | Fermilab | MandS[32,000] | 8 wks | 0 | 0 | 32000 | 0 | 364 | 32000 | 32000 | WBS Description: This task involves developing and building the Light Injection system necessary for testing PMT's....
394 | 1295 | 5.8 | Light Injection R&D | 2006-10-02 08:00 | 2006-11-28 17:00 | Yes | Fermilab | MandS[13,000] | 8 wks | 0 | 0 | 13000 | 0 | 616 | 13000 | 13000 | WBS Description: This task involves developing and building the Light Injection system necessary for testing PMT's....
395 | 1421 | 5.9 | Light injection system | 2006-11-29 08:00 | 2007-11-26 17:00 | No | Fermilab | MandS[150,000] | 50 wks | 0 | 0 | 150000 | 150000 | 394 | 150000 | 300000

## wbs 6
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
396 | 153 | 6 | PMT Procurement and Testing | 2005-06-01 08:00 | 2008-01-29 17:00 | No |  |  | 133.6 wks | 83912 | 24673 | 961359 | 311091.13 |  | 1045271 | 1380035.13
397 | 294 | 6.1 | PMT R&D, Alignment Station, and Test Stand | 2005-08-01 08:00 | 2006-06-27 17:00 | No |  |  | 45.8 wks | 2000 | 500 | 77364 | 23969.28 |  | 79364 | 103833.28
398 | 1285 | 6.1.1 | Purchase 5 photomultiplier tubes | 2005-08-01 08:00 | 2005-09-12 17:00 | Yes | Fermilab |  | 6 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This is for the initial purchase of phototubes from Hammamatsu....
399 | 1286 | 6.1.2 | Purchase 5 photomultiplier tubes | 2005-10-03 08:00 | 2005-12-13 17:00 | Yes | Fermilab | MandS[20,000] | 10 wks | 0 | 0 | 20000 | 6000 | 398 | 20000 | 26000 | WBS Description: This is for the initial purchase of phototubes from Hammamatsu....
400 | 859 | 6.1.3 | Purchase alignment station materials (JMU) | 2005-10-03 08:00 | 2005-12-02 17:00 | Yes | JMU | MandS[8,500] | 9 wks | 0 | 0 | 8500 | 2040 | 615,399 | 8500 | 10540 | WBS Description: Purchase of alignment stand materials for use at JMU.
401 | 296 | 6.1.4 | Purchase test stand materials (JMU) | 2005-10-03 08:00 | 2006-05-26 17:00 | Yes | JMU | MandS[23,208] | 34 wks | 0 | 0 | 23208 | 7658.64 | 400 | 23208 | 30866.64 | WBS Description: Purchase of the test stand materials at JMU
402 | 870 | 6.1.5 | Purchase test stand materials (Athens) | 2006-02-28 08:00 | 2006-06-27 17:00 | Yes | Athens | MandS[23,208] | 17 wks | 0 | 0 | 23208 | 7658.64 | 400 | 23208 | 30866.64 | WBS Description: Purchase of the test stand materials at Athens
403 | 56 | 6.1.6 | Assemble alignment stand and test stand (JMU) | 2005-10-30 08:00 | 2006-05-26 17:00 | Yes | JMU | 2 JMU-Undergrad[50%] | 34 wks | 2000 | 500 | 0 | 0 | 401SS | 2000 | 2500 | WBS Description: Building the alignment and test stands at JMU
404 | 871 | 6.1.7 | Assemble test stand (Athens) | 2006-02-28 08:00 | 2006-06-27 17:00 | Yes | Athens | Athens Student[40%],MandS[2,448] | 17 wks | 0 | 0 | 2448 | 612 | 402SS | 2448 | 3060 | WBS Description: Building the test stand at Athens
405 | 298 | 6.2 | Encapsulate, Align, and Test Initial PMT's | 2006-05-29 08:00 | 2006-10-06 17:00 | no |  |  | 18 wks | 8000 | 2000 | 21000 | 4620 |  | 29000 | 35620
|  | 6.2.1 | Purchase initial alignment materials (JMU) | 2006-05-29 | 2006-07-14 | yes | JMU | MandS[5000] | 7 wks | 0 | 0 | 5000 | 1100 |  | 5000 | 6100 | WBS Description: Purchase initial alignment materials (JMU)
406 | 297 | 6.2.2 | Purchase initial testing materials (JMU) | 2006-07-17 08:00 | 2006-10-06 17:00 | Yes | JMU | MandS[8000] | 18 wks | 0 | 0 | 8000 | 1760 | 403,366 | 8000 | 9760 | WBS Description: Purchase initial testing materials (JMU)
407 | 874 | 6.2.3 | Purchase initial testing materials (Athens) | 2006-06-28 08:00 | 2006-10-05 17:00 | Yes | Athens | MandS[8,000] | 14 wks | 0 | 0 | 8000 | 1760 | 404,402 | 8000 | 9760 | WBS Description: Purchase initial testing materials (Athens)
408 | 905 | 6.2.3 | Pittsburg puts a PC board onto PMT's first? | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone is for the ...
409 | 181 | 6.2.4 | Conduct initial PMT alignment (JMU) | 2006-05-29 08:00 | 2006-07-14 17:00 | Yes | JMU | 2 JMU-Undergrad[40%] | 7 wks | 3200 | 800 | 0 | 0 | 406SS,368,400,401 | 3200 | 4000 | WBS Description: Align the first 10 PMTs and send 5 to Athens for testing
410 | 860 | 6.2.5 | Conduct initial PMT testing (JMU) | 2006-07-17 08:00 | 2006-10-06 17:00 | Yes | JMU | 2 JMU-Undergrad[60%] | 11 wks | 4800 | 1200 | 0 | 0 | 409,482,406SS | 4800 | 6000 | WBS Description: Test 5 PMTs to specify their characteristics and to test the test stand (JMU)
|  | 6.2.6 | Conduct initial PMT testing (Athens) | 2006-07-17 08:00 | 2006-10-06 17:00 | yes | Athens |  | 11 wks | [7 empty] | WBS Description: Test 5 PMTs to specify their characteristics and to test the test stand (Athens)
411 | 182 | 6.3 | Bulk PMT Procurement and Testing | 2006-10-09 08:00 | 2008-01-29 17:00 | No |  |  | 65.2 wks | 73912 | 22173 | 845875 | 280789.85 |  | 919787 | 1222749.85
412 | 204 | 6.3.1 | Deliver 360 PMTs from manufacturer (40 PMts per month) | 2007-01-09 08:00 | 2007-10-09 17:00 | No | Fermilab | MandS[517,737] | 9 months | 0 | 0 | 517737 | 170853.21 | 616 | 517737 | 688590.21 | WBS Description: This is for the purchase of 360 phototubes from Hammamatsu....
413 | 862 | 6.3.2 | Align first bulk purchase PMTs (JMU) | 2007-01-09 08:00 | 2007-11-09 17:00 | No | JMU | JMU Undergrad,JMU-Tech | 10 months | 12382 | 3580 | 0 | 0 | 412SS+4 wks,406 | 12382 | 15962 | WBS Description: Align 360 PMTs
414 | 875 | 6.3.3 | Align first bulk purchase PMTs (Athens) | 2006-10-30 08:00 | 2007-10-04 17:00 | No | Athens | Athens Student[90%],MandS[15,811] | 47 wks | 0 | 0 | 0 | 0 | 412SS+4 wks,407 | 0 | 0 | WBS Description: This task involves ...
415 | 861 | 6.3.4 | Test first bulk purchase PMTs (JMU) | 2007-01-09 08:00 | 2007-11-09 17:00 | No | JMU | JMU-Undergrad,JMU-Tech | 10 months | 37528 | 11320 | 0 | 0 | 413SS | 37528 | 48848 | WBS Description: Test 180 PMTs (JMU)
416 | 876 | 6.3.5 | Test first bulk purchase PMTs (Athens) | 2006-10-30 08:00 | 2007-10-04 17:00 | No | Athens | Athens Student[385%],MandS[67,637] | 47 wks | 0 | 0 | 67637 | 23672.95 | 414SS | 67637 | 91309.95 | WBS Description: Test 180 PMTs (Athens)
417 | 1411 | 6.3.6 | 360 PMT Tests Complete | 2007-11-09 17:00 | 2007-11-09 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 412,413,414,415,416 | 0 | 0 | This milestone is for the completion of tests for 360 PMTs
418 | 205 | 6.3.7 | Deliver 171 PMTs from manufacturer | 2007-11-12 08:00 | 2008-03-12 17:00 | No | Fermilab | MandS[245,583] | 5 months | 0 | 0 | 245583 | 81042.39 | 617 | 245583 | 326625.39 | WBS Description: This is for the delivery of 171 phototubes from Hammamatsu....
419 | 863 | 6.3.8 | Align final bulk purchase PMTs (JMU) | 2007-11-12 08:00 | 2008-05-05 | No | JMU | JMU-Undergrad,JMU-Tech | 5.25 months | 5400 | 1605 | 0 | 0 | 418SS+4 wks | 5400 | 7005 | WBS Description: Align 171 PMTs
420 | 877 | 6.3.9 | Align final bulk purchase PMTs (Athens) | 2007-10-29 08:00 | 2008-01-14 17:00 | No | Athens | Athens Student,MandS[4,032] | 10 wks | 0 | 0 | 0 | 0 | 418SS+4 wks | 0 | 0 | WBS Description: This task involves ...
421 | 864 | 6.3.10 | Test final bulk purchase PMTs (JMU) | 2007-11-12 08:00 | 2008-05-05 | No | JMU | JMU-Undergrad,JMU-Tech | 5.25 months | 18602 | 5668 | 0 | 0 | 419SS,417 | 18602 | 24270 | WBS Description: Test 85 PMTs (JMU)
422 | 878 | 6.3.11 | Test final bulk purchase PMTs (Athens) | 2007-10-29 08:00 | 2008-01-14 17:00 | No | Athens | Athens Student[370%],MandS[14,918] | 10 wks | 0 | 0 | 14918 | 5221.3 | 420SS | 14918 | 20139.3 | WBS Description: Test 86 PMTs (Athens)
423 | 1410 | 6.3.12 | All PMT Tests Complete | 2008-05-05 | 2008-05-05 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 418,419,420,421,422 | 0 | 0
424 | 924 | 6.4 | Ship Completed PMT's | 2006-07-27 08:00 | 2008-05-05 | No |  |  | 75.4 wks | 0 | 0 | 17120 | 1712 |  | 17120 | 17832
425 | 925 | 6.4.1 | Ship first 10% of PMT's from JMU to Tufts | 2006-07-27 08:00 | 2006-08-09 17:00 | Yes | JMU |  | 2 wks | 0 | 0 | 0 | 0 | 410 | 0 | 0 | WBS Description: This task involves ...
426 | 926 | 6.4.2 | Ship first 10% of PMT's from Athens to Rutgers | 2006-07-27 08:00 | 2006-08-23 17:00 | Yes | Athens |  | 4 wks | 0 | 0 | 0 | 0 | 425SS | 0 | 0 | WBS Description: This task involves ...
|  | 6.4.1 | Ship aligned PMTs from JMU to Athens (first 180) | 2007-01-09 | 2007-11-09 | no | JMU |  | 43.5 wks |  |  | 8190 | 819 |  | 8190 | 9009 | This task involves shipping 180 aligned PMTs from JMU to Athens for testing (20 PMTs per month)
|  | 6.4.2 | Ship aligned PMTs from JMU to Athens (last 86) | 2007-11-12 | 2008-05-05 | no | JMU |  | 24 wks |  |  | 3640 | 364 |  | 3640 | 4004 | This task involves shipping 86 aligned PMTs from JMU to Athens for testing (20 PMTs per month)
427 | 927 | 6.4.3 | Ship first bulk PMT's from JMU to Tufts | 2006-11-29 08:00 | 2006-12-28 12:00 | No | JMU |  | 4 wks | 0 | 0 | 500 | 50 | 425,415SS+4 wks | 500 | 50 | WBS Description: This task involves shipping 180 aligned and tested PMTs from JMU to Tufts
428 | 928 | 6.4.4 | Ship first bulk PMT's from Athens to Rutgers | 2006-11-29 08:00 | 2006-12-28 12:00 | No | Athens |  | 4 wks | 0 | 0 | 2860 | 286 | 426,414SS+4 wks | 2860 | 3146 | WBS Description: This task involves shipping 180 aligned and tested PMTs from Athens to Rutgers
429 | 929 | 6.4.5 | Ship last bulk PMT's from JMU to Tufts | 2008-05-05 | 2008-06-02 | No | JMU |  | 4 wks | 0 | 0 | 500 | 50 | 427,421SS+4 wks | 500 | 50 | WBS Description: This task involves shipping 85 aligned and tested PMTs from JMU to Tufts
430 | 930 | 6.4.6 | Ship last bulk PMT's from Athens to Rutgers | 2007-11-28 08:00 | 2007-12-27 17:00 | No | Athens |  | 4 wks | 0 | 0 | 1430 | 143 | 428,422SS+4 wks | 1430 | 1573 | WBS Description: This task involves shipping 86 aligned and tested PMTs from Athens to Rutgers
431 | 931 | 6.4.7 | All PMT's Shipped | 2008-06-02 | 2008-06-02 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 429,430,423 | 0 | 0 | WBS Description: This milestone is for completion of all PMT tests
508 | 800 | 8 | Frame, Absorbers and Stand | 2005-06-01 08:00 | 2008-06-11 17:00 | No |  |  | 152.6 wks | 209072 | 104360 | 624254 | 155636 |  | 833326 | 1093322
509 | 801 | 8.1 | Design | 2005-06-01 08:00 | 2006-08-02 17:00 | No |  |  | 59.2 wks | 172488 | 86068 | 31680 | 15840 |  | 204168 | 306076
510 | 802 | 8.1.1 | Design OD Frame (FY05) | 2005-06-01 08:00 | 2005-09-30 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%] | 17.2 wks | 352 | 0 | 0 | 0 |  | 352 | 352 | WBS Description: This task covers the design of the OD frame....
511 | 1293 | 8.1.2 | Design OD Frame (FY06) | 2005-10-03 08:00 | 2005-11-18 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%],MandS[9,240] | 7 wks | 0 | 0 | 9240 | 4620 | 510,615 | 9240 | 13860 | WBS Description: This task involves ...
512 | 803 | 8.1.3 | Design absorbers (FNAL) | 2005-10-17 08:00 | 2005-11-04 17:00 | Yes | Fermilab | DrafterF | 3 wks | 5160 | 2580 | 0 | 0 |  | 5160 | 7740 | WBS Description: Documentation of the design and engineering analysis of the absorber....
513 | 1422 | 8.1.4 | Design absorbers (Roch) | 2005-10-17 08:00 | 2005-11-04 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight,MandS[7,920] | 3 wks | 0 | 0 | 7920 | 3960 | 512SS | 7920 | 11880 | WBS Description: Design and engineering analysis of the absorber....
514 | 804 | 8.1.5 | Design Detector Stand and Bookend | 2005-10-17 08:00 | 2005-10-28 17:00 | Yes | Fermilab | MEF,DrafterF | 2 wks | 9120 | 4560 | 0 | 0 |  | 9120 | 13680 | WBS Description: This task involves final design of the detector stand. A first pass of the stand has been designed and analyzed for stresses. This short period of time will be needed to only adjust the design for the final location in the cavern....
515 | 1296 | 8.1.6 | Design Axial Bolts | 2005-10-31 08:00 | 2005-11-11 17:00 | Yes | Fermilab | MEF[20%],DrafterF[50%] | 2 wks | 2856 | 1428 | 0 | 0 | 514 | 2856 | 4284 | WBS Description: This task involves final design of the detector stand. A first pass of the stand has been designed and analyzed for stresses. This short period of time will be needed to only adjust the design for the final location in the cavern....
516 | 805 | 8.1.7 | Design Strongbacks (FNAL) | 2005-10-31 08:00 | 2006-01-23 17:00 | Yes | Fermilab | MEF[50%],DrafterF | 11 wks | 34540 | 17270 | 0 | 0 | 514 | 34540 | 51810 | WBS Description: This task involves design of the production strongback for assembling and manipulating the frames ...
517 | 1423 | 8.1.8 | Design Strongbacks (Roch) | 2005-10-31 08:00 | 2006-01-23 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%],MandS[14,520] | 11 wks | 0 | 0 | 14520 | 7260 | 516SS | 14520 | 21780 | WBS Description: This task involves design of the production strongback for assembling and manipulating the frames ...
518 | 806 | 8.1.9 | Design Cart modifications | 2006-01-24 08:00 | 2006-02-20 17:00 | Yes | Fermilab | MEF,DrafterF | 4 wks | 18240 | 9120 | 0 | 0 | 516 | 18240 | 27360 | WBS Description: This task is to redesign the cart from the Minos experiment to work for Minerva. Some small modifications to the connection system that allows it to hold a Minerva strongback are needed. Those changes need to be designed and analyze...
519 | 807 | 8.1.10 | Design Installation Procedure | 2006-02-21 08:00 | 2006-07-05 17:00 | Yes | Fermilab | MEF,DrafterF[50%] | 19 wks | 70300 | 35150 | 0 | 0 | 518,515 | 70300 | 105450 | WBS Description: This task involves moving the frames from their construction area to the Minos surface building, lowering them down the shaft to the cart, transporting them to the cavern, and finally hanging them. All of the engineering details for ...
520 | 808 | 8.1.11 | Design modifcations to the MINOS platform | 2006-07-06 08:00 | 2006-08-02 17:00 | Yes | Fermilab | MEF,DrafterF | 4 wks | 18240 | 9120 | 0 | 0 | 519 | 18240 | 27360 | WBS Description: This task is required to modify the existing platform for the Minos detector to allow installation of the Minerva detector. It will be necessry to resolve any mechanical interferences, including any required Minerva work platforms....
521 | 809 | 8.1.12 | Design Prototype detector stand | 2005-10-31 08:00 | 2005-11-18 17:00 | Yes | Fermilab | MEF,DrafterF | 3 wks | 13680 | 6840 | 0 | 0 | 514 | 13680 | 20520 | WBS Description: This task provides engineering and drafting to build a support stand for the prototype frame in some surface building. The amount of effort is small because a preliminary design of a support exists and only one frame will be the load...
522 | 810 | 8.2 | Procure Prototype Materials | 2005-11-07 08:00 | 2006-03-20 17:00 | No |  |  | 18 wks | 0 | 0 | 80180 | 16036 |  | 80180 | 96216
523 | 811 | 8.2.1 | Procure Prototype OD Frame Wedges | 2005-11-21 08:00 | 2005-12-20 17:00 | Yes | Fermilab | MandS[37,780] | 4 wks | 0 | 0 | 37780 | 7556 | 615,511 | 37780 | 45336 | WBS Description: This task involves purchase of prototype segments to make several frames for testing and measurement....
524 | 812 | 8.2.2 | Procure prototype HCAL steel | 2005-11-07 08:00 | 2006-01-06 17:00 | Yes | Fermilab | MandS[2,000] | 8 wks | 0 | 0 | 2000 | 400 | 512,615,513 | 2000 | 2400 | WBS Description: This task involves purchase of a prototype steel piece for the Hadron calorimeter sections of the detector. ...
525 | 813 | 8.2.3 | Procure prototype ECAL lead (Pb) | 2005-11-07 08:00 | 2006-02-06 17:00 | Yes | Fermilab | MandS[18,000] | 12 wks | 0 | 0 | 18000 | 3600 | 512,615 | 18000 | 21600 | WBS Description: This task involves purchase of lead sheets for the prototype program....
526 | 814 | 8.2.4 | Procure prototype HCAL upstream graphite | 2005-11-07 08:00 | 2006-02-06 17:00 | Yes | Fermilab | MandS[1,200] | 12 wks | 0 | 0 | 1200 | 240 | 512,615 | 1200 | 1440 | WBS Description: This task involves purchase of one prototype sheet of graphite for the prototype program. ...
527 | 1297 | 8.2.5 | Procure prototype axial bolts | 2005-11-14 08:00 | 2006-01-13 17:00 | Yes | Fermilab | MandS[200] | 8 wks | 0 | 0 | 200 | 40 | 515 | 200 | 240 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
528 | 1298 | 8.2.6 | Procure prototype ear pieces | 2005-11-14 08:00 | 2006-01-13 17:00 | Yes | Fermilab | MandS[1,000] | 8 wks | 0 | 0 | 1000 | 200 | 527SS | 1000 | 1200 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
529 | 815 | 8.2.7 | Procure prototype strongback | 2006-01-24 08:00 | 2006-03-20 17:00 | Yes | Fermilab | MandS[15,000] | 8 wks | 0 | 0 | 15000 | 3000 | 516 | 15000 | 18000 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
530 | 816 | 8.2.8 | Procure prototype detector stand and bookend | 2006-01-11 08:00 | 2006-02-01 17:00 | Yes | Fermilab | MandS[5,000] | 3 wks | 0 | 0 | 5000 | 1000 | 521 | 5000 | 6000 | WBS Description: This task involves ...
531 | 817 | 8.3 | Procure Production Materials | 2006-01-17 08:00 | 2008-03-25 17:00 | No |  |  | 110.4 wks | 0 | 0 | 488352 | 122088 |  | 488352 | 610440
532 | 818 | 8.3.1 | Procure production strongbacks | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[45,000] | 8 wks | 0 | 0 | 45000 | 11250 | 516,543,529,617,517 | 45000 | 56250 | WBS Description: This task involves purchase of three final version strongbacks for production of the detector. This allows for the posdsibility that the prototype is not used in the final production....
533 | 1299 | 8.3.2 | Procure 2 production stands and bookends | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[13,000] | 8 wks | 0 | 0 | 13000 | 3250 | 532SS | 13000 | 16250 | WBS Description: This task involves purchase of three final version strongbacks for production of the detector. This allows for the posdsibility that the prototype is not used in the final production....
534 | 820 | 8.3.3 | Purchase Stand and Bookend for cavern | 2007-10-01 08:00 | 2008-02-26 17:00 | No | Fermilab | MandS[25,000] | 20 wks | 0 | 0 | 25000 | 6250 | 530,617 | 25000 | 31250 | WBS Description: This task involves purchase of the final support structure for the detector in the cavern. The structure as designed weighs 30,000....
535 | 822 | 8.3.4 | Procure Narrow OD Wedges | 2007-11-28 08:00 | 2008-03-25 17:00 | No | Fermilab | MandS[80,712] | 16 wks | 0 | 0 | 80712 | 20178 | 532,617,533 | 80712 | 100890 | WBS Description: This task involves purchase of all the segments for the fabrication of the narrow frames for the detector....
536 | 823 | 8.3.5 | Procure Wide OD Wedges | 2007-11-28 08:00 | 2008-03-25 17:00 | No | Fermilab | MandS[175,759] | 16 wks | 0 | 0 | 175759 | 43939.75 | 535SS | 175759 | 219698.75 | WBS Description: This task involves purchase of all of the segments for the wide frames....
537 | 1300 | 8.3.6 | Procure axial bolts | 2006-01-17 08:00 | 2006-03-13 17:00 | No | Fermilab | MandS[5,600] | 8 wks | 0 | 0 | 5600 | 1400 | 527 | 5600 | 7000 | WBS Description: This task involves ...
538 | 824 | 8.3.7 | Procure ear pieces | 2007-10-01 08:00 | 2008-01-29 17:00 | No | Fermilab | MandS[26,640] | 16 wks | 0 | 0 | 26640 | 6660 | 539SS,528 | 26640 | 33300 | WBS Description: This task involves ...
539 | 825 | 8.3.8 | Procure HCAL Steel | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[39,836] | 8 wks | 0 | 0 | 39836 | 9959 | 524,617 | 39836 | 49795 | WBS Description: This task involves purchase of 23 pieces of steel for the upstream and downstreamHadron calorimeter sections of he detector. The steel plates are cut into hexagonal pieces that are 48" across the flat and 97" from point to point. To...
540 | 826 | 8.3.9 | Procure ECAL Pb | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[72,005] | 12 wks | 0 | 0 | 72005 | 18001.25 | 525,617 | 72005 | 90006.25 | WBS Description: This task involves purchase of all of the lead sheets for the nuclear targets and the EMCAL sections of the detector....
541 | 827 | 8.3.10 | Procure US HCAL Graphite | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[4,800] | 12 wks | 0 | 0 | 4800 | 1200 | 526,617 | 4800 | 6000 | WBS Description: This task involves purchase of the graphite sheets for the nuclear targets section of the detector....
542 | 828 | 8.4 | Outer Detector Frame Prototyping | 2006-02-02 08:00 | 2006-02-15 17:00 | No |  |  | 2 wks | 4904 | 2452 | 0 | 0 |  | 4904 | 7356
543 | 829 | 8.4.1 | Test Frame Welding | 2006-02-02 08:00 | 2006-02-08 17:00 | Yes | Fermilab | MTF,WelderF | 1 wk | 4640 | 2320 | 0 | 0 | 523,530 | 4640 | 6960 | WBS Description: This task involves Welding up the first prototype frame....
544 | 830 | 8.4.2 | Make Flatness Measurements | 2006-02-09 08:00 | 2006-02-15 17:00 | Yes | Fermilab | MTF[20%] | 1 wk | 264 | 132 | 0 | 0 | 543 | 264 | 396 | WBS Description: This is an engineering estimate for the time it would take a mechanical tech to measure the flatness of the prototype frame....
545 | 831 | 8.5 | Outer Detector Fabrication | 2008-03-26 08:00 | 2008-06-11 17:00 | No |  |  | 11 wks | 31680 | 15840 | 24042 | 1672 |  | 55722 | 73234
546 | 832 | 8.5.1 | Frame Welding | 2008-03-26 08:00 | 2008-06-11 17:00 | No | Fermilab | MandS[20,698],WelderF[50%],MTF Supervisor[50%] | 11 wks | 31680 | 15840 | 20698 | 0 | 532,536,535,538,544,537 | 52378 | 68218 | WBS Description: This task involves just welding up the frames. it is based on doing two frames a day. Keeping this pace is not a problem. The issue is whether the physicists can measure two a day in testing, and how that is done. ...
547 | 833 | 8.5.2 | QC measurements | 2008-03-26 08:00 | 2008-06-11 17:00 | No | Rochester | Roch Tech[0%],MandS[3,344] | 11 wks | 0 | 0 | 3344 | 1672 | 546SS | 3344 | 5016 | WBS Description: This task measures the quality (flatness) of the frames as they are made. It would allow problems to be found and repaired as necessary. The engineering estimate is for one person to spend 8 hours a week to look at all of the frames...
548 | 44 | 9 | Module Assembly and Installation | 2005-06-01 08:00 | 2008-05-20 17:00 | No |  |  | 149.6 wks | 226485.28 | 55413.592 | 332862 | 118190.5 |  | 559347.28 | 732951.372
549 | 975 | 9.1 | Assembly R&D | 2005-06-01 08:00 | 2006-09-27 17:00 | No |  |  | 67 wks | 112365.28 | 30594.392 | 117542 | 35822.5 |  | 229907.28 | 296324.172
550 | 978 | 9.1.1 | Rochester Prototypes | 2005-06-01 08:00 | 2005-12-28 12:00 | No |  |  | 29 wks | 29773.28 | 3924.792 | 14012 | 4125 |  | 43785.28 | 51835.072
551 | 1305 | 9.1.1.1 | Design and construct 1/12th scale model | 2005-06-01 08:00 | 2005-07-27 17:00 | Yes | Rochester | MandS[512],Roch Machinist[22%] | 8 wks | 3608 | 0 | 512 | 0 |  | 4120 | 4120 | WBS Description: This task involves ...
552 | 976 | 9.1.1.2 | Fabricate PMT Rack prototypes | 2005-07-28 08:00 | 2005-09-29 17:00 | Yes | Rochester | Roch ME[5%],MandS[1,000],Roch Tech[8%] | 9 wks | 2469.28 | 370.392 | 1000 | 150 | 551 | 3469.28 | 3989.672 | WBS Description: This task involves the PMT Rack Prototype...
553 | 1306 | 9.1.1.3 | Fabricate scale model prototypes | 2005-09-30 08:00 | 2005-10-27 17:00 | Yes | Rochester | MandS[2,000],Roch Tech[25%] | 4 wks | 1680 | 252 | 2000 | 300 | 552 | 3680 | 4232 | Prototype costs:...
554 | 977 | 9.1.1.4 | Prototype studies | 2005-10-28 08:00 | 2005-12-28 12:00 | Yes | Rochester | Roch ME[40%],Roch Tech,MandS[10,500],Bob Flight[40%] | 8 wks | 22016 | 3302.4 | 10500 | 3675 | 553 | 32516 | 39493.4 | WBS Description: This task involves ...
555 | 1307 | 9.1.1.5 | Prototype Studies Complete | 2005-12-28 12:00 | 2005-12-28 12:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 554 | 0 | 0
556 | 65 | 9.1.2 | Full Module Prototype Preparation | 2005-12-28 13:00 | 2006-08-29 17:00 | No |  |  | 34 wks | 47912 | 12797.6 | 94300 | 28190 |  | 142212 | 183199.6
557 | 1424 | 9.1.2.1 | Assembly Fixtures | 2005-12-29 13:00 | 2006-05-15 17:00 | No |  |  | 19 wks | 31520 | 7880 | 6900 | 1970 |  | 38420 | 48270
558 | 1428 | 9.1.2.1.1 | Purchase assembly tooling | 2005-12-29 13:00 | 2006-01-30 17:00 | No | Rochester | MandS[2,000] | 4 wks | 0 | 0 | 2000 | 500 | 554FS+1 day | 2000 | 2500 | WBS Description: This task involves ...
559 | 1425 | 9.1.2.1.2 | Design assembly fixtures | 2006-02-28 08:00 | 2006-04-24 17:00 | No | Rochester | Roch ME,Bob Flight | 8 wks | 21440 | 5360 | 0 | 0 | 558FS+4 wks | 21440 | 26800 | WBS Description: This task involves ...
560 | 1426 | 9.1.2.1.3 | Fabricate assembly fixtures | 2006-03-28 08:00 | 2006-05-08 17:00 | No | Rochester | Roch Tech | 6 wks | 10080 | 2520 | 0 | 0 | 559FS-4 wks | 10080 | 12600 | WBS Description: This task involves ...
561 | 1427 | 9.1.2.1.4 | Procure hardware for assembly fixtures | 2006-05-02 08:00 | 2006-05-15 17:00 | No | Rochester | MandS[4,900] | 2 wks | 0 | 0 | 4900 | 1470 | 560FS-1 wk | 4900 | 6370 | WBS Description: This task involves ...
562 | 1429 | 9.1.2.2 | PMT Rack for Prototyping | 2006-05-02 08:00 | 2006-06-20 17:00 | No |  |  | 7 wks | 4360 | 1308 | 0 | 0 |  | 4360 | 5668
563 | 1430 | 9.1.2.2.1 | Dsign PMT Rack | 2006-05-02 08:00 | 2006-05-08 17:00 | No | Rochester | Roch ME,Bob Flight | 1 wk | 2680 | 804 | 0 | 0 | 561SS | 2680 | 3484 | WBS Description: This task involves ...
564 | 1431 | 9.1.2.2.2 | Fabricate PMT Rack | 2006-06-14 08:00 | 2006-06-20 17:00 | No | Rochester | Roch Tech | 1 wk | 1680 | 504 | 0 | 0 | 563FS+5 wks,561 | 1680 | 2184 | WBS Description: This task involves ...
565 | 48 | 9.1.2.3 | Design and Construct Mapper | 2005-12-28 13:00 | 2006-08-29 17:00 | No |  |  | 34 wks | 12032 | 3609.6 | 87400 | 26220 |  | 99432 | 129261.6
566 | 336 | 9.1.2.3.1 | Mapper Design | 2005-12-28 13:00 | 2006-03-24 17:00 | Yes | Rochester | MandS[26,400] | 12 wks | 0 | 0 | 26400 | 7920 | 555 | 26400 | 34320 | WBS Description: This task involves ...
567 | 337 | 9.1.2.3.2 | Mapper Materials | 2006-03-27 08:00 | 2006-05-19 17:00 | Yes | Rochester | MandS[35,000] | 8 wks | 0 | 0 | 35000 | 10500 | 566 | 35000 | 45500 | WBS Description: This task involves ...
568 | 335 | 9.1.2.3.3 | Mapper Assembly | 2006-04-10 08:00 | 2006-08-29 17:00 | Yes | Rochester | MandS[26,000],Roch Lead Tech[32%],Dan Ruggiero[32%] | 20 wks | 12032 | 3609.6 | 26000 | 7800 | 567SS+2 wks | 38032 | 49441.6 | WBS Description: This task involves ...
569 | 52 | 9.1.3 | Prototype Assembly | 2006-06-21 08:00 | 2006-09-27 17:00 | No |  |  | 13.8 wks | 34680 | 13872 | 9230 | 3507.5 |  | 43910 | 61289.5
570 | 1432 | 9.1.3.1 | Deliver materials to Fermilab | 2006-06-21 08:00 | 2006-06-27 17:00 | No | Rochester | MandS[1,230] | 1 wk | 0 | 0 | 1230 | 307.5 | 564 | 1230 | 1537.5
571 | 333 | 9.1.3.2 | University Prototype assembly labor | 2006-08-30 08:00 | 2006-09-27 17:00 | Yes | Rochester | Roch Tech[250%] | 4 wks | 17640 | 7056 | 0 | 0 | 543,570,568,567 | 17640 | 24696 | WBS Description: This task involves ...
572 | 271 | 9.1.3.3 | Fermilab Prototype assembly work | 2006-08-30 08:00 | 2006-09-27 17:00 | Yes | Fermilab | MEF[150%],ES&H-F[175%],MandS[8,000] | 4 wks | 17040 | 6816 | 8000 | 3200 | 571SS | 25040 | 35056 | WBS Description: This task involves ...
573 | 1308 | 9.1.3.4 | Full Module Prototype Assembly Complete | 2006-09-27 17:00 | 2006-09-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 572 | 0 | 0
574 | 1309 | 9.1.4 | Prototype Mapping Complete | 2006-08-29 17:00 | 2006-08-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 568 | 0 | 0
575 | 47 | 9.2 | Module Assembly and Mapping | 2006-09-28 08:00 | 2008-05-20 17:00 | No |  |  | 82.6 wks | 113120 | 24819.2 | 145920 | 55968 |  | 259040 | 339827.2
576 | 1433 | 9.2.1 | Assembly Preparations | 2006-09-28 08:00 | 2007-12-27 17:00 | No |  |  | 62.6 wks | 43904 | 10976 | 56000 | 20000 |  | 99904 | 130880
577 | 1434 | 9.2.1.1 | Evaluate functional prototype assembly | 2006-09-28 08:00 | 2006-10-11 17:00 | No | Rochester | Roch ME,Bob Flight | 2 wks | 5360 | 1340 | 0 | 0 | 573 | 5360 | 6700
578 | 1435 | 9.2.1.2 | Revise assembly design | 2006-10-12 08:00 | 2006-11-24 17:00 | No | Rochester | Roch ME,Bob Flight | 6 wks | 17152 | 4288 | 0 | 0 | 577 | 17152 | 21440
579 | 980 | 9.2.1.3 | Purchase bulk assembly tooling | 2006-11-27 08:00 | 2006-12-26 12:00 | Yes | Rochester | MandS[6,000] | 4 wks | 0 | 0 | 6000 | 6000 | 578 | 6000 | 12000 | WBS Description: This task involves ...
580 | 1436 | 9.2.1.4 | Fabricate assembly fixtures | 2006-12-26 13:00 | 2007-02-08 17:00 | No | Rochester | MandS[15,000] | 6 wks | 0 | 0 | 15000 | 4500 | 579 | 15000 | 19500
581 | 1437 | 9.2.1.5 | Procure bulk assembly fixtures hardware | 2006-12-26 13:00 | 2007-01-25 17:00 | No | Rochester | MandS[15,000] | 4 wks | 0 | 0 | 15000 | 4500 | 580SS | 15000 | 19500
582 | 1438 | 9.2.1.6 | Fabricate PMT rack | 2006-12-26 13:00 | 2007-02-08 17:00 | No | Rochester | MandS[20,000] | 6 wks | 0 | 0 | 20000 | 5000 | 580SS | 20000 | 25000
583 | 1439 | 9.2.1.7 | Design PMT lifting jig | 2007-02-09 08:00 | 2007-02-22 17:00 | No | Rochester | Roch ME,Bob Flight | 2 wks | 5360 | 1340 | 0 | 0 | 582 | 5360 | 6700
584 | 1440 | 9.2.1.8 | Fabricate PMT lifting jig | 2007-02-23 08:00 | 2007-03-08 17:00 | No | Rochester | Roch Machinist | 2 wks | 4000 | 1000 | 0 | 0 | 583 | 4000 | 5000
585 | 1441 | 9.2.1.9 | Optimize scanner | 2006-10-12 08:00 | 2006-11-24 17:00 | No | Rochester | Roch Lead Tech,Dan Ruggiero | 6 wks | 12032 | 3008 | 0 | 0 | 578SS | 12032 | 15040
586 | 1442 | 9.2.1.10 | Ready To Assemble Module | 2007-12-27 17:00 | 2007-12-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 580,581,571,539,540,541,584 | 0 | 0
587 | 277 | 9.2.2 | Assemble Module (FNAL) | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Fermilab | ES&H-F[70%],AlignmentF[5%],MandS[16,000] | 20 wks | 0 | 0 | 16000 | 6400 | 256,616,56,573,274,586 | 16000 | 22400 | WBS Description: This task involves ...
588 | 278 | 9.2.3 | Assemble Module (Rochester) | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Rochester | Roch Tech[200%] | 20 wks | 69216 | 13843.2 | 0 | 0 | 587SS | 69216 | 83059.2 | WBS Description: This task involves ...
589 | 49 | 9.2.4 | Map Modules | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Fermilab | MandS[73,920] | 20 wks | 0 | 0 | 73920 | 29568 | 587SS,574,585 | 73920 | 103488 | WBS Description: This task is meant to include SAG internal module fiducial installation....
590 | 154 | 9.3 | Veto Wall | 2005-07-11 08:00 | 2007-08-14 17:00 | No |  |  | 105.8 wks | 1000 | 0 | 69400 | 26400 |  | 70400 | 96800
591 | 51 | 9.3.1 | Veto Wall Counters | 2005-07-11 08:00 | 2006-08-21 17:00 | No |  |  | 56.4 wks | 0 | 0 | 6000 | 2100 |  | 6000 | 8100
592 | 343 | 9.3.1.1 | Counter Checkout FY05 | 2005-07-11 08:00 | 2005-09-19 17:00 | Yes | Rochester | MandS[3,000] | 10 wks | 0 | 0 | 3000 | 1050 |  | 3000 | 4050 | WBS Description: This task involves ...
593 | 1443 | 9.3.1.2 | Counter Checkout FY06 | 2006-06-12 08:00 | 2006-08-21 17:00 | Yes | Rochester | MandS[3,000] | 10 wks | 0 | 0 | 3000 | 1050 | 592 | 3000 | 4050 | WBS Description: This task involves ...
594 | 165 | 9.3.2 | Veto Wall Structure | 2006-05-01 08:00 | 2007-08-07 17:00 | No |  |  | 64.2 wks | 1000 | 0 | 62200 | 23880 |  | 63200 | 87080
595 | 778 | 9.3.2.1 | Veto Wall design | 2006-05-01 08:00 | 2006-05-26 17:00 | Yes | Rochester | MandS[10,000] | 4 wks | 0 | 0 | 10000 | 4000 |  | 10000 | 14000 | WBS Description: This task involves ...
596 | 345 | 9.3.2.2 | Procure parts for Veto Wall structure | 2007-04-02 08:00 | 2007-04-27 17:00 | No | Rochester | MandS[40,200] | 4 wks | 0 | 0 | 40200 | 16080 | 595 | 40200 | 56280 | WBS Description: This task involves ...
597 | 344 | 9.3.2.3 | Fabricate Veto Wall structure | 2007-04-02 08:00 | 2007-07-24 17:00 | No | Rochester | MandS[4,000] | 16 wks | 0 | 0 | 4000 | 1000 | 616,596SS | 4000 | 5000 | WBS Description: This task involves ...
598 | 342 | 9.3.2.4 | Counter Shipping Crate & Handling | 2007-07-25 08:00 | 2007-08-07 17:00 | No | Rochester | MandS[9,000] | 2 wks | 1000 | 0 | 8000 | 2800 | 592,616,593,596,597 | 9000 | 11800 | WBS Description: This task involves ...
599 | 50 | 9.3.3 | Assemble Veto Wall at Fermilab | 2007-08-08 08:00 | 2007-08-14 17:00 | No | Rochester | MandS[1,200] | 1 wk | 0 | 0 | 1200 | 420 | 598 | 1200 | 1620 | WBS Description: This task involves ...
600 | 156 | 10 | Project Management | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 604032 | 181209.6 | 0 | 0 |  | 604032 | 785241.6
601 | 848 | 10.1 | Prototyping and Testing | 2005-06-01 08:00 | 2005-06-28 17:00 | No |  |  | 4 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This section brings together all of the prototyping tests that need to be done throughout the Project R&D phase. They are included here because the tests span several different sections and components. The management section presen...
602 | 849 | 10.1.1 | Single Plane Vertical Slice Test | 2005-06-01 08:00 | 2005-06-28 17:00 | Yes | Fermilab | Roch Physicist | 4 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This test was done at the very beginnig of the Project and tested the front end electronics and the light levels of the array....
603 | 852 | 10.1.2 | VST with non-glued fibers | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | This uses Eljen paint
604 | 853 | 10.1.3 | VST with glued fibers and Bicron paint | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | Test Bicron paint...
605 | 854 | 10.1.4 | VST with co-extruded scintillator | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | Mirror fibers for VST 2 with co-extruded scintillator...
606 | 216 | 10.2 | Management and Administration | 2005-06-01 08:00 | 2008-09-26 17:00 | No |  |  | 167.6 wks | 604032 | 181209.6 | 0 | 0 |  | 604032 | 785241.6
607 | 646 | 10.2.1 | FY05 Project Management and Administration | 2005-06-01 08:00 | 2005-09-29 17:00 | Yes | Fermilab | PhysicistF[340%] | 17 wks | 0 | 0 | 0 | 0 | 613 | 0 | 0 | WBS Description: This task involves ...
608 | 934 | 10.2.2 | FY06 Project Management and Administration | 2005-10-03 08:00 | 2006-09-29 17:00 | Yes | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50.2 wks | 201344 | 60403.2 | 0 | 0 | 607 | 201344 | 261747.2 | WBS Description: This task involves ...
609 | 935 | 10.2.3 | FY07 Project Management and Administration | 2006-10-02 08:00 | 2007-09-28 17:00 | No | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50.2 wks | 201344 | 60403.2 | 0 | 0 | 608 | 201344 | 261747.2 | WBS Description: This task involves ...
610 | 936 | 10.2.4 | FY08 Project Management and Administration | 2007-10-01 08:00 | 2008-09-26 17:00 | No | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50 wks | 201344 | 60403.2 | 0 | 0 | 609 | 201344 | 261747.2 | WBS Description: This task involves ...
611 | 982 | 10.2.5 | Project Management and Administration Complete | 2008-09-26 17:00 | 2008-09-26 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 610,655 | 0 | 0
612 | 723 | 10.3 | Project Milestones | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks | 0 | 0 | 0 | 0 |  | 0 | 0
613 | 724 | 10.3.1 | Start MINERvA Project | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone is for the start date of the MINERvA Project....
614 | 725 | 10.3.2 | Preproduction Funds Released | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of preproduction funds by Fermilab....
615 | 726 | 10.3.3 | FY06 Funds Released by Fermilab | 2005-10-03 08:00 | 2005-10-03 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY06 funds by Fermilab....
616 | 727 | 10.3.4 | FY07 Construction Funds Released | 2006-10-02 08:00 | 2006-10-02 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY07 funds by Fermilab....
617 | 728 | 10.3.5 | FY08 Construction Funds Released | 2007-10-01 08:00 | 2007-10-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY08 funds by Fermilab....
618 | 1291 | 10.3.6 | MINERvA Detector Ready For Installation | 2008-06-11 17:00 | 2008-06-11 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 360,507,547,588,587,353 | 0 | 0 | WBS Description: This milestone is for the finish date of the MINERvA Project....
619 | 729 | 10.3.7 | Finish MINERvA Project | 2009-01-05 17:00 | 2009-01-05 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 654,631,653,618,611 | 0 | 0 | WBS Description: This milestone is for the finish date of the MINERvA Project....
620 | 983 | 11 | Installation and Infrastructure | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks | 286608 | 45323.2 | 235532 | 25644 |  | 522140 | 593107.2
621 | 984 | 11.1 | Scintilator Extrusion | 2005-09-30 08:00 | 2005-11-28 17:00 | No |  |  | 8 wks | 0 | 0 | 155117 | 0 |  | 155117 | 155117
622 | 988 | 11.1.1 | Purchase R&D Polystyrene | 2005-09-30 08:00 | 2005-11-28 17:00 | No | Fermilab | MandS[65,117] | 8 wks | 0 | 0 | 65117 | 0 | 4,5,6 | 65117 | 65117 | WBS Description: This task involves the purchase of polystyrene pettles, dopants, titanium dioxide pellets, labels, and other consumables for ID scintilattor production....
623 | 989 | 11.1.2 | Purchase Construction Scintillator Consumables | 2005-09-30 08:00 | 2005-11-28 17:00 | No | Fermilab | MandS[90,000] | 8 wks | 0 | 0 | 90000 | 0 | 622SS | 90000 | 90000 | WBS Description: Purchase of dopants for entire experiment....
624 | 896 | 11.2 | Purchase specialized miling machine for work at Tufts | 2005-06-01 08:00 | 2005-11-03 17:00 | No | Fermilab |  | 22 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: Purchase of a milling machine, at a cost of $30,000, that will be used by Tufts University to produce PMT Boxes....
625 | 171 | 11.3 | Electronics Infrastructure | 2007-10-01 08:00 | 2008-07-17 17:00 | No |  |  | 40 wks | 79168 | 0 | 57235 | 22894 |  | 136403 | 159297
626 | 172 | 11.3.1 | Quiet Power Panel Installation | 2007-10-01 08:00 | 2007-11-09 17:00 | No | Fermilab | T&M ElectricialF[225%],MandS[56,020] | 6 wks | 0 | 0 | 56020 | 22408 | 456,617 | 56020 | 78428 | WBS Description: Installation of the quiet power panel by T&M electricians at Fermilab....
627 | 600 | 11.3.2 | Install Electronics Racks - Rigging | 2007-12-28 08:00 | 2007-12-28 17:00 | No | Fermilab | T&M Rigging Crew[70%],MandS[1,215] | 1 day | 0 | 0 | 1215 | 486 | 626,507 | 1215 | 1701 | WBS Description: This task covers the rigging needed to install the electronic racks....
628 | 175 | 11.3.3 | Install LV System (through fanouts) | 2007-12-31 08:00 | 2008-01-15 17:00 | No | Fermilab | EEF | 2 wks | 7008 | 0 | 0 | 0 | 626,627 | 7008 | 7008 | WBS Description: This task involves ...
629 | 180 | 11.3.4 | LV Cable Installation | 2008-01-16 08:00 | 2008-01-30 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 628 | 0 | 0 | WBS Description: This task involves ...
630 | 210 | 11.3.5 | Electronics System Integration | 2008-03-26 08:00 | 2008-07-17 17:00 | No | Fermilab | EEF,ETF | 16 wks | 72160 | 0 | 0 | 0 | 506,505,500,488,628,501,629,504,467 | 72160 | 72160 | WBS Description: This task involves ...
631 | 699 | 11.4 | DAQ System Installation Complete | 2008-07-17 17:00 | 2008-07-17 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 495,630 | 0 | 0 | WBS Description: This milestone is for the ...
632 | 986 | 11.5 | Stand Structure Installation | 2006-10-02 08:00 | 2008-07-24 17:00 | No |  |  | 91.2 wks | 50198 | 15844 | 23180 | 2750 |  | 73378 | 91972
633 | 834 | 11.5.1 | Installation of Prototype | 2008-06-12 08:00 | 2008-07-02 17:00 | No |  |  | 3 wks | 17584 | 8792 | 2500 | 625 |  | 20084 | 29501
634 | 835 | 11.5.1.1 | Core drill Anchors for stand | 2008-06-12 08:00 | 2008-06-18 17:00 | No | Fermilab | MandS[2,500],MTF[20%] | 1 wk | 264 | 132 | 2500 | 625 | 546,547 | 2764 | 3521 | WBS Description: This task is to drill and install floor anchors for the prototype stand. It assumes an outside contractor doing the core drilling and techs installing the anchors....
635 | 1301 | 11.5.1.2 | Install welding stand | 2008-06-19 08:00 | 2008-06-25 17:00 | No | Fermilab | MTF Sr[200%],MTF Supervisor,WelderF | 1 wk | 10320 | 5160 | 0 | 0 | 634 | 10320 | 15480 | WBS Description: This task is to install a prototype bookend and stand in the assembly area. The estimate is an enginering estimate do in consultation with the Tech Supervisor....
636 | 836 | 11.5.1.3 | Install stand and Bookend | 2008-06-26 08:00 | 2008-07-02 17:00 | No | Fermilab | MTF Sr[200%],MTF Supervisor | 1 wk | 7000 | 3500 | 0 | 0 | 634,635 | 7000 | 10500 | WBS Description: This task is to install a prototype bookend and stand in the assembly area. The estimate is an enginering estimate do in consultation with the Tech Supervisor....
637 | 1302 | 11.5.2 | Installation of Production Equipment | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  |  | 1 wk | 7264 | 3632 | 2500 | 625 |  | 9764 | 14021
638 | 1303 | 11.5.2.1 | Core drill Anchors for stand | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  | MandS[2,500],MTF[20%] | 1 wk | 264 | 132 | 2500 | 625 | 533 | 2764 | 3521
639 | 1304 | 11.5.2.2 | Install stand and Bookend | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  | MTF Sr[200%],MTF Supervisor | 1 wk | 7000 | 3500 | 0 | 0 | 533 | 7000 | 10500
640 | 837 | 11.5.3 | Installation In The Cavern | 2006-10-02 08:00 | 2008-07-24 17:00 | No |  |  | 91.2 wks | 25350 | 3420 | 18180 | 1500 |  | 43530 | 48450
641 | 838 | 11.5.3.1 | Installation of the Stand and Bookend | 2008-07-03 08:00 | 2008-07-24 17:00 | No |  |  | 3 wks | 6840 | 3420 | 5000 | 1250 |  | 11840 | 16510
642 | 839 | 11.5.3.1.1 | Core Drill for anchors | 2008-07-03 08:00 | 2008-07-10 17:00 | No | Fermilab | MandS[5,000],MTF[50%] | 1 wk | 660 | 330 | 5000 | 1250 | 636,534,638,639 | 5660 | 7240 | WBS Description: This task involves core drilling holes for floor anchors and using a Fermilab mechancial tech to install them....
643 | 840 | 11.5.3.1.2 | Position the stand | 2008-07-11 08:00 | 2008-07-17 17:00 | No | Fermilab | MTF,AlignmentF[50%] | 1 wk | 1320 | 660 | 0 | 0 | 642 | 1320 | 1980 | WBS Description: This task involves setting the stand in position and marking the location of the anchor holes....
644 | 841 | 11.5.3.1.3 | Align and weld the stand in place | 2008-07-18 08:00 | 2008-07-24 17:00 | No | Fermilab | WelderF[50%],MTF[150%],MTF Supervisor[50%] | 1 wk | 4860 | 2430 | 0 | 0 | 643 | 4860 | 7290 | WBS Description: This task involves Assembling the stand in the cavern from the various pieces. This stand weighs about 15 tons....
645 | 842 | 11.5.3.2 | Modify Cart | 2006-10-02 08:00 | 2006-10-06 17:00 | No |  |  | 1 wk | 5910 | 0 | 1000 | 250 |  | 6910 | 7160
646 | 843 | 11.5.3.2.1 | Technician Cart Modification | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | MTF[200%],MTF Supervisor,MandS[1,000] | 1 wk | 5080 | 0 | 1000 | 250 | 516,616 | 6080 | 6330 | WBS Description: This task involves the mechanical tech work to modify the Minos cart to support Minerva strongbacks and frames. The cart is structurally sound for the load and only needs to have the connections between cart and strongback modified....
647 | 844 | 11.5.3.2.2 | Cart Welding and Rigging | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | WelderF[25%] | 1 wk | 830 | 0 | 0 | 0 | 646SS | 830 | 830 | WBS Description: This task involves the welding to do the cart modifications....
648 | 845 | 11.5.3.3 | MINOS Electronics Platform Modification | 2006-10-02 08:00 | 2006-10-13 17:00 | No |  |  | 2 wks | 12600 | 0 | 12180 | 0 |  | 24780 | 24780
649 | 846 | 11.5.3.3.1 | Procure Frame and Grating | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | MandS[12,180] | 1 wk | 0 | 0 | 12180 | 0 | 514,616,520 | 12180 | 12180 | WBS Description: This task involves purchasing the framing material and grating required to modify the platform....
650 | 847 | 11.5.3.3.2 | Modify Platform | 2006-10-09 08:00 | 2006-10-13 17:00 | No | Fermilab | MTF Sr[300%],MTF Supervisor,WelderF | 1 wk | 12600 | 0 | 0 | 0 | 649 | 12600 | 12600 | WBS Description: This task involves modifying the electroncis platform in place now for Minos to make room for the Minerva detector....
651 | 987 | 11.6 | Module Installation | 2007-08-15 08:00 | 2009-01-05 17:00 | No |  |  | 69.4 wks | 83544 | 0 | 0 | 0 |  | 83544 | 83544
652 | 169 | 11.6.1 | Module Installation | 2008-10-20 08:00 | 2009-01-05 17:00 | No | Fermilab | MTF Supervisor,MTF[400%] | 10 wks | 78744 | 0 | 0 | 0 | 589FF+3 days,644,647,587,360,646,650,384,392,394,395 | 78744 | 78744 | WBS Description: This task involves ...
653 | 354 | 11.6.2 | Final Detector Alignment | 2008-10-22 08:00 | 2009-01-05 17:00 | No | Fermilab | AlignmentF[30%] | 9.6 wks | 0 | 0 | 0 | 0 | 652SS+2 days | 0 | 0 | WBS Description: This task involves ...
654 | 168 | 11.6.3 | Install Veto Wall | 2007-08-15 08:00 | 2007-08-21 17:00 | No | Fermilab | MTF[225%],MTF Supervisor[75%] | 1 wk | 4800 | 0 | 0 | 0 | 599 | 4800 | 4800 | WBS Description: This task involves ...
655 | 350 | 11.7 | Installation Manager | 2006-10-02 08:00 | 2008-09-25 17:00 | No | Fermilab | MEF[25%] | 100 wks | 73698 | 29479.2 | 0 | 0 | 607FF,616SS | 73698 | 103177.2 | WBS Description: This task involves ...
296 | 145 | 4.4.1.2 | 400 R&D optical connector procurement | 2005-10-27 08:00 | 2005-12-27 12:00 | Yes | Rochester | MandS[32,500] | 8 wks | 0 | 0 | 32500 | 9750 | 295 | 32500 | 42250 | WBS Description: Purchase order from FNAL to buy initial order of 400 connectors....
297 | 1420 | 4.4.1.3 | Ship R&D optical connector to W&M | 2005-12-27 13:00 | 2006-01-11 17:00 | No |  |  | 2 wks | 0 | 0 | 0 | 0 | 296 | 0 | 0
298 | 144 | 4.4.1.4 | QC of optical connector | 2005-12-27 13:00 | 2006-01-26 17:00 | Yes | Fermilab | MTF | 4 wks | 5280 | 0 | 0 | 0 | 296,307,324 | 5280 | 5280 | WBS Description: Quality control check of intial connectors....
299 | 715 | 4.4.1.5 | Qualified Optical Connector | 2006-01-26 17:00 | 2006-01-26 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 298 | 0 | 0 | WBS Description: This milestone is for the ...
300 | 143 | 4.4.2 | Prototype and Production of Optical Connectors | 2006-01-27 08:00 | 2006-11-10 17:00 | No |  |  | 40.6 wks | 2640 | 0 | 61351 | 17490.2 |  | 63991 | 81481.2
301 | 614 | 4.4.2.1 | Purchase prototype cable optical connectors | 2006-01-27 08:00 | 2006-03-09 17:00 | Yes | Rochester | MandS[9,151] | 6 wks | 0 | 0 | 9151 | 1830.2 | 299 | 9151 | 10981.2 | WBS Description: Purchase a small number of connectors for R&D activities. There may be a significant lead time for this purchase due to varying levels of signature review and authorization....
302 | 265 | 4.4.2.2 | Procure production optical connectors | 2006-09-01 08:00 | 2006-10-27 17:00 | No | Rochester | MandS[52,200] | 8 wks | 0 | 0 | 52200 | 15660 | 299,616FS-4 wks,301 | 52200 | 67860 | WBS Description: Bulk purchase of the rest of the connectors needed for the project....
303 | 792 | 4.4.2.3 | QC of production connectors | 2006-10-30 08:00 | 2006-11-10 17:00 | No | Fermilab | MTF | 2 wks | 2640 | 0 | 0 | 0 | 302 | 2640 | 2640 | WBS Description: Quality control check of intial connectors....
304 | 10 | 4.5 | Cable Light-Tight Mold | 2005-06-01 08:00 | 2007-03-26 17:00 | No |  |  | 91.4 wks | 0 | 0 | 73684 | 0 |  | 73684 | 73684
305 | 62 | 4.5.1 | Design a single light tight mold | 2005-06-01 08:00 | 2005-08-10 17:00 | Yes | Rochester | Roch ME[0%],MandS[12,072] | 10 wks | 0 | 0 | 12072 | 0 | 613 | 12072 | 12072 | WBS Description: This task involves ...
306 | 666 | 4.5.2 | Fabricate R&D light tight mold | 2005-08-10 17:00 | 2005-08-24 17:00 | Yes | Rochester | MandS[3,500],Roch Tech[0%] | 2 wks | 0 | 0 | 3500 | 0 | 305 | 3500 | 3500 | WBS Description: This task involves ...
307 | 665 | 4.5.3 | Test R&D and redesign mold | 2005-08-24 17:00 | 2005-10-06 17:00 | Yes | Rochester | Roch ME[0%],MandS[3,168] | 6 wks | 0 | 0 | 3168 | 0 | 306 | 3168 | 3168 | WBS Description: This task involves ...
308 | 670 | 4.5.4 | Qualified Light-Tight Cable | 2005-10-06 17:00 | 2005-10-06 17:00 | Yes | Rochester |  | 0 wks | 0 | 0 | 0 | 0 | 307 | 0 | 0 | WBS Description: This task involves ...
309 | 61 | 4.5.5 | Produce production light tight molds | 2006-10-02 08:00 | 2007-03-26 17:00 | Yes | Rochester | Roch Machinist[0%],MandS[54,944] | 24 wks | 0 | 0 | 54944 | 0 | 308,616 | 54944 | 54944 | WBS Description: This task involves additional molds for production....
310 | 671 | 4.6 | Optical Connector Polishing R&D | 2005-07-11 08:00 | 2006-03-17 17:00 | No |  |  | 34.6 wks | 7238 | 0 | 13328 | 0 |  | 20566 | 20566
311 | 676 | 4.6.1 | Produce R&D pigtails for polish tests | 2005-12-22 17:00 | 2006-01-10 17:00 | Yes | Fermilab | Roch Lead Tech[0%],Dan Ruggiero[50%],MandS[2,288] | 2 wks | 0 | 0 | 2288 | 0 | 280 | 2288 | 2288 | WBS Description: This task involves ...
312 | 677 | 4.6.2 | Design connector polish holding fixture | 2005-07-11 08:00 | 2005-07-15 17:00 | Yes | Fermilab | MEF[50%] | 1 wk | 1420 | 0 | 0 | 0 |  | 1420 | 1420 | WBS Description: This task involves machining the polishing fixtures....
313 | 678 | 4.6.3 | Produce default connector polish holding fixture | 2005-07-25 08:00 | 2005-07-29 17:00 | Yes | Fermilab | MandS[3,900] | 1 wk | 0 | 0 | 3900 | 0 | 312 | 3900 | 3900 | WBS Description: This task involves testing the connector fixture....
314 | 672 | 4.6.4 | Produce MSU technique connector polish holding fixture | 2005-10-03 08:00 | 2005-10-07 17:00 | Yes | Fermilab | MEF[5%],MachinistF[10%],MandS[200],MTF Sr Lab7,Eileen Hahn | 1 wk | 2914 | 0 | 200 | 0 | 313,615 | 3114 | 3114 | WBS Description: This task involves understanding the transmission of polished connectors....
315 | 673 | 4.6.5 | Polish R&D Cables and Pigtails | 2006-01-11 17:00 | 2006-02-09 17:00 | Yes | Rochester | Roch Tech[0%],MandS[3,040] | 4 wks | 0 | 0 | 3040 | 0 | 313,311,314,323,340FF | 3040 | 3040 | WBS Description: This task involves understanding the transmissoin of polished connectors....
316 | 674 | 4.6.6 | Tests with R&D Cable and Pigtails | 2006-02-24 08:00 | 2006-03-10 17:00 | Yes | Fermilab | MTF | 2.2 wks | 2904 | 0 | 0 | 0 | 315,325 | 2904 | 2904 | WBS Description: Test the number of polishes that can be successfully achieved using the diamonds....
317 | 675 | 4.6.7 | Qualified ODU Fabrication Technique | 2006-03-10 17:00 | 2006-03-10 17:00 | Yes | Rochester |  | 0 wks | 0 | 0 | 0 | 0 | 316 | 0 | 0 | WBS Description: Test the number of polishes that can be successfully achieved using the diamonds....
318 | 679 | 4.6.8 | Produce second connector polish holding fixture | 2006-03-13 08:00 | 2006-03-17 17:00 | Yes | Rochester | MandS[3,900] | 1 wk | 0 | 0 | 3900 | 0 | 317 | 3900 | 3900 | WBS Description: This task involves ...
319 | 680 | 4.7 | Cable Tester and Optical Cable Mapper | 2005-10-03 08:00 | 2006-02-23 17:00 | No |  |  | 19.6 wks | 3544 | 0 | 27488 | 750 |  | 31032 | 31782
320 | 793 | 4.7.1 | Light Injector | 2005-10-03 08:00 | 2006-02-23 17:00 | No |  |  | 19.6 wks | 3200 | 0 | 6548 | 500 |  | 9748 | 10248
321 | 681 | 4.7.1.1 | Design Light Injector | 2005-10-03 08:00 | 2005-10-07 17:00 | Yes | Rochester | Roch Physicist | 1 wk | 0 | 0 | 0 | 0 | 615 | 0 | 0 | WBS Description: This task involves ...
322 | 683 | 4.7.1.2 | Purchase light injector parts | 2005-10-10 08:00 | 2005-11-18 17:00 | Yes | Rochester | MandS[2,500] | 6 wks | 0 | 0 | 2500 | 500 | 321 | 2500 | 3000 | WBS Description: This task covers purchase of the parts and materials needed for the light injector. ...
323 | 1419 | 4.7.1.3 | Produce Pigtails for cable testers | 2005-12-27 12:00 | 2006-01-11 17:00 | No |  | Roch Lead Tech[0%],Dan Ruggiero,MandS[4,048] | 2 wks | 0 | 0 | 4048 | 0 | 296,78,279 | 4048 | 4048 | WBS Description: This task covers ...
324 | 796 | 4.7.1.4 | Fabricate light injector parts (incl. electronics for readout box) | 2005-11-21 08:00 | 2005-12-06 17:00 | Yes | Fermilab | MTF Lab7[50%] | 2 wks | 1584 | 0 | 0 | 0 | 322 | 1584 | 1584 | WBS Description: This task involves ...
325 | 682 | 4.7.1.5 | Assemble Light Injector | 2006-02-10 08:00 | 2006-02-23 17:00 | Yes | Fermilab | ETF[10%],MTF[50%],Roch Physicist[20%] | 2 wks | 1616 | 0 | 0 | 0 | 324,323,315 | 1616 | 1616 | WBS Description: This task involves actual construction of the light injector....
326 | 1446 | 4.7.2 | Cable Tester readout | 2005-10-10 08:00 | 2005-12-20 17:00 | No |  |  | 10 wks | 0 | 0 | 16000 | 0 |  | 16000 | 16000
327 | 1447 | 4.7.2.1 | Design cable tester readout box | 2005-10-10 08:00 | 2005-10-21 17:00 | No |  | Roch Physicist | 2 wks | 0 | 0 | 0 | 0 | 321 | 0 | 0
328 | 1448 | 4.7.2.2 | Obtain and fabricate readout box parts | 2005-10-24 08:00 | 2005-11-04 17:00 | No |  |  | 2 wks | 0 | 0 | 0 | 0 | 327 | 0 | 0
329 | 1449 | 4.7.2.3 | Obtain readout electronics | 2005-10-24 08:00 | 2005-11-04 17:00 | No |  | MandS[16,000] | 2 wks | 0 | 0 | 16000 | 0 | 327 | 16000 | 16000
330 | 1450 | 4.7.2.4 | Assemble Readout Box | 2005-12-07 08:00 | 2005-12-20 17:00 | No |  |  | 2 wks | 0 | 0 | 0 | 0 | 324,328,329 | 0 | 0
331 | 794 | 4.7.3 | Optical Cable Mapper | 2005-10-03 08:00 | 2005-11-29 17:00 | No |  |  | 8 wks | 344 | 0 | 4940 | 250 |  | 5284 | 5534
332 | 687 | 4.7.3.1 | Design a Optical Cable Mapper (FNAL) | 2005-10-03 08:00 | 2005-10-14 17:00 | Yes | Rochester | DrafterF[10%] | 2 wks | 344 | 0 | 0 | 0 | 615 | 344 | 344 | WBS Description: This task involves ...
333 | 1451 | 4.7.3.2 | Design a Optical Cable Mapper (Rochester) | 2005-10-03 08:00 | 2005-10-14 17:00 | Yes | Rochester | Roch Physicist[10%],Roch ME[0%],MandS[1,320] | 2 wks | 0 | 0 | 1320 | 0 | 332SS | 1320 | 1320 | WBS Description: This task involves ...
334 | 688 | 4.7.3.3 | Machine parts for Optical Cable Mapper | 2005-10-14 17:00 | 2005-10-28 17:00 | Yes | Rochester | MandS[1,600],Roch Machinist[0%] | 2 wks | 0 | 0 | 1600 | 0 | 332,333 | 1600 | 1600 | WBS Description: This task involves ...
335 | 689 | 4.7.3.4 | Purchase parts for Optical Cable Mapper | 2005-10-31 08:00 | 2005-11-11 17:00 | Yes | Rochester | MandS[500] | 2 wks | 0 | 0 | 500 | 250 | 334 | 500 | 750 | WBS Description: This task involves ...
336 | 690 | 4.7.3.5 | Build Optical Cable Mapper | 2005-11-11 17:00 | 2005-11-29 17:00 | Yes | Rochester | Roch Tech[0%],MandS[1,520] | 2 wks | 0 | 0 | 1520 | 0 | 335 | 1520 | 1520 | WBS Description: This task involves ...
337 | 691 | 4.8 | Fabricate Cables and ODU's | 2005-11-07 08:00 | 2008-01-02 17:00 | No |  |  | 107.8 wks | 23072 | 0 | 307252 | 0 |  | 330324 | 330324
338 | 692 | 4.8.1 | Fabricate R&D Cables and ODUs | 2005-11-07 08:00 | 2006-03-03 17:00 | Yes | Rochester |  | 15.8 wks | 3008 | 0 | 12682 | 0 |  | 15690 | 15690 | WBS Description: This task covers the purchase of consumable materials and tooling for the ODU factory....
339 | 693 | 4.8.1.1 | Outfit Cable and ODU Factory | 2005-11-07 08:00 | 2005-11-29 17:00 | Yes | Rochester | MandS[3,440] | 3 wks | 0 | 0 | 3440 | 0 |  | 3440 | 3440 | WBS Description: This covers the cost of the consumable materials that are necessary for the ODU and some of the cable production....
340 | 694 | 4.8.1.2 | Fabicate ODUs and Cables for R&D | 2005-12-27 13:00 | 2006-01-20 17:00 | Yes | Rochester | MandS[9,242] | 3.2 wks | 0 | 0 | 9242 | 0 | 339,279,296 | 9242 | 9242 | WBS Description: This task involves ...
341 | 1290 | 4.8.1.3 | Ship subsample (24) ODUs to Tufts | 2006-02-10 08:00 | 2006-03-03 17:00 | Yes | Fermilab | MTF Lab7[25%],MTF Sr Lab7[25%] | 3.2 wks | 3008 | 0 | 0 | 0 | 340,315 | 3008 | 3008 | WBS Description: This task involves ...
342 | 711 | 4.8.2 | Fabricate Prototype Cables and ODUs | 2006-06-23 17:00 | 2006-12-07 17:00 | Yes | Rochester |  | 23 wks | 18048 | 0 | 69920 | 0 |  | 87968 | 87968 | WBS Description: This task involves ...
343 | 856 | 4.8.2.1 | Fabricate Prototype ODUs and Cables | 2006-06-23 17:00 | 2006-10-31 17:00 | Yes | Fermilab | Roch Tech[0%],MandS[69,920] | 18 wks | 0 | 0 | 69920 | 0 | 287,317,615,330,336 | 69920 | 69920 | WBS Description: This task involves ...
344 | 695 | 4.8.2.2 | Polish Prototype ODUs and Cables | 2006-07-11 08:00 | 2006-11-21 17:00 | No | Rochester | MTF Lab7[25%],MTF Sr Lab7[25%] | 19 wks | 18048 | 0 | 0 | 0 | 343SS+2 wks | 18048 | 18048 | WBS Description: This task involves moving to full production capacity....
345 | 730 | 4.8.2.3 | Ship Prototype ODUs to Tufts | 2006-11-22 08:00 | 2006-12-07 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 344 | 0 | 0 | WBS Description: This task involves ...
346 | 857 | 4.8.2.4 | Light-Tight Prototype Cables | 2006-11-22 08:00 | 2006-12-07 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 344,343 | 0 | 0 | WBS Description: This task involves ...
347 | 858 | 4.8.2.5 | Prototype ODUs and Cables Complete | 2006-12-07 17:00 | 2006-12-07 17:00 | No | Fermilab |  | 0 wks | 0 | 0 | 0 | 0 | 346 | 0 | 0 | WBS Description: This task involves ...
348 | 184 | 4.8.3 | Fabrication Production Cables and ODUs | 2007-04-11 08:00 | 2007-11-13 17:00 | No |  |  | 30.4 wks | 2016 | 0 | 224450 | 0 |  | 226466 | 226466
349 | 185 | 4.8.3.1 | Fabricate Production ODUs | 2007-04-11 08:00 | 2007-08-16 17:00 | No |  | MandS[68,840] | 18 wks | 0 | 0 | 68840 | 0 | 292,303,347,318 | 68840 | 68840 | WBS Description: This task is defined to be first 20% of cable production...
350 | 303 | 4.8.3.2 | Polish Production ODUs | 2007-04-25 08:00 | 2007-05-22 17:00 | Yes | Rochester | MandS[4,128] | 4 wks | 0 | 0 | 4128 | 0 | 349SS+2 wks | 4128 | 4128 | WBS Description: This task involves ...
351 | 713 | 4.8.3.3 | Ship production ODU's to Tufts | 2007-08-17 08:00 | 2007-09-03 17:00 | Yes | Rochester | Roch Tech[50%] | 2.4 wks | 2016 | 0 | 0 | 0 | 350,349 | 2016 | 2016 | This will produce a small number of cables.
352 | 304 | 4.8.3.4 | Ship production ODU's to Rutgers | 2007-05-23 08:00 | 2007-06-06 17:00 | No | Rochester | MandS[51,000] | 2 wks | 0 | 0 | 51000 | 0 | 350 | 51000 | 51000 | WBS Description: This covers the cost of the consumable materials that are necessary for the ODU and some of the cable production. (i.e. epoxies, glues, syringes, etc.)...
353 | 890 | 4.8.3.5 | ODU shipments complete | 2007-09-03 17:00 | 2007-09-03 17:00 | No | Rochester |  | 0 wks | 0 | 0 | 0 | 0 | 351,352 | 0 | 0
354 | 714 | 4.8.3.6 | Fabricate Production Cables | 2007-09-03 17:00 | 2007-10-16 17:00 | No |  | MandS[41,222],Roch Tech[0%] | 6 wks | 0 | 0 | 41222 | 0 | 292,303,347,353 | 41222 | 41222 | WBS Description: This section covers the work to bring the cable factory up to full production status....
355 | 731 | 4.8.3.7 | Polish Production Cables | 2007-09-18 17:00 | 2007-10-16 17:00 | No | Rochester | Roch Tech[0%],MandS[18,240] | 4 wks | 0 | 0 | 18240 | 0 | 354SS+2 wks | 18240 | 18240 | WBS Description: This task involves ...
356 | 733 | 4.8.3.8 | Light-Tight Production Cables | 2007-10-17 08:00 | 2007-11-13 17:00 | No | Fermilab | MandS[41,020] | 4 wks | 0 | 0 | 41020 | 0 | 355,309 | 41020 | 41020 | WBS Description: This task involves ...
357 | 892 | 4.8.3.9 | Cable production complete | 2007-11-13 17:00 | 2007-11-13 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 356,354 | 0 | 0 | WBS Description: This task involves ...
358 | 891 | 4.8.4 | Cable storage | 2007-11-14 08:00 | 2008-01-02 17:00 | No |  |  | 6 wks | 0 | 0 | 200 | 0 |  | 200 | 200
359 | 893 | 4.8.4.1 | Construct storage containers for cables | 2007-11-14 08:00 | 2007-12-13 17:00 | No | Rochester | MandS[200] | 4 wks | 0 | 0 | 200 | 0 | 357 | 200 | 200 | WBS Description: This task involves ...
360 | 894 | 4.8.4.2 | Cable containers stored until ready for use | 2007-12-14 08:00 | 2008-01-02 17:00 | No | Rochester |  | 2 wks | 0 | 0 | 0 | 0 | 359 | 0 | 0 | WBS Description: This task involves ...
361 | 152 | 5 | PMT Boxes | 2005-07-28 08:00 | 2008-10-17 17:00 | No |  |  | 162.6 wks | 0 | 0 | 885549 | 366284.21 |  | 885549 | 1251833.21
362 | 13 | 5.1 | PMT Box Prototyping | 2005-07-28 08:00 | 2006-12-28 12:00 | No |  |  | 71.4 wks | 0 | 0 | 82720 | 19979 |  | 82720 | 102699
363 | 288 | 5.1.1 | Set up prototyping box factory shop at Tufts (FY05) | 2005-07-28 08:00 | 2005-09-30 17:00 | Yes | Tufts |  | 9.2 wks | 0 | 0 | 0 | 0 | 624FS-14 wks | 0 | 0 | WBS Description: Tufts will purchase tooling required to construct the prototypes. This task involves the work of technicians and a machinist are required to assist facultly researchers with the design and implement the four fabrication workstations ...
364 | 1310 | 5.1.2 | Set up prototyping box factory shop at Tufts (FY06) | 2005-10-03 08:00 | 2006-01-30 17:00 | No | Tufts | MandS[14,000] | 16 wks | 0 | 0 | 14000 | 3360 | 363 | 14000 | 17360 | WBS Description: Tufts will purchase tooling required to construct the prototypes. This task involves the work of facultly researchers to design and implement the four fabrication workstations which are required at each of the box factories at Tufts ...
365 | 716 | 5.1.3 | Tufts produces 100 alignment holders | 2006-01-31 08:00 | 2006-02-27 17:00 | Yes | Tufts | MandS[2,500] | 4 wks | 0 | 0 | 2500 | 500 | 83,364 | 2500 | 3000 | WBS Description: This is to produce the initial 100 alignment holders for JMU....
366 | 897 | 5.1.4 | Ship 100 alignment holders to JMU | 2006-02-14 08:00 | 2006-02-20 17:00 | Yes | Tufts | MandS[200] | 1 wk | 0 | 0 | 200 | 40 | 365FS-2 wks | 200 | 240 | WBS Description: This task involves shipment of the first 100 holders to JMU....
367 | 900 | 5.1.5 | Prepare fiber loaded cookies for JMU and Athens | 2006-03-28 08:00 | 2006-05-08 17:00 | Yes | Tufts | Tufts-Physicist[50%],Tufts-Assmbly Techs,MandS[7,920] | 6 wks | 0 | 0 | 7920 | 1584 | 393,280 | 7920 | 9504 | WBS Description: Receive ODU's from Fermi, cut ODU's, weave the fibre ends into the cookie, epoxy the fibers into the cookie and flycut the cookie. (6 cookies)...
368 | 901 | 5.1.6 | Ship fiber loaded cookies to JMU and Athens | 2006-05-09 08:00 | 2006-05-30 17:00 | Yes | Tufts | MandS[600] | 3 wks | 0 | 0 | 600 | 120 | 367 | 600 | 720 | WBS Description: This task covers shipment of fiber loaded cookies to JMU and Athens as needed....
369 | 902 | 5.1.7 | Set up Rutgers workstations - Part 1 | 2005-11-30 08:00 | 2006-05-01 17:00 | Yes | Rutgers | MandS[13,000] | 21 wks | 0 | 0 | 13000 | 3250 | 364SS+8 wks | 13000 | 16250 | WBS Description: This task involves ...
370 | 1294 | 5.1.8 | Set up Rutgers workstations - Part 2 | 2006-10-02 08:00 | 2006-12-28 12:00 | Yes | Rutgers | MandS[44,500] | 12 wks | 0 | 0 | 44500 | 11125 | 616,369,394SS | 44500 | 55625 | WBS Description: This task involves ...
371 | 290 | 5.2 | PMT Box Construction | 2006-05-31 08:00 | 2008-09-19 17:00 | No |  |  | 116.4 wks | 0 | 0 | 572229 | 184925.21 |  | 572229 | 757154.21 | WBS Description: This sub-section applies to the assembly of PMT boxes at Tufts and Rutgers....
372 | 615 | 5.2.1 | Produce rest of alignment holders | 2006-10-02 08:00 | 2007-02-19 17:00 | Yes | Tufts | Tufts-Machinist[50%],MandS[13,332] | 19 wks | 0 | 0 | 13332 | 3333 | 365,616 | 13332 | 16665 | WBS Description: This task involves ...
373 | 904 | 5.2.2 | Continue cookie production | 2007-02-20 08:00 | 2008-02-18 17:00 | No | Tufts | MandS[7,432],Tufts-Machinist[5%] | 50 wks | 0 | 0 | 7432 | 2452.56 | 367,372 | 7432 | 9884.56 | WBS Description: This task involves the completion of the cookie production. ...
374 | 712 | 5.2.3 | Exercise PMT Box Factory at Tufts | 2006-05-31 08:00 | 2006-10-19 17:00 | Yes | Tufts | MandS[10,000] | 20 wks | 0 | 0 | 10000 | 2500 | 368 | 10000 | 12500 | WBS Description: This task involves the initial test cycle for the box factory workstations....
375 | 14 | 5.2.4 | Manufacture first 10% of PMT boxes at Tufts | 2006-10-20 08:00 | 2007-03-21 17:00 | No | Tufts | MandS[39,984],Tufts-Assmbly Techs[85%],Tufts-Machinist[15%] | 20.6 wks | 0 | 0 | 39984 | 9996 | 616,374,364,425FS-3 wks | 39984 | 49980 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
376 | 1405 | 5.2.5 | Manufacture first 10% of PMT boxes at Rutgers | 2006-10-20 08:00 | 2007-03-21 17:00 | No | Rutgers | Rutgers-Tech[115%],Rutgers-Machinist[15%],MandS[48,379] | 20.6 wks | 0 | 0 | 48379 | 16932.65 | 375SS,426FS-3 wks | 48379 | 65311.65 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
377 | 1404 | 5.2.6 | Manufacture 11% to 50% of PMT boxes at Tufts | 2007-03-22 08:00 | 2008-01-17 17:00 | No | Tufts | Tufts-Assmbly Techs[85%],Tufts-Machinist[15%],MandS[104,500] | 41.4 wks | 0 | 0 | 104500 | 28215 | 375,427FS-3 wks | 104500 | 132715 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
378 | 360 | 5.2.7 | Manufacture 11% to 50% of PMT boxes at Rutgers | 2007-03-22 08:00 | 2008-01-17 17:00 | No | Rutgers | Rutgers-Tech[115%],Rutgers-Machinist[15%],MandS[121,445] | 41.4 wks | 0 | 0 | 121445 | 42505.75 | 370,376,428FS-4 wks,346 | 121445 | 163950.75 | WBS Description: This task is for the assembly of PMT boxes at Rutgers....
379 | 1407 | 5.2.8 | Manufacture 51% to 100% of PMT boxes at Tufts | 2008-01-30 08:00 | 2008-09-19 17:00 | No | Tufts | Tufts-Assmbly Techs[85%],Tufts-Machinist[15%],MandS[104,352] | 33 wks | 0 | 0 | 104352 | 36523.2 | 377,431 | 104352 | 140875.2 | WBS Description: This task is for the assembly of PMT boxes at Tufts....
380 | 1406 | 5.2.9 | Manufacture 51% to 100% of PMT boxes at Rutgers | 2008-01-30 08:00 | 2008-09-19 17:00 | No | Rutgers | Rutgers-Tech[115%],Rutgers-Machinist[15%],MandS[117,658] | 33 wks | 0 | 0 | 117658 | 41180.3 | 378,431 | 117658 | 158838.3 | WBS Description: This task is for the assembly of PMT boxes at Rutgers....
381 | 15 | 5.2.10 | Install ODUs into Cookie | 2007-03-13 08:00 | 2008-04-07 17:00 | No | Tufts | MandS[5,147],Tufts-Assmbly Techs[7%] | 54 wks | 0 | 0 | 5147 | 1286.75 | 373SS+3 wks | 5147 | 6433.75 | WBS Description: This task involves fiber cookie loading...
382 | 77 | 5.3 | PMT Box Frame Construction (FY07) | 2006-10-02 08:00 | 2006-12-28 12:00 | No | Rochester | MandS[5,000] | 12 wks | 0 | 0 | 5000 | 2000 | 616,573,364 | 5000 | 7000 | WBS Description: This task involves construction of lattice-work mounting frames, totaling 42 sectioned pieces. Pieces include steel framework, aluminum standoff pieces, hinges, assorted joint pieces, nuts, bolts, screws and will be made at Rochest...
383 | 1408 | 5.4 | PMT Box Frame Construction (FY08) | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Rochester | MandS[5,000] | 12 wks | 0 | 0 | 5000 | 2000 | 617,382 | 5000 | 7000 | WBS Description: This task involves construction of lattice-work mounting frames, totaling 42 sectioned pieces. Pieces include steel framework, aluminum standoff pieces, hinges, assorted joint pieces, nuts, bolts, screws and will be made at Rochest...
384 | 1292 | 5.5 | Ship PMT frame to Fermilab | 2007-12-28 08:00 | 2008-01-29 17:00 | No | Rochester | MandS[1,000] | 4 wks | 0 | 0 | 1000 | 0 | 383 | 1000 | 1000
385 | 914 | 5.6 | Ship Completed PMT Boxes | 2007-03-22 08:00 | 2008-10-17 17:00 | No |  |  | 79.8 wks | 0 | 0 | 24600 | 7380 |  | 24600 | 31980
386 | 915 | 5.6.1 | Ship first 10% of PMT boxes from Tufts to Fermi | 2007-03-22 08:00 | 2007-04-18 17:00 | Yes | Tufts | MandS[1,600] | 4 wks | 0 | 0 | 1600 | 480 | 375 | 1600 | 2080 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
387 | 916 | 5.6.2 | Ship first 10% of PMT boxes from Rutgers to Fermi | 2007-03-22 08:00 | 2007-04-18 17:00 | Yes | Rutgers | MandS[1,600] | 4 wks | 0 | 0 | 1600 | 480 | 376 | 1600 | 2080 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
388 | 917 | 5.6.3 | Ship first bulk PMT boxes from Tufts to Fermi | 2008-01-18 08:00 | 2008-02-15 17:00 | No | Tufts | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 386,377 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
389 | 918 | 5.6.4 | Ship first bulk PMT boxes from Rutgers to Fermi | 2008-01-18 08:00 | 2008-02-15 17:00 | No | Rutgers | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 387,378 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
390 | 919 | 5.6.5 | Ship last bulk PMT boxes from Tufts to Fermi | 2008-09-22 08:00 | 2008-10-17 17:00 | No | Tufts | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 388,379 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
391 | 920 | 5.6.6 | Ship last bulk PMT boxes from Rutgers to Fermi | 2008-09-22 08:00 | 2008-10-17 17:00 | No | Rutgers | MandS[5,350] | 4 wks | 0 | 0 | 5350 | 1605 | 389,380 | 5350 | 6955 | WBS Description: This task involves shipments, from Tufts & Rutgers to FNAL, of wood-frame shipping containers with completed optical boxes and mounting frames. This will take place at two-month intervals. Regular UPS shipments of optical box compon...
392 | 921 | 5.6.7 | All PMT Boxes Shipped to Fermilab | 2008-10-17 17:00 | 2008-10-17 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 390,391,381,373 | 0 | 0 | WBS Description: This milestone is for the ...
393 | 969 | 5.7 | Light Injection R&D | 2006-01-31 08:00 | 2006-03-27 17:00 | Yes | Fermilab | MandS[32,000] | 8 wks | 0 | 0 | 32000 | 0 | 364 | 32000 | 32000 | WBS Description: This task involves developing and building the Light Injection system necessary for testing PMT's....
394 | 1295 | 5.8 | Light Injection R&D | 2006-10-02 08:00 | 2006-11-28 17:00 | Yes | Fermilab | MandS[13,000] | 8 wks | 0 | 0 | 13000 | 0 | 616 | 13000 | 13000 | WBS Description: This task involves developing and building the Light Injection system necessary for testing PMT's....
395 | 1421 | 5.9 | Light injection system | 2006-11-29 08:00 | 2007-11-26 17:00 | No | Fermilab | MandS[150,000] | 50 wks | 0 | 0 | 150000 | 150000 | 394 | 150000 | 300000
396 | 153 | 6 | PMT Procurement and Testing | 2005-06-01 08:00 | 2008-01-29 17:00 | No |  |  | 133.6 wks | 0 | 0 | 1066815 | 346394.03 |  | 1066815 | 1413209.03
397 | 294 | 6.1 | PMT R&D, Alignment Station, and Test Stand | 2005-08-01 08:00 | 2006-06-27 17:00 | No |  |  | 45.8 wks | 0 | 0 | 79812 | 24581.28 |  | 79812 | 104393.28
398 | 1285 | 6.1.1 | Purchase 5 photomultiplier tubes | 2005-08-01 08:00 | 2005-09-12 17:00 | Yes | Fermilab |  | 6 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This is for the initial purchase of phototubes from Hammamatsu....
399 | 1286 | 6.1.2 | Purchase 5 photomultiplier tubes | 2005-10-03 08:00 | 2005-12-13 17:00 | Yes | Fermilab | MandS[20,000] | 10 wks | 0 | 0 | 20000 | 6000 | 398 | 20000 | 26000 | WBS Description: This is for the initial purchase of phototubes from Hammamatsu....
400 | 859 | 6.1.3 | Purchase alignment station materials (JMU) | 2005-12-14 08:00 | 2006-02-27 17:00 | Yes | JMU | MandS[8,500] | 10 wks | 0 | 0 | 8500 | 2040 | 615,399 | 8500 | 10540 | WBS Description: Purchase of alignment stand materials for use at JMU....
401 | 296 | 6.1.4 | Purchase test stand materials (JMU) | 2006-02-28 08:00 | 2006-06-27 17:00 | Yes | JMU | MandS[23,208] | 17 wks | 0 | 0 | 23208 | 7658.64 | 400 | 23208 | 30866.64 | WBS Description: This task involves ...
402 | 870 | 6.1.5 | Purchase test stand materials (Athens) | 2006-02-28 08:00 | 2006-06-27 17:00 | Yes | Athens | MandS[23,208] | 17 wks | 0 | 0 | 23208 | 7658.64 | 400 | 23208 | 30866.64 | WBS Description: This task involves ...
403 | 56 | 6.1.6 | Assemble test stand (JMU) | 2006-02-28 08:00 | 2006-06-27 17:00 | Yes | JMU | JMU-Undergrad[40%],MandS[2,448] | 17 wks | 0 | 0 | 2448 | 612 | 401SS | 2448 | 3060 | WBS Description: This task involves ...
404 | 871 | 6.1.7 | Assemble test stand (Athens) | 2006-02-28 08:00 | 2006-06-27 17:00 | Yes | Athens | Athens Student[40%],MandS[2,448] | 17 wks | 0 | 0 | 2448 | 612 | 402SS | 2448 | 3060 | WBS Description: This task involves ...
405 | 298 | 6.2 | Encapsulate, Align, and Test Initial PMT's | 2005-06-01 08:00 | 2006-10-05 17:00 | No |  |  | 68.2 wks | 0 | 0 | 24969 | 367.25 |  | 24969 | 25336.25
406 | 297 | 6.2.1 | Purchase initial alignment and testing materials (JMU) | 2006-06-28 08:00 | 2006-10-05 17:00 | Yes | JMU | MandS[15,500] | 14 wks | 0 | 0 | 15500 | 0 | 403,366 | 15500 | 15500 | WBS Description: This task involves ...
407 | 874 | 6.2.2 | Purchase initial testing materials (Athens) | 2006-06-28 08:00 | 2006-10-05 17:00 | Yes | Athens | MandS[8,000] | 14 wks | 0 | 0 | 8000 | 0 | 404,402 | 8000 | 8000 | WBS Description: This task involves ...
408 | 905 | 6.2.3 | Pittsburg puts a PC board onto PMT's first? | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone is for the ...
409 | 181 | 6.2.4 | Conduct initial (10%) PMT alignment (JMU) | 2006-06-28 08:00 | 2006-07-12 17:00 | Yes | JMU | JMU-Undergrad[40%],MandS[317] | 2 wks | 0 | 0 | 317 | 79.25 | 406SS,368,400,401 | 317 | 396.25 | WBS Description: This task involves ...
410 | 860 | 6.2.5 | Conduct initial PMT testing (JMU) | 2006-07-13 08:00 | 2006-07-26 17:00 | Yes | JMU | JMU-Undergrad[160%],MandS[1,152] | 2 wks | 0 | 0 | 1152 | 288 | 409,482,406SS | 1152 | 1440 | WBS Description: This task involves ...
411 | 182 | 6.3 | Bulk PMT Procurement and Testing | 2006-10-02 08:00 | 2008-01-29 17:00 | No |  |  | 66.2 wks | 0 | 0 | 962034 | 321445.5 |  | 962034 | 1283479.5
412 | 204 | 6.3.1 | Deliver 360 PMTs from manufacturer | 2006-10-02 08:00 | 2007-01-29 17:00 | No | Fermilab | MandS[517,737] | 16 wks | 0 | 0 | 517737 | 170853.21 | 616 | 517737 | 688590.21 | WBS Description: This is for the purchase of 360 phototubes from Hammamatsu....
413 | 862 | 6.3.2 | Align first bulk purchase PMTs (JMU) | 2006-10-30 08:00 | 2007-10-04 17:00 | No | JMU | JMU-Undergrad[10%],JMU-Tech[20%],MandS[15,030] | 47 wks | 0 | 0 | 15030 | 5260.5 | 412SS+4 wks,406 | 15030 | 20290.5 | WBS Description: This task involves ...
414 | 875 | 6.3.3 | Align first bulk purchase PMTs (Athens) | 2006-10-30 08:00 | 2007-10-04 17:00 | No | Athens | Athens Student[90%],MandS[15,811] | 47 wks | 0 | 0 | 15811 | 5533.85 | 412SS+4 wks,407 | 15811 | 21344.85 | WBS Description: This task involves ...
415 | 861 | 6.3.4 | Test first bulk purchase PMTs (JMU) | 2006-10-30 08:00 | 2007-10-04 17:00 | No | JMU | JMU-Undergrad[60%],JMU-Tech[80%],MandS[63,635] | 47 wks | 0 | 0 | 63635 | 22272.25 | 413SS | 63635 | 85907.25 | WBS Description: This task involves ...
416 | 876 | 6.3.5 | Test first bulk purchase PMTs (Athens) | 2006-10-30 08:00 | 2007-10-04 17:00 | No | Athens | Athens Student[385%],MandS[67,637] | 47 wks | 0 | 0 | 67637 | 23672.95 | 414SS | 67637 | 91309.95 | WBS Description: This task involves ...
417 | 1411 | 6.3.6 | 360 PMT Tests Complete | 2007-10-04 17:00 | 2007-10-04 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 412,413,414,415,416 | 0 | 0
418 | 205 | 6.3.7 | Deliver 171 PMTs from manufacturer | 2007-10-01 08:00 | 2008-01-29 17:00 | No | Fermilab | MandS[245,583] | 16 wks | 0 | 0 | 245583 | 81042.39 | 617 | 245583 | 326625.39 | WBS Description: This is for the delivery of 171 phototubes from Hammamatsu....
419 | 863 | 6.3.8 | Align final bulk purchase PMTs (JMU) | 2007-10-29 08:00 | 2008-01-14 17:00 | No | JMU | JMU-Undergrad[30%],JMU-Tech[20%],MandS[4,256] | 10 wks | 0 | 0 | 4256 | 1489.6 | 418SS+4 wks | 4256 | 5745.6 | WBS Description: This task involves ...
420 | 877 | 6.3.9 | Align final bulk purchase PMTs (Athens) | 2007-10-29 08:00 | 2008-01-14 17:00 | No | Athens | Athens Student,MandS[4,032] | 10 wks | 0 | 0 | 4032 | 1411.2 | 418SS+4 wks | 4032 | 5443.2 | WBS Description: This task involves ...
421 | 864 | 6.3.10 | Test final bulk purchase PMTs (JMU) | 2007-10-29 08:00 | 2008-01-14 17:00 | No | JMU | JMU-Undergrad[30%],JMU-Tech[80%],MandS[13,395] | 10 wks | 0 | 0 | 13395 | 4688.25 | 419SS,417 | 13395 | 18083.25 | WBS Description: This task involves ...
422 | 878 | 6.3.11 | Test final bulk purchase PMTs (Athens) | 2007-10-29 08:00 | 2008-01-14 17:00 | No | Athens | Athens Student[370%],MandS[14,918] | 10 wks | 0 | 0 | 14918 | 5221.3 | 420SS | 14918 | 20139.3 | WBS Description: This task involves ...
423 | 1410 | 6.3.12 | All PMT Tests Complete | 2008-01-29 17:00 | 2008-01-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 418,419,420,421,422 | 0 | 0
424 | 924 | 6.4 | Ship Completed PMT's | 2006-07-27 08:00 | 2008-01-29 17:00 | No |  |  | 75.4 wks | 0 | 0 | 0 | 0 |  | 0 | 0
425 | 925 | 6.4.1 | Ship first 10% of PMT's from JMU to Tufts | 2006-07-27 08:00 | 2006-08-09 17:00 | Yes | JMU |  | 2 wks | 0 | 0 | 0 | 0 | 410 | 0 | 0 | WBS Description: This task involves ...
426 | 926 | 6.4.2 | Ship first 10% of PMT's from Athens to Rutgers | 2006-07-27 08:00 | 2006-08-23 17:00 | Yes | Athens |  | 4 wks | 0 | 0 | 0 | 0 | 425SS | 0 | 0 | WBS Description: This task involves ...
427 | 927 | 6.4.3 | Ship first bulk PMT's from JMU to Tufts | 2006-11-29 08:00 | 2006-12-28 12:00 | No | JMU |  | 4 wks | 0 | 0 | 0 | 0 | 425,415SS+4 wks | 0 | 0 | WBS Description: This task involves ...
428 | 928 | 6.4.4 | Ship first bulk PMT's from Athens to Rutgers | 2006-11-29 08:00 | 2006-12-28 12:00 | No | Athens |  | 4 wks | 0 | 0 | 0 | 0 | 426,414SS+4 wks | 0 | 0 | WBS Description: This task involves ...
429 | 929 | 6.4.5 | Ship last bulk PMT's from JMU to Tufts | 2007-11-28 08:00 | 2007-12-27 17:00 | No | JMU |  | 4 wks | 0 | 0 | 0 | 0 | 427,421SS+4 wks | 0 | 0 | WBS Description: This task involves ...
430 | 930 | 6.4.6 | Ship last bulk PMT's from Athens to Rutgers | 2007-11-28 08:00 | 2007-12-27 17:00 | No | Athens |  | 4 wks | 0 | 0 | 0 | 0 | 428,422SS+4 wks | 0 | 0 | WBS Description: This task involves ...
431 | 931 | 6.4.7 | All PMT's Shipped | 2008-01-29 17:00 | 2008-01-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 429,430,423 | 0 | 0 | WBS Description: This milestone is for the ...
432 | 76 | 7 | Electronics and DAQ | 2005-08-15 08:00 | 2008-03-25 17:00 | No |  |  | 131.2 wks | 281952 | 0 | 782330 | 21624 |  | 1064282 | 1085906
433 | 19 | 7.1 | Front-End Electronics | 2005-08-15 08:00 | 2008-03-25 17:00 | No |  |  | 131.2 wks | 169992 | 0 | 443050 | 16953 |  | 613042 | 629995
434 | 942 | 7.1.1 | FE First Prototytpe | 2005-08-15 08:00 | 2005-11-07 17:00 | No |  |  | 12 wks | 5840 | 0 | 0 | 0 |  | 5840 | 5840
435 | 943 | 7.1.1.1 | Design and build 16 channel board | 2005-08-15 08:00 | 2005-08-26 17:00 | Yes | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This task involves ...
436 | 951 | 7.1.1.2 | High Voltage first prototype | 2005-08-29 08:00 | 2005-09-12 17:00 | Yes | Fermilab | EEF | 2 wks | 5840 | 0 | 0 | 0 | 435 | 5840 | 5840 | WBS Description: This task involves ...
437 | 974 | 7.1.1.3 | Test HV Prototype | 2005-09-13 08:00 | 2005-11-07 17:00 | Yes | Fermilab |  | 8 wks | 0 | 0 | 0 | 0 | 436 | 0 | 0
438 | 945 | 7.1.2 | TriP Procurement | 2005-10-28 08:00 | 2006-04-21 17:00 | No |  |  | 24 wks | 0 | 0 | 77000 | 11200 |  | 77000 | 88200
439 | 973 | 7.1.2.1 | TriP-T Decision Finalized | 2005-10-28 08:00 | 2005-10-28 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0
440 | 948 | 7.1.2.2 | TriP Refabrication | 2005-10-28 08:00 | 2006-01-27 17:00 | Yes | Fermilab | MandS[50,000] | 12 wks | 0 | 0 | 50000 | 10000 | 439 | 50000 | 60000 | WBS Description: This task involves production and packaginf of TriP chips (or possibly TriPt)....
441 | 949 | 7.1.2.3 | TriP Chip packaging | 2006-01-30 08:00 | 2006-02-24 17:00 | Yes | Fermilab | MandS[12,000] | 4 wks | 0 | 0 | 12000 | 1200 | 440 | 12000 | 13200 | WBS Description: This task involves ...
442 | 950 | 7.1.2.4 | TriP Checkout | 2006-02-27 08:00 | 2006-04-21 17:00 | Yes | Fermilab | MandS[15,000] | 8 wks | 0 | 0 | 15000 | 0 | 441 | 15000 | 15000 | WBS Description: This task involves ...
443 | 940 | 7.1.3 | FE 2nd prototype | 2006-01-02 08:00 | 2006-07-06 17:00 | No |  |  | 26 wks | 51708 | 0 | 12120 | 0 |  | 63828 | 63828
444 | 109 | 7.1.3.1 | FE 2nd Prototype Design | 2006-01-02 08:00 | 2006-03-14 17:00 | Yes | Fermilab | EEF[50%],ETF[25%] | 10 wks | 18300 | 0 | 0 | 0 |  | 18300 | 18300 | WBS Description: This task involves ...
445 | 701 | 7.1.3.2 | Begin Front End 2nd Prototype Production | 2006-03-14 17:00 | 2006-03-14 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 444 | 0 | 0 | WBS Description: This milestone is for the ...
446 | 88 | 7.1.3.3 | FE 2nd Prototype Production | 2006-03-15 08:00 | 2006-04-11 17:00 | Yes | Fermilab | MandS[12,120] | 4 wks | 0 | 0 | 12120 | 0 | 444,445 | 12120 | 12120 | WBS Description: This task involves ...
447 | 605 | 7.1.3.4 | FE 2nd Prototype Firmware | 2006-03-01 08:00 | 2006-05-23 17:00 | Yes | Fermilab | EEF[20%] | 12 wks | 7008 | 0 | 0 | 0 | 444SS+2 mons | 7008 | 7008 | WBS Description: This task involves ...
448 | 87 | 7.1.3.5 | FE 2nd Prototype Testing | 2006-04-12 08:00 | 2006-07-06 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 12 wks | 26400 | 0 | 0 | 0 | 446 | 26400 | 26400 | WBS Description: This task involves ...
449 | 967 | 7.1.3.6 | 2nd Prototype Testing Complete | 2006-07-06 17:00 | 2006-07-06 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 448 | 0 | 0 | WBS Description: This milestone is for the ...
450 | 946 | 7.1.4 | Base Second Prototype | 2005-10-17 08:00 | 2006-03-07 17:00 | No |  |  | 19.2 wks | 2648 | 0 | 250 | 0 |  | 2898 | 2898
451 | 616 | 7.1.4.1 | Provide 5 Feedthough board to Tufts | 2005-10-17 08:00 | 2005-11-11 17:00 | No | Fermilab | MandS[250],ETF[25%],EEF[10%] | 4 wks | 2648 | 0 | 250 | 0 |  | 2898 | 2898 | WBS Description: This task involves ...
452 | 952 | 7.1.4.2 | Design base second prototype | 2005-11-08 08:00 | 2005-12-07 17:00 | Yes | Fermilab |  | 4 wks | 0 | 0 | 0 | 0 | 437 | 0 | 0 | WBS Description: This task involves ...
453 | 953 | 7.1.4.3 | Produce base second prototype | 2005-12-08 08:00 | 2006-01-09 17:00 | Yes | Fermilab |  | 4 wks | 0 | 0 | 0 | 0 | 452 | 0 | 0 | WBS Description: This task involves ...
454 | 954 | 7.1.4.4 | Test base second prototype | 2006-01-10 08:00 | 2006-03-07 17:00 | Yes | Fermilab |  | 8 wks | 0 | 0 | 0 | 0 | 453 | 0 | 0 | WBS Description: This task involves ...
455 | 955 | 7.1.5 | FE Production | 2006-07-07 08:00 | 2008-03-25 17:00 | No |  |  | 86.2 wks | 109796 | 0 | 353680 | 5753 |  | 463476 | 469229
456 | 64 | 7.1.5.1 | FE Final Design (post 2nd prototype) | 2006-07-07 08:00 | 2006-09-22 17:00 | Yes | Fermilab | EEF,ETF[50%] | 11 wks | 40260 | 0 | 0 | 0 | 481,448,482,454 | 40260 | 40260 | WBS Description: This task involves ...
457 | 173 | 7.1.5.2 | Design LV Distribution System | 2006-09-25 08:00 | 2007-01-18 17:00 | Yes | Fermilab | EEF | 78 days | 49056 | 0 | 0 | 0 | 456 | 49056 | 49056 | WBS Description: This task involves ...
458 | 107 | 7.1.5.3 | FE Board Firmware | 2006-08-04 08:00 | 2006-09-29 17:00 | Yes | Fermilab | EEF[50%] | 8 wks | 11680 | 0 | 0 | 0 | 456SS+1 mon,447 | 11680 | 11680 | WBS Description: This task involves ...
459 | 606 | 7.1.5.4 | FE Board commissioning | 2006-10-02 08:00 | 2006-10-27 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 4 wks | 8800 | 0 | 0 | 0 | 458 | 8800 | 8800 | WBS Description: This task involves ...
460 | 966 | 7.1.5.5 | FE Component Procurement | 2006-09-25 08:00 | 2006-11-17 17:00 | No | Pitt |  | 8 wks | 0 | 0 | 0 | 0 | 456 | 0 | 0 | WBS Description: This task involves ...
461 | 968 | 7.1.5.6 | Begin Front End Production | 2006-10-27 17:00 | 2006-10-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 459,442 | 0 | 0 | WBS Description: This milestone is for the ...
462 | 91 | 7.1.5.7 | FE Board Initial Production | 2006-11-20 08:00 | 2007-01-22 17:00 | Yes | Fermilab | MandS[169,680] | 8 wks | 0 | 0 | 169680 | 0 | 460,461 | 169680 | 169680 | WBS Description: This task involves ...
463 | 83 | 7.1.5.8 | FE Test Stand Development | 2006-11-20 08:00 | 2007-01-22 17:00 | Yes | Pitt | Pitt-Electronics Shop[70%],MandS[7,470] | 8 wks | 0 | 0 | 7470 | 2988 | 462SS | 7470 | 10458 | WBS Description: This task involves ...
464 | 84 | 7.1.5.9 | FE Board Final Production | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[169,680] | 8 wks | 0 | 0 | 169680 | 0 | 463,617,462 | 169680 | 169680 | WBS Description: This task involves ...
465 | 965 | 7.1.5.10 | FE Board Checkout with Testing | 2007-11-28 08:00 | 2008-03-11 17:00 | No | Pitt | Pitt-Undergrad,MandS[6,600] | 14 wks | 0 | 0 | 6600 | 2640 | 464 | 6600 | 9240 | WBS Description: This task involves ...
466 | 704 | 7.1.5.11 | FE Board Production Complete | 2008-03-11 17:00 | 2008-03-11 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 465 | 0 | 0 | WBS Description: This milestone is for the ...
467 | 972 | 7.1.5.12 | Ship FE Boards to Fermilab | 2008-03-12 08:00 | 2008-03-25 17:00 | No | Pitt | MandS[250] | 2 wks | 0 | 0 | 250 | 125 | 466 | 250 | 375
468 | 956 | 7.1.6 | PMT Base Production | 2006-03-08 08:00 | 2006-05-16 17:00 | No |  |  | 10 wks | 0 | 0 | 0 | 0 |  | 0 | 0
469 | 957 | 7.1.6.1 | PMT Base final design | 2006-03-08 08:00 | 2006-03-14 17:00 | Yes | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 454 | 0 | 0 | WBS Description: This task involves ...
470 | 958 | 7.1.6.2 | PMT Base commissioning | 2006-03-15 08:00 | 2006-03-21 17:00 | Yes | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 469 | 0 | 0 | WBS Description: This task involves ...
471 | 959 | 7.1.6.3 | PMT Base Initial production | 2006-03-22 08:00 | 2006-03-28 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 470 | 0 | 0 | WBS Description: This task involves ...
472 | 960 | 7.1.6.4 | PMT Base test stand development | 2006-03-29 08:00 | 2006-04-04 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 471 | 0 | 0 | WBS Description: This task involves ...
473 | 961 | 7.1.6.5 | PMT Base final production | 2006-04-05 08:00 | 2006-04-11 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 472 | 0 | 0 | WBS Description: This task involves ...
474 | 964 | 7.1.6.6 | PMT Base checkout with testing | 2006-04-12 08:00 | 2006-04-18 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 473 | 0 | 0 | WBS Description: This task involves ...
475 | 962 | 7.1.6.7 | PMT Base Production Complete | 2006-04-18 17:00 | 2006-04-18 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 474 | 0 | 0 | WBS Description: This milestone is for the ...
476 | 24 | 7.1.6.8 | Ship PMT Bases | 2006-04-19 08:00 | 2006-05-16 17:00 | No | Pitt |  | 4 wks | 0 | 0 | 0 | 0 | 475 | 0 | 0 | WBS Description: This task involves ...
477 | 67 | 7.2 | Clock and Readout Control (CROC) Board | 2005-10-17 08:00 | 2007-10-08 12:00 | No |  |  | 99.5 wks | 111960 | 0 | 59120 | 1836 |  | 171080 | 172916
478 | 27 | 7.2.1 | CROC Design | 2005-10-17 08:00 | 2006-02-13 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 16 wks | 35200 | 0 | 0 | 0 |  | 35200 | 35200 | WBS Description: This task involves ...
479 | 702 | 7.2.2 | Begin CROC Prototype Production | 2006-02-13 17:00 | 2006-02-13 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 478 | 0 | 0 | WBS Description: This milestone is for the ...
480 | 85 | 7.2.3 | CROC Prototype Production | 2006-02-14 08:00 | 2006-03-27 17:00 | Yes | Fermilab | MandS[5,000] | 6 wks | 0 | 0 | 5000 | 0 | 479 | 5000 | 5000 | WBS Description: This task involves ...
481 | 86 | 7.2.4 | CROC Protoype Testing | 2006-04-12 08:00 | 2006-05-23 17:00 | Yes | Irvine | MandS[3,240],Irvine-Undergrad[150%] | 6 wks | 0 | 0 | 3240 | 972 | 480,446,490,491 | 3240 | 4212 | WBS Description: This task involves ...
482 | 700 | 7.2.5 | Prototype System Integration Test Complete | 2006-07-06 17:00 | 2006-07-06 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 448,481,449 | 0 | 0 | WBS Description: This milestone is for the ...
483 | 89 | 7.2.6 | CROC Final Design | 2006-09-25 08:00 | 2006-12-12 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 11 wks | 24200 | 0 | 0 | 0 | 481,456,482 | 24200 | 24200 | WBS Description: This task involves ...
484 | 108 | 7.2.7 | CROC Firmware | 2006-09-25 08:00 | 2007-01-26 17:00 | Yes | Fermilab | EEF | 84 days | 52560 | 0 | 0 | 0 | 483SS | 52560 | 52560 | WBS Description: This task involves ...
485 | 28 | 7.2.8 | CROC Board Production | 2006-12-13 08:00 | 2007-02-12 17:00 | No | Fermilab | MandS[48,000] | 8 wks | 0 | 0 | 48000 | 0 | 483 | 48000 | 48000 | WBS Description: This task involves ...
486 | 703 | 7.2.9 | CROC Board Production Complete | 2007-02-12 17:00 | 2007-02-12 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 485 | 0 | 0 | WBS Description: This milestone is for the ...
487 | 29 | 7.2.10 | CROC Board Checkout | 2007-03-20 08:00 | 2007-04-23 17:00 | No | Irvine | Irvine-Undergrad,MandS[1,800] | 5 wks | 0 | 0 | 1800 | 540 | 485,492,484,458,486 | 1800 | 2340 | WBS Description: This task involves ...
488 | 102 | 7.2.11 | CROC Board Installation | 2007-09-27 08:00 | 2007-10-08 12:00 | No | Irvine | Irvine-Undergrad[200%],MandS[1,080] | 1.5 wks | 0 | 0 | 1080 | 324 | 500SS,487 | 1080 | 1404 | WBS Description: This task involves ...
489 | 69 | 7.3 | DAQ and Slow Control | 2005-10-03 08:00 | 2007-10-29 17:00 | No |  |  | 104.6 wks | 0 | 0 | 166760 | 2835 |  | 166760 | 169595
490 | 33 | 7.3.1 | DAQ Prototype Hardware Procurement | 2005-10-03 08:00 | 2005-11-29 17:00 | Yes | Fermilab | MandS[55,500] | 8 wks | 0 | 0 | 55500 | 0 | 615 | 55500 | 55500 | WBS Description: This task involves ...
491 | 92 | 7.3.2 | VME Interface Software | 2005-11-30 08:00 | 2005-12-29 12:00 | Yes | Irvine |  | 4 wks | 0 | 0 | 0 | 0 | 490 | 0 | 0 | WBS Description: This task involves ...
492 | 34 | 7.3.3 | DAQ Readout Software | 2006-09-25 08:00 | 2007-03-19 17:00 | Yes | Irvine |  | 24 wks | 0 | 0 | 0 | 0 | 483SS,456 | 0 | 0 | WBS Description: This task involves ...
493 | 96 | 7.3.4 | LVDS Cable Procurement | 2006-10-02 08:00 | 2006-11-28 17:00 | No | Fermilab | MandS[15,750] | 8 wks | 0 | 0 | 15750 | 0 | 616 | 15750 | 15750 | WBS Description: This task involves ...
494 | 97 | 7.3.5 | LVDS Cable Testing | 2006-11-29 08:00 | 2006-12-26 17:00 | No | Irvine | Irvine-Undergrad[200%],MandS[2,880] | 3.7 wks | 0 | 0 | 2880 | 864 | 493 | 2880 | 3744 | WBS Description: This task involves ...
495 | 179 | 7.3.6 | LVDS Cable Installation | 2007-10-08 13:00 | 2007-10-22 12:00 | No | Irvine | Irvine-Undergrad[400%],MandS[2,880] | 2 wks | 0 | 0 | 2880 | 864 | 494,488 | 2880 | 3744 | WBS Description: This task involves ...
496 | 95 | 7.3.7 | DAQ Hardware Procurement | 2006-10-02 08:00 | 2006-12-28 12:00 | Yes | Fermilab | MandS[63,500] | 12 wks | 0 | 0 | 63500 | 0 | 616 | 63500 | 63500 | WBS Description: This task involves ...
497 | 705 | 7.3.8 | DAQ Hardware Procurement Complete | 2006-12-28 12:00 | 2006-12-28 12:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 496 | 0 | 0 | WBS Description: This milestone is for the ...
498 | 100 | 7.3.9 | DAQ Hardware Testing | 2006-12-28 13:00 | 2007-02-23 17:00 | Yes | Irvine | Irvine-Undergrad[25%],MandS[720] | 7.8 wks | 0 | 0 | 720 | 216 | 491,497 | 720 | 936 | WBS Description: This task involves ...
499 | 330 | 7.3.10 | DAQ Hardware Installation | 2007-09-27 08:00 | 2007-10-17 17:00 | No |  |  | 3 wks | 0 | 0 | 7530 | 891 |  | 7530 | 8421
500 | 101 | 7.3.10.1 | DAQ Hardware Labor | 2007-09-27 08:00 | 2007-10-17 17:00 | No | Irvine | Irvine-Undergrad[275%],MandS[2,970] | 3 wks | 0 | 0 | 2970 | 891 | 498,503SS | 2970 | 3861 | WBS Description: This task involves ...
501 | 328 | 7.3.10.2 | DAQ Hardware Materials | 2007-09-27 08:00 | 2007-10-17 17:00 | No | Fermilab | MandS[4,560] | 3 wks | 0 | 0 | 4560 | 0 | 500SS | 4560 | 4560 | WBS Description: This task involves ...
502 | 98 | 7.3.11 | DAQ Computer Procurement | 2007-08-01 08:00 | 2007-09-26 17:00 | Yes | Fermilab | MandS[18,000] | 8 wks | 0 | 0 | 18000 | 0 |  | 18000 | 18000 | WBS Description: This task involves ...
503 | 104 | 7.3.12 | DAQ Computer Installation | 2007-09-27 08:00 | 2007-10-29 17:00 | No | Irvine | Irvine-Physicist | 4.6 wks | 0 | 0 | 0 | 0 | 502,498,487 | 0 | 0 | WBS Description: This task involves ...
504 | 706 | 7.3.13 | DAQ Computer Installation Complete | 2007-10-29 17:00 | 2007-10-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 503 | 0 | 0 | WBS Description: This milestone is for the ...
505 | 106 | 7.3.14 | Slow Control Software | 2006-12-13 08:00 | 2007-04-03 17:00 | Yes | Irvine | Irvine-Physicist | 15.2 wks | 0 | 0 | 0 | 0 | 456,483,491 | 0 | 0 | WBS Description: This task involves ...
506 | 99 | 7.3.15 | DAQ Run Control Software | 2007-04-04 08:00 | 2007-07-26 17:00 | Yes | Irvine | Irvine-Physicist | 16 wks | 0 | 0 | 0 | 0 | 492,505,483,456,484,458 | 0 | 0 | WBS Description: This task involves ...
507 | 174 | 7.4 | Procure LV System | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[113,400] | 12 wks | 0 | 0 | 113400 | 0 | 457,617 | 113400 | 113400 | WBS Description: This task involves ...
508 | 800 | 8 | Frame, Absorbers and Stand | 2005-06-01 08:00 | 2008-06-11 17:00 | No |  |  | 152.6 wks | 209072 | 104360 | 624254 | 155636 |  | 833326 | 1093322
509 | 801 | 8.1 | Design | 2005-06-01 08:00 | 2006-08-02 17:00 | No |  |  | 59.2 wks | 172488 | 86068 | 31680 | 15840 |  | 204168 | 306076
510 | 802 | 8.1.1 | Design OD Frame (FY05) | 2005-06-01 08:00 | 2005-09-30 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%] | 17.2 wks | 352 | 0 | 0 | 0 |  | 352 | 352 | WBS Description: This task covers the design of the OD frame....
511 | 1293 | 8.1.2 | Design OD Frame (FY06) | 2005-10-03 08:00 | 2005-11-18 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%],MandS[9,240] | 7 wks | 0 | 0 | 9240 | 4620 | 510,615 | 9240 | 13860 | WBS Description: This task involves ...
512 | 803 | 8.1.3 | Design absorbers (FNAL) | 2005-10-17 08:00 | 2005-11-04 17:00 | Yes | Fermilab | DrafterF | 3 wks | 5160 | 2580 | 0 | 0 |  | 5160 | 7740 | WBS Description: Documentation of the design and engineering analysis of the absorber....
513 | 1422 | 8.1.4 | Design absorbers (Roch) | 2005-10-17 08:00 | 2005-11-04 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight,MandS[7,920] | 3 wks | 0 | 0 | 7920 | 3960 | 512SS | 7920 | 11880 | WBS Description: Design and engineering analysis of the absorber....
514 | 804 | 8.1.5 | Design Detector Stand and Bookend | 2005-10-17 08:00 | 2005-10-28 17:00 | Yes | Fermilab | MEF,DrafterF | 2 wks | 9120 | 4560 | 0 | 0 |  | 9120 | 13680 | WBS Description: This task involves final design of the detector stand. A first pass of the stand has been designed and analyzed for stresses. This short period of time will be needed to only adjust the design for the final location in the cavern....
515 | 1296 | 8.1.6 | Design Axial Bolts | 2005-10-31 08:00 | 2005-11-11 17:00 | Yes | Fermilab | MEF[20%],DrafterF[50%] | 2 wks | 2856 | 1428 | 0 | 0 | 514 | 2856 | 4284 | WBS Description: This task involves final design of the detector stand. A first pass of the stand has been designed and analyzed for stresses. This short period of time will be needed to only adjust the design for the final location in the cavern....
516 | 805 | 8.1.7 | Design Strongbacks (FNAL) | 2005-10-31 08:00 | 2006-01-23 17:00 | Yes | Fermilab | MEF[50%],DrafterF | 11 wks | 34540 | 17270 | 0 | 0 | 514 | 34540 | 51810 | WBS Description: This task involves design of the production strongback for assembling and manipulating the frames ...
517 | 1423 | 8.1.8 | Design Strongbacks (Roch) | 2005-10-31 08:00 | 2006-01-23 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%],MandS[14,520] | 11 wks | 0 | 0 | 14520 | 7260 | 516SS | 14520 | 21780 | WBS Description: This task involves design of the production strongback for assembling and manipulating the frames ...
518 | 806 | 8.1.9 | Design Cart modifications | 2006-01-24 08:00 | 2006-02-20 17:00 | Yes | Fermilab | MEF,DrafterF | 4 wks | 18240 | 9120 | 0 | 0 | 516 | 18240 | 27360 | WBS Description: This task is to redesign the cart from the Minos experiment to work for Minerva. Some small modifications to the connection system that allows it to hold a Minerva strongback are needed. Those changes need to be designed and analyze...
519 | 807 | 8.1.10 | Design Installation Procedure | 2006-02-21 08:00 | 2006-07-05 17:00 | Yes | Fermilab | MEF,DrafterF[50%] | 19 wks | 70300 | 35150 | 0 | 0 | 518,515 | 70300 | 105450 | WBS Description: This task involves moving the frames from their construction area to the Minos surface building, lowering them down the shaft to the cart, transporting them to the cavern, and finally hanging them. All of the engineering details for ...
520 | 808 | 8.1.11 | Design modifcations to the MINOS platform | 2006-07-06 08:00 | 2006-08-02 17:00 | Yes | Fermilab | MEF,DrafterF | 4 wks | 18240 | 9120 | 0 | 0 | 519 | 18240 | 27360 | WBS Description: This task is required to modify the existing platform for the Minos detector to allow installation of the Minerva detector. It will be necessry to resolve any mechanical interferences, including any required Minerva work platforms....
521 | 809 | 8.1.12 | Design Prototype detector stand | 2005-10-31 08:00 | 2005-11-18 17:00 | Yes | Fermilab | MEF,DrafterF | 3 wks | 13680 | 6840 | 0 | 0 | 514 | 13680 | 20520 | WBS Description: This task provides engineering and drafting to build a support stand for the prototype frame in some surface building. The amount of effort is small because a preliminary design of a support exists and only one frame will be the load...
522 | 810 | 8.2 | Procure Prototype Materials | 2005-11-07 08:00 | 2006-03-20 17:00 | No |  |  | 18 wks | 0 | 0 | 80180 | 16036 |  | 80180 | 96216
523 | 811 | 8.2.1 | Procure Prototype OD Frame Wedges | 2005-11-21 08:00 | 2005-12-20 17:00 | Yes | Fermilab | MandS[37,780] | 4 wks | 0 | 0 | 37780 | 7556 | 615,511 | 37780 | 45336 | WBS Description: This task involves purchase of prototype segments to make several frames for testing and measurement....
524 | 812 | 8.2.2 | Procure prototype HCAL steel | 2005-11-07 08:00 | 2006-01-06 17:00 | Yes | Fermilab | MandS[2,000] | 8 wks | 0 | 0 | 2000 | 400 | 512,615,513 | 2000 | 2400 | WBS Description: This task involves purchase of a prototype steel piece for the Hadron calorimeter sections of the detector. ...
525 | 813 | 8.2.3 | Procure prototype ECAL lead (Pb) | 2005-11-07 08:00 | 2006-02-06 17:00 | Yes | Fermilab | MandS[18,000] | 12 wks | 0 | 0 | 18000 | 3600 | 512,615 | 18000 | 21600 | WBS Description: This task involves purchase of lead sheets for the prototype program....
526 | 814 | 8.2.4 | Procure prototype HCAL upstream graphite | 2005-11-07 08:00 | 2006-02-06 17:00 | Yes | Fermilab | MandS[1,200] | 12 wks | 0 | 0 | 1200 | 240 | 512,615 | 1200 | 1440 | WBS Description: This task involves purchase of one prototype sheet of graphite for the prototype program. ...
527 | 1297 | 8.2.5 | Procure prototype axial bolts | 2005-11-14 08:00 | 2006-01-13 17:00 | Yes | Fermilab | MandS[200] | 8 wks | 0 | 0 | 200 | 40 | 515 | 200 | 240 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
528 | 1298 | 8.2.6 | Procure prototype ear pieces | 2005-11-14 08:00 | 2006-01-13 17:00 | Yes | Fermilab | MandS[1,000] | 8 wks | 0 | 0 | 1000 | 200 | 527SS | 1000 | 1200 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
529 | 815 | 8.2.7 | Procure prototype strongback | 2006-01-24 08:00 | 2006-03-20 17:00 | Yes | Fermilab | MandS[15,000] | 8 wks | 0 | 0 | 15000 | 3000 | 516 | 15000 | 18000 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
530 | 816 | 8.2.8 | Procure prototype detector stand and bookend | 2006-01-11 08:00 | 2006-02-01 17:00 | Yes | Fermilab | MandS[5,000] | 3 wks | 0 | 0 | 5000 | 1000 | 521 | 5000 | 6000 | WBS Description: This task involves ...
531 | 817 | 8.3 | Procure Production Materials | 2006-01-17 08:00 | 2008-03-25 17:00 | No |  |  | 110.4 wks | 0 | 0 | 488352 | 122088 |  | 488352 | 610440
532 | 818 | 8.3.1 | Procure production strongbacks | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[45,000] | 8 wks | 0 | 0 | 45000 | 11250 | 516,543,529,617,517 | 45000 | 56250 | WBS Description: This task involves purchase of three final version strongbacks for production of the detector. This allows for the posdsibility that the prototype is not used in the final production....
533 | 1299 | 8.3.2 | Procure 2 production stands and bookends | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[13,000] | 8 wks | 0 | 0 | 13000 | 3250 | 532SS | 13000 | 16250 | WBS Description: This task involves purchase of three final version strongbacks for production of the detector. This allows for the posdsibility that the prototype is not used in the final production....
534 | 820 | 8.3.3 | Purchase Stand and Bookend for cavern | 2007-10-01 08:00 | 2008-02-26 17:00 | No | Fermilab | MandS[25,000] | 20 wks | 0 | 0 | 25000 | 6250 | 530,617 | 25000 | 31250 | WBS Description: This task involves purchase of the final support structure for the detector in the cavern. The structure as designed weighs 30,000....
535 | 822 | 8.3.4 | Procure Narrow OD Wedges | 2007-11-28 08:00 | 2008-03-25 17:00 | No | Fermilab | MandS[80,712] | 16 wks | 0 | 0 | 80712 | 20178 | 532,617,533 | 80712 | 100890 | WBS Description: This task involves purchase of all the segments for the fabrication of the narrow frames for the detector....
536 | 823 | 8.3.5 | Procure Wide OD Wedges | 2007-11-28 08:00 | 2008-03-25 17:00 | No | Fermilab | MandS[175,759] | 16 wks | 0 | 0 | 175759 | 43939.75 | 535SS | 175759 | 219698.75 | WBS Description: This task involves purchase of all of the segments for the wide frames....
537 | 1300 | 8.3.6 | Procure axial bolts | 2006-01-17 08:00 | 2006-03-13 17:00 | No | Fermilab | MandS[5,600] | 8 wks | 0 | 0 | 5600 | 1400 | 527 | 5600 | 7000 | WBS Description: This task involves ...
538 | 824 | 8.3.7 | Procure ear pieces | 2007-10-01 08:00 | 2008-01-29 17:00 | No | Fermilab | MandS[26,640] | 16 wks | 0 | 0 | 26640 | 6660 | 539SS,528 | 26640 | 33300 | WBS Description: This task involves ...
539 | 825 | 8.3.8 | Procure HCAL Steel | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[39,836] | 8 wks | 0 | 0 | 39836 | 9959 | 524,617 | 39836 | 49795 | WBS Description: This task involves purchase of 23 pieces of steel for the upstream and downstreamHadron calorimeter sections of he detector. The steel plates are cut into hexagonal pieces that are 48" across the flat and 97" from point to point. To...
540 | 826 | 8.3.9 | Procure ECAL Pb | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[72,005] | 12 wks | 0 | 0 | 72005 | 18001.25 | 525,617 | 72005 | 90006.25 | WBS Description: This task involves purchase of all of the lead sheets for the nuclear targets and the EMCAL sections of the detector....
541 | 827 | 8.3.10 | Procure US HCAL Graphite | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[4,800] | 12 wks | 0 | 0 | 4800 | 1200 | 526,617 | 4800 | 6000 | WBS Description: This task involves purchase of the graphite sheets for the nuclear targets section of the detector....
542 | 828 | 8.4 | Outer Detector Frame Prototyping | 2006-02-02 08:00 | 2006-02-15 17:00 | No |  |  | 2 wks | 4904 | 2452 | 0 | 0 |  | 4904 | 7356
543 | 829 | 8.4.1 | Test Frame Welding | 2006-02-02 08:00 | 2006-02-08 17:00 | Yes | Fermilab | MTF,WelderF | 1 wk | 4640 | 2320 | 0 | 0 | 523,530 | 4640 | 6960 | WBS Description: This task involves Welding up the first prototype frame....
544 | 830 | 8.4.2 | Make Flatness Measurements | 2006-02-09 08:00 | 2006-02-15 17:00 | Yes | Fermilab | MTF[20%] | 1 wk | 264 | 132 | 0 | 0 | 543 | 264 | 396 | WBS Description: This is an engineering estimate for the time it would take a mechanical tech to measure the flatness of the prototype frame....
545 | 831 | 8.5 | Outer Detector Fabrication | 2008-03-26 08:00 | 2008-06-11 17:00 | No |  |  | 11 wks | 31680 | 15840 | 24042 | 1672 |  | 55722 | 73234
546 | 832 | 8.5.1 | Frame Welding | 2008-03-26 08:00 | 2008-06-11 17:00 | No | Fermilab | MandS[20,698],WelderF[50%],MTF Supervisor[50%] | 11 wks | 31680 | 15840 | 20698 | 0 | 532,536,535,538,544,537 | 52378 | 68218 | WBS Description: This task involves just welding up the frames. it is based on doing two frames a day. Keeping this pace is not a problem. The issue is whether the physicists can measure two a day in testing, and how that is done. ...
547 | 833 | 8.5.2 | QC measurements | 2008-03-26 08:00 | 2008-06-11 17:00 | No | Rochester | Roch Tech[0%],MandS[3,344] | 11 wks | 0 | 0 | 3344 | 1672 | 546SS | 3344 | 5016 | WBS Description: This task measures the quality (flatness) of the frames as they are made. It would allow problems to be found and repaired as necessary. The engineering estimate is for one person to spend 8 hours a week to look at all of the frames...
548 | 44 | 9 | Module Assembly and Installation | 2005-06-01 08:00 | 2008-05-20 17:00 | No |  |  | 149.6 wks | 226485.28 | 55413.592 | 332862 | 118190.5 |  | 559347.28 | 732951.372
549 | 975 | 9.1 | Assembly R&D | 2005-06-01 08:00 | 2006-09-27 17:00 | No |  |  | 67 wks | 112365.28 | 30594.392 | 117542 | 35822.5 |  | 229907.28 | 296324.172
550 | 978 | 9.1.1 | Rochester Prototypes | 2005-06-01 08:00 | 2005-12-28 12:00 | No |  |  | 29 wks | 29773.28 | 3924.792 | 14012 | 4125 |  | 43785.28 | 51835.072
551 | 1305 | 9.1.1.1 | Design and construct 1/12th scale model | 2005-06-01 08:00 | 2005-07-27 17:00 | Yes | Rochester | MandS[512],Roch Machinist[22%] | 8 wks | 3608 | 0 | 512 | 0 |  | 4120 | 4120 | WBS Description: This task involves ...
552 | 976 | 9.1.1.2 | Fabricate PMT Rack prototypes | 2005-07-28 08:00 | 2005-09-29 17:00 | Yes | Rochester | Roch ME[5%],MandS[1,000],Roch Tech[8%] | 9 wks | 2469.28 | 370.392 | 1000 | 150 | 551 | 3469.28 | 3989.672 | WBS Description: This task involves the PMT Rack Prototype...
553 | 1306 | 9.1.1.3 | Fabricate scale model prototypes | 2005-09-30 08:00 | 2005-10-27 17:00 | Yes | Rochester | MandS[2,000],Roch Tech[25%] | 4 wks | 1680 | 252 | 2000 | 300 | 552 | 3680 | 4232 | Prototype costs:...
554 | 977 | 9.1.1.4 | Prototype studies | 2005-10-28 08:00 | 2005-12-28 12:00 | Yes | Rochester | Roch ME[40%],Roch Tech,MandS[10,500],Bob Flight[40%] | 8 wks | 22016 | 3302.4 | 10500 | 3675 | 553 | 32516 | 39493.4 | WBS Description: This task involves ...
555 | 1307 | 9.1.1.5 | Prototype Studies Complete | 2005-12-28 12:00 | 2005-12-28 12:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 554 | 0 | 0
556 | 65 | 9.1.2 | Full Module Prototype Preparation | 2005-12-28 13:00 | 2006-08-29 17:00 | No |  |  | 34 wks | 47912 | 12797.6 | 94300 | 28190 |  | 142212 | 183199.6
557 | 1424 | 9.1.2.1 | Assembly Fixtures | 2005-12-29 13:00 | 2006-05-15 17:00 | No |  |  | 19 wks | 31520 | 7880 | 6900 | 1970 |  | 38420 | 48270
558 | 1428 | 9.1.2.1.1 | Purchase assembly tooling | 2005-12-29 13:00 | 2006-01-30 17:00 | No | Rochester | MandS[2,000] | 4 wks | 0 | 0 | 2000 | 500 | 554FS+1 day | 2000 | 2500 | WBS Description: This task involves ...
559 | 1425 | 9.1.2.1.2 | Design assembly fixtures | 2006-02-28 08:00 | 2006-04-24 17:00 | No | Rochester | Roch ME,Bob Flight | 8 wks | 21440 | 5360 | 0 | 0 | 558FS+4 wks | 21440 | 26800 | WBS Description: This task involves ...
560 | 1426 | 9.1.2.1.3 | Fabricate assembly fixtures | 2006-03-28 08:00 | 2006-05-08 17:00 | No | Rochester | Roch Tech | 6 wks | 10080 | 2520 | 0 | 0 | 559FS-4 wks | 10080 | 12600 | WBS Description: This task involves ...
561 | 1427 | 9.1.2.1.4 | Procure hardware for assembly fixtures | 2006-05-02 08:00 | 2006-05-15 17:00 | No | Rochester | MandS[4,900] | 2 wks | 0 | 0 | 4900 | 1470 | 560FS-1 wk | 4900 | 6370 | WBS Description: This task involves ...
562 | 1429 | 9.1.2.2 | PMT Rack for Prototyping | 2006-05-02 08:00 | 2006-06-20 17:00 | No |  |  | 7 wks | 4360 | 1308 | 0 | 0 |  | 4360 | 5668
563 | 1430 | 9.1.2.2.1 | Dsign PMT Rack | 2006-05-02 08:00 | 2006-05-08 17:00 | No | Rochester | Roch ME,Bob Flight | 1 wk | 2680 | 804 | 0 | 0 | 561SS | 2680 | 3484 | WBS Description: This task involves ...
564 | 1431 | 9.1.2.2.2 | Fabricate PMT Rack | 2006-06-14 08:00 | 2006-06-20 17:00 | No | Rochester | Roch Tech | 1 wk | 1680 | 504 | 0 | 0 | 563FS+5 wks,561 | 1680 | 2184 | WBS Description: This task involves ...
565 | 48 | 9.1.2.3 | Design and Construct Mapper | 2005-12-28 13:00 | 2006-08-29 17:00 | No |  |  | 34 wks | 12032 | 3609.6 | 87400 | 26220 |  | 99432 | 129261.6
566 | 336 | 9.1.2.3.1 | Mapper Design | 2005-12-28 13:00 | 2006-03-24 17:00 | Yes | Rochester | MandS[26,400] | 12 wks | 0 | 0 | 26400 | 7920 | 555 | 26400 | 34320 | WBS Description: This task involves ...
567 | 337 | 9.1.2.3.2 | Mapper Materials | 2006-03-27 08:00 | 2006-05-19 17:00 | Yes | Rochester | MandS[35,000] | 8 wks | 0 | 0 | 35000 | 10500 | 566 | 35000 | 45500 | WBS Description: This task involves ...
568 | 335 | 9.1.2.3.3 | Mapper Assembly | 2006-04-10 08:00 | 2006-08-29 17:00 | Yes | Rochester | MandS[26,000],Roch Lead Tech[32%],Dan Ruggiero[32%] | 20 wks | 12032 | 3609.6 | 26000 | 7800 | 567SS+2 wks | 38032 | 49441.6 | WBS Description: This task involves ...
569 | 52 | 9.1.3 | Prototype Assembly | 2006-06-21 08:00 | 2006-09-27 17:00 | No |  |  | 13.8 wks | 34680 | 13872 | 9230 | 3507.5 |  | 43910 | 61289.5
570 | 1432 | 9.1.3.1 | Deliver materials to Fermilab | 2006-06-21 08:00 | 2006-06-27 17:00 | No | Rochester | MandS[1,230] | 1 wk | 0 | 0 | 1230 | 307.5 | 564 | 1230 | 1537.5
571 | 333 | 9.1.3.2 | University Prototype assembly labor | 2006-08-30 08:00 | 2006-09-27 17:00 | Yes | Rochester | Roch Tech[250%] | 4 wks | 17640 | 7056 | 0 | 0 | 543,570,568,567 | 17640 | 24696 | WBS Description: This task involves ...
572 | 271 | 9.1.3.3 | Fermilab Prototype assembly work | 2006-08-30 08:00 | 2006-09-27 17:00 | Yes | Fermilab | MEF[150%],ES&H-F[175%],MandS[8,000] | 4 wks | 17040 | 6816 | 8000 | 3200 | 571SS | 25040 | 35056 | WBS Description: This task involves ...
573 | 1308 | 9.1.3.4 | Full Module Prototype Assembly Complete | 2006-09-27 17:00 | 2006-09-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 572 | 0 | 0
574 | 1309 | 9.1.4 | Prototype Mapping Complete | 2006-08-29 17:00 | 2006-08-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 568 | 0 | 0
575 | 47 | 9.2 | Module Assembly and Mapping | 2006-09-28 08:00 | 2008-05-20 17:00 | No |  |  | 82.6 wks | 113120 | 24819.2 | 145920 | 55968 |  | 259040 | 339827.2
576 | 1433 | 9.2.1 | Assembly Preparations | 2006-09-28 08:00 | 2007-12-27 17:00 | No |  |  | 62.6 wks | 43904 | 10976 | 56000 | 20000 |  | 99904 | 130880
577 | 1434 | 9.2.1.1 | Evaluate functional prototype assembly | 2006-09-28 08:00 | 2006-10-11 17:00 | No | Rochester | Roch ME,Bob Flight | 2 wks | 5360 | 1340 | 0 | 0 | 573 | 5360 | 6700
578 | 1435 | 9.2.1.2 | Revise assembly design | 2006-10-12 08:00 | 2006-11-24 17:00 | No | Rochester | Roch ME,Bob Flight | 6 wks | 17152 | 4288 | 0 | 0 | 577 | 17152 | 21440
579 | 980 | 9.2.1.3 | Purchase bulk assembly tooling | 2006-11-27 08:00 | 2006-12-26 12:00 | Yes | Rochester | MandS[6,000] | 4 wks | 0 | 0 | 6000 | 6000 | 578 | 6000 | 12000 | WBS Description: This task involves ...
580 | 1436 | 9.2.1.4 | Fabricate assembly fixtures | 2006-12-26 13:00 | 2007-02-08 17:00 | No | Rochester | MandS[15,000] | 6 wks | 0 | 0 | 15000 | 4500 | 579 | 15000 | 19500
581 | 1437 | 9.2.1.5 | Procure bulk assembly fixtures hardware | 2006-12-26 13:00 | 2007-01-25 17:00 | No | Rochester | MandS[15,000] | 4 wks | 0 | 0 | 15000 | 4500 | 580SS | 15000 | 19500
582 | 1438 | 9.2.1.6 | Fabricate PMT rack | 2006-12-26 13:00 | 2007-02-08 17:00 | No | Rochester | MandS[20,000] | 6 wks | 0 | 0 | 20000 | 5000 | 580SS | 20000 | 25000
583 | 1439 | 9.2.1.7 | Design PMT lifting jig | 2007-02-09 08:00 | 2007-02-22 17:00 | No | Rochester | Roch ME,Bob Flight | 2 wks | 5360 | 1340 | 0 | 0 | 582 | 5360 | 6700
584 | 1440 | 9.2.1.8 | Fabricate PMT lifting jig | 2007-02-23 08:00 | 2007-03-08 17:00 | No | Rochester | Roch Machinist | 2 wks | 4000 | 1000 | 0 | 0 | 583 | 4000 | 5000
585 | 1441 | 9.2.1.9 | Optimize scanner | 2006-10-12 08:00 | 2006-11-24 17:00 | No | Rochester | Roch Lead Tech,Dan Ruggiero | 6 wks | 12032 | 3008 | 0 | 0 | 578SS | 12032 | 15040
586 | 1442 | 9.2.1.10 | Ready To Assemble Module | 2007-12-27 17:00 | 2007-12-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 580,581,571,539,540,541,584 | 0 | 0
587 | 277 | 9.2.2 | Assemble Module (FNAL) | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Fermilab | ES&H-F[70%],AlignmentF[5%],MandS[16,000] | 20 wks | 0 | 0 | 16000 | 6400 | 256,616,56,573,274,586 | 16000 | 22400 | WBS Description: This task involves ...
588 | 278 | 9.2.3 | Assemble Module (Rochester) | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Rochester | Roch Tech[200%] | 20 wks | 69216 | 13843.2 | 0 | 0 | 587SS | 69216 | 83059.2 | WBS Description: This task involves ...
589 | 49 | 9.2.4 | Map Modules | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Fermilab | MandS[73,920] | 20 wks | 0 | 0 | 73920 | 29568 | 587SS,574,585 | 73920 | 103488 | WBS Description: This task is meant to include SAG internal module fiducial installation....
590 | 154 | 9.3 | Veto Wall | 2005-07-11 08:00 | 2007-08-14 17:00 | No |  |  | 105.8 wks | 1000 | 0 | 69400 | 26400 |  | 70400 | 96800
591 | 51 | 9.3.1 | Veto Wall Counters | 2005-07-11 08:00 | 2006-08-21 17:00 | No |  |  | 56.4 wks | 0 | 0 | 6000 | 2100 |  | 6000 | 8100
592 | 343 | 9.3.1.1 | Counter Checkout FY05 | 2005-07-11 08:00 | 2005-09-19 17:00 | Yes | Rochester | MandS[3,000] | 10 wks | 0 | 0 | 3000 | 1050 |  | 3000 | 4050 | WBS Description: This task involves ...
593 | 1443 | 9.3.1.2 | Counter Checkout FY06 | 2006-06-12 08:00 | 2006-08-21 17:00 | Yes | Rochester | MandS[3,000] | 10 wks | 0 | 0 | 3000 | 1050 | 592 | 3000 | 4050 | WBS Description: This task involves ...
594 | 165 | 9.3.2 | Veto Wall Structure | 2006-05-01 08:00 | 2007-08-07 17:00 | No |  |  | 64.2 wks | 1000 | 0 | 62200 | 23880 |  | 63200 | 87080
595 | 778 | 9.3.2.1 | Veto Wall design | 2006-05-01 08:00 | 2006-05-26 17:00 | Yes | Rochester | MandS[10,000] | 4 wks | 0 | 0 | 10000 | 4000 |  | 10000 | 14000 | WBS Description: This task involves ...
596 | 345 | 9.3.2.2 | Procure parts for Veto Wall structure | 2007-04-02 08:00 | 2007-04-27 17:00 | No | Rochester | MandS[40,200] | 4 wks | 0 | 0 | 40200 | 16080 | 595 | 40200 | 56280 | WBS Description: This task involves ...
597 | 344 | 9.3.2.3 | Fabricate Veto Wall structure | 2007-04-02 08:00 | 2007-07-24 17:00 | No | Rochester | MandS[4,000] | 16 wks | 0 | 0 | 4000 | 1000 | 616,596SS | 4000 | 5000 | WBS Description: This task involves ...
598 | 342 | 9.3.2.4 | Counter Shipping Crate & Handling | 2007-07-25 08:00 | 2007-08-07 17:00 | No | Rochester | MandS[9,000] | 2 wks | 1000 | 0 | 8000 | 2800 | 592,616,593,596,597 | 9000 | 11800 | WBS Description: This task involves ...
599 | 50 | 9.3.3 | Assemble Veto Wall at Fermilab | 2007-08-08 08:00 | 2007-08-14 17:00 | No | Rochester | MandS[1,200] | 1 wk | 0 | 0 | 1200 | 420 | 598 | 1200 | 1620 | WBS Description: This task involves ...
600 | 156 | 10 | Project Management | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 604032 | 181209.6 | 0 | 0 |  | 604032 | 785241.6
601 | 848 | 10.1 | Prototyping and Testing | 2005-06-01 08:00 | 2005-06-28 17:00 | No |  |  | 4 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This section brings together all of the prototyping tests that need to be done throughout the Project R&D phase. They are included here because the tests span several different sections and components. The management section presen...
602 | 849 | 10.1.1 | Single Plane Vertical Slice Test | 2005-06-01 08:00 | 2005-06-28 17:00 | Yes | Fermilab | Roch Physicist | 4 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This test was done at the very beginnig of the Project and tested the front end electronics and the light levels of the array....
603 | 852 | 10.1.2 | VST with non-glued fibers | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | This uses Eljen paint
604 | 853 | 10.1.3 | VST with glued fibers and Bicron paint | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | Test Bicron paint...
605 | 854 | 10.1.4 | VST with co-extruded scintillator | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | Mirror fibers for VST 2 with co-extruded scintillator...
606 | 216 | 10.2 | Management and Administration | 2005-06-01 08:00 | 2008-09-26 17:00 | No |  |  | 167.6 wks | 604032 | 181209.6 | 0 | 0 |  | 604032 | 785241.6
607 | 646 | 10.2.1 | FY05 Project Management and Administration | 2005-06-01 08:00 | 2005-09-29 17:00 | Yes | Fermilab | PhysicistF[340%] | 17 wks | 0 | 0 | 0 | 0 | 613 | 0 | 0 | WBS Description: This task involves ...
608 | 934 | 10.2.2 | FY06 Project Management and Administration | 2005-10-03 08:00 | 2006-09-29 17:00 | Yes | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50.2 wks | 201344 | 60403.2 | 0 | 0 | 607 | 201344 | 261747.2 | WBS Description: This task involves ...
609 | 935 | 10.2.3 | FY07 Project Management and Administration | 2006-10-02 08:00 | 2007-09-28 17:00 | No | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50.2 wks | 201344 | 60403.2 | 0 | 0 | 608 | 201344 | 261747.2 | WBS Description: This task involves ...
610 | 936 | 10.2.4 | FY08 Project Management and Administration | 2007-10-01 08:00 | 2008-09-26 17:00 | No | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50 wks | 201344 | 60403.2 | 0 | 0 | 609 | 201344 | 261747.2 | WBS Description: This task involves ...
611 | 982 | 10.2.5 | Project Management and Administration Complete | 2008-09-26 17:00 | 2008-09-26 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 610,655 | 0 | 0
612 | 723 | 10.3 | Project Milestones | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks | 0 | 0 | 0 | 0 |  | 0 | 0
613 | 724 | 10.3.1 | Start MINERvA Project | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone is for the start date of the MINERvA Project....
614 | 725 | 10.3.2 | Preproduction Funds Released | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of preproduction funds by Fermilab....
615 | 726 | 10.3.3 | FY06 Funds Released by Fermilab | 2005-10-03 08:00 | 2005-10-03 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY06 funds by Fermilab....
616 | 727 | 10.3.4 | FY07 Construction Funds Released | 2006-10-02 08:00 | 2006-10-02 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY07 funds by Fermilab....
617 | 728 | 10.3.5 | FY08 Construction Funds Released | 2007-10-01 08:00 | 2007-10-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY08 funds by Fermilab....
618 | 1291 | 10.3.6 | MINERvA Detector Ready For Installation | 2008-06-11 17:00 | 2008-06-11 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 360,507,547,588,587,353 | 0 | 0 | WBS Description: This milestone is for the finish date of the MINERvA Project....
619 | 729 | 10.3.7 | Finish MINERvA Project | 2009-01-05 17:00 | 2009-01-05 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 654,631,653,618,611 | 0 | 0 | WBS Description: This milestone is for the finish date of the MINERvA Project....
620 | 983 | 11 | Installation and Infrastructure | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks | 286608 | 45323.2 | 235532 | 25644 |  | 522140 | 593107.2
621 | 984 | 11.1 | Scintilator Extrusion | 2005-09-30 08:00 | 2005-11-28 17:00 | No |  |  | 8 wks | 0 | 0 | 155117 | 0 |  | 155117 | 155117
622 | 988 | 11.1.1 | Purchase R&D Polystyrene | 2005-09-30 08:00 | 2005-11-28 17:00 | No | Fermilab | MandS[65,117] | 8 wks | 0 | 0 | 65117 | 0 | 4,5,6 | 65117 | 65117 | WBS Description: This task involves the purchase of polystyrene pettles, dopants, titanium dioxide pellets, labels, and other consumables for ID scintilattor production....
623 | 989 | 11.1.2 | Purchase Construction Scintillator Consumables | 2005-09-30 08:00 | 2005-11-28 17:00 | No | Fermilab | MandS[90,000] | 8 wks | 0 | 0 | 90000 | 0 | 622SS | 90000 | 90000 | WBS Description: Purchase of dopants for entire experiment....
624 | 896 | 11.2 | Purchase specialized miling machine for work at Tufts | 2005-06-01 08:00 | 2005-11-03 17:00 | No | Fermilab |  | 22 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: Purchase of a milling machine, at a cost of $30,000, that will be used by Tufts University to produce PMT Boxes....
625 | 171 | 11.3 | Electronics Infrastructure | 2007-10-01 08:00 | 2008-07-17 17:00 | No |  |  | 40 wks | 79168 | 0 | 57235 | 22894 |  | 136403 | 159297
626 | 172 | 11.3.1 | Quiet Power Panel Installation | 2007-10-01 08:00 | 2007-11-09 17:00 | No | Fermilab | T&M ElectricialF[225%],MandS[56,020] | 6 wks | 0 | 0 | 56020 | 22408 | 456,617 | 56020 | 78428 | WBS Description: Installation of the quiet power panel by T&M electricians at Fermilab....
627 | 600 | 11.3.2 | Install Electronics Racks - Rigging | 2007-12-28 08:00 | 2007-12-28 17:00 | No | Fermilab | T&M Rigging Crew[70%],MandS[1,215] | 1 day | 0 | 0 | 1215 | 486 | 626,507 | 1215 | 1701 | WBS Description: This task covers the rigging needed to install the electronic racks....
628 | 175 | 11.3.3 | Install LV System (through fanouts) | 2007-12-31 08:00 | 2008-01-15 17:00 | No | Fermilab | EEF | 2 wks | 7008 | 0 | 0 | 0 | 626,627 | 7008 | 7008 | WBS Description: This task involves ...
629 | 180 | 11.3.4 | LV Cable Installation | 2008-01-16 08:00 | 2008-01-30 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 628 | 0 | 0 | WBS Description: This task involves ...
630 | 210 | 11.3.5 | Electronics System Integration | 2008-03-26 08:00 | 2008-07-17 17:00 | No | Fermilab | EEF,ETF | 16 wks | 72160 | 0 | 0 | 0 | 506,505,500,488,628,501,629,504,467 | 72160 | 72160 | WBS Description: This task involves ...
631 | 699 | 11.4 | DAQ System Installation Complete | 2008-07-17 17:00 | 2008-07-17 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 495,630 | 0 | 0 | WBS Description: This milestone is for the ...
632 | 986 | 11.5 | Stand Structure Installation | 2006-10-02 08:00 | 2008-07-24 17:00 | No |  |  | 91.2 wks | 50198 | 15844 | 23180 | 2750 |  | 73378 | 91972
633 | 834 | 11.5.1 | Installation of Prototype | 2008-06-12 08:00 | 2008-07-02 17:00 | No |  |  | 3 wks | 17584 | 8792 | 2500 | 625 |  | 20084 | 29501
634 | 835 | 11.5.1.1 | Core drill Anchors for stand | 2008-06-12 08:00 | 2008-06-18 17:00 | No | Fermilab | MandS[2,500],MTF[20%] | 1 wk | 264 | 132 | 2500 | 625 | 546,547 | 2764 | 3521 | WBS Description: This task is to drill and install floor anchors for the prototype stand. It assumes an outside contractor doing the core drilling and techs installing the anchors....
635 | 1301 | 11.5.1.2 | Install welding stand | 2008-06-19 08:00 | 2008-06-25 17:00 | No | Fermilab | MTF Sr[200%],MTF Supervisor,WelderF | 1 wk | 10320 | 5160 | 0 | 0 | 634 | 10320 | 15480 | WBS Description: This task is to install a prototype bookend and stand in the assembly area. The estimate is an enginering estimate do in consultation with the Tech Supervisor....
636 | 836 | 11.5.1.3 | Install stand and Bookend | 2008-06-26 08:00 | 2008-07-02 17:00 | No | Fermilab | MTF Sr[200%],MTF Supervisor | 1 wk | 7000 | 3500 | 0 | 0 | 634,635 | 7000 | 10500 | WBS Description: This task is to install a prototype bookend and stand in the assembly area. The estimate is an enginering estimate do in consultation with the Tech Supervisor....
637 | 1302 | 11.5.2 | Installation of Production Equipment | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  |  | 1 wk | 7264 | 3632 | 2500 | 625 |  | 9764 | 14021
638 | 1303 | 11.5.2.1 | Core drill Anchors for stand | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  | MandS[2,500],MTF[20%] | 1 wk | 264 | 132 | 2500 | 625 | 533 | 2764 | 3521
639 | 1304 | 11.5.2.2 | Install stand and Bookend | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  | MTF Sr[200%],MTF Supervisor | 1 wk | 7000 | 3500 | 0 | 0 | 533 | 7000 | 10500
640 | 837 | 11.5.3 | Installation In The Cavern | 2006-10-02 08:00 | 2008-07-24 17:00 | No |  |  | 91.2 wks | 25350 | 3420 | 18180 | 1500 |  | 43530 | 48450
641 | 838 | 11.5.3.1 | Installation of the Stand and Bookend | 2008-07-03 08:00 | 2008-07-24 17:00 | No |  |  | 3 wks | 6840 | 3420 | 5000 | 1250 |  | 11840 | 16510
642 | 839 | 11.5.3.1.1 | Core Drill for anchors | 2008-07-03 08:00 | 2008-07-10 17:00 | No | Fermilab | MandS[5,000],MTF[50%] | 1 wk | 660 | 330 | 5000 | 1250 | 636,534,638,639 | 5660 | 7240 | WBS Description: This task involves core drilling holes for floor anchors and using a Fermilab mechancial tech to install them....
643 | 840 | 11.5.3.1.2 | Position the stand | 2008-07-11 08:00 | 2008-07-17 17:00 | No | Fermilab | MTF,AlignmentF[50%] | 1 wk | 1320 | 660 | 0 | 0 | 642 | 1320 | 1980 | WBS Description: This task involves setting the stand in position and marking the location of the anchor holes....
644 | 841 | 11.5.3.1.3 | Align and weld the stand in place | 2008-07-18 08:00 | 2008-07-24 17:00 | No | Fermilab | WelderF[50%],MTF[150%],MTF Supervisor[50%] | 1 wk | 4860 | 2430 | 0 | 0 | 643 | 4860 | 7290 | WBS Description: This task involves Assembling the stand in the cavern from the various pieces. This stand weighs about 15 tons....
645 | 842 | 11.5.3.2 | Modify Cart | 2006-10-02 08:00 | 2006-10-06 17:00 | No |  |  | 1 wk | 5910 | 0 | 1000 | 250 |  | 6910 | 7160
646 | 843 | 11.5.3.2.1 | Technician Cart Modification | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | MTF[200%],MTF Supervisor,MandS[1,000] | 1 wk | 5080 | 0 | 1000 | 250 | 516,616 | 6080 | 6330 | WBS Description: This task involves the mechanical tech work to modify the Minos cart to support Minerva strongbacks and frames. The cart is structurally sound for the load and only needs to have the connections between cart and strongback modified....
647 | 844 | 11.5.3.2.2 | Cart Welding and Rigging | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | WelderF[25%] | 1 wk | 830 | 0 | 0 | 0 | 646SS | 830 | 830 | WBS Description: This task involves the welding to do the cart modifications....
648 | 845 | 11.5.3.3 | MINOS Electronics Platform Modification | 2006-10-02 08:00 | 2006-10-13 17:00 | No |  |  | 2 wks | 12600 | 0 | 12180 | 0 |  | 24780 | 24780
649 | 846 | 11.5.3.3.1 | Procure Frame and Grating | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | MandS[12,180] | 1 wk | 0 | 0 | 12180 | 0 | 514,616,520 | 12180 | 12180 | WBS Description: This task involves purchasing the framing material and grating required to modify the platform....
650 | 847 | 11.5.3.3.2 | Modify Platform | 2006-10-09 08:00 | 2006-10-13 17:00 | No | Fermilab | MTF Sr[300%],MTF Supervisor,WelderF | 1 wk | 12600 | 0 | 0 | 0 | 649 | 12600 | 12600 | WBS Description: This task involves modifying the electroncis platform in place now for Minos to make room for the Minerva detector....
651 | 987 | 11.6 | Module Installation | 2007-08-15 08:00 | 2009-01-05 17:00 | No |  |  | 69.4 wks | 83544 | 0 | 0 | 0 |  | 83544 | 83544
652 | 169 | 11.6.1 | Module Installation | 2008-10-20 08:00 | 2009-01-05 17:00 | No | Fermilab | MTF Supervisor,MTF[400%] | 10 wks | 78744 | 0 | 0 | 0 | 589FF+3 days,644,647,587,360,646,650,384,392,394,395 | 78744 | 78744 | WBS Description: This task involves ...
653 | 354 | 11.6.2 | Final Detector Alignment | 2008-10-22 08:00 | 2009-01-05 17:00 | No | Fermilab | AlignmentF[30%] | 9.6 wks | 0 | 0 | 0 | 0 | 652SS+2 days | 0 | 0 | WBS Description: This task involves ...
654 | 168 | 11.6.3 | Install Veto Wall | 2007-08-15 08:00 | 2007-08-21 17:00 | No | Fermilab | MTF[225%],MTF Supervisor[75%] | 1 wk | 4800 | 0 | 0 | 0 | 599 | 4800 | 4800 | WBS Description: This task involves ...
655 | 350 | 11.7 | Installation Manager | 2006-10-02 08:00 | 2008-09-25 17:00 | No | Fermilab | MEF[25%] | 100 wks | 73698 | 29479.2 | 0 | 0 | 607FF,616SS | 73698 | 103177.2 | WBS Description: This task involves ...

## wbs 7
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
432 | 76 | 7 | Electronics and DAQ | 2005-08-15 08:00 | 2008-03-25 17:00 | No |  |  | 131.2 wks | 281952 | 0 | 782330 | 21624 |  | 1064282 | 1085906
433 | 19 | 7.1 | Front-End Electronics | 2005-08-15 08:00 | 2008-03-25 17:00 | No |  |  | 131.2 wks | 169992 | 0 | 443050 | 16953 |  | 613042 | 629995
434 | 942 | 7.1.1 | FE First Prototytpe | 2005-08-15 08:00 | 2005-11-07 17:00 | No |  |  | 12 wks | 5840 | 0 | 0 | 0 |  | 5840 | 5840
435 | 943 | 7.1.1.1 | Design and build 16 channel board | 2005-08-15 08:00 | 2005-08-26 17:00 | Yes | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This task involves ...
436 | 951 | 7.1.1.2 | High Voltage first prototype | 2005-08-29 08:00 | 2005-09-12 17:00 | Yes | Fermilab | EEF | 2 wks | 5840 | 0 | 0 | 0 | 435 | 5840 | 5840 | WBS Description: This task involves ...
437 | 974 | 7.1.1.3 | Test HV Prototype | 2005-09-13 08:00 | 2005-11-07 17:00 | Yes | Fermilab |  | 8 wks | 0 | 0 | 0 | 0 | 436 | 0 | 0
438 | 945 | 7.1.2 | TriP Procurement | 2005-10-28 08:00 | 2006-04-21 17:00 | No |  |  | 24 wks | 0 | 0 | 77000 | 11200 |  | 77000 | 88200
439 | 973 | 7.1.2.1 | TriP-T Decision Finalized | 2005-10-28 08:00 | 2005-10-28 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0
440 | 948 | 7.1.2.2 | TriP Refabrication | 2005-10-28 08:00 | 2006-01-27 17:00 | Yes | Fermilab | MandS[50,000] | 12 wks | 0 | 0 | 50000 | 10000 | 439 | 50000 | 60000 | WBS Description: This task involves production and packaginf of TriP chips (or possibly TriPt)....
441 | 949 | 7.1.2.3 | TriP Chip packaging | 2006-01-30 08:00 | 2006-02-24 17:00 | Yes | Fermilab | MandS[12,000] | 4 wks | 0 | 0 | 12000 | 1200 | 440 | 12000 | 13200 | WBS Description: This task involves ...
442 | 950 | 7.1.2.4 | TriP Checkout | 2006-02-27 08:00 | 2006-04-21 17:00 | Yes | Fermilab | MandS[15,000] | 8 wks | 0 | 0 | 15000 | 0 | 441 | 15000 | 15000 | WBS Description: This task involves ...
443 | 940 | 7.1.3 | FE 2nd prototype | 2006-01-02 08:00 | 2006-07-06 17:00 | No |  |  | 26 wks | 51708 | 0 | 12120 | 0 |  | 63828 | 63828
444 | 109 | 7.1.3.1 | FE 2nd Prototype Design | 2006-01-02 08:00 | 2006-03-14 17:00 | Yes | Fermilab | EEF[50%],ETF[25%] | 10 wks | 18300 | 0 | 0 | 0 |  | 18300 | 18300 | WBS Description: This task involves ...
445 | 701 | 7.1.3.2 | Begin Front End 2nd Prototype Production | 2006-03-14 17:00 | 2006-03-14 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 444 | 0 | 0 | WBS Description: This milestone is for the ...
446 | 88 | 7.1.3.3 | FE 2nd Prototype Production | 2006-03-15 08:00 | 2006-04-11 17:00 | Yes | Fermilab | MandS[12,120] | 4 wks | 0 | 0 | 12120 | 0 | 444,445 | 12120 | 12120 | WBS Description: This task involves ...
447 | 605 | 7.1.3.4 | FE 2nd Prototype Firmware | 2006-03-01 08:00 | 2006-05-23 17:00 | Yes | Fermilab | EEF[20%] | 12 wks | 7008 | 0 | 0 | 0 | 444SS+2 mons | 7008 | 7008 | WBS Description: This task involves ...
448 | 87 | 7.1.3.5 | FE 2nd Prototype Testing | 2006-04-12 08:00 | 2006-07-06 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 12 wks | 26400 | 0 | 0 | 0 | 446 | 26400 | 26400 | WBS Description: This task involves ...
449 | 967 | 7.1.3.6 | 2nd Prototype Testing Complete | 2006-07-06 17:00 | 2006-07-06 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 448 | 0 | 0 | WBS Description: This milestone is for the ...
450 | 946 | 7.1.4 | Base Second Prototype | 2005-10-17 08:00 | 2006-03-07 17:00 | No |  |  | 19.2 wks | 2648 | 0 | 250 | 0 |  | 2898 | 2898
451 | 616 | 7.1.4.1 | Provide 5 Feedthough board to Tufts | 2005-10-17 08:00 | 2005-11-11 17:00 | No | Fermilab | MandS[250],ETF[25%],EEF[10%] | 4 wks | 2648 | 0 | 250 | 0 |  | 2898 | 2898 | WBS Description: This task involves ...
452 | 952 | 7.1.4.2 | Design base second prototype | 2005-11-08 08:00 | 2005-12-07 17:00 | Yes | Fermilab |  | 4 wks | 0 | 0 | 0 | 0 | 437 | 0 | 0 | WBS Description: This task involves ...
453 | 953 | 7.1.4.3 | Produce base second prototype | 2005-12-08 08:00 | 2006-01-09 17:00 | Yes | Fermilab |  | 4 wks | 0 | 0 | 0 | 0 | 452 | 0 | 0 | WBS Description: This task involves ...
454 | 954 | 7.1.4.4 | Test base second prototype | 2006-01-10 08:00 | 2006-03-07 17:00 | Yes | Fermilab |  | 8 wks | 0 | 0 | 0 | 0 | 453 | 0 | 0 | WBS Description: This task involves ...
455 | 955 | 7.1.5 | FE Production | 2006-07-07 08:00 | 2008-03-25 17:00 | No |  |  | 86.2 wks | 109796 | 0 | 353680 | 5753 |  | 463476 | 469229
456 | 64 | 7.1.5.1 | FE Final Design (post 2nd prototype) | 2006-07-07 08:00 | 2006-09-22 17:00 | Yes | Fermilab | EEF,ETF[50%] | 11 wks | 40260 | 0 | 0 | 0 | 481,448,482,454 | 40260 | 40260 | WBS Description: This task involves ...
457 | 173 | 7.1.5.2 | Design LV Distribution System | 2006-09-25 08:00 | 2007-01-18 17:00 | Yes | Fermilab | EEF | 78 days | 49056 | 0 | 0 | 0 | 456 | 49056 | 49056 | WBS Description: This task involves ...
458 | 107 | 7.1.5.3 | FE Board Firmware | 2006-08-04 08:00 | 2006-09-29 17:00 | Yes | Fermilab | EEF[50%] | 8 wks | 11680 | 0 | 0 | 0 | 456SS+1 mon,447 | 11680 | 11680 | WBS Description: This task involves ...
459 | 606 | 7.1.5.4 | FE Board commissioning | 2006-10-02 08:00 | 2006-10-27 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 4 wks | 8800 | 0 | 0 | 0 | 458 | 8800 | 8800 | WBS Description: This task involves ...
460 | 966 | 7.1.5.5 | FE Component Procurement | 2006-09-25 08:00 | 2006-11-17 17:00 | No | Pitt |  | 8 wks | 0 | 0 | 0 | 0 | 456 | 0 | 0 | WBS Description: This task involves ...
461 | 968 | 7.1.5.6 | Begin Front End Production | 2006-10-27 17:00 | 2006-10-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 459,442 | 0 | 0 | WBS Description: This milestone is for the ...
462 | 91 | 7.1.5.7 | FE Board Initial Production | 2006-11-20 08:00 | 2007-01-22 17:00 | Yes | Fermilab | MandS[169,680] | 8 wks | 0 | 0 | 169680 | 0 | 460,461 | 169680 | 169680 | WBS Description: This task involves ...
463 | 83 | 7.1.5.8 | FE Test Stand Development | 2006-11-20 08:00 | 2007-01-22 17:00 | Yes | Pitt | Pitt-Electronics Shop[70%],MandS[7,470] | 8 wks | 0 | 0 | 7470 | 2988 | 462SS | 7470 | 10458 | WBS Description: This task involves ...
464 | 84 | 7.1.5.9 | FE Board Final Production | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[169,680] | 8 wks | 0 | 0 | 169680 | 0 | 463,617,462 | 169680 | 169680 | WBS Description: This task involves ...
465 | 965 | 7.1.5.10 | FE Board Checkout with Testing | 2007-11-28 08:00 | 2008-03-11 17:00 | No | Pitt | Pitt-Undergrad,MandS[6,600] | 14 wks | 0 | 0 | 6600 | 2640 | 464 | 6600 | 9240 | WBS Description: This task involves ...
466 | 704 | 7.1.5.11 | FE Board Production Complete | 2008-03-11 17:00 | 2008-03-11 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 465 | 0 | 0 | WBS Description: This milestone is for the ...
467 | 972 | 7.1.5.12 | Ship FE Boards to Fermilab | 2008-03-12 08:00 | 2008-03-25 17:00 | No | Pitt | MandS[250] | 2 wks | 0 | 0 | 250 | 125 | 466 | 250 | 375
468 | 956 | 7.1.6 | PMT Base Production | 2006-03-08 08:00 | 2006-05-16 17:00 | No |  |  | 10 wks | 0 | 0 | 0 | 0 |  | 0 | 0
469 | 957 | 7.1.6.1 | PMT Base final design | 2006-03-08 08:00 | 2006-03-14 17:00 | Yes | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 454 | 0 | 0 | WBS Description: This task involves ...
470 | 958 | 7.1.6.2 | PMT Base commissioning | 2006-03-15 08:00 | 2006-03-21 17:00 | Yes | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 469 | 0 | 0 | WBS Description: This task involves ...
471 | 959 | 7.1.6.3 | PMT Base Initial production | 2006-03-22 08:00 | 2006-03-28 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 470 | 0 | 0 | WBS Description: This task involves ...
472 | 960 | 7.1.6.4 | PMT Base test stand development | 2006-03-29 08:00 | 2006-04-04 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 471 | 0 | 0 | WBS Description: This task involves ...
473 | 961 | 7.1.6.5 | PMT Base final production | 2006-04-05 08:00 | 2006-04-11 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 472 | 0 | 0 | WBS Description: This task involves ...
474 | 964 | 7.1.6.6 | PMT Base checkout with testing | 2006-04-12 08:00 | 2006-04-18 17:00 | No | Pitt |  | 1 wk | 0 | 0 | 0 | 0 | 473 | 0 | 0 | WBS Description: This task involves ...
475 | 962 | 7.1.6.7 | PMT Base Production Complete | 2006-04-18 17:00 | 2006-04-18 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 474 | 0 | 0 | WBS Description: This milestone is for the ...
476 | 24 | 7.1.6.8 | Ship PMT Bases | 2006-04-19 08:00 | 2006-05-16 17:00 | No | Pitt |  | 4 wks | 0 | 0 | 0 | 0 | 475 | 0 | 0 | WBS Description: This task involves ...
477 | 67 | 7.2 | Clock and Readout Control (CROC) Board | 2005-10-17 08:00 | 2007-10-08 12:00 | No |  |  | 99.5 wks | 111960 | 0 | 59120 | 1836 |  | 171080 | 172916
478 | 27 | 7.2.1 | CROC Design | 2005-10-17 08:00 | 2006-02-13 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 16 wks | 35200 | 0 | 0 | 0 |  | 35200 | 35200 | WBS Description: This task involves ...
479 | 702 | 7.2.2 | Begin CROC Prototype Production | 2006-02-13 17:00 | 2006-02-13 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 478 | 0 | 0 | WBS Description: This milestone is for the ...
480 | 85 | 7.2.3 | CROC Prototype Production | 2006-02-14 08:00 | 2006-03-27 17:00 | Yes | Fermilab | MandS[5,000] | 6 wks | 0 | 0 | 5000 | 0 | 479 | 5000 | 5000 | WBS Description: This task involves ...
481 | 86 | 7.2.4 | CROC Protoype Testing | 2006-04-12 08:00 | 2006-05-23 17:00 | Yes | Irvine | MandS[3,240],Irvine-Undergrad[150%] | 6 wks | 0 | 0 | 3240 | 972 | 480,446,490,491 | 3240 | 4212 | WBS Description: This task involves ...
482 | 700 | 7.2.5 | Prototype System Integration Test Complete | 2006-07-06 17:00 | 2006-07-06 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 448,481,449 | 0 | 0 | WBS Description: This milestone is for the ...
483 | 89 | 7.2.6 | CROC Final Design | 2006-09-25 08:00 | 2006-12-12 17:00 | Yes | Fermilab | EEF[50%],ETF[50%] | 11 wks | 24200 | 0 | 0 | 0 | 481,456,482 | 24200 | 24200 | WBS Description: This task involves ...
484 | 108 | 7.2.7 | CROC Firmware | 2006-09-25 08:00 | 2007-01-26 17:00 | Yes | Fermilab | EEF | 84 days | 52560 | 0 | 0 | 0 | 483SS | 52560 | 52560 | WBS Description: This task involves ...
485 | 28 | 7.2.8 | CROC Board Production | 2006-12-13 08:00 | 2007-02-12 17:00 | No | Fermilab | MandS[48,000] | 8 wks | 0 | 0 | 48000 | 0 | 483 | 48000 | 48000 | WBS Description: This task involves ...
486 | 703 | 7.2.9 | CROC Board Production Complete | 2007-02-12 17:00 | 2007-02-12 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 485 | 0 | 0 | WBS Description: This milestone is for the ...
487 | 29 | 7.2.10 | CROC Board Checkout | 2007-03-20 08:00 | 2007-04-23 17:00 | No | Irvine | Irvine-Undergrad,MandS[1,800] | 5 wks | 0 | 0 | 1800 | 540 | 485,492,484,458,486 | 1800 | 2340 | WBS Description: This task involves ...
488 | 102 | 7.2.11 | CROC Board Installation | 2007-09-27 08:00 | 2007-10-08 12:00 | No | Irvine | Irvine-Undergrad[200%],MandS[1,080] | 1.5 wks | 0 | 0 | 1080 | 324 | 500SS,487 | 1080 | 1404 | WBS Description: This task involves ...
489 | 69 | 7.3 | DAQ and Slow Control | 2005-10-03 08:00 | 2007-10-29 17:00 | No |  |  | 104.6 wks | 0 | 0 | 166760 | 2835 |  | 166760 | 169595
490 | 33 | 7.3.1 | DAQ Prototype Hardware Procurement | 2005-10-03 08:00 | 2005-11-29 17:00 | Yes | Fermilab | MandS[55,500] | 8 wks | 0 | 0 | 55500 | 0 | 615 | 55500 | 55500 | WBS Description: This task involves ...
491 | 92 | 7.3.2 | VME Interface Software | 2005-11-30 08:00 | 2005-12-29 12:00 | Yes | Irvine |  | 4 wks | 0 | 0 | 0 | 0 | 490 | 0 | 0 | WBS Description: This task involves ...
492 | 34 | 7.3.3 | DAQ Readout Software | 2006-09-25 08:00 | 2007-03-19 17:00 | Yes | Irvine |  | 24 wks | 0 | 0 | 0 | 0 | 483SS,456 | 0 | 0 | WBS Description: This task involves ...
493 | 96 | 7.3.4 | LVDS Cable Procurement | 2006-10-02 08:00 | 2006-11-28 17:00 | No | Fermilab | MandS[15,750] | 8 wks | 0 | 0 | 15750 | 0 | 616 | 15750 | 15750 | WBS Description: This task involves ...
494 | 97 | 7.3.5 | LVDS Cable Testing | 2006-11-29 08:00 | 2006-12-26 17:00 | No | Irvine | Irvine-Undergrad[200%],MandS[2,880] | 3.7 wks | 0 | 0 | 2880 | 864 | 493 | 2880 | 3744 | WBS Description: This task involves ...
495 | 179 | 7.3.6 | LVDS Cable Installation | 2007-10-08 13:00 | 2007-10-22 12:00 | No | Irvine | Irvine-Undergrad[400%],MandS[2,880] | 2 wks | 0 | 0 | 2880 | 864 | 494,488 | 2880 | 3744 | WBS Description: This task involves ...
496 | 95 | 7.3.7 | DAQ Hardware Procurement | 2006-10-02 08:00 | 2006-12-28 12:00 | Yes | Fermilab | MandS[63,500] | 12 wks | 0 | 0 | 63500 | 0 | 616 | 63500 | 63500 | WBS Description: This task involves ...
497 | 705 | 7.3.8 | DAQ Hardware Procurement Complete | 2006-12-28 12:00 | 2006-12-28 12:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 496 | 0 | 0 | WBS Description: This milestone is for the ...
498 | 100 | 7.3.9 | DAQ Hardware Testing | 2006-12-28 13:00 | 2007-02-23 17:00 | Yes | Irvine | Irvine-Undergrad[25%],MandS[720] | 7.8 wks | 0 | 0 | 720 | 216 | 491,497 | 720 | 936 | WBS Description: This task involves ...
499 | 330 | 7.3.10 | DAQ Hardware Installation | 2007-09-27 08:00 | 2007-10-17 17:00 | No |  |  | 3 wks | 0 | 0 | 7530 | 891 |  | 7530 | 8421
500 | 101 | 7.3.10.1 | DAQ Hardware Labor | 2007-09-27 08:00 | 2007-10-17 17:00 | No | Irvine | Irvine-Undergrad[275%],MandS[2,970] | 3 wks | 0 | 0 | 2970 | 891 | 498,503SS | 2970 | 3861 | WBS Description: This task involves ...
501 | 328 | 7.3.10.2 | DAQ Hardware Materials | 2007-09-27 08:00 | 2007-10-17 17:00 | No | Fermilab | MandS[4,560] | 3 wks | 0 | 0 | 4560 | 0 | 500SS | 4560 | 4560 | WBS Description: This task involves ...
502 | 98 | 7.3.11 | DAQ Computer Procurement | 2007-08-01 08:00 | 2007-09-26 17:00 | Yes | Fermilab | MandS[18,000] | 8 wks | 0 | 0 | 18000 | 0 |  | 18000 | 18000 | WBS Description: This task involves ...
503 | 104 | 7.3.12 | DAQ Computer Installation | 2007-09-27 08:00 | 2007-10-29 17:00 | No | Irvine | Irvine-Physicist | 4.6 wks | 0 | 0 | 0 | 0 | 502,498,487 | 0 | 0 | WBS Description: This task involves ...
504 | 706 | 7.3.13 | DAQ Computer Installation Complete | 2007-10-29 17:00 | 2007-10-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 503 | 0 | 0 | WBS Description: This milestone is for the ...
505 | 106 | 7.3.14 | Slow Control Software | 2006-12-13 08:00 | 2007-04-03 17:00 | Yes | Irvine | Irvine-Physicist | 15.2 wks | 0 | 0 | 0 | 0 | 456,483,491 | 0 | 0 | WBS Description: This task involves ...
506 | 99 | 7.3.15 | DAQ Run Control Software | 2007-04-04 08:00 | 2007-07-26 17:00 | Yes | Irvine | Irvine-Physicist | 16 wks | 0 | 0 | 0 | 0 | 492,505,483,456,484,458 | 0 | 0 | WBS Description: This task involves ...
507 | 174 | 7.4 | Procure LV System | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[113,400] | 12 wks | 0 | 0 | 113400 | 0 | 457,617 | 113400 | 113400 | WBS Description: This task involves ...

## wbs 8
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
508 | 800 | 8 | Frame, Absorbers and Stand | 2005-06-01 08:00 | 2008-06-11 17:00 | No |  |  | 152.6 wks | 209072 | 104360 | 624254 | 155636 |  | 833326 | 1093322
509 | 801 | 8.1 | Design | 2005-06-01 08:00 | 2006-08-02 17:00 | No |  |  | 59.2 wks | 172488 | 86068 | 31680 | 15840 |  | 204168 | 306076
510 | 802 | 8.1.1 | Design OD Frame (FY05) | 2005-06-01 08:00 | 2005-09-30 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%] | 17.2 wks | 352 | 0 | 0 | 0 |  | 352 | 352 | WBS Description: This task covers the design of the OD frame....
511 | 1293 | 8.1.2 | Design OD Frame (FY06) | 2005-10-03 08:00 | 2005-11-18 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%],MandS[9,240] | 7 wks | 0 | 0 | 9240 | 4620 | 510,615 | 9240 | 13860 | WBS Description: This task involves ...
512 | 803 | 8.1.3 | Design absorbers (FNAL) | 2005-10-17 08:00 | 2005-11-04 17:00 | Yes | Fermilab | DrafterF | 3 wks | 5160 | 2580 | 0 | 0 |  | 5160 | 7740 | WBS Description: Documentation of the design and engineering analysis of the absorber....
513 | 1422 | 8.1.4 | Design absorbers (Roch) | 2005-10-17 08:00 | 2005-11-04 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight,MandS[7,920] | 3 wks | 0 | 0 | 7920 | 3960 | 512SS | 7920 | 11880 | WBS Description: Design and engineering analysis of the absorber....
514 | 804 | 8.1.5 | Design Detector Stand and Bookend | 2005-10-17 08:00 | 2005-10-28 17:00 | Yes | Fermilab | MEF,DrafterF | 2 wks | 9120 | 4560 | 0 | 0 |  | 9120 | 13680 | WBS Description: This task involves final design of the detector stand. A first pass of the stand has been designed and analyzed for stresses. This short period of time will be needed to only adjust the design for the final location in the cavern....
515 | 1296 | 8.1.6 | Design Axial Bolts | 2005-10-31 08:00 | 2005-11-11 17:00 | Yes | Fermilab | MEF[20%],DrafterF[50%] | 2 wks | 2856 | 1428 | 0 | 0 | 514 | 2856 | 4284 | WBS Description: This task involves final design of the detector stand. A first pass of the stand has been designed and analyzed for stresses. This short period of time will be needed to only adjust the design for the final location in the cavern....
516 | 805 | 8.1.7 | Design Strongbacks (FNAL) | 2005-10-31 08:00 | 2006-01-23 17:00 | Yes | Fermilab | MEF[50%],DrafterF | 11 wks | 34540 | 17270 | 0 | 0 | 514 | 34540 | 51810 | WBS Description: This task involves design of the production strongback for assembling and manipulating the frames ...
517 | 1423 | 8.1.8 | Design Strongbacks (Roch) | 2005-10-31 08:00 | 2006-01-23 17:00 | Yes | Rochester | Roch ME[0%],Bob Flight[50%],MandS[14,520] | 11 wks | 0 | 0 | 14520 | 7260 | 516SS | 14520 | 21780 | WBS Description: This task involves design of the production strongback for assembling and manipulating the frames ...
518 | 806 | 8.1.9 | Design Cart modifications | 2006-01-24 08:00 | 2006-02-20 17:00 | Yes | Fermilab | MEF,DrafterF | 4 wks | 18240 | 9120 | 0 | 0 | 516 | 18240 | 27360 | WBS Description: This task is to redesign the cart from the Minos experiment to work for Minerva. Some small modifications to the connection system that allows it to hold a Minerva strongback are needed. Those changes need to be designed and analyze...
519 | 807 | 8.1.10 | Design Installation Procedure | 2006-02-21 08:00 | 2006-07-05 17:00 | Yes | Fermilab | MEF,DrafterF[50%] | 19 wks | 70300 | 35150 | 0 | 0 | 518,515 | 70300 | 105450 | WBS Description: This task involves moving the frames from their construction area to the Minos surface building, lowering them down the shaft to the cart, transporting them to the cavern, and finally hanging them. All of the engineering details for ...
520 | 808 | 8.1.11 | Design modifcations to the MINOS platform | 2006-07-06 08:00 | 2006-08-02 17:00 | Yes | Fermilab | MEF,DrafterF | 4 wks | 18240 | 9120 | 0 | 0 | 519 | 18240 | 27360 | WBS Description: This task is required to modify the existing platform for the Minos detector to allow installation of the Minerva detector. It will be necessry to resolve any mechanical interferences, including any required Minerva work platforms....
521 | 809 | 8.1.12 | Design Prototype detector stand | 2005-10-31 08:00 | 2005-11-18 17:00 | Yes | Fermilab | MEF,DrafterF | 3 wks | 13680 | 6840 | 0 | 0 | 514 | 13680 | 20520 | WBS Description: This task provides engineering and drafting to build a support stand for the prototype frame in some surface building. The amount of effort is small because a preliminary design of a support exists and only one frame will be the load...
522 | 810 | 8.2 | Procure Prototype Materials | 2005-11-07 08:00 | 2006-03-20 17:00 | No |  |  | 18 wks | 0 | 0 | 80180 | 16036 |  | 80180 | 96216
523 | 811 | 8.2.1 | Procure Prototype OD Frame Wedges | 2005-11-21 08:00 | 2005-12-20 17:00 | Yes | Fermilab | MandS[37,780] | 4 wks | 0 | 0 | 37780 | 7556 | 615,511 | 37780 | 45336 | WBS Description: This task involves purchase of prototype segments to make several frames for testing and measurement....
524 | 812 | 8.2.2 | Procure prototype HCAL steel | 2005-11-07 08:00 | 2006-01-06 17:00 | Yes | Fermilab | MandS[2,000] | 8 wks | 0 | 0 | 2000 | 400 | 512,615,513 | 2000 | 2400 | WBS Description: This task involves purchase of a prototype steel piece for the Hadron calorimeter sections of the detector. ...
525 | 813 | 8.2.3 | Procure prototype ECAL lead (Pb) | 2005-11-07 08:00 | 2006-02-06 17:00 | Yes | Fermilab | MandS[18,000] | 12 wks | 0 | 0 | 18000 | 3600 | 512,615 | 18000 | 21600 | WBS Description: This task involves purchase of lead sheets for the prototype program....
526 | 814 | 8.2.4 | Procure prototype HCAL upstream graphite | 2005-11-07 08:00 | 2006-02-06 17:00 | Yes | Fermilab | MandS[1,200] | 12 wks | 0 | 0 | 1200 | 240 | 512,615 | 1200 | 1440 | WBS Description: This task involves purchase of one prototype sheet of graphite for the prototype program. ...
527 | 1297 | 8.2.5 | Procure prototype axial bolts | 2005-11-14 08:00 | 2006-01-13 17:00 | Yes | Fermilab | MandS[200] | 8 wks | 0 | 0 | 200 | 40 | 515 | 200 | 240 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
528 | 1298 | 8.2.6 | Procure prototype ear pieces | 2005-11-14 08:00 | 2006-01-13 17:00 | Yes | Fermilab | MandS[1,000] | 8 wks | 0 | 0 | 1000 | 200 | 527SS | 1000 | 1200 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
529 | 815 | 8.2.7 | Procure prototype strongback | 2006-01-24 08:00 | 2006-03-20 17:00 | Yes | Fermilab | MandS[15,000] | 8 wks | 0 | 0 | 15000 | 3000 | 516 | 15000 | 18000 | WBS Description: This task involves involves purchase of a prototype strongback used to build the prototype and determine the performance of the design....
530 | 816 | 8.2.8 | Procure prototype detector stand and bookend | 2006-01-11 08:00 | 2006-02-01 17:00 | Yes | Fermilab | MandS[5,000] | 3 wks | 0 | 0 | 5000 | 1000 | 521 | 5000 | 6000 | WBS Description: This task involves ...
531 | 817 | 8.3 | Procure Production Materials | 2006-01-17 08:00 | 2008-03-25 17:00 | No |  |  | 110.4 wks | 0 | 0 | 488352 | 122088 |  | 488352 | 610440
532 | 818 | 8.3.1 | Procure production strongbacks | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[45,000] | 8 wks | 0 | 0 | 45000 | 11250 | 516,543,529,617,517 | 45000 | 56250 | WBS Description: This task involves purchase of three final version strongbacks for production of the detector. This allows for the posdsibility that the prototype is not used in the final production....
533 | 1299 | 8.3.2 | Procure 2 production stands and bookends | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[13,000] | 8 wks | 0 | 0 | 13000 | 3250 | 532SS | 13000 | 16250 | WBS Description: This task involves purchase of three final version strongbacks for production of the detector. This allows for the posdsibility that the prototype is not used in the final production....
534 | 820 | 8.3.3 | Purchase Stand and Bookend for cavern | 2007-10-01 08:00 | 2008-02-26 17:00 | No | Fermilab | MandS[25,000] | 20 wks | 0 | 0 | 25000 | 6250 | 530,617 | 25000 | 31250 | WBS Description: This task involves purchase of the final support structure for the detector in the cavern. The structure as designed weighs 30,000....
535 | 822 | 8.3.4 | Procure Narrow OD Wedges | 2007-11-28 08:00 | 2008-03-25 17:00 | No | Fermilab | MandS[80,712] | 16 wks | 0 | 0 | 80712 | 20178 | 532,617,533 | 80712 | 100890 | WBS Description: This task involves purchase of all the segments for the fabrication of the narrow frames for the detector....
536 | 823 | 8.3.5 | Procure Wide OD Wedges | 2007-11-28 08:00 | 2008-03-25 17:00 | No | Fermilab | MandS[175,759] | 16 wks | 0 | 0 | 175759 | 43939.75 | 535SS | 175759 | 219698.75 | WBS Description: This task involves purchase of all of the segments for the wide frames....
537 | 1300 | 8.3.6 | Procure axial bolts | 2006-01-17 08:00 | 2006-03-13 17:00 | No | Fermilab | MandS[5,600] | 8 wks | 0 | 0 | 5600 | 1400 | 527 | 5600 | 7000 | WBS Description: This task involves ...
538 | 824 | 8.3.7 | Procure ear pieces | 2007-10-01 08:00 | 2008-01-29 17:00 | No | Fermilab | MandS[26,640] | 16 wks | 0 | 0 | 26640 | 6660 | 539SS,528 | 26640 | 33300 | WBS Description: This task involves ...
539 | 825 | 8.3.8 | Procure HCAL Steel | 2007-10-01 08:00 | 2007-11-27 17:00 | No | Fermilab | MandS[39,836] | 8 wks | 0 | 0 | 39836 | 9959 | 524,617 | 39836 | 49795 | WBS Description: This task involves purchase of 23 pieces of steel for the upstream and downstreamHadron calorimeter sections of he detector. The steel plates are cut into hexagonal pieces that are 48" across the flat and 97" from point to point. To...
540 | 826 | 8.3.9 | Procure ECAL Pb | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[72,005] | 12 wks | 0 | 0 | 72005 | 18001.25 | 525,617 | 72005 | 90006.25 | WBS Description: This task involves purchase of all of the lead sheets for the nuclear targets and the EMCAL sections of the detector....
541 | 827 | 8.3.10 | Procure US HCAL Graphite | 2007-10-01 08:00 | 2007-12-27 17:00 | No | Fermilab | MandS[4,800] | 12 wks | 0 | 0 | 4800 | 1200 | 526,617 | 4800 | 6000 | WBS Description: This task involves purchase of the graphite sheets for the nuclear targets section of the detector....
542 | 828 | 8.4 | Outer Detector Frame Prototyping | 2006-02-02 08:00 | 2006-02-15 17:00 | No |  |  | 2 wks | 4904 | 2452 | 0 | 0 |  | 4904 | 7356
543 | 829 | 8.4.1 | Test Frame Welding | 2006-02-02 08:00 | 2006-02-08 17:00 | Yes | Fermilab | MTF,WelderF | 1 wk | 4640 | 2320 | 0 | 0 | 523,530 | 4640 | 6960 | WBS Description: This task involves Welding up the first prototype frame....
544 | 830 | 8.4.2 | Make Flatness Measurements | 2006-02-09 08:00 | 2006-02-15 17:00 | Yes | Fermilab | MTF[20%] | 1 wk | 264 | 132 | 0 | 0 | 543 | 264 | 396 | WBS Description: This is an engineering estimate for the time it would take a mechanical tech to measure the flatness of the prototype frame....
545 | 831 | 8.5 | Outer Detector Fabrication | 2008-03-26 08:00 | 2008-06-11 17:00 | No |  |  | 11 wks | 31680 | 15840 | 24042 | 1672 |  | 55722 | 73234
546 | 832 | 8.5.1 | Frame Welding | 2008-03-26 08:00 | 2008-06-11 17:00 | No | Fermilab | MandS[20,698],WelderF[50%],MTF Supervisor[50%] | 11 wks | 31680 | 15840 | 20698 | 0 | 532,536,535,538,544,537 | 52378 | 68218 | WBS Description: This task involves just welding up the frames. it is based on doing two frames a day. Keeping this pace is not a problem. The issue is whether the physicists can measure two a day in testing, and how that is done. ...
547 | 833 | 8.5.2 | QC measurements | 2008-03-26 08:00 | 2008-06-11 17:00 | No | Rochester | Roch Tech[0%],MandS[3,344] | 11 wks | 0 | 0 | 3344 | 1672 | 546SS | 3344 | 5016 | WBS Description: This task measures the quality (flatness) of the frames as they are made. It would allow problems to be found and repaired as necessary. The engineering estimate is for one person to spend 8 hours a week to look at all of the frames...

## wbs 9
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
548 | 44 | 9 | Module Assembly and Installation | 2005-06-01 08:00 | 2008-05-20 17:00 | No |  |  | 149.6 wks | 226485.28 | 55413.592 | 332862 | 118190.5 |  | 559347.28 | 732951.372
549 | 975 | 9.1 | Assembly R&D | 2005-06-01 08:00 | 2006-09-27 17:00 | No |  |  | 67 wks | 112365.28 | 30594.392 | 117542 | 35822.5 |  | 229907.28 | 296324.172
550 | 978 | 9.1.1 | Rochester Prototypes | 2005-06-01 08:00 | 2005-12-28 12:00 | No |  |  | 29 wks | 29773.28 | 3924.792 | 14012 | 4125 |  | 43785.28 | 51835.072
551 | 1305 | 9.1.1.1 | Design and construct 1/12th scale model | 2005-06-01 08:00 | 2005-07-27 17:00 | Yes | Rochester | MandS[512],Roch Machinist[22%] | 8 wks | 3608 | 0 | 512 | 0 |  | 4120 | 4120 | WBS Description: This task involves ...
552 | 976 | 9.1.1.2 | Fabricate PMT Rack prototypes | 2005-07-28 08:00 | 2005-09-29 17:00 | Yes | Rochester | Roch ME[5%],MandS[1,000],Roch Tech[8%] | 9 wks | 2469.28 | 370.392 | 1000 | 150 | 551 | 3469.28 | 3989.672 | WBS Description: This task involves the PMT Rack Prototype...
553 | 1306 | 9.1.1.3 | Fabricate scale model prototypes | 2005-09-30 08:00 | 2005-10-27 17:00 | Yes | Rochester | MandS[2,000],Roch Tech[25%] | 4 wks | 1680 | 252 | 2000 | 300 | 552 | 3680 | 4232 | Prototype costs:...
554 | 977 | 9.1.1.4 | Prototype studies | 2005-10-28 08:00 | 2005-12-28 12:00 | Yes | Rochester | Roch ME[40%],Roch Tech,MandS[10,500],Bob Flight[40%] | 8 wks | 22016 | 3302.4 | 10500 | 3675 | 553 | 32516 | 39493.4 | WBS Description: This task involves ...
555 | 1307 | 9.1.1.5 | Prototype Studies Complete | 2005-12-28 12:00 | 2005-12-28 12:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 554 | 0 | 0
556 | 65 | 9.1.2 | Full Module Prototype Preparation | 2005-12-28 13:00 | 2006-08-29 17:00 | No |  |  | 34 wks | 47912 | 12797.6 | 94300 | 28190 |  | 142212 | 183199.6
557 | 1424 | 9.1.2.1 | Assembly Fixtures | 2005-12-29 13:00 | 2006-05-15 17:00 | No |  |  | 19 wks | 31520 | 7880 | 6900 | 1970 |  | 38420 | 48270
558 | 1428 | 9.1.2.1.1 | Purchase assembly tooling | 2005-12-29 13:00 | 2006-01-30 17:00 | No | Rochester | MandS[2,000] | 4 wks | 0 | 0 | 2000 | 500 | 554FS+1 day | 2000 | 2500 | WBS Description: This task involves ...
559 | 1425 | 9.1.2.1.2 | Design assembly fixtures | 2006-02-28 08:00 | 2006-04-24 17:00 | No | Rochester | Roch ME,Bob Flight | 8 wks | 21440 | 5360 | 0 | 0 | 558FS+4 wks | 21440 | 26800 | WBS Description: This task involves ...
560 | 1426 | 9.1.2.1.3 | Fabricate assembly fixtures | 2006-03-28 08:00 | 2006-05-08 17:00 | No | Rochester | Roch Tech | 6 wks | 10080 | 2520 | 0 | 0 | 559FS-4 wks | 10080 | 12600 | WBS Description: This task involves ...
561 | 1427 | 9.1.2.1.4 | Procure hardware for assembly fixtures | 2006-05-02 08:00 | 2006-05-15 17:00 | No | Rochester | MandS[4,900] | 2 wks | 0 | 0 | 4900 | 1470 | 560FS-1 wk | 4900 | 6370 | WBS Description: This task involves ...
562 | 1429 | 9.1.2.2 | PMT Rack for Prototyping | 2006-05-02 08:00 | 2006-06-20 17:00 | No |  |  | 7 wks | 4360 | 1308 | 0 | 0 |  | 4360 | 5668
563 | 1430 | 9.1.2.2.1 | Dsign PMT Rack | 2006-05-02 08:00 | 2006-05-08 17:00 | No | Rochester | Roch ME,Bob Flight | 1 wk | 2680 | 804 | 0 | 0 | 561SS | 2680 | 3484 | WBS Description: This task involves ...
564 | 1431 | 9.1.2.2.2 | Fabricate PMT Rack | 2006-06-14 08:00 | 2006-06-20 17:00 | No | Rochester | Roch Tech | 1 wk | 1680 | 504 | 0 | 0 | 563FS+5 wks,561 | 1680 | 2184 | WBS Description: This task involves ...
565 | 48 | 9.1.2.3 | Design and Construct Mapper | 2005-12-28 13:00 | 2006-08-29 17:00 | No |  |  | 34 wks | 12032 | 3609.6 | 87400 | 26220 |  | 99432 | 129261.6
566 | 336 | 9.1.2.3.1 | Mapper Design | 2005-12-28 13:00 | 2006-03-24 17:00 | Yes | Rochester | MandS[26,400] | 12 wks | 0 | 0 | 26400 | 7920 | 555 | 26400 | 34320 | WBS Description: This task involves ...
567 | 337 | 9.1.2.3.2 | Mapper Materials | 2006-03-27 08:00 | 2006-05-19 17:00 | Yes | Rochester | MandS[35,000] | 8 wks | 0 | 0 | 35000 | 10500 | 566 | 35000 | 45500 | WBS Description: This task involves ...
568 | 335 | 9.1.2.3.3 | Mapper Assembly | 2006-04-10 08:00 | 2006-08-29 17:00 | Yes | Rochester | MandS[26,000],Roch Lead Tech[32%],Dan Ruggiero[32%] | 20 wks | 12032 | 3609.6 | 26000 | 7800 | 567SS+2 wks | 38032 | 49441.6 | WBS Description: This task involves ...
569 | 52 | 9.1.3 | Prototype Assembly | 2006-06-21 08:00 | 2006-09-27 17:00 | No |  |  | 13.8 wks | 34680 | 13872 | 9230 | 3507.5 |  | 43910 | 61289.5
570 | 1432 | 9.1.3.1 | Deliver materials to Fermilab | 2006-06-21 08:00 | 2006-06-27 17:00 | No | Rochester | MandS[1,230] | 1 wk | 0 | 0 | 1230 | 307.5 | 564 | 1230 | 1537.5
571 | 333 | 9.1.3.2 | University Prototype assembly labor | 2006-08-30 08:00 | 2006-09-27 17:00 | Yes | Rochester | Roch Tech[250%] | 4 wks | 17640 | 7056 | 0 | 0 | 543,570,568,567 | 17640 | 24696 | WBS Description: This task involves ...
572 | 271 | 9.1.3.3 | Fermilab Prototype assembly work | 2006-08-30 08:00 | 2006-09-27 17:00 | Yes | Fermilab | MEF[150%],ES&H-F[175%],MandS[8,000] | 4 wks | 17040 | 6816 | 8000 | 3200 | 571SS | 25040 | 35056 | WBS Description: This task involves ...
573 | 1308 | 9.1.3.4 | Full Module Prototype Assembly Complete | 2006-09-27 17:00 | 2006-09-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 572 | 0 | 0
574 | 1309 | 9.1.4 | Prototype Mapping Complete | 2006-08-29 17:00 | 2006-08-29 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 568 | 0 | 0
575 | 47 | 9.2 | Module Assembly and Mapping | 2006-09-28 08:00 | 2008-05-20 17:00 | No |  |  | 82.6 wks | 113120 | 24819.2 | 145920 | 55968 |  | 259040 | 339827.2
576 | 1433 | 9.2.1 | Assembly Preparations | 2006-09-28 08:00 | 2007-12-27 17:00 | No |  |  | 62.6 wks | 43904 | 10976 | 56000 | 20000 |  | 99904 | 130880
577 | 1434 | 9.2.1.1 | Evaluate functional prototype assembly | 2006-09-28 08:00 | 2006-10-11 17:00 | No | Rochester | Roch ME,Bob Flight | 2 wks | 5360 | 1340 | 0 | 0 | 573 | 5360 | 6700
578 | 1435 | 9.2.1.2 | Revise assembly design | 2006-10-12 08:00 | 2006-11-24 17:00 | No | Rochester | Roch ME,Bob Flight | 6 wks | 17152 | 4288 | 0 | 0 | 577 | 17152 | 21440
579 | 980 | 9.2.1.3 | Purchase bulk assembly tooling | 2006-11-27 08:00 | 2006-12-26 12:00 | Yes | Rochester | MandS[6,000] | 4 wks | 0 | 0 | 6000 | 6000 | 578 | 6000 | 12000 | WBS Description: This task involves ...
580 | 1436 | 9.2.1.4 | Fabricate assembly fixtures | 2006-12-26 13:00 | 2007-02-08 17:00 | No | Rochester | MandS[15,000] | 6 wks | 0 | 0 | 15000 | 4500 | 579 | 15000 | 19500
581 | 1437 | 9.2.1.5 | Procure bulk assembly fixtures hardware | 2006-12-26 13:00 | 2007-01-25 17:00 | No | Rochester | MandS[15,000] | 4 wks | 0 | 0 | 15000 | 4500 | 580SS | 15000 | 19500
582 | 1438 | 9.2.1.6 | Fabricate PMT rack | 2006-12-26 13:00 | 2007-02-08 17:00 | No | Rochester | MandS[20,000] | 6 wks | 0 | 0 | 20000 | 5000 | 580SS | 20000 | 25000
583 | 1439 | 9.2.1.7 | Design PMT lifting jig | 2007-02-09 08:00 | 2007-02-22 17:00 | No | Rochester | Roch ME,Bob Flight | 2 wks | 5360 | 1340 | 0 | 0 | 582 | 5360 | 6700
584 | 1440 | 9.2.1.8 | Fabricate PMT lifting jig | 2007-02-23 08:00 | 2007-03-08 17:00 | No | Rochester | Roch Machinist | 2 wks | 4000 | 1000 | 0 | 0 | 583 | 4000 | 5000
585 | 1441 | 9.2.1.9 | Optimize scanner | 2006-10-12 08:00 | 2006-11-24 17:00 | No | Rochester | Roch Lead Tech,Dan Ruggiero | 6 wks | 12032 | 3008 | 0 | 0 | 578SS | 12032 | 15040
586 | 1442 | 9.2.1.10 | Ready To Assemble Module | 2007-12-27 17:00 | 2007-12-27 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 580,581,571,539,540,541,584 | 0 | 0
587 | 277 | 9.2.2 | Assemble Module (FNAL) | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Fermilab | ES&H-F[70%],AlignmentF[5%],MandS[16,000] | 20 wks | 0 | 0 | 16000 | 6400 | 256,616,56,573,274,586 | 16000 | 22400 | WBS Description: This task involves ...
588 | 278 | 9.2.3 | Assemble Module (Rochester) | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Rochester | Roch Tech[200%] | 20 wks | 69216 | 13843.2 | 0 | 0 | 587SS | 69216 | 83059.2 | WBS Description: This task involves ...
589 | 49 | 9.2.4 | Map Modules | 2007-12-28 08:00 | 2008-05-20 17:00 | No | Fermilab | MandS[73,920] | 20 wks | 0 | 0 | 73920 | 29568 | 587SS,574,585 | 73920 | 103488 | WBS Description: This task is meant to include SAG internal module fiducial installation....
590 | 154 | 9.3 | Veto Wall | 2005-07-11 08:00 | 2007-08-14 17:00 | No |  |  | 105.8 wks | 1000 | 0 | 69400 | 26400 |  | 70400 | 96800
591 | 51 | 9.3.1 | Veto Wall Counters | 2005-07-11 08:00 | 2006-08-21 17:00 | No |  |  | 56.4 wks | 0 | 0 | 6000 | 2100 |  | 6000 | 8100
592 | 343 | 9.3.1.1 | Counter Checkout FY05 | 2005-07-11 08:00 | 2005-09-19 17:00 | Yes | Rochester | MandS[3,000] | 10 wks | 0 | 0 | 3000 | 1050 |  | 3000 | 4050 | WBS Description: This task involves ...
593 | 1443 | 9.3.1.2 | Counter Checkout FY06 | 2006-06-12 08:00 | 2006-08-21 17:00 | Yes | Rochester | MandS[3,000] | 10 wks | 0 | 0 | 3000 | 1050 | 592 | 3000 | 4050 | WBS Description: This task involves ...
594 | 165 | 9.3.2 | Veto Wall Structure | 2006-05-01 08:00 | 2007-08-07 17:00 | No |  |  | 64.2 wks | 1000 | 0 | 62200 | 23880 |  | 63200 | 87080
595 | 778 | 9.3.2.1 | Veto Wall design | 2006-05-01 08:00 | 2006-05-26 17:00 | Yes | Rochester | MandS[10,000] | 4 wks | 0 | 0 | 10000 | 4000 |  | 10000 | 14000 | WBS Description: This task involves ...
596 | 345 | 9.3.2.2 | Procure parts for Veto Wall structure | 2007-04-02 08:00 | 2007-04-27 17:00 | No | Rochester | MandS[40,200] | 4 wks | 0 | 0 | 40200 | 16080 | 595 | 40200 | 56280 | WBS Description: This task involves ...
597 | 344 | 9.3.2.3 | Fabricate Veto Wall structure | 2007-04-02 08:00 | 2007-07-24 17:00 | No | Rochester | MandS[4,000] | 16 wks | 0 | 0 | 4000 | 1000 | 616,596SS | 4000 | 5000 | WBS Description: This task involves ...
598 | 342 | 9.3.2.4 | Counter Shipping Crate & Handling | 2007-07-25 08:00 | 2007-08-07 17:00 | No | Rochester | MandS[9,000] | 2 wks | 1000 | 0 | 8000 | 2800 | 592,616,593,596,597 | 9000 | 11800 | WBS Description: This task involves ...
599 | 50 | 9.3.3 | Assemble Veto Wall at Fermilab | 2007-08-08 08:00 | 2007-08-14 17:00 | No | Rochester | MandS[1,200] | 1 wk | 0 | 0 | 1200 | 420 | 598 | 1200 | 1620 | WBS Description: This task involves ...

## wbs 10
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
600 | 156 | 10 | Project Management | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 604032 | 181209.6 | 0 | 0 |  | 604032 | 785241.6
601 | 848 | 10.1 | Prototyping and Testing | 2005-06-01 08:00 | 2005-06-28 17:00 | No |  |  | 4 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This section brings together all of the prototyping tests that need to be done throughout the Project R&D phase. They are included here because the tests span several different sections and components. The management section presen...
602 | 849 | 10.1.1 | Single Plane Vertical Slice Test | 2005-06-01 08:00 | 2005-06-28 17:00 | Yes | Fermilab | Roch Physicist | 4 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This test was done at the very beginnig of the Project and tested the front end electronics and the light levels of the array....
603 | 852 | 10.1.2 | VST with non-glued fibers | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | This uses Eljen paint
604 | 853 | 10.1.3 | VST with glued fibers and Bicron paint | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | Test Bicron paint...
605 | 854 | 10.1.4 | VST with co-extruded scintillator | 2005-06-01 08:00 | 2005-06-01 17:00 | Yes | Fermilab |  | 0.2 wks? | 0 | 0 | 0 | 0 |  | 0 | 0 | Mirror fibers for VST 2 with co-extruded scintillator...
606 | 216 | 10.2 | Management and Administration | 2005-06-01 08:00 | 2008-09-26 17:00 | No |  |  | 167.6 wks | 604032 | 181209.6 | 0 | 0 |  | 604032 | 785241.6
607 | 646 | 10.2.1 | FY05 Project Management and Administration | 2005-06-01 08:00 | 2005-09-29 17:00 | Yes | Fermilab | PhysicistF[340%] | 17 wks | 0 | 0 | 0 | 0 | 613 | 0 | 0 | WBS Description: This task involves ...
608 | 934 | 10.2.2 | FY06 Project Management and Administration | 2005-10-03 08:00 | 2006-09-29 17:00 | Yes | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50.2 wks | 201344 | 60403.2 | 0 | 0 | 607 | 201344 | 261747.2 | WBS Description: This task involves ...
609 | 935 | 10.2.3 | FY07 Project Management and Administration | 2006-10-02 08:00 | 2007-09-28 17:00 | No | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50.2 wks | 201344 | 60403.2 | 0 | 0 | 608 | 201344 | 261747.2 | WBS Description: This task involves ...
610 | 936 | 10.2.4 | FY08 Project Management and Administration | 2007-10-01 08:00 | 2008-09-26 17:00 | No | Fermilab | PhysicistF[340%],BudgetOfficerF[20%],SchedulerF[20%],EEF[50%],MEF[50%],ES&H-F[20%] | 50 wks | 201344 | 60403.2 | 0 | 0 | 609 | 201344 | 261747.2 | WBS Description: This task involves ...
611 | 982 | 10.2.5 | Project Management and Administration Complete | 2008-09-26 17:00 | 2008-09-26 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 610,655 | 0 | 0
612 | 723 | 10.3 | Project Milestones | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks | 0 | 0 | 0 | 0 |  | 0 | 0
613 | 724 | 10.3.1 | Start MINERvA Project | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone is for the start date of the MINERvA Project....
614 | 725 | 10.3.2 | Preproduction Funds Released | 2005-06-01 08:00 | 2005-06-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of preproduction funds by Fermilab....
615 | 726 | 10.3.3 | FY06 Funds Released by Fermilab | 2005-10-03 08:00 | 2005-10-03 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY06 funds by Fermilab....
616 | 727 | 10.3.4 | FY07 Construction Funds Released | 2006-10-02 08:00 | 2006-10-02 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY07 funds by Fermilab....
617 | 728 | 10.3.5 | FY08 Construction Funds Released | 2007-10-01 08:00 | 2007-10-01 08:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: This milestone marks the release of FY08 funds by Fermilab....
618 | 1291 | 10.3.6 | MINERvA Detector Ready For Installation | 2008-06-11 17:00 | 2008-06-11 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 360,507,547,588,587,353 | 0 | 0 | WBS Description: This milestone is for the finish date of the MINERvA Project....
619 | 729 | 10.3.7 | Finish MINERvA Project | 2009-01-05 17:00 | 2009-01-05 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 654,631,653,618,611 | 0 | 0 | WBS Description: This milestone is for the finish date of the MINERvA Project....

## wbs 11
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes
0 | 0 | 0 | MINERvA_27Oct05_v1.mpp | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks? | 2775646.48 | 773455.752 | 5620360 | 1447706.84 |  | 8396006.48 | 10617169.072 | Built from the 26Oct05_v2 schedule.
620 | 983 | 11 | Installation and Infrastructure | 2005-06-01 08:00 | 2009-01-05 17:00 | No |  |  | 180.6 wks | 286608 | 45323.2 | 235532 | 25644 |  | 522140 | 593107.2
621 | 984 | 11.1 | Scintilator Extrusion | 2005-09-30 08:00 | 2005-11-28 17:00 | No |  |  | 8 wks | 0 | 0 | 155117 | 0 |  | 155117 | 155117
622 | 988 | 11.1.1 | Purchase R&D Polystyrene | 2005-09-30 08:00 | 2005-11-28 17:00 | No | Fermilab | MandS[65,117] | 8 wks | 0 | 0 | 65117 | 0 | 4,5,6 | 65117 | 65117 | WBS Description: This task involves the purchase of polystyrene pettles, dopants, titanium dioxide pellets, labels, and other consumables for ID scintilattor production....
623 | 989 | 11.1.2 | Purchase Construction Scintillator Consumables | 2005-09-30 08:00 | 2005-11-28 17:00 | No | Fermilab | MandS[90,000] | 8 wks | 0 | 0 | 90000 | 0 | 622SS | 90000 | 90000 | WBS Description: Purchase of dopants for entire experiment....
624 | 896 | 11.2 | Purchase specialized miling machine for work at Tufts | 2005-06-01 08:00 | 2005-11-03 17:00 | No | Fermilab |  | 22 wks | 0 | 0 | 0 | 0 |  | 0 | 0 | WBS Description: Purchase of a milling machine, at a cost of $30,000, that will be used by Tufts University to produce PMT Boxes....
625 | 171 | 11.3 | Electronics Infrastructure | 2007-10-01 08:00 | 2008-07-17 17:00 | No |  |  | 40 wks | 79168 | 0 | 57235 | 22894 |  | 136403 | 159297
626 | 172 | 11.3.1 | Quiet Power Panel Installation | 2007-10-01 08:00 | 2007-11-09 17:00 | No | Fermilab | T&M ElectricialF[225%],MandS[56,020] | 6 wks | 0 | 0 | 56020 | 22408 | 456,617 | 56020 | 78428 | WBS Description: Installation of the quiet power panel by T&M electricians at Fermilab....
627 | 600 | 11.3.2 | Install Electronics Racks - Rigging | 2007-12-28 08:00 | 2007-12-28 17:00 | No | Fermilab | T&M Rigging Crew[70%],MandS[1,215] | 1 day | 0 | 0 | 1215 | 486 | 626,507 | 1215 | 1701 | WBS Description: This task covers the rigging needed to install the electronic racks....
628 | 175 | 11.3.3 | Install LV System (through fanouts) | 2007-12-31 08:00 | 2008-01-15 17:00 | No | Fermilab | EEF | 2 wks | 7008 | 0 | 0 | 0 | 626,627 | 7008 | 7008 | WBS Description: This task involves ...
629 | 180 | 11.3.4 | LV Cable Installation | 2008-01-16 08:00 | 2008-01-30 17:00 | No | Fermilab |  | 2 wks | 0 | 0 | 0 | 0 | 628 | 0 | 0 | WBS Description: This task involves ...
630 | 210 | 11.3.5 | Electronics System Integration | 2008-03-26 08:00 | 2008-07-17 17:00 | No | Fermilab | EEF,ETF | 16 wks | 72160 | 0 | 0 | 0 | 506,505,500,488,628,501,629,504,467 | 72160 | 72160 | WBS Description: This task involves ...
631 | 699 | 11.4 | DAQ System Installation Complete | 2008-07-17 17:00 | 2008-07-17 17:00 | No |  |  | 0 wks | 0 | 0 | 0 | 0 | 495,630 | 0 | 0 | WBS Description: This milestone is for the ...
632 | 986 | 11.5 | Stand Structure Installation | 2006-10-02 08:00 | 2008-07-24 17:00 | No |  |  | 91.2 wks | 50198 | 15844 | 23180 | 2750 |  | 73378 | 91972
633 | 834 | 11.5.1 | Installation of Prototype | 2008-06-12 08:00 | 2008-07-02 17:00 | No |  |  | 3 wks | 17584 | 8792 | 2500 | 625 |  | 20084 | 29501
634 | 835 | 11.5.1.1 | Core drill Anchors for stand | 2008-06-12 08:00 | 2008-06-18 17:00 | No | Fermilab | MandS[2,500],MTF[20%] | 1 wk | 264 | 132 | 2500 | 625 | 546,547 | 2764 | 3521 | WBS Description: This task is to drill and install floor anchors for the prototype stand. It assumes an outside contractor doing the core drilling and techs installing the anchors....
635 | 1301 | 11.5.1.2 | Install welding stand | 2008-06-19 08:00 | 2008-06-25 17:00 | No | Fermilab | MTF Sr[200%],MTF Supervisor,WelderF | 1 wk | 10320 | 5160 | 0 | 0 | 634 | 10320 | 15480 | WBS Description: This task is to install a prototype bookend and stand in the assembly area. The estimate is an enginering estimate do in consultation with the Tech Supervisor....
636 | 836 | 11.5.1.3 | Install stand and Bookend | 2008-06-26 08:00 | 2008-07-02 17:00 | No | Fermilab | MTF Sr[200%],MTF Supervisor | 1 wk | 7000 | 3500 | 0 | 0 | 634,635 | 7000 | 10500 | WBS Description: This task is to install a prototype bookend and stand in the assembly area. The estimate is an enginering estimate do in consultation with the Tech Supervisor....
637 | 1302 | 11.5.2 | Installation of Production Equipment | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  |  | 1 wk | 7264 | 3632 | 2500 | 625 |  | 9764 | 14021
638 | 1303 | 11.5.2.1 | Core drill Anchors for stand | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  | MandS[2,500],MTF[20%] | 1 wk | 264 | 132 | 2500 | 625 | 533 | 2764 | 3521
639 | 1304 | 11.5.2.2 | Install stand and Bookend | 2007-11-28 08:00 | 2007-12-04 17:00 | No |  | MTF Sr[200%],MTF Supervisor | 1 wk | 7000 | 3500 | 0 | 0 | 533 | 7000 | 10500
640 | 837 | 11.5.3 | Installation In The Cavern | 2006-10-02 08:00 | 2008-07-24 17:00 | No |  |  | 91.2 wks | 25350 | 3420 | 18180 | 1500 |  | 43530 | 48450
641 | 838 | 11.5.3.1 | Installation of the Stand and Bookend | 2008-07-03 08:00 | 2008-07-24 17:00 | No |  |  | 3 wks | 6840 | 3420 | 5000 | 1250 |  | 11840 | 16510
642 | 839 | 11.5.3.1.1 | Core Drill for anchors | 2008-07-03 08:00 | 2008-07-10 17:00 | No | Fermilab | MandS[5,000],MTF[50%] | 1 wk | 660 | 330 | 5000 | 1250 | 636,534,638,639 | 5660 | 7240 | WBS Description: This task involves core drilling holes for floor anchors and using a Fermilab mechancial tech to install them....
643 | 840 | 11.5.3.1.2 | Position the stand | 2008-07-11 08:00 | 2008-07-17 17:00 | No | Fermilab | MTF,AlignmentF[50%] | 1 wk | 1320 | 660 | 0 | 0 | 642 | 1320 | 1980 | WBS Description: This task involves setting the stand in position and marking the location of the anchor holes....
644 | 841 | 11.5.3.1.3 | Align and weld the stand in place | 2008-07-18 08:00 | 2008-07-24 17:00 | No | Fermilab | WelderF[50%],MTF[150%],MTF Supervisor[50%] | 1 wk | 4860 | 2430 | 0 | 0 | 643 | 4860 | 7290 | WBS Description: This task involves Assembling the stand in the cavern from the various pieces. This stand weighs about 15 tons....
645 | 842 | 11.5.3.2 | Modify Cart | 2006-10-02 08:00 | 2006-10-06 17:00 | No |  |  | 1 wk | 5910 | 0 | 1000 | 250 |  | 6910 | 7160
646 | 843 | 11.5.3.2.1 | Technician Cart Modification | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | MTF[200%],MTF Supervisor,MandS[1,000] | 1 wk | 5080 | 0 | 1000 | 250 | 516,616 | 6080 | 6330 | WBS Description: This task involves the mechanical tech work to modify the Minos cart to support Minerva strongbacks and frames. The cart is structurally sound for the load and only needs to have the connections between cart and strongback modified....
647 | 844 | 11.5.3.2.2 | Cart Welding and Rigging | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | WelderF[25%] | 1 wk | 830 | 0 | 0 | 0 | 646SS | 830 | 830 | WBS Description: This task involves the welding to do the cart modifications....
648 | 845 | 11.5.3.3 | MINOS Electronics Platform Modification | 2006-10-02 08:00 | 2006-10-13 17:00 | No |  |  | 2 wks | 12600 | 0 | 12180 | 0 |  | 24780 | 24780
649 | 846 | 11.5.3.3.1 | Procure Frame and Grating | 2006-10-02 08:00 | 2006-10-06 17:00 | No | Fermilab | MandS[12,180] | 1 wk | 0 | 0 | 12180 | 0 | 514,616,520 | 12180 | 12180 | WBS Description: This task involves purchasing the framing material and grating required to modify the platform....
650 | 847 | 11.5.3.3.2 | Modify Platform | 2006-10-09 08:00 | 2006-10-13 17:00 | No | Fermilab | MTF Sr[300%],MTF Supervisor,WelderF | 1 wk | 12600 | 0 | 0 | 0 | 649 | 12600 | 12600 | WBS Description: This task involves modifying the electroncis platform in place now for Minos to make room for the Minerva detector....
651 | 987 | 11.6 | Module Installation | 2007-08-15 08:00 | 2009-01-05 17:00 | No |  |  | 69.4 wks | 83544 | 0 | 0 | 0 |  | 83544 | 83544
652 | 169 | 11.6.1 | Module Installation | 2008-10-20 08:00 | 2009-01-05 17:00 | No | Fermilab | MTF Supervisor,MTF[400%] | 10 wks | 78744 | 0 | 0 | 0 | 589FF+3 days,644,647,587,360,646,650,384,392,394,395 | 78744 | 78744 | WBS Description: This task involves ...
653 | 354 | 11.6.2 | Final Detector Alignment | 2008-10-22 08:00 | 2009-01-05 17:00 | No | Fermilab | AlignmentF[30%] | 9.6 wks | 0 | 0 | 0 | 0 | 652SS+2 days | 0 | 0 | WBS Description: This task involves ...
654 | 168 | 11.6.3 | Install Veto Wall | 2007-08-15 08:00 | 2007-08-21 17:00 | No | Fermilab | MTF[225%],MTF Supervisor[75%] | 1 wk | 4800 | 0 | 0 | 0 | 599 | 4800 | 4800 | WBS Description: This task involves ...
655 | 350 | 11.7 | Installation Manager | 2006-10-02 08:00 | 2008-09-25 17:00 | No | Fermilab | MEF[25%] | 100 wks | 73698 | 29479.2 | 0 | 0 | 607FF,616SS | 73698 | 103177.2 | WBS Description: This task involves ...

## Sheet3
ID | UID | WBS | Task | Start | End | R&D? | Institituion | Resource names | Duration | Labor Cost (FY06) | Labor Cont. | M&S Cost (FY06) | M&S Cont. | Predecessors | Total base cost (FY06) | Total Project Cost ((fully burdened) | Notes