## Contract Select 7-12
|  | Start of Proc Clock | [12 empty] | Goal
Title/Description | Requisition Date | Complete Requisiton Package | Synopsis - Presolicitation Notice Published | Draft Solicitation Released | Final Solicitation Released | Offers Received | Evaluation Complete | Competitive Range Determined | Discussions Complete | Final Proposal Revisions Received | Source Selection Decision | Negotiations Complete | Award | Total
Comp - >$100K - $10M | 0 | 14 | 7 | N/A | 22 | 30 | 30 | 15 | 15 | 7 | 5 | N/A | 10 | 155
Non-Comp - >$100K - $10M | 0 | 14 | 14 | N/A | 60 | 30 | 30 | N/A | N/A | N/A | N/A | 30 | 30 | 208
Competitve - >$10M - $50M | 0 | 21 | 7 | 30 | 45 | 45 | 40 | 20 | 20 | 10 | 15 | N/A | 15 | 268 | 120
Non-Comp - >$10M - $50M | 0 | 21 | 14 | N/A | 60 | 45 | 30 | N/A | N/A | N/A | N/A | 45 | 30 | 245 | 120
Competitive - >$50M | 0 | 30 | 7 | 30 | 50 | 60 | 40 | 20 | 20 | 10 | 15 | N/A | 15 | 297 | 120
Non-Comp - >$50M | 0 | 30 | 14 | N/A | 60 | 60 | 45 | N/A | N/A | N/A | N/A | 45 | 30 | 284 | 120
Test Program for Certain Commercial Items (FAR 13.5) Using Simplified Procedures (Including Combined Solicitation/Synopsis ) | 0 | 14 | 7 | N/A | 7 | 20 | 20 | 5 | 14 | 7 | 14 | N/A | 3 | 111
Test Program for Commercial Items, which utilizes Simplified Procedures is included on this sheet solely to reflect additional milestone events over those identified for simplified acquisitions which may normally occur for acqusition subject to the Test Program.

## BAA
Title/Description | Requisition Date | Complete Requisiton Package | BAA Announcement Published | BAA Released | Offers Received | Evaluation Complete | Committee Review | Source Selection Decision | Model Contract, Additional Certifications, Update of Proposal Required as a Rresult of Selection Decision, and Additional Cost Information Requested | Model Contract and Additional Information Received | Negotiations Complete | Award | Total
BAA - HQ Issued | 0 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | 30 | 21 | 30 | 10 | 105
BAA - Center Issued | 0 | 21 | 7 | 22 | 60 | 60 | 30 | 15 | 15 | 21 | 15 | 15 | 281
BAA includes Announcements of Opportunity (AO), NASA Research Announcement (NRA), Cooperative Agreement Notice (CAN), Grant Notice, and SBIR/STTR Solicitations.
Complete Requisition Package for HQ issued BAA means all documentation needed to initiate discussions with the selection entity. This documentation generally includes copies of the BAA, Selection Statement, Letter of Notification of Selection, the selected proposal, and any additional instructions regarding desired changes to the selected proposal statement of work and deliverables, if applicable, and anticipated affect on level of funding, and a funded requisition.

## Award Fee
Title Description | Days
Award Fee Period End Date | 0
FDO Determination | 0
Notification of FDO Determination | 45
Award Fee Payment Authorized | 0
Date of AF Payment | 15
Fee Dollars Available ($)
Fee Dollars Earned ($)
Award Fee Score (#)
PRISM Milestone Events only capture dates - Must use comment field for additional information

## Simplified Select 7-12
Title/Description | Requisition Date | Complete Requisition Package | Sole Source Synopsized - Responses Dispositioned - Sole Source Approved | Quotes Received | Award | Total
Simplied -- Oral Quotes >$3,000 - <$25,000 | 0 | 4 |  | 7 | 6 | 17
Simplied -- Written RFQ or Posting >$3,000 - <$25,000 | 0 | 4 |  | 15 | 6 | 25
Simplified >$25,000 - <$100,000 | 0 | 4 |  | 40 | 10 | 54
Simplified >$25K - <$100K Combined Synopsis/Solicitation | 0 | 4 |  | 20 | 10 | 34
Simplified Non-Comp >$25,000 - <$100,000 | 0 | 10 | 50 | 7 | 6 | 73
Simplified - Includes GSA awards
No Milestone plan has been developed for GSA Supply acquisitions where a written or oral RFQ is not needed to determine best value. Having the PRISM system automatically capture the requisition received date and the award date is sufficient for any reporting requirement.

## IAA
Activity | Duration
Requisition Date | 0
Complete Requisition Package | 0
D&F Prepared | 10
Award | 20
Acceptance | 30
TOTAL | 60

## UCA
Activity | Duration
Complete change documentation received | 0
Change Order Issued | 10
Proposal Received | 60
Evaluation Complete | 30
Negotiations Complete | 30
Definitization Complete | 15
Total | 145

## Closeout
DESCRIPTION | FIRM FIXED PRICE | SAP | COST/OTHER FP | QUICK CLOSEOUT COST | GRANT & COOPERATIVE AGREEMENT | IAA
PHYSICALLY COMPLETE (FAR 4.804-4) | 0 | 0 | 0 | 0 | 0 | 0
TRANSFER CONTRACT TO CLOSEOUT (date from which other milestones are calculated) | 0 | 0 | 0 | 0 | 0 | 0
ALL ClOSEOUT DOCUMENTATION RECEIVED | 60 | NA | 230 | 230 | 90 | 175
FINAL AUDIT RECEIVED | NA | NA | 730 | 60 | NA | NA
COMPLETION INVOICE RCVD | 60 | 30 | 30 | 30 | 60 | 365
RELEASE & ASSIGNMENT FORMS RECEIVED | NA | NA | 30 | 30 | NA | NA
COMPLETION INVOICE APPROVED | 7 | 7 | 7 | 7 | 7 | 7
COMPLETION INVOICE PAID | 23 | 23 | 23 | 23 | 23 | 23
ADMINISTRATIVELY COMPLETE (FAR 4.804-5) | 30 | 0 | 30 | 30 | 30 | 30
TOTAL | 180 | 60 | 1080 | 410 | 210 | 600
DESTROY DATE (FAR 4.805)