| ``PROJ. NO. | FUND YEAR | IHS AREA | HEALTH CARE FACILITY (APPLICANT) [IHS AWARD AMT. / TOTAL PROJ COST] | LOCATION | PROJ. TYPE | P.L. 93-638 CONTRACT AWARD DATE | DES OFFICE (CO) [PM] | STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 508 | 2001 | PO | White Swan Health Clinic (Confederated Tribes and Bands of the Yakama Nation of Yakama Reservation, Washington) [$1,475,375 / $2,097,300] | White Swan, WA | R | 01/21/2003 | ES-S (LS) [PG] | DESIGN START: February 19, 2004 DESIGN COMPLETE: May, 2006 CONSTRUCTION START: June 6, 2007 CONSTRUCTION COMPLETE: January 2008 STATUS COMMENT: Construction completed in Jan 2008. Need final financial report showing zero balance, then close out. Tribe contacted again on 12/5/08 requesting close out info. |
| 510 | 2002 | PO | Inchelium Health Care Facility (Confederated Tribes of the Colville Reservation) [$2,000,000 / $3,868,572] | Inchelium, WA | R | 08/27/2002 | ES-S (LS) [PTN] | DESIGN START: July, 2001 DESIGN COMPLETE: July, 2002 CONSTRUCTION START: August 15, 2002 CONSTRUCTION COMPLETE: July 8, 2004 STATUS COMMENT: Contract close-out pending Tribe spending remaining funding. Latest letter requesting closeout info sent to Tribe Jan 2008. As of April 2008, the tribe indicated that the tribe has funds remaining ($11,800). They are planning to apply these funds towards radiology equipment. |
| 511 | 2002 | PH | Reno-Sparks Indian Colony Clinic (Reno-Sparks Indian Colony) [$2,000,000 / $8,640,621] | Reno, NV | R | 12/20/2002 | ES-D (B0) [MB] | DESIGN START: August 18, 2003 DESIGN COMPLETE: June 1, 2004 CONSTRUCTION START: July, 20006 CONSTRUCTION COMPLETE: March 2008 STATUS COMMENT: Punch list items are complete. Grand opening of the new facility was in May 2008. In warranty phase now. |
| 513 | 2002 | PO | Roger Saux Health Center (Quinault Indian Nation) [$968,931 / $1,446,124] | Taholah, WA | R | 11/09/2002 | ES-S (LS) [GFK] | DESIGN START: October, 2002 DESIGN COMPLETE: January, 2005 CONSTRUCTION START: May 5, 2005 CONSTRUCTION COMPLETE: November 1, 2006 STATUS COMMENT: Construction completed in Nov 2006. Need final financial report showing zero balance, then close out. |
| 518 | 2003 | AK | Chenega Bay Health Clinic (Chugachmiut) [$1,230,015 / $1,306,919] | Chenega Bay, AK | R | 10/03/2003 | ES-S (LS) [JB] | DESIGN START: May 28, 2004 DESIGN COMPLETE: May 16, 2005 CONSTRUCTION START: September 1, 2005 CONSTRUCTION COMPLETE: December 19, 2006 STATUS COMMENT: All Project funds confirmed expended. Project ready for close out. |
| 519 | 2003 | NS | Narragansett Indian Health Center (Narragansett Indian Tribe of Rhode Island) [$1,375,105 / 1,556,800] | Charlestown, RI | R | 11/21/2003 | ES-D (BO) [MB] | DESIGN START: August 9, 2004 DESIGN COMPLETE: ????? CONSTRUCTION START: ?????? CONSTRUCTION COMPLETE: ?????? STATUS COMMENT: Tribe waiting on additional funding for the project through loans and tribal funds. No estimated construction start/finish dates yet. |
| 520 | 2003 | BI | Chippewa Cree Health Center (Chippewa Cree Tribe) [$2,000,000 / $10,000,000] | Rocky Boy’s Indian Reservation, Bonneau Village, MT | R | 01/22/2004 | ES-S (LS) [HLP] | DESIGN START: December 1, 2003 DESIGN COMPLETE: October, 2004 CONSTRUCTION START: February 7, 2005 CONSTRUCTION COMPLETE: January 2007 STATUS COMMENT: Project construction completed in Jan 2007. Tribe completing punch list work in Feb. Contract Ready to close out. Tribe requested $500K additional funding from IHS in May 08 to address a serious structural foundation issue due to a shifting hillside adjacent to the facility. HQE will respond to this request. |
| 521 | 2006 | PO | Cowlitz Health Center Cowlitz Tribe [$1,010,500/$1,956,700} | Longview, WA | E&M | 05/17/2006 | ES-S (LS) [PG] | DESIGN START: August 2006 DESIGN COMPLETE: Nov 2008 CONSTRUCTION START: Nov 2008 CONSTRUCTION COMPLETE: Sept 2009 STATUS COMMENT: Phase I construction for a shell started in Dec 08. Phase II for the design and completion of the building mech and elec to follow. |
| 522 | 2006 | PO | Cow Creek Satellite Clinic Cow Creek Band of Umpqua Tribe of Indians [$1M/$2,195,752] | Canyonville, OR | E&M | 3/22/2007 | ES-S (LS) [PG] | DESIGN START: March 2009 DESIGN COMPLETE: Dec 2009 CONSTRUCTION START: March 2010 CONSTRUCTION COMPLETE: Dec 2010 STATUS COMMENT: Revised scope approved. NEPA needs Portland Area approval. |
| 523 | 2006 | PO | Siletz Clinic Expansion Confederated Tribes of Siletz Indians [$2M/$7.5M] | Siletz, OR | E&M | 05/17/2006 | ES-S (LS) [PG | DESIGN START: ???????? DESIGN COMPLETE: ???????? CONSTRUCTION START: ??????? CONSTRUCTION COMPLETE: ????? STATUS COMMENT: NEPA needs update and then review/approval by Portland Area. |
| 524 | 2006 | PO | Makah Health Center Makah Indian Tribe of the Makah Indian Reservation [$2M/$2,684,330] | Neah Bay, WA | R | 05/24/2006 | ES-S (LS) [PG] | DESIGN START: August 2006 DESIGN COMPLETE: ?????? CONSTRUCTION START: ?????? CONSTRUCTION COMPLETE: ????????? STATUS COMMENT: Tribe still seeking additional funding for project. NEPA still needs to be finalized by the Tribe and review/approved from the Area. |
| 525 | 2006 | AK | Hooper Bay Sub-Reg Clinic – YKHC – Village of Hopper Bay [$1.7M/$8,021,389] | Hooper Bay, AK | NS | 5/9/2007 | ES-S (LS) [JB] | DESIGN START: ????????? DESIGN COMPLETE: May 2007 CONSTRUCTION START: June 2007 CONSTRUCTION COMPLETE: May 2009 STATUS COMMENT: Construction completion moved back from Feb 2009 to May 2009. |
| 526 | 2006 | AK | Kake Clinic Exp SEARHC Village of Kake [$2M/$3,880,764] | Kake, AK | NS | 6/16/2006 | ES-S (LS) [JB] | DESIGN START: April 30, 2006 DESIGN COMPLETE: December 15, 2006 CONSTRUCTION START: August, 2007 CONSTRUCTION COMPLETE: April 2009 STATUS COMMENT: Project construction initiated in August 2007 and is on schedule. Addition work completed and renovation of the existing clinic complete in April 2009. |
| 527 | 2006 | CA | Shingle Springs Rancheria Health Clinic Shingle Springs Band of Miwok Indians [$2M/$8.5M] | El Dorado County, CA | R | 7/25/2006 | ES-S (LS) [JB] | DESIGN START: Aug 08 DESIGN COMPLETE: Feb 09 CONSTRUCTION START: March 09 CONSTRUCTION COMPLETE: May 10 STATUS COMMENT: Tribe selected a new site. Tribe completed new NEPA and Area has approved it. Tribe selected Flintco as their DB designer/contractor in Dec 08. |
| 528 | 2006 | BE | Peter Christian Health Clinic Replacement Lac du Flambeau Band of lake Superior Chippewa Indians [$2M/$5M] | Lac du Flambeau, WI | R | 8/31/07 | ES-S (LS) [JB] | DESIGN START: May 2007 DESIGN COMPLETE: October 2007 CONSTRUCTION START: July 2008 CONSTRUCTION COMPLETE: May 2009 STATUS COMMENT: Construction completion extended to May 2009. |
| 529 | 2008 | BE | Bad River Replacement Clinic [$2M/$5.7M] | Bad River, WI | R |  | ES-S (LS) [JB] | DESIGN START: ??????? DESIGN COMPLETE: ?????? CONSTRUCTION START: ??????? CONSTRUCTION COMPLETE: ????? STATUS COMMENT: SAP grant approved in August 2008. Tribe needs to secure funding and then sign off on T-I Agreement. |
| 530 | 2008 | PO | Warm Springs Clinic Renovation [$1.23M/$1.32] | Warm Springs, OR | E |  | ES-S (LS) [PG] | DESIGN START: ??????? DESIGN COMPLETE: ?????? CONSTRUCTION START: ??????? CONSTRUCTION COMPLETE: ????? STATUS COMMENT: SAP grant approved in August 2008. Tribe needs to secure their funding ($90K), provide a schedule, and then sign off on T-I Agreement. |

# LEGEND FOR IHS AREAS:		LEGEND FOR DES:

AQ	=	Albuquerque		DES	=	Division of Engineering Services, OEHE, IHS

AK	=	Alaska		ES-D	=	Engineering Services-Dallas

BE	=	Bemidji		ES-S	=	Engineering Services-Seattle

BI	=	Billings		OEHE	=	Office of Environmental Health and Engineering

CA	=	California	CO	=	DES Contracting Officer

NS	=	Nashville	PM	=	DES Project Manager

PO	=	Portland	LS	=	Linda Shaw, ES-Seattle

LEGEND FOR PROJECT TYPE:	MB	=	Mark Burke, ES-Dallas

E	=	expansion	PTN	=	Paul Ninomura, ES-Seattle

E & M	=	expansion and modernization	PG	=	Paul Geisert, ES-Seattle

NS	=	new satellite	JB 	= 	John Bausch, ES - Seattle

R	=	replacement	BO	=	Bill Obershaw, ES-Dallas

Note, all dates in (   ) are estimated dates.  Dates without (   ) are actual dates that milestones

SAP Contract (Completed-Closed Out-Achieved)

Project No. 501	Purcell Outpatient Clinic					Project No. 509	Santa Ysabel Health Care Facility

Project No. 502	Mariposa Indian Health Clinic					Project No. 512	Las Vegas Paiute Colony Health Care Facility

Project No. 503	Tribal Medical & Dental Clinic-The Klamath Tribes			Project No. 515	Bois Forte Health Clinic of Minnesota Chippewa Tribe

Project No. 504	Pueblo Jemez Health and Dental Clinic				Project No. 517	Campo Satellite Clinic –Southern Indian Health Council

Project No. 505	Stigler Clinic –Choctaw Nation of Oklahoma			Project No. 521	Ball Club Village Clinic-Leech Lake Bank of Ojibwe

Project No. 506	Yreka Clinic – Karuk Tribe of California

Project No. 507	Ho-Chunk Health Care Center