March 30, 1999

RESPONSE TO THE

U.S. ATLAS PIXEL INTERNAL REVIEW

11-12 MARCH 1999

This is the response of the Pixel System Team to the reviewer's comments, questions and suggestions. For clarity, the review report is reproduced in its entirety along with our responses in italics.

General Comments

- All changes to the goals that appear in the project management plan must be accompanied by baseline change proposals.

We expect the detailed goals (U.S. deliverables) to be defined at the time of the baseline review in 2000. Given the evolution of the project, technical choices made in the last two years and the needs of the project, it's certain that there will be some changes from the goals appearing in the Project Management plan. Since a baseline will only be defined after the baseline review (by definition), a BCP would seem unnecessary, but this is up to the Project Office.

- It is difficult for reviewers to follow progress without clearly identified specifications and/or goals.

We fundamentally disagree with this comment (at this time) but understand the difficulty of the reviewers and will attempt to provide the desired information at the next review.

- There is a lot of critical work scheduled to be completed in September 1999.  It may not be possible to determine project readiness for a summer 2000 baseline review until September.  A slip in completion of those critical milestones should have a corresponding slip in the baseline review.

We agree with the sense of this comment but believe September may be too early to tell if a baseline review in summer 2000 is feasible. A more realistic assessment will only be possible after the 2nd internal review, currently scheduled for December 1999. The date for this 2nd internal review was set before the date for a complete U.S. ATLAS cost-to-complete exercise was scheduled. We propose to modify the date of the 2nd internal review so that the review becomes part of the cost-to-complete activity, and plan to have a draft  baseline cost estimate at that time as well as a technical and schedule update.

Electronics

The U.S.ATLAS pixel group has made significant progress on electronics.  It is believed that they are on the right track in several areas:

- By combining the chip design efforts at CPPM, Bonn, and LBNL, all teams can share ownership of the final design

No comment.

- The two vendor choices are reasonable at this time but cannot continue indefinitely. If one vendor is found that meets the basic chip requirements, that vendor may need to be chosen due to schedule requirements.

It is our plan to make a vendor choice after evaluation of the DMILL and HSOI prototypes. However, we agree with the statement.

- It is appropriate to work on the DMILL submission first since there is more experience with DMILL than HSOI.

No comment.

- It is appropriate to isolate each module as much as possible with separate power supplies and optical fibers.

No comment.

- The removable B-layer is necessary despite the increased complexity associated with it, due to the high radiation levels close to the beam pipe.

No comment.

There are, however, several weak points in the pixel design effort.

- The Honeywell SOI design effort is based on single transistor measurements and the HEP community has little experience with the HSOI process.

We have designed two prototype chips which include complete analog designs, with approximately 100 pixel preamplifier/discriminator channels, biassing circuitry, current-mode DACs and current references. This is all of the critical analog circuitry that exists in the present pixel FE chips. These designs were submitted for fabrication in an HSOI run in Nov. 98, and are due for delivery in early April. We also have individual transistors from these analog designs available for characterization. We intend to measure the performance of these test chips completely, and compare it against our simulations, using the actual performance of single transistors from the same run. We believe this will significantly reduce the chances of any surprises when we fabricate a complete FE pixel chip in HSOI. This information will be available rather early in the design cycle. In addition, the CMS collaboration has compared the same preamplifier design in both DMILL and HSOI, including irradiation effects. These results have been presented at conferences, and indicate that the analog performance of the HSOI process after irradiation is at least as good as that of DMILL.

- There is only time for one DMILL and HSOI submission before baselining.   A great deal of checking must be done to insure success.

We have significantly improved our verification procedures for the

these submissions compared to what we did previously for our radsoft

chips. We are now doing complete, delay-annotated Verilog simulations

for the typical, best, and worst case transistor parameters. We intend

to perform these simulations on the complete chip if possible. We will

also do more extensive SPICE simulations than before. Finally, we plan

to do a full flat LVS of the entire chip at least once (in the past,

subsets of the complete chips were LVSed due to the extreme

CPU/memory/disk requirements of the complete LVS). We are reasonably

confident that no significant errors will sneak through these

procedures.

- Consideration should be given to the impact of single event upset (SEU).  A detailed schematic of the minimum size flip-flop should be given to Honeywell to review SEU susceptibility.

We have limited the use of dynamic CMOS logic to circuits whose values

do not need to remain valid for longer than a few microsecs, in part

to avoid nodes which are sensitive to small charge depositions from

SEU. All FF which must store data for longer periods of time are

static designs which require very large charges to change their

states. In addition, the only critical FF (in which a change in state

could affect the operation of the chip for an extended period of time)

are in control registers at the bottom of the FE chip. These registers

include a parity bit and continuous parity-check circuitry which will

flag all events transmitted from the FE chip during the period in which

the register parity is wrong. We intend to characterize these chips

and measure the SEU rate. If it appears to be too high, we will

replace these critical registers with more fault-tolerant designs

in which injecting charge on a single node is not sufficient to

change the stored value. We have discussed rad-hard FF designs with

Honeywell, and the techniques which they use in their SRAM's could

also be used by us, but with some potential speed penalties.

- Corner models for the HSOI do not exist. This makes the performance difficult to predict.

We agree that this is a significant issue. In studying the DMILL

corner models, we have realized that there are a small number of

process parameters that the vendor is tracking, and then modifying

in the SPICE models. We will discuss with Honeywell to get reasonable

estimates for the variations in these parameters (mainly thresholds,

mobilities, oxide thickness, and some capacitances), and use those

for a corner analysis. This will be less rigorous than we would like,

but should produce a design with decent yield and radiation hardness.

- Long power supply leads to the modules may cause chip or performance failures due to spikes and transients.

We agree that this is a risk, and are beginning to design, simulate,

and prototype the proposed power distribution and filtering system.

We have some flexibility in the supply lead sizing, and also some

space in one patch panel (PPB2) to add additional filtering and

transient protection. The next generation of module support cards

will allow us to build a realistic prototype of the entire supply

plus cable plus module chain and operate it under various worst

case scenarios. Until these tests are complete, we agree that this

approach retains some significant risks.

- The division of the design work between CPPM, Bonn, and LBNL appears reasonable (i.e. CPPM- frontend, LBNL- digital, Bonn- integration coordination).  However the separation of design activities has its problems.  A complete chip simulation is highly recommended.

We completely agree with this, and are trying to carry out parallel

(almost independent and equivalent) simulations of the critical

sub-circuits. We believe we will be able to perform a series of

Verilog simulations (tuned to give realistic results at the

sub-circuit level) on the full chip. We are also trying to review

critical schematics and layout separately at two institutions to

avoid slippage between different parts of the design. We believe

we have established good, open relationships between the critical

players at the three institutions, and we maintain frequent telephone

contact.

- The baseline review in May 2000 is expected to be based on well-tested and understood rad hard chip designs from both DMILL and HSOI.  The schedule for baselining is success oriented.  No room is left for an extra DMILL run or, in particular, another HSOI run if there is a design or foundry problem. Efforts to develop a 100 Mrad chip solution should not interfere with development of a 25 Mrad solution until a removable B-layer is well in hand.

We certainly agree that having a baseline review in May 2000 depends on a success-oriented schedule for the DMILL and HSOI prototypes. In fact, we noted at the review that we currently cannot meet this date and are projecting a few month delay. We plan to make every effort to restore the HSOI schedule, and thus the schedule for a baseline review. No separate development aimed at a 100 Mrad chip is planned at this time. However, we will irradiate the FE-D and FE-H (and the associated test chips) up to 100 Mrad or until failure. In addition to the intrinsic interest, it's clearly of importance to understand how much "headroom" exists even for the 25 Mrad requirement.

Hybrids

The decision to use flexhybrids seems the right choice for the module hybridization.  The density and feature sizes used are conservative when compared to other flexhybrids produced for other projects.  However:

- All materials must be qualified for the radiation environment.

We agree and these tests are (just) underway and are expected to continue well into 2000.

- A thermal analysis is needed.

We are not quite sure what this means. Measurements have been done, for example, of the temperature of the MCC chip mounted on a flex hybrid and this does not appear to be a problem.

- Revise hybrid schedule to show milestones for all prototype iterations.

This will be done in time for the May monthly report.

Module

- The pixel group must work with manufacturers to develop a bump bonding process that is more reliable and producible.

The focus of the bump bonding effort so far has been two-fold. One, to support the electronics + detector testing. Two, to demonstrate a proof-of-principle that fine-pitch bump bonding is feasible. Both of these have been successful. Production and quality issues are just starting to be addressed now and we expect to make 50-100 modules over the next year to gain valuable experience with at least two vendors and possibly more.

RODs

1. The decision between DSP and FPGA based readout drivers is overdue and should not be delayed any longer.

A review to select a design approach is scheduled for March 25-26, 1999.

Sensors

The work on sensor development is well along and in good shape.  A good understanding of sensor properties and evolution with radiation has been developed.

- We would recommend that the collaboration explore some mechanism to certify each batch of sensors to radiation hardness, either by developing a test structure on each so that each batch can be radiation tested, or by using sample detectors from each batch.

It was stated at the review that there was no such plan. However, it would be possible to test single-chip detector assemblies from each batch after irradiation and we will explore this possibility with the collaboration.

# MECHANICS

## OVERVIEW

Some mechanics issues require resolution at a higher level and need coordination with groups outside of the Pixel System.

We provided an overview of the mechanics system, including aspects for which the U.S. has no current responsibility, in order to give the review committee a global view of the mechanics and integration. We concur with the statement from the committee but have limited capability to resolve all interface issues with other systems.

The timing for the Review is appropriate.  It is early enough that the Committee recommendations may be pursued without adverse impact to project cost or schedule, as long as the recommendations are considered now.  These recommendations are intended to address weaknesses in the current design and current development program, as well as identify issues that are not yet addressed by the Pixel project effort.

## ATLAS LEVEL ISSUES

- The ATLAS Project Engineer must define guidelines for acceptable resonant frequencies.

We note that there is a tradeoff between material and resonant frequencies of the relevant structures. Since material has a direct impact on track reconstruction, it's not the responsibility of the Project Engineer alone to define guidelines for allowable resonant frequencies. We have embarked on a careful prototype program to build and evaluate all components of the mechanical structure. Only after this evaluation is complete(by early 2000) is it appropriate to establish firmer guidelines for acceptable resonant frequencies.

- The Pixel Project Engineer responsibilities are being transferred and this may impact the schedule.   CAD integration is important and must be continued.

We are working hard to avoid any schedule impact. The current Project Engineer(E. Anderssen) will continue to have integration responsibility for the collaboration for services and cooling/power interconnect design and fabrication in general.

There are always problems with sharing CAD data, most stem from lack of common data and established boundaries, not the actual ability of the CAD packages to import and export accurate geometry data, though this can be a problem.  For a collaborative effort to proceed there must be definite check points at which ownership of geometry changes hands—this is particularly important for sharing of native CAD files.  To affect this, compartments are established, Solid geometry representing the current design envelopes will be banked centrally (EDMS) in a neutral format, e.g. IGES and SET and native for those who can benefit.  This geometry is used by all to represent common boundaries for parts designed in the neighborhood.  Changes to envelope geometry require an Engineering Change Request (ECR).  It will be strongly suggested that no two parties design parts in the same neighborhood at the same time.  This can be affected either through creation of a new bounding envelope or through a more rigorous checkout procedure where ownership of part geometries/responsibilities is transferred wholly, if only temporarily.  This is the most reliable way to work without the two parties sharing a much closer link, namely residing on the same cad system where this can be achieved via permissions.  As designs become baselined, geometry for baselined designs will be logged in EDMS and subject to strict controls.  Due to current limitations of EDMS, it will be necessary for the Project Engineer to manually implement the ECR procedure and to ensure proper design practice.

Concerns that remain are specifically tied to the ability to share data with EUCLID, which is the CAD package CERN is using for the overall integration of ATLAS.  In principle, this should not be a problem as the Pixel Detector’s primary integration path is through the Inner Detector, which is currently handled by Rutherford Appleton Laboratory (RAL) which has begun using Pro/Engineer.  RAL, however, is not currently effective in this role. Noting also, that they have very little experience with Pro/E, it is not reasonable to assume that “CAD Integration” is something that the Inner Detector will see unless this responsibility is taken over elsewhere.  Directly this means that the Pixel detector must seek an integration tie with its nearest neighbor, the SCT Barrel that is currently engineered at the University of Geneva, which uses EUCLID.  It must suffice to say that EUCLID is an extremely primitive package used mostly due to a large amount of legacy data.  Unfortunately, CERN and most other institutes in France and Switzerland have opted to maintain it through the life of LEP, and as such are using it to design the LHC.  It is difficult, though not impossible to share data with EUCLID.  Generally, it is easier to get information out of EUCLID than into it, therefore integration is more of a problem for people with EUCLID than other users, however this muddles the concept of “sharing” data and can lead to problems.  CERN is, of course working on this problem, though is typically unhelpful to non-CERN-based users.  Some tools are available, but none are readily supported.  We may have to resort to drawings to share geometry with EUCLID.

The rest of the Pixel collaboration, with the exception of our French collaborator, use Pro/E or I-DEAS, both of which share data fairly readily.  Hytec uses SolidWorks, which is also easy to share data with, so this is not viewed as a problem area.

- The ATLAS Inner Detector needs Configuration Control.  There is significant potential for interference and incompatibility between the various components of the Inner Detector.

We couldn't agree more with this statement but do not have the authority to force compliance by the inner detector community. The best we can do on our own is to institute configuration control (including interfaces) for our deliverables and we are in the process of doing so.

- A decision must be made soon regarding the cooling system fluid. The different cooling systems may have an effect on the vibrations transmitted through the cooling lines, and the different fluids may present compatibility issues with Pixel components.

The U.S. has no direct responsibility for the pixel cooling system but obviously we depend on its success. The review highlighted the need for us to provide more input into the choice of a cooling fluid and in general to the design of the cooling system. Just subsequent to the review, we agreed on a program of measurements (pressure and pressure cycling tests, distortions under pressure, change in thermal performance after pressure cycling, etc) that can be completed (we hope) in the next few months by us. In addition, we will attempt to provide additional fluid flow calculations to evaluate the feasibility of evaporative systems with different fluids. Finally, we brought these issues and our concerns to the attention of the Pixel Project Leader.

PIXEL DESIGN ISSUES

- There is a need to define thermal barrier requirements for the Pixel detector.  This may be an ATLAS issue.  The current design is anticipating the use of heater strips to prevent condensation.  This will drive up the power consumption for the overall detector.

The existence or not of thermal barriers is certainly an ATLAS issue. We have taken the lead in the conceptual design and prototyping of a thermal barrier but, as was presented to the committee, are exploring means to eliminate the need for such barriers

There are two types of thermal barriers bounding the volume of the Silicon Trackers (SCT + Pixels).  For lack of any terminology, I will refer to them as types I and II.  Type I is active at all times and is necessary to maintain the thermal gradients between the SCT and the TRT, and between the end faces of the Forward SCT and the LAr Endcap Calorimeter. Because of the limited space available to maintain this ~30Deg C gradient, Type I thermal barriers require heat input on the exterior surface and cooling channels on the interior surface.  The Type I boundary at the end face actually seals to the Beam-Pipe, but is made of two annular parts.  The innermost annulus is removable for B-Layer and/or SCT Forward Removals (B-layer is always removed before removal of SCT Forward).  These interfaces must be kept thermally neutral at all times to prevent cooling of the TRT/Cryostat, or conversely heating of the SCT Barrel/Forward.  During shutdown periods, these surfaces must be maintained above the dewpoint to deter condensation.  Because the cooling and heating channels are sized to establish thermal neutrality, they to not contribute to the power budget of the detector as it relates to cooling.

Type II thermal barriers lie between detector volumes that are at the same temperature during detector operation, i.e. between SCT Barrel and Forward, Pixel Layer 1 and B-Layer, and SCT Forward and Beampipe volume (bounded by the Type I barrier at the end of the bore).  The B-Layer is enclosed in this last volume during detector operation.  Type II thermal barriers are only in operation (heated) during maintenance periods that require access to the bore of the detector,  during which, 13DegC-dewpoint cavern air is introduced into the bore of the detector.  ATLAS requires that no condensation be allowed on any surface anywhere within the cavern.  To accomplish this in the limited space, heat is input on the exterior surface of the Type II barrier.  For mass reasons, it is deemed unfeasible to also include a cooled interior surface so there will be a net heat influx into the detector volume from the Type II thermal barriers.  A design comprised of two thin GFRP shells with a non-convecting gas gap as insulation and custom Al-kapton heater has been proposed.  For the 1.6m section that runs through the volume of the Pixel Detector, this design requires a heat input of 330W to maintain an exterior surface temperature of 13.5DegC. This is ~2% of the heat already budgeted for module and cable dissipation—15kW, implying that the thermal barrier may be run with all of the electronics running, however this is not the intention.  It is foreseen that the detector will be off (all FE-electronics will not be powered) during detector opening scenarios, however the volume will be cooled using the detector cooling system.  This makes available the 15kW of cooling power from the Pixel detector, however the thermal coupling to Layer 1 and the disks has not been determined; local affects could still be a problem.  Because there is no thermal gradient across these barriers during detector operation, they require no heat input, and thus do not affect the power budget of the detector as it relates to cooling of an operating detector.

All space allocations for the thermal barriers, including power cables, cooling circuits and insulation thickness have already been included in the current Inner Tracker layout.  However, structural designs do not yet include thermal barrier supports, constraints or other effects.   Power budgets already include the dissipation of the power and cooling supply lines of the thermal barriers both types II and I.  Type II barriers are only necessary if detector must remain cold during maintenance operations.  Work within the sensor group on the effects of warm-up on depletion voltage are ongoing, but promising.  Type I barriers are fundamental to the interface between TRT and SCT and must be installed.

- The electrical design currently has no margin for an increase in power requirements.  This is not advisable this early in the design effort.

- There did not seem to be any extra cooling capacity in the Pixel thermal management system.

Items 2 and 3 are related. It was an oversight on our part to not present a more coherent picture of the power requirements and the uncertainties, and of the thermal measurements done to assess margin in the cooling system. We recognize that appropriate margins have not yet been defined for power requirements and cooling capacity. Measurements are underway to assess the "headroom" available in the cooling system. For example, the average temperature of an ESLI prototype sector increased by 1.4 degrees C when the power density was increased from 0.6 W/cm**2 to 0.7 W/cm**2, or by about 1.4 degrees C per Watt per module. Temperature increases of this scale can likely be offset, if necessary, by lowering the exhaust pressure of the evaporative C4F10 system. However, this statement has only had limited  validation by measurements. Furthermore, we must understand the cooling headroom  in the context of a complete system design, which will only begin later this year.

Services are sized based on electronics that met the power budget of 0.6W/cm^2 for the worst case cable lengths.  A packing factor of 2 is used for ribbons and slightly more for round cable leading to only a 40% occupancy for our quoted envelope section.  It was assumed that electronics would make or beat the power budget which was considered to be a limit.  Therefore, no margin was placed on top of the cable size, which was already viewed at the time to be conservative via conservatism in the power budget, and the use of longest routing lengths.  It was also considered unreasonable to oversize the cables at that point due to extreme material budget constraints and to allow some freedom in the choice of routing.  It should be noted that our envelope is not tied to what space is available or a specific physical routing; as such it is not strictly an envelope.  Our envelope is essentially just a measure of the section of particular bundles and a quantity of bundles.  It is somewhat misleading to say that any increase in power leads to our exceeding our envelope as our envelope, by definition, is sized based on our power budget.  Our service bundle envelope is more of a size parameter, which is then taken and routed through the service volumes.  Any change in the size of the bundle (what has been termed our envelope) may or may not change the routing, depending on local effects.  Unfortunately, it is not easy to determine if there is a problem as we are not responsible for the external routing of services.  Only global figures and percentages are available.  For instance certain areas have a 70% volume occupancy for bundles—with packing factor ~2.  Particular problems occur at the patch panels which are not based on cable sizing.  Pixel cables represent only ~ 10% of the entire cross section, so to first order we could double and not change the situation much.  This does not address localized problems, but these cannot be easily assessed as the only CAD integration being done right now on this is in 2D at Rutherford (RAL).  CAD integration for the Inner Detector stops at the second Patch Panel (PPB/F2).  Afterward, service integration is handled by ATLAS Technical Coordination.  The CAD situation is abysmal as the part up to PPB2 is only in 2D, and the parts after are all in EUCLID.  Physical models of the PPB2 and PPB1 region are being fabricated to alleviate this problem.  The models will include surrounding geometry to simulate the runs into and out of the areas.

Cooling as a system is poorly understood at best, however it is presently designed to have an overhead on the order of factor 2.  This is based on tubing sized to deliver twice the mass flow necessary to extract the heat of 80W/stave (72W is nominal if electronics are in spec—0.6W/cm^2).  It is unclear if the tubing is sized properly however, and work is being done to verify this as quickly as possible.

- The Committee views the sector cooling tube joint as a concern.  There is a risk to the Pixel project schedule and the sector design development if the proposed tubing joint prototype is not successful.

We have started to build prototypes of the cooling tube joint and will test them over the next few months.

- Final design for B-Layer depends upon finalization of bake-out jacket design, beam pipe support design and vacuum system design.  To this end, the B-layer design requires close coordination with beam tube and bake-out jacket design.  The NEG changes discussed in the Review (moving NEG inboard) is viewed as good for B-layer design.

No comments.

- ATLAS must define the B-layer installation method (insertion tool versus rails) now.  This has a significant impact on B-Layer and Inner Detector design and is viewed as the very next step to be resolved before B-Layer and adjacent systems mechanical design may continue. Several systems may need modification if the rail option is adopted. The insertion tool may need to be developed further.

We agree with these statements and are working towards resolving these issues.

- B-layer cable routing must be developed by ATLAS before more of the Pixel System mechanics can be designed, and must be done in conjunction with the installation and beam tube vacuum development.  It may be very difficult to have cables connected to each end if the barrel is removable.

We agree with this also.

- During the Review it was stated that the alignment tolerance is 25 – 50 (m, but this was not critical because Pixel systems can rely upon x-ray for alignment calibration.  However, the viability of the x-ray alignment is not well known for Pixels.

Strictly speaking this was the placement tolerance and we expect to also do optical surveys of each module on each sector, as well optical or CMM measurements of all sectors within a disk. The X-ray measurements are done after the system is assembled. There is an extensive program of development, including prototype measurements, underway for X-ray alignment of the SCT system by Oxford. So far, the responsibility for similar measurements and the possibility to utilize the SCT system for the pixels has not been fully developed. We are working to help resolve this but it will likely require either new groups or groups not currently involved in the pixel mechanics to become involved.

- The Committee recommends the Pixel Project evaluate the repeatability of distortion on sectors under temperature cycling (hysterisis).

Some such measurements have already been done but not in a systematic way and we appreciate the suggestion.

- The global support progress is encouraging. The decision to go to a flat panel configuration as opposed to a truss structure should save both time and construction costs. A continued concern is the effect of services (which include both cables and cooling tubes) on the mechanical stability of the system. A strain relief system must be well thought out to avoid putting oblique forces on this precision structure.

We agree and will have to do measurements on prototype structures to really assess this problem.

- ATLAS needs to be determining whether the flat side of the omega section will warp and potentially contribute to the dimensional instability.

This is not a U.S. responsibility but we will bring this concern to the attention of the party responsible.

- The interconnect flex hybrid should be connected to the silicon with a flexible adhesive to avoid distortion.  The CTEs for Kapton and silicon differ substantially.   There is a potential for distortion of the silicon if a rigid adhesive is used.  This should be evaluated.

This is a good point that we have not yet addressed. We believe it will be possible to make these measurements, to some extent, using flex 1.0 prototypes mounted on sectors with dummy silicon(unpowered) by lowering the temperature and measuring the distortion with TV holography. Clearly this has to be done also after irradiation.

- There is a lot of work done on 3-D modeling for the Pixel System.  This is a good approach, and permits some early evaluation of interference.  However, mock-ups also should be constructed to ensure all potential interference is identified.

We are doing this and have an extensive mockup program in place.

- The current disk design uses a continuous disk.  These disks are captive on a welded beam tube. Since the pipe must be installed after the detector is in place, detector delays could affect the beam-commissioning schedule. Disk repair also requires beam line cutting. The consequences of a captive disk system should be fully recognized before the disk and beam pipe designs are finalized.

This was fully recognized some years ago. The flanges on the beam pipe are capable of passing through the pixel detector (B-layer not in place).

## PIXEL PROGRAMMATIC ISSUES

- Final Design Reviews must be conducted before the PRR. In addition the design must be finalized before the PRR.

We have not been entirely consistent in enumerating design reviews and will fix this.

- This Review indicated the stave and cooling tube back-up designs would be pursued right up to the PRR. We need to make the decision before the PRR.  The purpose of the PRR is not a design blessing, but a determination of readiness to proceed to production (design is complete, drawings completed, validation testing is completed, QA program in place, etc.).  If the design cannot be finalized in time for the PRR, then perhaps we need to recommend later dates for the CERN PRRs.

This was stated in the case of the European development of the stave. We agree with the comment of the committee. We do not intend to do this for the sectors and related items, a U.S. responsibility. We will make a final choice relatively early so that a final design is done on only one choice.

- Schedules need refinement; for example, the test of the second prototype occurs only three weeks after the second prototype design review.  Design reviews must be scheduled so their findings may influence the design they are reviewing; e.g. the second prototype design review should be scheduled sufficiently in advance of commencement of second prototype fabrication so issues and conclusions may be addressed in the second prototype.

We will revise the schedule as needed to clarify this issue.