Corporate Property 
Automated Information System

Data Conversion Strategy and Plan

Version 1.3

January 6, 2004

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 9/03/03 | 0.1 | Initial outline | RL/SC |
| 9/24/03 | 0.5 | Compiled into single document and added placeholder sections discussed during 9/11/03 pre-draft walkthrough. | RL/SC |
| 11/04/03 | 0.6 | Added comments discussed during 10/17/03 walkthrough and updates from Agency meetings. | RL/SC |
| 12/01/03 | 1.0 | Added remaining placeholder sections, comments received and updates from Agency meetings. | RL/SC |
| 12/19/03 | 1.1 | Added comments received. | RL/SC |
| 12/31/03 | 1.2 | Added comments received. | RL/SC |
| 1/6/04 | 1.3 | Incorporated Comments | GC/CW |

Table of Contents

Introduction	1

Background	1

Purpose	2

Scope	2

Stakeholders	2

Assumptions	3

Issues	6

Key Definitions	7

USDA-Owned Property	7

GSA Assignments	7

Lease	7

Agreements	8

Conversion Methods	8

Conversion Criteria	8

Historical Real Property Inventory Conversion Strategy	9

Beginning Balances Conversion Strategy	9

Recommendations by Agency	11

Current Environment	11

Gaps	17

Data Conversion Issues	17

Conversion Process	18

Roles and Responsibilities	18

Conversion Process Description	18

Technical Approach	19

Leased and Owned Property from INFRA	19

Leased and Owned Property from FIRM	23

GSA Assigned Property from STAR	25

Accounting Data from Excel	28

Manual Data Entry	29

Data Preparation Approach	30

Categories of Data Preparation	30

Test Conversion	32

Validation Approach	33

Appendix A Documents Reviewed	A1

Appendix B Source to Target Mappings	B1

Appendix C Conversion Work Breakdown Structure	C1

Appendix D Conversion Problem Resolution and Escalation Procedures	D1

Appendix E Financial Reconciliation	E1

Appendix F GSA STAR Rent Conversion File	F1

Appendix G GSA STAR Rent Staging Table	G1

Appendix H FIRM Data Mapping	H1

Appendix I Accounting Template	I1

Appendix J Unique Asset Identifier (UAI) Format	J1

Appendix K Data Validation Reports	K1

Appendix L Conversion Certification Form	L1

List of Tables

Table 1. Summary: Conversion Method Recommendations	12

Table 2. Conversion Roles and Responsibilities	19

Table 3.  Mandatory Data Elements: Leased and Owned Property	21

Table 4. Mandatory Data Elements: GSA Assigned Property	26

Table 5. Review of APHIS Data Export From 5/2003	35

Table 6. Review of DA Data Export From 11/2003	42

Table 7. Review of ARS (1205) FIRM Data Export From 5/2003	49

Table 8. Review of FSA (1201, 1293) FIRM Data Export on NITC FIRM CD	52

Table 9. Review of NRCS (1235) FIRM Data Export on NITC FIRM CD	55

Table 10. Review of RD (1215) FIRM Data Export on NITC FIRM CD	56

Table 11. Data Conversion WBS Activities	62

Table 12. GSA STAR Rent Bill Source Data	67

Table 13. GSA STAR Rent Bill	69

Table 14. FIRM Data Mapping	71

List of Figures

Figure 1. Current Environment	12

Figure 2. INFRA Conversion Approach	20

Figure 3. FIRM Conversion Approach	24

Figure 4. STAR Conversion Approach	26

Figure 5. Accounting Conversion Approach	29

Figure 6. Manual Conversion Approach	30

# Introduction

## Background

The United States Department of Agriculture (USDA) reported more than $8 billion in assets in FY02. As the second largest landholder in the federal government, USDA owns approximately 192 million acres of land and occupies approximately 51 million square feet of space (owned and leased).

During FY02, USDA initiated an effort to address its need for a department-wide system for managing both real and personal property assets. Without such a system, USDA cannot comply with applicable laws and regulations for financial management, information security, and internal controls. Such a system is also critical to USDA’s ability to improve customer service, organizational productivity, accountability, and performance.

To identify a systematic, long-term solution to its asset management requirements, USDA conducted a business case analysis in accordance with Office of Management and Budget (OMB) requirements for investments. The analysis included a market survey. One of the entities responding to the survey was USDA’s Forest Service (FS), which proposed its government off-the-shelf (GOTS) Infrastructure System (INFRA) as a potential solution. INFRA is a mixed system, with a real property component. The real property currently being managed by INFRA represents approximately 85 percent of USDA’s owned real property assets. In addition, INFRA substantially meets USDA requirements as well as Joint Financial Management Improvement Program (JFMIP) and other federal requirements.

As a result of the market survey, USDA identified three alternatives for CPAIS: (1) deploy a commercial off-the-shelf (COTS) product, (2) deploy an enhanced GOTS solution, and (3) deploy a hybrid solution that uses INFRA for real property management and a COTS product for personal property management. USDA then evaluated these alternatives using the following criteria: performance (defined as alignment, requirements, interoperability, and scalability); cost; schedule; and risk.

This evaluation resulted in USDA deciding to first implement INFRA department-wide and then decide whether to enhance it to include personal property assets or acquire a COTS product for managing those assets. In either case, the combination of real property and personal property management capability constitutes Corporate Property Automated Information System (CPAIS). Using INFRA as the core for CPAIS would enable USDA to leverage the existing real property management capability and user base.

### Purpose

For CPAIS to become operational, the data required to support the existing real property processes must be converted into CPAIS. This document supports that conversion by:

Identifying the data elements of the real property systems required to support the processes outlined in the functional requirements

Presenting conversion options for the identified processes

Recommending a preferred method of converting the data elements, including real property balances, based on the information provided by the various sources, such as real property policy documents, system documentation, and user questionnaires

Describing technical, data preparation and data reconciliation approaches for loading the required property and financial data into CPAIS.

It also provides the data extract agreements between CPAIS and INFRA; the GSA System for Tracking and Accounting for Real Property (STAR) Billing System; the GSA Federal Real Property Profile (FRPP) for annual reporting; and Foundation Financial Information System (FFIS) for booking converted transactions into the general ledger.

### Scope

This document recommends a data conversion strategy and plan for real property and financial data. It also includes non-automated conversions (manual entry) in the data conversion strategy.

## Stakeholders

CPAIS must meet the needs and expectations of several different stakeholders, including the following:

- Departmental Administrative and Staff Offices (DASO), such as

Departmental Administration (DA)

Office of the Chief Financial Officer (OCFO)

Office of the Chief Information Officer (OCIO)

Office of General Council (OGC)

Office of Procurement and Property Management (OPPM)

- Agricultural Marketing Service (AMS)

- Agricultural Research Service (ARS)

- Animal and Plant Health Inspection Service (APHIS)

- Cooperative State Research, Education, and Extension Service (CSREES)

- Economic Research Service (ERS)

- Foreign Agricultural Service (FAS)

- Farm Service Agency (FSA)

- Food and Nutrition Services (FNS)

- Food Safety and Inspection Service (FSIS)

- Forest Service (FS)

- Grain Inspection, Packers and Stockyards Administration (GIPSA)

- National Agricultural Statistics Service (NASS)

- National Appeals Division (NAD)

- Natural Resources Conservation Service (NRCS)

- Office of the Inspector General (OIG)

- Risk Management Agency (RMA)

- Rural Development (RD).

Other CPAIS stakeholders are agency personnel and real property managers, Chief Financial Officers (CFOs), financial personnel, and the National Information Technology Center (NITC).

## Assumptions

The CPAIS data conversion activities are based upon the following assumptions:

Automated conversions for data sources with fewer than 100 property records will far exceed the level-of-effort (LOE) and cost of manual entry.

Several different versions and releases of the Foundation Information for Real Property Management (FIRM) software are being used by ARS, FSA, NRCS, and RD. However, those versions and releases will have a high percentage of common data elements to support the LOE and cost of developing routines for an automated data conversion for data that are stored in FIRM. CPAIS developers will need to undertake a source-to-target mapping for each unique occurrence of FIRM.

Data from FRPP (i.e., federal installation number) does not need to be converted.

Mapping (or standardizing) the source code values to CPAIS will be a key component of the conversion strategy.

Conversion will be tied to the system implementation-fielding plan and will occur in the third quarter of FY04 to facilitate user acceptance testing. Training will occur prior to implementation.

The conversion strategy and plan is dependent on the CPAIS physical data model and codes being documented in order to perform the source-to-target mappings.

Data conversion depends on the FFIS accounting code structure (ACS), which will provide the subledger detail needed for CPAIS processing. Agencies will provide a valid unique asset identifier (UAI) and a valid FFIS ACS for all capitalized property.

Conversion materials will be leveraged for user training.

OIG will review and concur with the data conversion strategy because of CPAIS’ subledger details.

The data converted in Phase I from FIRM to CPAIS will be used to produce the FRPP, but not detailed reports or the Space Budget Justification (Exhibit 54).

All property will be loaded into CPAIS regardless of the capital value. CPAIS needs to be able to account for property under the $25,000 threshold for inventory and reporting purposes.

Only leased properties terminated after 10/1/2002 through conversion cut-off will be converted.

FRPP will not be a source for data conversion because it contains highly summarized data.

Because of differences in the data between FRPP and FIRM, FRPP will not be a good source for reconciliation after the conversion.

FRPP will be a good source for data analysis and gap identification between the inventory stored in FIRM (and other systems) and what is being reported.

Agencies will verify STAR rent baselines with their own data sources and resolve discrepancies prior to conversion; the exception reporting process is only for the operational month-to-month reconciliation process.

A memorandum of agreement (MOA) will be established for obtaining a monthly extract of STAR rent data.

A MOA will be established for providing a complete replacement of 1166 data to the FRPP on an annual basis.

ARS will provide its FIRM data for conversion.

APHIS will provide its leased property database and owned property data for conversion.

CPAIS developers will provide help desk support while the agencies are converting/populating their data into CPAIS.

Accounting transactions for all agencies, with the exception of the Forest Service, will be reestablished manually; no data will be converted from FFIS.

A complete list of organization (Org) codes will be setup.

Complete LOVs for various data fields will be defined.

Agency users will have access to CPAIS accounts so they can verify the conversion.

At a minimum, disposal processing in Phase 1 of CPAIS will include updating the “Status of Buildings, Other Structures” to “disposed” and storing the date of disposal.

Funding on space assignment will not be included in Phase 1 of CPAIS.

Land easements (“Type of Land Unit”) will not be tracked in Phase 1 of CPAIS.

## Issues

The following is a list of open issues related to the data conversion effort. The issues are being discussed at various levels within the CPAIS teams. Decisions made with respect to the items in the list may affect the overall data conversion plan by requiring additional data or a change in the current conversion approach.

FIRM is missing the Administrative Organization breakout, which is needed to support reporting and database update access. FIRM agencies are required to provide organization codes.

Where data elements will not be included in Phase 1 (first delivery), the gap will be documented and the agencies will be informed of eligible default values. For example, ARS stores housing detail data elements in its modified FIRM, but these elements will not be converted because this data should be managed in the Department of the Interior system.

FS has historical transactions where the original source document is assigned to wrong GL Job Code for WIP. FS does not currently use the Fund Code and Program Code in the value stream. However, this is part of the value stream in CPAIS.

Findings and Recommendations

This chapter addresses the issues related to converting data to support the real property processes outlined in the CPAIS functional requirements1 for leased, owned and GSA-assigned property. We define the conversion options and methods, provide a summary table of the recommended conversion options by property type for each agency. (This document does not address the tracking and maintaining of real property after it is established in CPAIS.)

## Key Definitions

### USDA-Owned Property

CPAIS tracks USDA-owned property for work in progress (WIP) accounting, inventory reporting, and depreciation purposes, whether the property was purchased or constructed by a USDA agency or received through donation, exchange, or transfer. CPAIS interfaces with the Corporate Financial Management System to receive financial transactions that are either manually entered into that system or automatically generated by the procurement system (e.g., IAS or PRCH). CPAIS is the system of record for USDA-owned real property.

### GSA Assignments

CPAIS maintains data elements required for managing GSA assignments, including those in the National Capital Region, which is managed by the Departmental Administration Office. Part of GSA’s role is to secure space at favorable terms on behalf of federal agencies. Regardless of whether the space is owned by the government or leased to GSA, the space is said to be under GSA assignment to the agency with the terms and conditions spelled out in an occupancy agreement (OA) between GSA and the agency.

### Lease

CPAIS maintains data elements for tracking and managing USDA commercial leases. It also creates reports that delineate the leases. Financial data warehouses contain the financial information on these leases. The agency reviews the market and follows the government’s bidding process to assure fair competition and competitive terms. After negotiating the final terms and conditions of a commercial lease and coordinating any build out, the agency accepts the space and records the lease details in CPAIS.  CPAIS will not capture accounting-related data for leases as it does for owned property.

CPAIS must maintain data elements required for tracking and managing land leases and a data warehouse will maintain data for reporting financial information on land leases.

### Agreements

CPAIS maintains data elements required for managing shared space agreements. The term ‘agreement’ is a broad term applied to an instrument that a third party uses to transfer certain rights to an agency of the federal government, or an agency of the federal government transfers certain rights to a third party, for a specified use and a specified term. Agencies refer to agreements in several different ways, including permit, cooperative agreement, agreement, license, government to government, government to third party, and third party to government. Although these are all unique arrangements, CPAIS’ functional workflow and system requirements for agreements are essentially the same.

### Conversion Methods

Two methods will be used to convert real property data into CPAIS: manual and automated. The manual method requires data entry directly into CPAIS, while the automated method involves developing conversion routines for extracting data from the source system and importing it into CPAIS. Some automated conversion data may be missing and require manual capture. See Conversion Process for a discussion of data preparation.

### Conversion Criteria

Property records for all GSA-assigned properties used by USDA will be created from the latest STAR Rent Bill. Some agencies track property in FIRM, while others use MS Access, Excel spreadsheets, and miscellaneous databases. The following criteria will be used to determine which property data would be converted automatically:

100 or more records in FIRM database

Consistent data values

Complete mandatory data elements.

Based on a survey performed in July, the following agencies met these criteria:

Owned property:

APHIS, approximately 600 records in spreadsheet

ARS, approximately 3,044 records in FIRM

DA, approximately 6,000 records

FS, approximately 16,851 records in INFRA

NRCS, approximately 1,127 records in FIRM at NITC

Leased property:

APHIS, approximately 213 records in Access DB

FSA, approximately 1,201 records in FIRM at NITC

NRCS, approximately 2,150 records in FIRM at NITC

RD, approximately 718 records in FIRM at NITC

FS, approximately 498 records in INFRA.

### Historical Real Property Inventory Conversion Strategy

This section provides the strategy for converting the historical real property asset records into CPAIS.

The agency will provide all leased and owned inventory records from their source system. All data provided will be stored in a conversion archive file for future reference. Then conversion scripts will select and load into CPAIS all active records and only those disposed records that meet the following disposal selection criteria.

Convert all owned disposed inventory records from 1/1/02 through the conversion cutoff (which may be 3/31/04).

Convert all terminated leases from 10/1/2002 through the conversion cutoff date.

For GSA assignments, the latest rent bill, which includes the year to date billing, will be loaded into CPAIS.

### Beginning Balances Conversion Strategy

This section presents a high-level discussion on converting mandatory data and beginning balances into CPAIS.

Before converting their data into CPAIS, agencies along with the Controller Operations Division (COD), will be required to reconcile real property as of March 31, 2004.  In addition, any single asset that does not meet the threshold for the year placed in service will be written off.  This means that in-service items prior to 10/1/2001 will use a $5,000 threshold while in-service items after that date will use a $25,000 threshold.  The reconciliation of assets and accumulated depreciation should occur between the agency’s real property source documentation/system and the Foundation Financial Information System (FFIS). The reconciliation should occur at the general ledger account, accounting strip, and budget object class levels.

The following general ledger accounts in FFIS should be used in making the reconciliation:  Land (1710)), Land and Land Rights (1711), Improvements to Land (1712), Accumulated Depreciation on Improvements to Land (1719), Buildings, Improvements, and Renovations (1730), Accumulated Depreciation on Building, Improvements, and Renovations (1739), Other Structures and Facilities  (1740), Accumulated Depreciation on Other Structures and Facilities (1749), Capital Leases (1810), Accumulated Depreciated Assets under Capital Lease (1819), Leasehold Improvements (1820), Accumulated Depreciation on Leasehold Improvements (1829), and Construction in Progress (1720).  All leased and GSA-assigned property will be converted into CPAIS, but they will not require financial reconciliation because these items are expensed.

If differences are identified during the reconciliation process, FFIS should be adjusted to agree with the agency’s real property source documentation/system.  All FFIS adjustments required to ensure that account balances are fully supported by the source documentation must be prepared and processed prior to March 31, 2004.  The reconciliation should take place before conversion of data/balances into CPAIS. After an agreement has been struck and adjustments made to FFIS, agencies are ready to begin converting their real property data, including the asset values and other mandatory elements, into CPAIS.  Additionally, all FFIS adjustments required to ensure that account balances are fully supported by the source documentation, must be prepared and processed prior to March 31,2004.

Conversion of real property into CPAIS will be performed in two distinct sessions.  Session one will be for the automated conversion of data from the various source files into the CPAIS production environment. All data being converted must be certified by the organization providing the source data. Once the data is converted, the various agencies will run specific reports from CPAIS to certify the data was converted correctly. The reports will be compared to the agency’s source data. Adjustments will be made in CPAIS, if necessary, to ensure that the data was accurately converted and equal to the source data. When the agencies are satisfied with their data, they will sign a certified conversion data form indicating consent.  (See Conversion Certification Form in Appendix K)

The second conversion session will be for those real property transactions that must be manually converted and will be performed subsequent to the automated conversion. Those agencies that perform manual conversion will enter data directly into the CPAIS production environment including all mandatory data elements. When conversion is completed, they will run specific reports from CPAIS and compare the reports to their source data.  Adjustments will be made in CPAIS, if necessary, to ensure that the converted data is in agreement with their source data. When the agencies are satisfied with their data in CPAIS, they will sign a certified conversion data form indicating consent.  (See Conversion Certification Form in Appendix K)

Accumulated Depreciation values will not be converted; they will be calculated by CPAIS and posted to FFIS.  Agencies must zero out their FFIS real property general ledger asset and depreciation balances as of March 31,2004, after the reconciliation has been performed and before CPAIS reestablishes the asset and accumulated balance in FFIS. Accumulated Depreciation will be calculated based on the mid-year convention, which means that all property will be depreciated after June 30th of the year that the property is placed in service.

When all certification has been received, CPAIS will become operational and the data will become production data.

Conversion will occur in the third quarter of FY04 and will include all activity through March 31, 2004.

## Recommendations by Agency

In this section, we provide our recommendations for converting each agency’s real property data. For each agency, we provide

Current volume of open real property

Recommended conversion option and method

### Current Environment

Figure 1 shows CPAIS and the systems with which it will interface. The source systems are depicted on the left of the figure. The real property data within these applications will be converted for use in CPAIS. The arrows represent the flow of information between systems. Solid lines depict an automated interface performs the information exchange. Dotted lines indicate that some manual effort is required to exchange information (i.e., pull data from the GSA STAR web site before loading the GSA assignment data in CPAIS.)

Figure 1. Current Environment

#### Summary of Conversion Method Recommendations

Table 1 shows the recommended conversion methods (automated or manual) and the number of properties by data category for each agency. The gray shading indicates the agency does not have that type of property to convert. Details of the findings and alternative considerations are available and will be provided upon request.

| Table 1. Summary: Conversion Method Recommendations |
| --- |
| Agency | Data category | Automated | Manual |
| Agricultural Marketing Service | Leased | 96 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 56 |  |
| Animal and Plant Health Inspection Service | Leased | 324 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned | 600 |  |
|  | Work in progress | 10 |  |
|  | GSA assigned | 303 |  |
| Agricultural Research Service | Leased | 70 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned | 176 |  |
|  | Work in progress | 50 |  |
|  | GSA assigned | 15 |  |
| Cooperative State Research, Education, and Extension Service | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 1 |  |
| Departmental Administration | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned | 5 |  |
|  | Work in progress |  |  |
|  | GSA assigned | 17 |  |
| Economic Research Service | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 1 |  |
| Foreign Agricultural Service | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 1 |  |
| Food and Nutrition Service | Leased |  | 1 |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 70 |  |
| Forest Service | Leased (including land leases) | 643 |  |
|  | Capital leases | 30 |  |
|  | Leasehold improvements |  |  |
|  | Owned (buildings) | 52,285 |  |
|  | Work in progress |  |  |
|  | GSA assigned | 129 |  |
| Farm Service Agency | Leased | 2,392 |  |
| (Farm Service Agency County) | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 91 70 (county) |  |
| Food Safety Inspection Service | Leased |  | 4 |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 91 |  |
| Grain Inspection, Packers and Stockyards Administration | Leased | 11 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned | 2 |  |
|  | Work in progress |  |  |
|  | GSA assigned | 13 |  |
| National Appeals Division | Leased | 2 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 25 |  |
| National Agricultural Statistics Service | Leased | 1 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 25 |  |
| Natural Resources Conservation Service | Leased | 2,150 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned | 19 |  |
|  | Work in progress |  |  |
|  | GSA assigned | 153 |  |
| Office of Chief Information Officer | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 4 |  |
| Office of Chief Financial Officer | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 2 |  |
| Office of General Counsel | Leased |  |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 20 |  |
| Office of Inspector General | Leased |  | 1 |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 69 |  |
| Rural Development | Leased | 110 |  |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 117 |  |
| Risk Management Agency | Leased |  | 4 |
|  | Capital leases |  |  |
|  | Leasehold improvements |  |  |
|  | Owned |  |  |
|  | Work in progress |  |  |
|  | GSA assigned | 13 |  |
| Total |  | 60,262 | 10 |
| Note: The subtotals for automated conversion are 5,799 leases, 60 WIP, 53,087 owned, 30 capital leases, and 1,286 GSA assigned. At this time, the STAR data contain gaps in mandatory data for conversion. Default values will be identified for all mandatory data that are not available from STAR. Each agency will need to resolve these default values after completing their conversion. The leasehold improvement information is still being gathered. |

## Gaps

In this section, we identify the gaps in source data and suggest ways to mitigate them.

### Data Conversion Issues

These issues are based on an analysis of ARS’ FIRM database; FSA, RD and NRCS FIRM database from NITC; DA’s MS Access database, APHIS’ MS Access database and spreadsheet, and the GSA STAR rent bill format from their web site. Also, all data not in the initial conversion of CPAIS will be stored.

The following ARS data is not included in the initial conversion of CPAIS:

Housing attributes

Some lease data such as details for next payment term and lessee

Disposal data (beyond the disposal date)

Land rights.

The GSA assigned property rent information from GSA STAR contains gaps in the mandatory data for conversion. Default values have been identified for all mandatory data that are not available from STAR. Each Agency will need to resolve these default values after completing their conversion.

# Conversion Process

## Roles and Responsibilities

In this section, we describe the roles and responsibilities of the key participants in USDA’s real property conversion (see Table 2).

| Table 2. Conversion Roles and Responsibilities |
| --- |
| Role | Responsibility |
| OCFO ACFO-FS | Program management |
| OPPM | Functional Proponent Final approval of all standard List of Value (LOV) changes |
| ACFO-FS-CSOB COD-PRB OCFO | Provide guidance for financial data conversion |
| Agencies COD-PRB | Provide input and support standardizing the List of Values (LOV) Prepare data for conversion Reconciliation/Clean-up/Adjustments Validate converted data |
| Forest Service ACFO-FS-FSSB | Identify source data issues Develop and test conversion scripts Quality Assurance Testing Provide support during conversion |
| Data Administrator | Assign global update access to all standard LOV tables |
| NITC | Provide computer environment. |

## Conversion Process Description

This section describes the data conversion process of data preparation, extraction, transformation, load (including manual entry), test conversion, and reconciliation of real property data.

Developer – Turn over conversion software (April 04)

Quality Assurance (QA) – Verify data population (May 04)

ACFO – Collect data file from agencies’ sources

OPPM – Provide Star Rent file

QA staff – convert data to test environment

QA and Agency – Review completeness and accuracy of converted data

Automated Conversion of owned data file (May ’04)

ACFO – Obtain data file from agencies

OPPM – Provide the latest Star Rent file 	(March 04 or April 04 file)

Production Operations Staff – Convert data to production environment

Agency – Review completeness and accuracy of converted data

Agency – Make corrections (i.e. update default values, add additional data, etc.)

Agency – Certify data

Manual data entry of lease data (May/June ’04)

Agency – Enter any manual data to complete inventory

Agency – Review completeness

Agency – Certify data

## Technical Approach

The technical conversion approach for converting real property data into CPAIS defines the format for data exchange, the data transmission mechanism, and the tools for data extract/transform/load. The logical conversion approach addresses all property types (e.g., leased, owned, and GSA assigned).

### Leased and Owned Property from INFRA

The following approach will be used for converting the FS owned and leased real property data from INFRA:

FS will stop processing their leased and owned real property updates in INFRA on a specified date.

The CPAIS developers will import the INFRA data into CPAIS.

When all real property data has been loaded, FS will begin the validation process for their leased and owned data.

Figure 2 presents the planned approach for automating the FS conversion from INFRA.

Figure 2. INFRA Conversion Approach

Leased and owned property records will be loaded directly from FIRM (for ARS, FSA, NRCS, and RD) into the CPAIS database.  Table 3 identifies the mandatory data elements for those records.

| Table 3. Mandatory Data Elements: Leased and Owned Property |
| --- |
| Type of data | Mandatory data elements for leased and owned | Default assignment |
| GSA installation |  | If any of the mandatory elements is missing, the record will be skipped. |
|  | Instl No |  |
|  | Installation Name |  |
|  | Agency |  |
|  | GSA Region |  |
|  | Org | A default Org will be identified and entered for each agency. |
| GSA installation site |  |  |
|  | Geo City | If Geo_City is missing, it will be derived from City. |
|  | Geo County | If Geo_County is missing, it will be derived from County. |
|  | Geo State | If Geo_State is missing, it will be derived from State. |
|  | Street Adr. 1 |  |
|  | City |  |
|  | State |  |
|  | Zip Code |  |
|  | Cong Districts IDs | Can be blank. |
| Lease |  |  |
|  | Lease No | If Lease No is missing, the record will be skipped. |
|  | Name | If Name is missing, the record will be skipped. |
|  | Expiration Date | Can be blank. |
|  | Admin Org | A default Org will be identified and entered for each agency. |
|  | Managing Org | Default to ADMIN ORG. |
|  | Status | Default to ACTIVE. |
|  | Effective Date | Can be blank. |
|  | Annual $ | Default to $1. |
| Buildings | Org | A default Org will be identified and entered for each agency. |
|  | ID | If ID is missing, the record will be skipped. |
|  | Name | If Name is missing, the record will be skipped. |
|  | Predominant Usage | Derive from Property Usage in FIRM. |
| (For owned buildings only) | Property Type | Default to USDA OWNED. |
|  | Status | Default to EXISTING - OPERATIONAL. |
| Floor/room usage | Floor Name |  |
|  | Room Name |  |
|  | Space Usage Type |  |
|  | Space |  |
|  | UOM |  |
| Occupancy (Owned Property only) |  | No occupancy data will be captured. Data will be manually entered after conversion. |
|  | Agency |  |
|  | Personnel Type |  |
|  | No of Personnel |  |
| Land units | Org | A default Org will be identified and entered for each agency. |
|  | ID | If ID is missing, the record will be skipped. |
|  | Name | If Name is missing, the record will be skipped. |
|  | Predominant Usage | Derive from Property Usage in FIRM. |
|  | Units |  |
|  | UOM |  |
|  | :Price/UOM |  |
| (for owned land units only) | Property Type | Default to USDA OWNED. |
|  | Type | Derive from govt_owned_leased_trust in FIRM. |
|  | Status | Default to EXISTING-OPERATIONAL. |
|  | Rural |  |
|  | Urban |  |
| Other Structures | Org | A default Org will be identified and entered for each agency. |
|  | ID | If ID is missing, the record will be skipped. |
|  | Name | If Name is missing, the record will be skipped. |
|  | Type |  |
|  | Predominant Usage | Derive from Property Usage in FIRM. |
|  | Units |  |
|  | UOM |  |
|  | :Price/UOM |  |
| (For owned buildings only) | Property Type | Default to USDA OWNED. |
|  | Status | Default to EXISTING - OPERATIONAL. |
| Mods | Mod Type |  |
|  | Effective Date | Default to lease effective date. |

## Leased and Owned Property from FIRM

The following approach will be used for converting the ARS, FSA, NRCS, and RD owned and leased real property data from FIRM:

ARS, FSA, NRCS, and RD will stop processing their leased and owned real property updates in FIRM on a specified date.

ARS, FSA, NRCS, and RD leased and owned real property will be extracted from FIRM.

ARS, FSA, NRCS, and RD leased and owned real property data will be sent to the CPAIS developers.

The CPAIS developers will run the conversion script(s) on the FIRM data collected to load the leased and owned data in CPAIS.

When all real property data has been loaded, ARS, FSA, NRCS, and RD will begin the validation process for their leased and owned data.

Figure 3 presents the planned approach for automating the conversions from FIRM.

Figure 3. FIRM Conversion Approach

## Leased Data from ACCESS Database

The following approach will be used for converting the APHIS leased real property data from an ACCESS database:

APHIS will stop processing their leased property updates in their ACCESS database on a specified date.

APHIS ACCESS database (leased real property data) will be sent to the CPAIS developers.

The CPAIS developers will run the conversion script(s) on the data collected to load the leased data in CPAIS.

When the leased real property data has been loaded APHIS will begin the validation process for their leased data.

Figure 4 presents the planned approach for automating the conversions from the ACCESS database.

Figure 4. ACCESS Database Conversion Approach

### GSA Assigned Property from STAR

The following approach will be used to load all GSA assigned real property data from STAR:

The CPAIS developers will collect the STAR rent data from the GSA website for all Agencies.

The CPAIS developers will run the conversion script on the STAR data collected to load the GSA assigned data in CPAIS.

When all real property data has been loaded, the Agencies will begin the validation process for their GSA assigned data.

Figure 5 presents the planned approach for automating the conversions from STAR.

Figure 5. STAR Conversion Approach

The STAR Rent bill file (FIRM format) is the primary source for loading all GSA assigned properties for USDA.  A staging file will be used in the process.  (See Appendix G for the format of this file.).

The STAR Rent bill file includes only billing data for the current month. Only GSA assignments on the bill will be loaded.  Expired assignments are excluded, which means that property not on the STAR Rent bill file at conversion time will not be migrated to CPAIS.

The conversion consists of two steps:

- Push STAR Rent file data into the staging table using SQL Loader or a similar tool.

- Run Scripts to query and insert data into appropriate database tables.

#### Mandatory Elements

Table 4 lists the mandatory data elements to be extracted from the source data, and the default assignment if any data is missing.

| Table 4. Mandatory Data Elements: GSA Assigned Property |
| --- |
| Type of data | Mandatory data elements for GSA assignments | Default assignment |
| GSA assignment | Agency Code | The GSA code will be mapped to USDA Agency code. |
|  | Contract No | OA number from the source file or CBR number if the OA number is not available. |
|  | Name | Same as the *Contract No. |
|  | Org | A default Org will be identified and entered for each agency. |
|  | Expiration Date | A default value of current date (date of conversion) + 60 days. |
|  | Effective Date | A default value of current date (date of conversion). |
|  | Annual Rental Amount | Sum of CBR Total * 12 for all CBRs under the OA. |
|  | Monthly Rental Amount | Sum of CBR Total for all CBRs under the OA. |
| Property details | Property ID | GSA Property ID from the source file. |
|  | Region | GSA Region Code from the source file. |
|  | CBR | GSA CBR# from the source file. |
|  | Acc’t Code | Station Symbol from the source file. |
| GSA rent charges | Charge Type | GSA Charge Type from the source file. |
|  | Units | Units from the source file. |
|  | Uom | Unit of Measure from the source file. |
|  | Rate/Year | Annual rate from the source file. |
|  | Monthly $ | Monthly Charge from the source file. |
| Adjustments |  | No records are captured. |
| Mods |  | No Mods are captured. |
| Building | Building ID | GSA Property ID from the source file. |
|  | Property Type | Default to GSA ASSIGNED. |
|  | Predominant Usage | Default to OFFICE. |
|  | Org | A default Org will be identified and entered for each agency. |
|  | Development Status | Default to EXISTING - OPERATIONAL. |
| Floor/room usage |  | A default record is created for each GSA assigned building if there is charge type of “10-Shell Rental Rate–General” in the source file for the CBR. |
|  | Floor Name | Default to FLDAR1. |
|  | Room Name | Default to RDAM1. |
|  | Space Usage Type | Default to USABLE - GENERAL OFFICE. |
|  | Space | Units of charge type 10 from the source file. |
| Occupancy |  | No Occupancy data will be captured; data will be manually entered after being converted. |
| Address |  | Data will be captured from the source file for all buildings. |

### Owned, WIP, and Accounting Data from Excel

The following approach will be used for converting all owned property data (for APHIS), WIP property records (FS, APHIS, and ARS), and accounting data for owned and WIP properties from Excel spreadsheets:

Agencies will enter owned property data, WIP transactions, and accounting data into EXCEL spreadsheets.  See Appendix I for a sample of the accounting template being used to record subledger and value stream data.

COD will reconcile to the corresponding 03/31/2004 FFIS Real Property balances.

COD will verify the values in FUND, PROGRAM, TREASURY SYMBOL, BUDGET ORG, DIVISION, BOC and BEG BUDGET FY to the appropriate FFIS table(s).

Scripts will be run to create the property records in CPAIS for the owned property and WIP.

Accounting data will be loaded from spreadsheets into temporary tables.

Program to create Value Streams and Value Trans (as current period adjustments; utilizing exiting logic) from temp tables will be run.

Value Trans from current period adjustment (P) type to Beg Bal (B) type will be altered.

File will be transferred to FFIS using standard FTP.

Process as normal “AM” monthly trans.

Agencies will validate the beginning balances in CPAIS with data from their spreadsheets.

Each line of accounting in the spreadsheet must include a Unique Asset Identifier (UAI), which will be used to match the accounting to the asset.  See Appendix J for a layout of the UAI for each agency.

Figure 6 depicts the approach for automating the conversion of data from EXCEL spreadsheets.

Figure 6. Owned, WIP, and Accounting Conversion Approach

### Manual Data Entry

The following approach will be used for manual entry:

Agency will stop processing real property updates in their source on a specified date.

Agency will gather all reports and forms that contain real property data for conversion.

Agency will log into CPAIS and enter their real property data.

Once all real property data has been entered, the Agency will begin the validation process.

Figure 7 depicts the approach for keying data directly into CPAIS for conversion.

Figure 7. Manual Conversion Approach

## Data Preparation Approach

Preparing data for conversion into CPAIS is a complex process that will involve several different systems, teams, and approaches. An integrated approach that involves data owners, process experts, and a suite of tools is imperative if the conversion is to be successful.

Data in systems such as an agency’s source systems, along with myriad spreadsheets, are prone to numerous preparation issues because of such factors as size (volume) of the data and complexity of the systems. Preparation of the data also depends on the conversion option chosen. Options that require balances to summarize detail activity will need to have the summary balances created and reconciled to verify their accuracy.

### Categories of Data Preparation

The ideal strategy for reviewing the data and preparing it to be imported involves both automated procedures as well as the knowledge of the experienced property management and accounting community. Agencies will prepare the data before extracting and sending it to CPAIS. This section outlines the data preparation strategy for both the property management community and the conversion team.

Preparing the legacy data for conversion into CPAIS can be broken into two categories:

- Source data preparation, which is each agency’s responsibility

- Target data preparation, which is the CPAIS conversion team’s responsibility.

#### Source Data Preparation

Many steps involved in preparing the source data for conversion can begin immediately, while others must wait until the data is in the source data staging area.

Whether data will be converted or manually entered, each agency must:

Provide its organization structure

Review the LOV to ensure that the fields required by the agency are on the list.

Review and adjust capitalized property that does not meet the capitalization threshold according to the in-service date, i.e., prior to 10/1/2001, the threshold is $5,000, after 10/1/2001, the threshold is $25,000.

Provide a cross check of capitalized property data as described above to accounting records.  (i.e. ensure all capitalized property has associated accounting.)

Provide a point of contact for conversion.

Ensure consistent use of all codes, such as building status, usage type, and property designation; periodic reviews should be made to check for consistency.

Ensure consistent use of address lines 1 and 2.

Ensure correct beginning balance.

Ensure consistent use of designating a property as disposed, which will mean that the property is designated correctly during conversion.

Ensure consistent use of free form remarks and description text fields. Some codified data is stored in these free form fields. The Agencies should develop and document a standard method for data entry to facilitate an automated method to derive the codes during conversion. For example, RD enters remarks on the FIRM Site Screen in the format “Office will relocate on 01-01-04.”

Review the records and populate all the mandatory data fields.

Remove any obsolete records. We recommend that all property that has been inactive for longer than 2 years be removed.

Generate a list of all property for validation purposes.

Derive and automatically populate missing source data mandatory for the CPAIS target.

Run queries/reports to assure the data is stored correctly in the source.  If errors are detected, the data must be corrected in the source system.  Continue until the data is ready for conversion.

#### Target Data Preparation

Many steps involved in preparing CPAIS for receiving the converted data can begin immediately, while others will need to be taken when the data is ready to be loaded into CPAIS.

##### Immediate Target Data Preparation

Develop standard LOV to represent the remaining codified data, such as personnel type.

Develop standard format for address lines 1 and 2.

Develop target data element requirements.

Develop crosswalks from source code values to CPAIS code values.

Develop conversion code that automatically transforms source code values into CPAIS code values.

Develop queries/reports to validate conversion.

## Test Conversion

Leased and owned property records are independently managed by each agency. Some agencies are tracking property in FIRM, while others use MS Access, Excel spreadsheets and miscellaneous databases. Scripts will be used to automatically load data from FIRM for ARS, FSA, NRCS, and RD. Additionally scripts will be used to load data automatically for APHIS lease data from MS Access database and owned data from Excel spreadsheets, and DA owned data from MS Access. Once the conversion scripts are completed and CPAIS is implemented in a test environment, the entire conversion process must be tested. For details on testing the conversion scripts and test plans, refer to the Test Strategy Document.

## Validation Approach

The purpose of validation during data conversion is to verify that data extracted from the legacy system for leased, owned and GSA assignments are tracked through to its final disposition. Verification will take place after every step in the conversion process. This section outlines the reports and steps used during real property asset verification.

The following reports are examples of reports to be created from CPAIS and used for data validation (see Appendix K). Agencies should run reports of their property data in the source system at the cut-off for conversion to capture the exact data that they need to validate after conversion.

#### Reports for the Validation of Property Data

Installation Sites and Addresses

Inventory–Government Owned and Leased

Lease Basics

Lease Details

GSA Assignment Details

Subledger Summary

Value Stream

Miscellaneous Year-end Reconciliation.

#### Validation Steps

Ensure that the data extracted from the source system is properly loaded in CPAIS.

Validate the real property asset data stored in CPAIS to the data in the source system.

Load monthly TRANS File to create subledgers and value streams.

Validate accounting data in CPAIS to source spreadsheet.

Appendix A
Documents Reviewed

This appendix lists the documents reviewed when developing the CPAIS real property data conversion strategy.

Rural Development regarding use of the Foundation Information for Real Property Management (FIRM), 1_V11P27_1.doc.

U.S. Department of Agriculture, Corporate Property Automated Information System to Corporate Financial System (CPAIS - FFIS Interface) Detailed Design, August 29, 2003, Version 1.0.

U.S. Department of Agriculture, Corporate Property Automated Information System (CPAIS), Functional Requirements Analysis, June 13, 2003, Draft, Version 1.0.

U.S. Department of Agriculture, Service Level Agreement for USDA’s Real Property Management System, April 2003.

U.S. Department of Agriculture, Workshop and JAD Session Working Papers, March 2003.

U.S. Department of Agriculture, Leasing Handbook, October 2000.

CPAIS LOVs version 7.

FIRM table structures

CPAIS table structures

CPAIS screens as of September 9, 2003

APHIS database table structures

CPAIS Data Conversion in a Nutshell, November 10, 2003

CPAIS Property and Lease Data Conversion, Version 1.0, March 4, 2004

Appendix B
Source to Target Mappings

In this appendix, we provide all source-to-target data element mappings.

| Table 5. Review of APHIS Data Export From 5/2003 |
| --- |
| APHIS tables | APHIS Key | Format | CPAIS tables | Comments |
| leases |  |  | accplishment_instruments ai,ii_leases ls, ii_gsa_installation_site gsa, ii_property_addresses addr, land_units lu, ii_lease_line_items lli |  |
| TYPE_OF_ACTION |  | VARCHAR2(50) | ai.obj_name |  |
| LEASE_NUMBER | NOT NULL | VARCHAR2(6) | ai.id |  |
| STREET_ADDRESS |  | VARCHAR2(50) | addr.line_1 | for gsa? |
| CITY |  | VARCHAR2(50) | addr.city_name | for gsa? |
| STATE |  | VARCHAR2(2) | addr.state_code | for gsa? |
| ZIP |  | VARCHAR2(50) | addr.postal_code | for gsa? |
| COUNTY |  | VARCHAR2(50) | addr.county_country_name | for gsa? |
| CONGRESSIONAL_DIST |  | VARCHAR2(50) | get cong.cn from lu with this code as id for the state_abbrv | has a list of congressional districts |
| LESSOR_NAME |  | VARCHAR2(50) | ii_contacts, etc from lessor_cont_cn |  |
| LESSOR_ADDRESS |  | VARCHAR2(50) | ii_contacts, etc from lessor_cont_cn |  |
| LESSOR_CITY |  | VARCHAR2(50) | ii_contacts, etc from lessor_cont_cn |  |
| LESSOR_STATE |  | VARCHAR2(2) | ii_contacts, etc from lessor_cont_cn |  |
| LESSOR_ZIP |  | VARCHAR2(50) | ii_contacts, etc from lessor_cont_cn |  |
| LESSOR_PHONE_NUMBER |  | VARCHAR2(50) | ii_contacts, etc from lessor_cont_cn |  |
| LESSOR_FAX_NUMBER |  | VARCHAR2(50) | ii_contacts, etc from lessor_cont_cn |  |
| LEASE_START_DATE |  | VARCHAR2(10) | ls.effective_date |  |
| LEASE_EXPIRATION_DATE |  | VARCHAR2(10) | ai.exp_expiration_date |  |
| LEASE_ADJUSTMENT_DATE |  | VARCHAR2(10) |  |  |
| TERMINATION_RIGHTS_DATE |  | VARCHAR2(10) |  |  |
| TERMINATION_RIGHTS_DAYS |  | VARCHAR2(3) | ls.termination_notice_days |  |
| RENEWAL_RIGHTS_DATE |  | VARCHAR2(50) |  |  |
| RENEWAL_RIGHTS_DAYS |  | VARCHAR2(50) | ls.option_period, ls.number_of_options = 1 |  |
| TIN |  | VARCHAR2(9) | ls.tin_number |  |
| DUNS |  | VARCHAR2(50) | ls.duns_number |  |
| VXP |  | VARCHAR2(50) |  |  |
| TYPE_OF_CONTRACTOR |  | VARCHAR2(50) |  |  |
| TOTAL_SQUARE_FDAT |  | NUMBER(11) |  |  |
| INSTALLATION_NUMBER |  | VARCHAR2(5) | lu.id for ‘GSA_INSTALLATION_SITE’ | use lu.cn for ls.gsa-installation_site_cn |
| ANNUAL_RENT |  | NUMBER(13,2) | ls.annual_rental_amount |  |
| RATEPSF |  | NUMBER(13,2) |  |  |
| BORDER_STATION |  | VARCHAR2(5) |  |  |
| UTILITIES |  | VARCHAR2(50) |  |  |
| JANITORIAL |  | VARCHAR2(50) |  |  |
| CBA |  | VARCHAR2(50) |  |  |
| HISTORICAL |  | VARCHAR2(50) | gsa.historical_indicator |  |
| SPECIALIST_INITIALS |  | VARCHAR2(50) |  |  |
| LAND |  | NUMBER(11) |  |  |
| ACRES_OR_SF |  | VARCHAR2(50) | lli.uom_code |  |
| HANDICAP_ACCESSIBLE |  | VARCHAR2(50) |  |  |
| COLLOCATION |  | VARCHAR2(50) |  |  |
| non_leases |  |  |  |  |
| ID |  | VARCHAR2(34) | ai.id |  |
| TYPE_OF_ACTION |  | VARCHAR2(50) | ai.obj_name | values FREE, AGREEMENT, CDAPERATIVE AGREEMENT, PERMIT |
| AGENCY |  | VARCHAR2(50) |  |  |
| PROGRAM |  | VARCHAR2(50) |  |  |
| REGION |  | VARCHAR2(50) |  |  |
| STREET_ADDRESS |  | VARCHAR2(50) |  |  |
| CITY |  | VARCHAR2(50) |  |  |
| STATE |  | VARCHAR2(50) |  |  |
| ZIP |  | VARCHAR2(50) |  |  |
| PROGRAM_PHONE_NUM |  | VARCHAR2(50) |  |  |
| PROGRAM_FAX |  | VARCHAR2(50) |  |  |
| LESSOR_NAME |  | VARCHAR2(50) |  |  |
| LESSOR_PHONE_NUM |  | VARCHAR2(50) |  |  |
| LESSOR_FAX_NUM |  | VARCHAR2(50) |  |  |
| LESSOR_STREET_ADDRESS |  | VARCHAR2(50) |  |  |
| LESSOR_CITY |  | VARCHAR2(50) |  |  |
| LESSOR_STATE |  | VARCHAR2(50) |  |  |
| LESSOR_ZIP |  | VARCHAR2(50) |  |  |
| REMARKS |  | VARCHAR2(255) |  |  |
| STATUS |  | VARCHAR2(50) |  |  |
| STATUS_EFFECTIVE_DATE |  | DATE |  |  |
| TYPE_OF_CONTRACTOR |  | VARCHAR2(50) |  |  |
| EMPLOYEES |  | VARCHAR2(50) |  |  |
| OFFICE |  | NUMBER(11) |  |  |
| STORAGE |  | NUMBER(11) |  |  |
| OTHER |  | NUMBER(11) |  |  |
| START_DATE |  | DATE |  |  |
| EXPIRATION_DATE |  | DATE |  |  |
| SPEC_INTI |  | VARCHAR2(50) |  |  |
| TOTAL_SQUARE_FEET |  | VARCHAR2(50) |  |  |
| PARKING_SPACES |  | VARCHAR2(50) |  |  |
| COLLOCATION |  | VARCHAR2(50) |  |  |
| HANDICAPPED_ACCESSIBLE |  | VARCHAR2(50) |  |  |
| UTILITIES |  | VARCHAR2(50) |  |  |
| JANITORIAL |  | VARCHAR2(50) |  |  |
| CBA |  | VARCHAR2(50) |  |  |
| HISTORICAL |  | VARCHAR2(50) |  |  |
| ANNUAL_RENT |  | NUMBER(13,2) |  |  |
| tblprogram |  |  | ii_lease_line_items lli, accplishment_instruments ai |  |
| ID |  | VARCHAR2(34) | lli.line_item_no |  |
| FIELD1 |  | VARCHAR2(50) |  |  |
| LEASE_NUMBER |  | VARCHAR2(6) | ai.id |  |
| AGENCY |  | VARCHAR2(50) | ai.agency_code |  |
| PROGRAM |  | VARCHAR2(50) |  |  |
| REGION |  | VARCHAR2(50) |  |  |
| ANNUAL_RENT |  | NUMBER(13,2) |  |  |
| PROGRAM_PHONE |  | VARCHAR2(50) |  |  |
| PROGRAM_FAX |  | VARCHAR2(50) |  |  |
| EMPLOYEES |  | VARCHAR2(50) |  |  |
| OFFICE |  | NUMBER(11) |  |  |
| STORAGE |  | NUMBER(11) |  |  |
| OTHER |  | NUMBER(11) |  |  |
| PARKING_SPACES |  | VARCHAR2(50) |  |  |
| TOTAL_SQUARE_FEET |  | NUMBER(11) |  |  |
| FY_APPROPRIATION1 |  | VARCHAR2(3) |  |  |
| ACCT_PROGRAM1 |  | VARCHAR2(4) |  |  |
| PROJECT1 |  | VARCHAR2(3) |  |  |
| PERCENTAGE1 |  | VARCHAR2(50) |  |  |
| FY2 |  | VARCHAR2(3) |  |  |
| ACCT_PROGRAM2 |  | VARCHAR2(4) |  |  |
| PROJECT2 |  | VARCHAR2(3) |  |  |
| PERCENTAGE2 |  | VARCHAR2(50) |  |  |
| FY3 |  | VARCHAR2(3) |  |  |
| ACC_PROGRAM3 |  | VARCHAR2(4) |  |  |
| PROJECT3 |  | VARCHAR2(3) |  |  |
| PERCENTAGE |  | VARCHAR2(50) |  |  |
| FY4 |  | VARCHAR2(3) |  |  |
| ACCT_PROGRAM4 |  | VARCHAR2(4) |  |  |
| PROJECT4 |  | VARCHAR2(3) |  |  |
| PERCENTAGE4 |  | VARCHAR2(50) |  |  |
| FY5 |  | VARCHAR2(3) |  |  |
| ACCT_PROGRAM5 |  | VARCHAR2(4) |  |  |
| PROJECT5 |  | VARCHAR2(3) |  |  |
| PERCENTAGE5 |  | VARCHAR2(50) |  |  |
| FY6 |  | VARCHAR2(3) |  |  |
| ACCT_CODE6 |  | VARCHAR2(4) |  |  |
| PROJECT6 |  | VARCHAR2(3) |  |  |
| PERCENTAGE6 |  | VARCHAR2(50) |  |  |
| REMARKS |  | VARCHAR2(255) |  |  |
| RATEPSF |  | NUMBER(13,2) |  |  |
| UTILITIZATION_RATE |  | VARCHAR2(50) |  |  |
| EMERGENCY |  | VARCHAR2(5) |  |  |
| STATUS |  | VARCHAR2(50) |  |  |
| EFFECTIVE_DATE |  | DATE |  |  |
| aphis_gl |  |  | ii_features fea, ii_rpa_value_streams vs |  |
| Sequence No. |  |  |  | don’t know how to map this to above tables |
| Location No. |  |  |  | don’t know how to map this to above tables |
| Site Visit/Desktop |  |  |  |  |
| Control No. |  |  |  | don’t know how to map this to above tables |
| Location |  |  |  | don’t know how to map this to above tables |
| Agency Code |  |  | fea.agency_code |  |
| Owned/Leased |  |  | fea.property_type |  |
| Building No. |  |  | fea.id | if id is not null then obj_name = ‘BUILDING’ else other structure, seq based on control no |
| QTY |  |  |  | number of properties |
| Description |  |  | fea.remarks | use to determine obj_name for other structures |
| Account |  |  | va.gl_account | different values than FS |
| Acquisition Code |  |  | fea.acquisition_method |  |
| ConditionCode |  |  | fea.condition_rating |  |
| Gross S.F./Capacity |  |  | fea.gross_sqft |  |
| Date Built |  |  | fea.year_constructed |  |
| Date Acquired |  |  | fea.acquisition_date |  |
| Cost |  |  | vs.amount |  |
| Depreciable Life |  |  | vs.life |  |
| Elapsed Life |  |  | vs.in_service_date = current date - elapsed life |  |
| Life-To-Date Depreciation |  |  | vs.amount for Depreciation GL Account |  |

| Table 6. Review of DA Data Export From 11/2003 |
| --- |
| DA tables | Format | CPAIS tables | Comments |
| fcadmin_saclass |  | ii_codes | space class code, reference table |
| saclass_code | VARCHAR2(20) | ii_building_floor_rooms.space_usage_type | PERS, SERV, CORE |
| description | VARCHAR2(32) |  | Personnel Space, Service Space, Building Core Space |
| status | VARCHAR2(1) |  |  |
| user_name_created | VARCHAR2(12) |  |  |
| date_created | DATE |  |  |
| user_name_modified | VARCHAR2(12) |  |  |
| date_modified | DATE |  |  |
| group_owned_by | VARCHAR2(12) |  |  |
| soft_delete_flag | VARCHAR2(1) |  |  |
| spanlink_num | VARCHAR2(2) |  |  |
| fcadmin_saclstyp |  |  | more detail on space class |
| saclass_code | VARCHAR2(20) | ii_codes |  |
| saclstyp_code | VARCHAR2(20) | ii_building_floor_rooms.space_usage_type |  |
| description | VARCHAR2(32) |  |  |
| functional_use | VARCHAR2(32) |  |  |
| capacity | VARCHAR2(2) |  |  |
| user_name_created | VARCHAR2(12) |  |  |
| date_created | DATE |  |  |
| user_name_modified | VARCHAR2(12) |  |  |
| date_modified | DATE |  |  |
| group_owned_by | VARCHAR2(12) |  |  |
| soft_delete_flag | VARCHAR2(1) |  |  |
| spanlink_num | VARCHAR2(2) |  |  |
| fcadmin_spbldinf |  | ii_features fea, ii_property_addresses adr, ii_leases ls, ii_bldg_floors_rooms rm | building data |
| spbldinf_code | VARCHAR2(16) | fea.id |  |
| splocation_code | VARCHAR2(72) | fea.id |  |
| spproinf_code | VARCHAR2(20) |  |  |
| pmmntctr_code | VARCHAR2(2) |  | no data |
| spcost_code | VARCHAR2(30) |  | no data |
| name | VARCHAR2(32) | fea.name |  |
| address_1 | VARCHAR2(32) | adr.line_1 |  |
| address_2 | VARCHAR2(32) | adr.line_2 |  |
| phone | VARCHAR2(16) |  |  |
| own_lease | VARCHAR2(1) | fea.property_type |  |
| tot_usable_area | NUMBER(12,4) | ? |  |
| tot_gross_area | NUMBER(12,4) | fea.gross_sqft |  |
| notes | VARCHAR2(12) |  | no data |
| tot_const_area | NUMBER(12,4) | ? |  |
| tot_rent_area | NUMBER(12,4) | rm.space for space_usage_type 'USABLE - GENERAL OFFICE' |  |
| tot_shaft_area | NUMBER(12,4) | ? |  |
| tot_flr_common | NUMBER(12,4) | rm.space for space_usage_type 'JOINT USE _ BUILDING COMMON' |  |
| tot_bldg_common | NUMBER(12,4) | computed |  |
| tot_ten_common | NUMBER(12,4) | computed |  |
| tot_prop_common | NUMBER(12,4) | ? |  |
| tot_company_common | NUMBER(12,4) | ? |  |
| tot_circ_area | NUMBER(12,4) | ? |  |
| tot_direct_area | NUMBER(12,4) | ? |  |
| calc_flag | VARCHAR2(1) |  | no data |
| user_name_created | VARCHAR2(12) |  | no data |
| date_created | DATE |  | no data |
| user_name_modified | VARCHAR2(12) |  | no data |
| date_modified | DATE |  | no data |
| group_owned_by | VARCHAR2(12) |  | no data |
| soft_delete_flag | VARCHAR2(1) |  | no data |
| spanlink_num | VARCHAR2(2) |  | no data |
| picture | VARCHAR2(255) |  | no data |
| timezone | VARCHAR2(20) |  | no data |
| ru_factor | NUMBER(12,4) | ? |  |
| annual_rent | NUMBER(12) | ls.annual_rent |  |
| fcadmin_spbldloc |  | ii_bldg_floors_rooms rm, ii_features fea, ii_ga_tenant_no_sur_space_asn ten | building floor data |
| spbldinf_code | VARCHAR2(16) | fea.id |  |
| spbldloc_code | VARCHAR2(8) | fea.id |  |
| splocation_code | VARCHAR2(72) | fea.id with floor id |  |
| spfloors_code | VARCHAR2(8) |  |  |
| sploctyp_code | VARCHAR2(20) |  | all 'AREA' |
| description | VARCHAR2(25) | rm.floor_name |  |
| phone | VARCHAR2(16) |  | no data |
| area | NUMBER(12,4) | rm.gross_sqft |  |
| unit_cost | NUMBER(12,4) |  |  |
| total_cost | NUMBER(12,4) | ten.monthly_amt |  |
| notes | VARCHAR2(12) |  | no data |
| occ_vac | VARCHAR2(1) |  | all 'O' |
| rentable_area | NUMBER(12,4) |  | all 0 |
| flr_common_area | NUMBER(12,4) |  | all 0 |
| bld_common_area | NUMBER(12,4) |  | all 0 |
| ten_common_area | NUMBER(12,4) |  | all 0 |
| shaft_area | NUMBER(12,4) |  | all 0 |
| usable_area | NUMBER(12,4) |  | all 0 |
| direct_area | NUMBER(12,4) |  | all 0 |
| circ_area | NUMBER(12,4) |  | all 0 |
| location_type | VARCHAR2(4) |  | all 'CI' |
| user_name_created | VARCHAR2(12) |  | no data |
| date_created | DATE |  | no data |
| user_name_modified | VARCHAR2(12) |  | no data |
| date_modified | DATE |  | no data |
| group_owned_by | VARCHAR2(12) |  | no data |
| soft_delete_flag | VARCHAR2(1) |  | no data |
| spanlink_num | VARCHAR2(2) |  | no data |
| fcadmin_spbldrom |  | ii_features fea, ii_bldg_floors_rooms rm | building floor rooms and space class data |
| spbldinf_code | VARCHAR2(16) | fea.id |  |
| spbldrom_code | VARCHAR2(16) | rm.room_name |  |
| spfloors_code | VARCHAR2(8) |  |  |
| splocation_code | VARCHAR2(72) | fea.id with floor id and room id |  |
| spbldloc_code | VARCHAR2(8) |  |  |
| saclass_code | VARCHAR2(20) | rm.space_usage_type |  |
| saclstyp_code | VARCHAR2(20) | rm.space_usage_type |  |
| description | VARCHAR2(25) |  |  |
| phone | VARCHAR2(16) |  | no data |
| area | NUMBER(12,4) | rm.space |  |
| notes | VARCHAR2(12) |  | no data |
| occ_vac | VARCHAR2(1) |  | O' or 'V' |
| storageyn | VARCHAR2(1) |  |  |
| location_code | VARCHAR2(10) |  | no data |
| subloc_type | VARCHAR2(18) | ? |  |
| user_name_created | VARCHAR2(12) |  | no data |
| date_created | DATE |  | no data |
| user_name_modified | VARCHAR2(12) |  | no data |
| date_modified | DATE |  | no data |
| group_owned_by | VARCHAR2(12) |  | no data |
| soft_delete_flag | VARCHAR2(1) |  | no data |
| spanlink_num | VARCHAR2(2) |  | no data |
| haz_mat | VARCHAR2(1) |  | no data |
| reservable_flag | VARCHAR2(2) |  | all 0 |
| fcadmin_spbldrom_attrib |  | ii_features fea, ii_bldg_floors_rooms rm | building room space attribute (all Building Renovation) |
| spattrib_code | VARCHAR2(20) |  |  |
| spbldinf_code | VARCHAR2(16) | fea.id |  |
| spbldrom_code | VARCHAR2(16) | rm.room_name |  |
| spattrib_category_code | VARCHAR2(40) |  | all 'Building Renovation' |
| spnotes_id | VARCHAR2(12) |  | no data |
| string_value | VARCHAR2(40) |  | no data |
| num_value | VARCHAR2(2) |  |  |
| dec_value | NUMBER(12,4) |  | all 0 |
| date_value | DATE |  | no data |
| time_value | DATE |  | no data |
| user_name_created | VARCHAR2(12) |  | no data |
| date_created | DATE |  | no data |
| user_name_modified | VARCHAR2(12) |  | no data |
| date_modified | DATE |  | no data |
| group_owned_by | VARCHAR2(12) |  | no data |
| soft_delete_flag | VARCHAR2(1) |  | no data |
| spanlink_num | VARCHAR2(2) |  | no data |
| fcadmin_spcharge |  | ii_features fea, ii_bldg_floors_rooms rm, ii_ga_tenant_no_shr_space_asn ten, ii_contacts co | building floor room area data by tenant |
| sporg_code | VARCHAR2(18) | co.id |  |
| spcharge_seq_num | NUMBER(12,4) |  |  |
| spbldinf_code | VARCHAR2(16) | fea.id |  |
| spfloors_code | VARCHAR2(8) | flr.id |  |
| spbldrom_code | VARCHAR2(16) | rm.id |  |
| area | NUMBER(12,4) | ten.space |  |
| pct | NUMBER(12,4) |  | all 100 |
| user_name_created | VARCHAR2(12) |  | no data |
| date_created | DATE |  | no data |
| user_name_modified | VARCHAR2(12) |  | no data |
| date_modified | DATE |  | no data |

| Table 7. Review of ARS (1205) FIRM Data Export From 5/2003 |
| --- |
| CPAIS mandatory elements | Total count | Count of ARS records missing data | Action |
| Installation (Owned and Leased) | 156 |  |  |
| *Instl.No. |  | 0 |  |
| *Installation Name |  | 0 |  |
| *Agency |  | 0 |  |
| *GSA Region |  | 156 | Derive from Site Geo Code |
| *Org |  | 156 | Derive from property |
| Site (Owned and Leased) | 433 |  |  |
| *Inst. No. |  | 0 |  |
| *Geo City |  | 0 |  |
| *Geo County |  | 0 |  |
| *Geo State |  | 0 |  |
| *Street Adr. 1 |  | 20 | ARS will complete |
| *City |  | 0 |  |
| *County |  | 12 | ARS will complete |
| *State |  | 0 |  |
| *Zip Code |  | 2 | ARS will complete |
| Congressional Districts (Owned and Leased) | 433 |  |  |
| *Cong Districts IDs |  | 19 | ARS will complete |
| Lease Module Mandatory Elements |  |  |  |
| Lease | 12 |  |  |
| *Lease No |  | 0 |  |
| *Name |  | 0 |  |
| *Expiration Date |  | 12 | Free space, no action |
| *Admin Org |  | 12 | Assign default |
| *Managing Org |  | 12 | Assign default |
| *Status |  | 12 | Free space, no action |
| *Effective Date |  | 12 | Free space, no action |
| *Annual $ |  | 12 | Free space, no action |
| Building | 54 |  |  |
| *Org |  | 54 | Derive from ID |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Land Units | 115 |  |  |
| *Org |  | 115 | Derive from ID |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Units |  | 115 | Some space data on lease |
| *UOM |  | 115 | Some space data on lease |
| *Price/UOM |  | 115 |  |
| Other Structures | 10 |  |  |
| *Org |  | 10 | Derive from ID |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Units |  | 10 |  |
| *UOM |  | 10 |  |
| *Price/UOM |  | 10 |  |
| Mods (move to ii_acc_inst_amendments) | 0 |  |  |
| *Mod Type |  |  |  |
| *Effective Date |  |  |  |
| Owned Property Module Mandatory Elements |  |  |  |
| Building | 3570 |  |  |
| *Org |  | 3570 | Derive from ID |
| *Building ID |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Development Status |  | 3570 | Assign default EXISTING - OPERATIONAL |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| Occupancy | no data |  |  |
| *Agency |  |  |  |
| *Personnel Type |  |  |  |
| *No. of Personnel |  |  |  |
| Land Units | 178 |  |  |
| *Org |  | 178 | Derive from ID |
| *Land Unit ID |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Type |  | 0 |  |
| *Development Status |  | 178 | Assign default EXISTING - OPERATIONAL |
| *Rural/Urban |  | 0 |  |
| Other Structures | 1645 |  |  |
| *Org |  | 1645 | Derive from ID |
| *Feature ID |  | 0 |  |
| *Type |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predom Usage |  | 0 |  |
| *Development Status |  | 1645 | Assign default EXISTING - OPERATIONAL |
| GSA Assignment Module Mandatory Elements | no GSA Assignments |  |  |

| Table 8. Review of FSA (1201, 1293) FIRM Data Export on NITC FIRM CD |
| --- |
| CPAIS mandatory elements | Total count | Count of FSA records missing data | Action |
| Installation (Owned and Leased) | 60 |  | State Offices |
| *Instl.No. |  | 0 |  |
| *Installation Name |  | 0 |  |
| *Agency |  | 0 |  |
| *GSA Region |  | 60 | Derive from Site Geo Code |
| *Org |  | 60 | Derive from property |
| Site (Owned and Leased) | 133 |  | County Offices |
| *Inst. No. |  | 0 |  |
| *Geo City |  | 0 |  |
| *Geo County |  | 0 |  |
| *Geo State |  | 0 |  |
| *Street Adr. 1 |  | 98 |  |
| *City |  | 98 | Derive from Geo City |
| *County |  | 100 | Derive from Geo County |
| *State |  | 98 | Derive from Geo State |
| *Zip Code |  | 98 |  |
| Congressional Districts (Owned and Leased) | 101 |  |  |
| *Cong Districts IDs |  | 101 | Derive from Geo data |
| Lease Module Mandatory Elements |  |  |  |
| Lease | 2483 |  | Should be 2359 commercial leases |
| *Lease No |  | 0 |  |
| *Name |  | 67 |  |
| *Expiration Date |  | 67 |  |
| *Admin Org |  | 2483 | Assign default |
| *Managing Org |  | 2483 | Assign default |
| *Status |  | 2483 | Assign default ACTIVE |
| *Effective Date |  | 68 |  |
| *Annual $ |  | 67 |  |
| Building | 2487 |  | see note |
| *Org |  | 2487 | Assign default |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Land Units | 0 |  |  |
| *Org |  |  |  |
| *ID |  |  |  |
| *Name |  |  |  |
| *Predominant Usage |  |  |  |
| *Units |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Other Structures | 0 |  |  |
| *Org |  |  |  |
| *ID |  |  |  |
| *Name |  |  |  |
| *Type |  |  |  |
| *Predominant Usage |  |  |  |
| *Units |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Mods (move to ii_acc_inst_amendments) | 0 |  |  |
| *Mod Type |  |  |  |
| *Effective Date |  |  |  |
| Owned Property Module Mandatory Elements |  |  |  |
| Building | 76 |  | All records are GSA Assigned Rent |
| *Org |  | 76 | Assign default |
| *Building ID |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Development Status |  | 76 |  |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| Occupancy | no data |  |  |
| *Agency |  |  |  |
| *Personnel Type |  |  |  |
| *No. of Personnel |  |  |  |
| Land Units | 0 |  |  |
| *Org |  |  |  |
| *Land Unit ID |  |  |  |
| *Property Type |  |  |  |
| *Predominant Usage |  |  |  |
| *Type |  |  |  |
| *Development Status |  |  |  |
| *Rural |  |  |  |
| *Urban |  |  |  |
| Other Structures | 0 |  |  |
| *Org |  |  |  |
| *Feature ID |  |  |  |
| *Type |  |  |  |
| *Property Type |  |  |  |
| *Predom Usage |  |  |  |
| *Development Status |  |  |  |
| GSA Assignment Module Mandatory Elements |  |  |  |
| will come from GSA Rent Bill |  |  |  |
| Note: Not using GSA Assigned indicator on property, only 75 records where GSA Assigned = 'N'. None of the 2487 leased buildings have GSA Assigned detailed data. |

| Table 9. Review of NRCS (1235) FIRM Data Export on NITC FIRM CD |
| --- |
| CPAIS mandatory elements | Total count | Count of NRCS records missing data | Action |
| Installation (Owned and Leased) | 4169 |  |  |
| *Instl.No. |  | 0 |  |
| *Installation Name |  | 0 |  |
| *Agency |  | 0 |  |
| *GSA Region |  | 4169 | Derive from Site Geo Code |
| *Org |  | 4169 | Derive from property |
| Site (Owned and Leased) | 4175 |  |  |
| *Inst. No. |  | 0 |  |
| *Geo City |  | 0 |  |
| *Geo County |  | 0 |  |
| *Geo State |  | 0 |  |
| *Street Adr. 1 |  | 52 | NRCS will complete |
| *City |  | 513 | NRCS will complete |
| *County |  | 1875 | NRCS will complete |
| *State |  | 514 | NRCS will complete |
| *Zip Code |  | 518 | NRCS will complete |
| Congressional Districts (Owned and Leased) | 2974 |  |  |
| *Cong Districts IDs |  | 1201 | NRCS will complete |
| Lease Module Mandatory Elements |  |  |  |
| Lease | 2105 |  |  |
| *Lease No |  | 0 |  |
| *Name |  | 480 |  |
| *Expiration Date |  | 173 |  |
| *Admin Org |  | 2105 | Assign default |
| *Managing Org |  | 2105 | Assign default |
| *Status |  | 2105 |  |
| *Effective Date |  | 168 |  |
| *Annual $ |  | 75 |  |
| Building | 2100 |  | 4 are GSA Assignments? |
| *Org |  | 2100 | Derive from ID |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Land Units | 9 |  |  |
| *Org |  | 9 | Derive from ID |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Units |  | 0 | 33 |
| *UOM |  | 0 |  |
| *Price/UOM |  | 9 | Derive from lease? |
| Other Structures | 3 |  |  |
| *Org |  | 3 | Derive from ID |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Units |  | 3 | Not on lease? |
| *UOM |  | 3 | Not on lease? |
| *Price/UOM |  | 3 | Derive from lease? |
| Mods (move to ii_acc_inst_amendments) | 0 |  |  |
| *Mod Type |  |  |  |
| *Effective Date |  |  |  |
| Owned Property Module Mandatory Elements |  |  |  |
| Building | 594 |  |  |
| *Org |  | 594 | Derive from ID |
| *Building ID |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Development Status |  | 594 | Assign default EXISTING - OPERATIONAL |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| Occupancy | no data |  |  |
| *Agency |  |  |  |
| *Personnel Type |  |  |  |
| *No. of Personnel |  |  |  |
| Land Units | 548 |  |  |
| *Org |  | 548 | Derive from ID |
| *Land Unit ID |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Type |  | 0 |  |
| *Development Status |  | 548 | Assign default EXISTING - OPERATIONAL |
| *Rural/Urban |  | 0 |  |
| Other Structures | 8 |  |  |
| *Org |  | 8 | Derive from ID |
| *Feature ID |  | 0 |  |
| *Type |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predom Usage |  | 0 |  |
| *Development Status |  | 8 | Assign default EXISTING - OPERATIONAL |
| GSA Assignment Module Mandatory Elements |  |  |  |
| will come from GSA Rent Bill |  |  |  |

| Table 10. Review of RD (1215) FIRM Data Export on NITC FIRM CD |
| --- |
| CPAIS mandatory elements | Total count | Count of RD records missing data | Action/comment |
| Installation (Owned and Leased) | 1553 |  |  |
| *Instl.No. |  | 0 |  |
| *Installation Name |  | 0 |  |
| *Agency |  | 0 |  |
| *GSA Region |  | 1553 | Assign default |
| *Org |  | 1553 |  |
| Site (Owned and Leased) | 1616 |  |  |
| *Inst. No. |  | 0 |  |
| *Geo City |  | 0 |  |
| *Geo County |  | 0 |  |
| *Geo State |  | 0 |  |
| *Street Adr. 1 |  | 29 | Need from RD |
| *City |  | 15 | Derive from geo city |
| *County |  | 246 | Derive from geo county |
| *State |  | 14 | Derive from geo state |
| *Zip Code |  | 14 | Need for RD |
| Congressional Districts (Owned and Leased) | 1055 |  |  |
| *Cong Districts IDs |  | 1055 | RD will complete |
| Lease Module Mandatory Elements |  |  |  |
| Lease | 1368 |  |  |
| *Lease No |  | 0 |  |
| *Name |  | 7 |  |
| *Expiration Date |  | 485 |  |
| *Admin Org |  | 1368 |  |
| *Managing Org |  | 1368 |  |
| *Status |  | 1368 | Assign default Active |
| *Effective Date |  | 53 |  |
| *Annual $ |  | 6 |  |
| Building | 1564 |  | 241 are GSA Assigned property |
| *Org |  | 1564 | Derive from ID (2 chars for state¦¦0¦¦2 chars for county |
| *ID |  | 0 |  |
| *Name |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Land Units | 0 |  |  |
| *Org |  |  |  |
| *ID |  |  |  |
| *Name |  |  |  |
| *Predominant Usage |  |  |  |
| *Units |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Other Structures | 0 |  |  |
| *Org |  |  |  |
| *ID |  |  |  |
| *Name |  |  |  |
| *Type |  |  |  |
| *Predominant Usage |  |  |  |
| *Units |  |  |  |
| *UOM |  |  |  |
| *Price/UOM |  |  |  |
| Mods (move to ii_acc_inst_amendments) | 0 |  |  |
| *Mod Type |  |  |  |
| *Effective Date |  |  |  |
| Owned Property Module Mandatory Elements |  |  |  |
| Building | 272 |  | 245 are GSA Assigned property |
| *Org |  | 272 | Derive from ID (2 chars for state¦¦0¦¦2 chars for county |
| *Building ID |  | 0 |  |
| *Property Type |  | 0 |  |
| *Predominant Usage |  | 0 |  |
| *Development Status |  | 272 | Assign default EXISTING - OPERATIONAL |
| Floor/Room Usage | no data |  |  |
| *Floor Name |  |  |  |
| *Room Name |  |  |  |
| *Space Usage Type |  |  |  |
| *Space |  |  |  |
| Occupancy | no data |  |  |
| *Agency |  |  |  |
| *Personnel Type |  |  |  |
| *No. of Personnel |  |  |  |
| Land Units | 0 |  |  |
| *Org |  |  |  |
| *Land Unit ID |  |  |  |
| *Property Type |  |  |  |
| *Predominant Usage |  |  |  |
| *Type |  |  |  |
| *Development Status |  |  |  |
| *Rural |  |  |  |
| *Urban |  |  |  |
| Other Structures | 0 |  |  |
| *Org |  |  |  |
| *Feature ID |  |  |  |
| *Type |  |  |  |
| *Property Type |  |  |  |
| *Predom Usage |  |  |  |
| *Development Status |  |  |  |
| GSA Assignment Module Mandatory Elements |  |  |  |
| will come from GSA Rent Bill |  |  |  |

Appendix C
Conversion Work Breakdown Structure

In this appendix, we provide the WBS for the data conversion activities.

We assume that CPAIS implementation will occur during May and list the activities, durations, start and end date, and responsibilities for each activity. This plan needs to be revised with the detailed conversion execution steps by the group with input from the agencies.

| Table 11. Data Conversion WBS Activities |
| --- |
| Task name | Duration | Start | End | Resource |
| Prepare environment for conversion | 15 | 10/13/03 | 10/31/03 | NITC, FS, INFRA Team |
| Develop and Test Conversion Code for other FIRM users, (RD, FSA, NRCS) | 34 days | 11/03/03 | 12/19/03 | FS, Infra Team |
| Develop and Test Conversion Code for NCR co-location | 18 days | 12/29/03 | 1/23/04 | FS, INFRA Team |
| Develop and Unit Test Conversion Code for APHIS data | 10 days | 1/26/04 | 2/6/04 | FS, INFRA Team |
| Receive Department Agency Codes |  | 10/27/03 | 11/7/03 | OPPM, Agencies |
| Receive Administrative Organization from each agency |  | 10/27/03 | 11/7/03 | OPPM, Agencies |
| Complete consolidation of LOV |  | 11/10/03 | 11/24/03 | OPPM |
| Develop and Unit Test Conversion Code |  | 8/20/03 | 2/16/04 | FS, INFRA Team |
| Execute Conversion |  |  |  |  |
| Collect Agency Data (some agencies will not complete their data clean-up in FIRM until end of Jan) | 10 days | 01/16/04 | 01/30/04 | FS, INFRA Team, Agencies |
| Customize conversion code as necessary after agencies perform data clean-up. | 6 days | 02/09/04 | 02/16/04 | FS, INFRA Team |
| Perform Mock Conversion | 5 days | 02/17/04 | 02/24/03 | FS, INFRA Team |
| Perform Mock Conversion Data Validation/Quality Assurance/Reconciliation | 10 days | 02/25/04 | 03/10/04 | FS, INFRA Team |
| Resolve Conversion Issues | 5 days | 03/11/04 | 03/17/04 | FS, INFRA Team |
| Update Conversion Procedures | 5 days | 03/18/04 | 03/26/04 | FS, INFRA Team |
| Obtain Final Conversion Go/No Go Decision | 3 days | 03/29/04 | 03/31/04 | FS, INFRA Team |
| Collect Agency Data | 10 days | 03/31/04 | 03/31/04 | FS, INFRA Team, Agencies |
| Perform Final Conversion | 5 days | 04/05/04 | 04/09/04 | FS, INFRA Team |
| Perform Data Validation/Quality Assurance/Reconciliation | 15 days | 04/12/04 | 04/30/04 | FS, INFRA Team, Agencies |
| Obtain Conversion Acceptance Approval | 1 day | 05/03/04 | 05/03/04 | FS, INFRA Team, OCFO |
| Perform Post Conversion Lessons Learned Review | 5 days | 05/04/04 | 05/10/04 | FS, INFRA Team |

Appendix D
Conversion Problem Resolution and Escalation Procedures

In this appendix, we provide the problem resolution and escalation procedures to be used during the real property data conversion.

## Purpose of a Conversion Problem Report

The CPAIS Data Conversion Team will conduct daily meetings during the conversion process to discuss problems and issues.  A problem report will be prepared for each error or issue that is identified.  The purpose of the problem report is to document, for tracking purposes, defects/issues with CPAIS or its interface with FFIS and INFRA during conversion.  Examples include:

Reports appear to be incorrect—subtotals incorrect, wrong sort sequence, etc.

An attempt to process a transaction resulted in the receipt of a fatal error.

While processing a document, the subsystem abended and returned an error code causing the user to be forced from the application.

User received error code that cannot be interpreted.

Source system issues.

Telecommunications problems.

## Preparer

Who should prepare a problem report? Agency CPAIS users, personnel at the NITC who are monitoring CPAIS in accordance with the Service Level Agreement, reports users, personnel in the CPAIS QA team, telecommunications personnel, and others.

The problem report process is open to anyone to document a defect or issues with the CPAIS application, the reports, the interface to INFRA, or functional accounting issues with the interface to FFIS during conversion.

## Conversion Problem Report Process

All problem reports are entered into the Customer Service tool for tracking purposes and analyzed to identify trends. If entry via the Web is not possible, the report should be faxed to the CPAIS Help Desk or sent via GroupWise to:

Brenda.Mandella@USDA.gov

Wendy.Snow@USDA.gov

Appendix E
Financial Reconciliation

COD will work with the individual agencies to determine the process for reconciliation during data conversion.  Accounting information for owned properties will be developed at this time.

Appendix F
GSA STAR Rent Conversion File

This appendix contains the file format for the GSA STAR Rent Bill source data.

| Table 12. GSA STAR Rent Bill Source Data |
| --- |
| Source field name | STAR table.field | Data type |
| Region | Tbiltran.c_region | A2 |
| Location Code/Building Number | Tbiltran.c_loc | A6 |
| Building Name | tbldg.n_bldg | A30 |
| Address 1 | tbldg.t_addr1 | A35 |
| Address 2 | tbldg.t_addr2 | A35 |
| City | tblg.t_bldg_cty | A23 |
| County | tbldg.t_bldg_cnty | A25 |
| State | tbldg.c_sta | A2 |
| Zip Code | tbldg.t_bldg_zip | A10 |
| Billing Agency Code | Tbiltran.c_bill_ab_code | A4 |
| Station Symbol | Tbiltran.c_station_symbol | A8 |
| Agency/Bureau Code | Tbiltran.c_ab_code | A4 |
| Current Billing Period | Tbiltran.q_bill_period | Integer |
| Document Reference Number | Tbiltran.t_docno | A10 |
| CBR Number | Tbiltran.i_agmt | A9 |
| OA Number | Tbiltran.c_oa_no | A8 |
| Facility Code (third and fourth characters) | Tbiltran.c_facility | A2 |
| Record Type | tbiltran.c_rectype | A3 |
| Billable Item Category | tbiltran.t_category | A55 |
| Billable Item Description | tbiltran.t_desc | A35 |
| Unit Quantity | tbiltran.a_quantity | Number (N13,2) |
| Type of Unit | tbiltran.c_unit | A2 |
| Annual Rate | tbiltran.a_rate | Number(N13,2) |
| Monthly Charge | tbiltran.a_bill | Number(N13,0) |
| GSA Contact | templ.t_email | A30 |
| Telephone Number | templ.t_wk_ph | A14 |
| Rebill Flag | tbiltran.f_rebill | A1 |
| Occupancy Right | tbiltran.c_occup_rt | A2 |
| Year to Date Bill Amount | sum(tbiltran.a_bill) | Number(N13,0) |
| Adjustment Start Date | tbiladj.q_adj_rec_st | Integer |
| Adjustment End Date | tbiladj.q_adj_rec_end | Integer |
| CBR R/U Factor | tcbbrru.a_ru_factor | Number(N13,5) |
| Reason for Charge | tbiltran.t_reason | A125 |

Appendix G
GSA STAR Rent Staging Table

| This appendix contains the file format for the GSA STAR Rent Bill staging table.Table 13. GSA STAR Rent Bill |
| --- |
| Source field name | Staging table field | Data type |
| Region | REGION | A2 |
| Location Code/Building Number | BUILDING_ID | A6 |
| Building Name | BUILDING_NAME | A30 |
| Address 1 | ADDRESS1 | A35 |
| Address 2 | ADDRESS2 | A35 |
| City | CITY | A23 |
| County | COUNTY | A25 |
| State | STATE | A2 |
| Zip Code | ZIP_CODE | A10 |
| Billing Agency Code | BILLING_AGENCY_CODE | A4 |
| Station Symbol | STATION_SYMBOL | A8 |
| Agency/Bureau Code | AGENCY_CODE | A4 |
| Current Billing Period | BILLING_PERIOD | Integer |
| Document Reference Number | DOCUMENT_REF_NO | A10 |
| CBR Number | CBR# | A9 |
| OA Number | OA_NUMBER | A8 |
| Facility Code (third and fourth characters) | FACILITY_CODE | A2 |
| Record Type | CHARGE_TYPE | A3 |
| Billable Item Category | CHARGE_TYPE_DESC | A55 |
| Billable Item Description | CHARGE_TYPE_DESC2 | A35 |
| Unit Quantity | UNITS | Number (N13,2) |
| Type of Unit | UOM | A2 |
| Annual Rate | ANNUAL_RATE | Number(N13,2) |
| Monthly Charge | MONTHLY_CHARGE | Number(N13,0) |
| GSA Contact | GSA_CONTACT | A30 |
| Telephone Number | PHONE_NUMBER | A14 |
| Rebill Flag | REBILL_FLAG | A1 |
| Occupancy Right | OCCUPANCY_RIGHT | A2 |
| Year to Date Bill Amount | Y_TO_D_BILL_AMOUNT | Number(N13,0) |
| Adjustment Start Date | ADJ_START_DATE | Integer |
| Adjustment End Date | ADJ_END_DATE | Integer |
| CBR R/U Factor | CBR_R_U_FACTOR | Number(N13,5) |
| Reason for Charge | CHARGE_REASON | A125 |

Appendix H
FIRM Data Mapping

This appendix contains the mapping of FIRM tables to CPAIS tables.

| Table 14. FIRM Data Mapping |
| --- |
| ARS-FIRM tables | FIRM Key | Format | CPAIS tables | Comments |
| installation |  |  | land_units lu, ii_gsa_installations gsa | use valid_installation table |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | lu.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | lu.agency_code |  |
| INST_SEQ_NO | NOT NULL | NUMBER | lu.cn, gsa.lu_cn |  |
| INSTALLATION_NUMBER | NOT NULL | VARCHAR2(5) | lu.id |  |
| INSTALLATION_NAME | NOT NULL | VARCHAR2(30) | lu.name |  |
| DATE_REC_ADDED | NOT NULL | DATE | lu.created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | lu.modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | lu.modified_by |  |
| INSTALLATION_DESC |  | VARCHAR2(30) |  | only 2 records with data |
| PROGRAM_CODE |  | VARCHAR2(5) |  | no data, see FIRM appendix |
| REGION_CODE |  | VARCHAR2(5) |  | alpha code |
| DISTRICT_CODE |  | VARCHAR2(5) |  | no data |
| IDENTIFICATION_CODE |  | VARCHAR2(5) |  |  |
| EST_CURRENT_VALUE_INST_THOUS |  | NUMBER(8) | gsa.estimated_current_value |  |
| HIGHEST_BEST_USE_CODE |  | VARCHAR2(2) | gsa.highest_best_use |  |
| EXCESS_IND_CODE |  | VARCHAR2(1) | gsa.excess_indicator |  |
| HISTORICAL_IND_INST_CODE |  | VARCHAR2(2) | gsa.historical_indicator |  |
| SURVEY_YEAR_GSA |  | NUMBER(4) | gsa.last_survey_year_by_gsa |  |
| SURVEY_YEAR_AGENCY |  | NUMBER(4) | gsa.last_survey_year_by_agency |  |
| FIELD_1 |  | VARCHAR2(4) |  |  |
| FIELD_2 |  | VARCHAR2(8) |  | no data |
| FIELD_3 |  | VARCHAR2(16) |  | no data |
| NOTES |  | VARCHAR2(512) | lu.remarks |  |
| site |  |  | land_units lu, ii_gsa_installation_sites site, ii_property_addresses addr, ii_gsa_nstlln_cngrss_dstrcts cong | use valid_site table |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | lu.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | lu.agency_code |  |
| SITE_SEQ_NO | NOT NULL | NUMBER | lu.cn, site.lu_cn |  |
| INST_SEQ_NO | NOT NULL | NUMBER | site.gsa_installation_mcn |  |
| SITE_NUMBER | NOT NULL | VARCHAR2(2) | lu.id |  |
| SUMMARY_DETAIL_INDICATOR | NOT NULL | VARCHAR2(1) |  | S' for summary, 'D' for detail record |
| GEO_LOC_STATE_CODE | NOT NULL | VARCHAR2(2) | site.geo_loc_state, site.gsa_region |  |
| GEO_LOC_COUNTY_CODE | NOT NULL | VARCHAR2(3) | site.geo_loc_county |  |
| GEO_LOC_CITY_CODE | NOT NULL | VARCHAR2(4) | site.geo_loc_city |  |
| DATE_REC_ADDED | NOT NULL | DATE | lu.created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | lu.modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | lu.modified_by |  |
| SITE_NAME |  | VARCHAR2(30) | lu.name |  |
| ADDRESS_1 |  | VARCHAR2(30) | addr.line_1 | type_of_adr = 'L' |
| ADDRESS_2 |  | VARCHAR2(30) | addr.line_2 |  |
| CITY_TOWN |  | VARCHAR2(23) | addr.city_name |  |
| STATE_ABBRV |  | VARCHAR2(2) | addr.state_code |  |
| ZIP_CODE |  | VARCHAR2(10) | addr.postal_code |  |
| COUNTY_COUNTRY |  | VARCHAR2(23) | addr.county_country_name |  |
| CONG_DISTRICT1_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT2_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT3_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT4_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT5_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT6_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT7_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT8_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT9_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| CONG_DISTRICT10_SITE_CODE |  | NUMBER(2) | id for congressional district land unit linked to this site |  |
| SURVEY_YEAR_GSA |  | NUMBER(4) | site.last_survey_year_by_gsa |  |
| SURVEY_YEAR_AGENCY |  | NUMBER(4) | site.last_survey_year_by_agency |  |
| REMARKS_1166 |  | VARCHAR2(700) |  | no data |
| FIELD_1 |  | VARCHAR2(4) |  |  |
| FIELD_2 |  | VARCHAR2(8) |  | no data |
| FIELD_3 |  | VARCHAR2(16) |  |  |
| NOTES |  | VARCHAR2(512) | lu.remarks |  |
| property |  |  | land_units lu, ii_property_addresses addr, ii_features fea, ii_buildings bld | use valid_property table |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | fea.agency_code, lu.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | fea.agency_code, lu.agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | fea.cn, lu.cn |  |
| SITE_SEQ_NO | NOT NULL | NUMBER | fea.gsa_installation_site_cn, lu.gsa_installation_site_cn |  |
| PROPERTY_ID | NOT NULL | VARCHAR2(10) | fea.id, lu.id |  |
| PROPERTY_NAME | NOT NULL | VARCHAR2(30) | fea.name, lu.name |  |
| GOVT_OWNED_LEASED_TRUST | NOT NULL | VARCHAR2(1) | lu.obj_name, lu.property_type |  |
| GSA_ASSIGNED | NOT NULL | VARCHAR2(1) |  | only 'N' in data |
| PENDING_INDICATOR | NOT NULL | VARCHAR2(1) |  |  |
| REPORTED_ON_1166 | NOT NULL | VARCHAR2(1) | fea.exclude_1166, lu.exclude_1166 |  |
| NO_OF_PROPERTY | NOT NULL | NUMBER(4) |  |  |
| GEO_LOC_STATE_CODE | NOT NULL | VARCHAR2(2) |  |  |
| GEO_LOC_COUNTY_CODE | NOT NULL | VARCHAR2(3) |  |  |
| GEO_LOC_CITY_CODE | NOT NULL | VARCHAR2(4) |  |  |
| PROPERTY_TYPE_CODE | NOT NULL | VARCHAR2(1) | fea.sub_type | defined in mt_property_type |
| PROPERTY_TYPE_SUFFIX | NOT NULL | VARCHAR2(2) | bld.subcategory | defined in mt_property_type |
| PROPERTY_PREDOM_USAGE_CODE | NOT NULL | VARCHAR2(2) | fea.gsa_predom_usage, lu.gsa_predom_usage |  |
| DATE_REC_ADDED | NOT NULL | DATE | fea.created_date, lu.created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | fea.modified_date, lu.modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | fea.modified_by, lu.modified_by |  |
| PROPERTY_NAME_ABBRV |  | VARCHAR2(15) |  |  |
| MAIL_ADDRESS_1 |  | VARCHAR2(30) | addr.line_1 | type_of_adr = 'M' |
| MAIL_ADDRESS_2 |  | VARCHAR2(30) | addr.line_2 |  |
| MAIL_CITY_TOWN |  | VARCHAR2(23) | addr.city_name |  |
| MAIL_STATE_ABBRV |  | VARCHAR2(2) | addr.state_code |  |
| MAIL_ZIP_CODE |  | VARCHAR2(10) | addr.postal_code |  |
| MAIL_COUNTY_COUNTRY |  | VARCHAR2(23) | addr.county_country_name |  |
| ADDRESS_1 |  | VARCHAR2(30) | addr.line_1 | type_of_adr = 'L' |
| ADDRESS_2 |  | VARCHAR2(30) | addr.line_2 |  |
| CITY_TOWN |  | VARCHAR2(23) | addr.city_name |  |
| STATE_ABBRV |  | VARCHAR2(2) | addr.state_code |  |
| ZIP_CODE |  | VARCHAR2(10) | addr.postal_code |  |
| COUNTY_COUNTRY |  | VARCHAR2(23) | addr.county_country_name |  |
| HISTORICAL_IND_PROP_CODE |  | VARCHAR2(2) | fea.historical_status |  |
| DELEGATION_CODE |  | VARCHAR2(1) |  | B' - building, 'L' - leased, 'N' - not delegated |
| AGENCY_INTEREST_CODE |  | VARCHAR2(1) |  | from mt_agency_interest |
| PRIMARY_FACILITY_TYPE_CODE |  | VARCHAR2(5) |  | no data |
| UTILIZATION_STATUS_CODE |  | VARCHAR2(2) | fea.development_status | from mt_code_2 |
| CONG_DIST_PROPERTY_CODE |  | NUMBER(2) |  |  |
| STAT_METRO_AREA_CODE |  | VARCHAR2(2) |  | no data |
| MCKINNEY_ACT_IND |  | VARCHAR2(2) |  | no data |
| SURVEY_DATE_GSA |  | DATE |  |  |
| SURVEY_DATE_AGENCY |  | DATE |  |  |
| CO_LOCATION |  | VARCHAR2(30) |  | no data |
| RESPONSIBLE_PERSON |  | VARCHAR2(23) |  |  |
| REAL_ESTATE_SPECIALIST |  | VARCHAR2(23) |  | no data |
| FIELD_1 |  | VARCHAR2(4) |  |  |
| FIELD_2 |  | VARCHAR2(8) |  |  |
| FIELD_3 |  | VARCHAR2(16) |  |  |
| NOTES |  | VARCHAR2(512) | lu.remarks |  |
| property_usage |  |  |  | only 5 records |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) |  |  |
| PROP_SEQ_NO | NOT NULL | NUMBER |  |  |
| PROP_USAGE_CODE | NOT NULL | VARCHAR2(5) |  |  |
| ORG_CODE | NOT NULL | VARCHAR2(5) |  |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| USAGE_UNITS |  | NUMBER(14,4) |  |  |
| USAGE_PERCENTAGE |  | NUMBER(5,2) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| acquisition |  |  | ii_features fea, land_units lu |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | fea.agency_code, lu.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | fea.agency_code, lu.agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | fea.cn, lu.cn |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| ESTIMATED_ACQUISITION_DATE |  | DATE |  |  |
| ACQUISITION_DATE |  | DATE | fea.acquisition_date, lu.acquisition_date |  |
| ACQUISITION_METHOD_CODE |  | VARCHAR2(2) | fea.acquisition_method, lu.acquisition_method |  |
| ACQUISITION_AUTHORITY_CODE |  | VARCHAR2(2) | fea.acquisition_authority, lu.acquisition_authority |  |
| ACQUISITION_COST_INITIAL |  | NUMBER(12,2) | fea.initial_acquisition_cost, lu.initial_acquisition_cost |  |
| APPRAISAL_METHOD_CODE |  | VARCHAR2(2) | fea.current_value_method, lu.current_value_method |  |
| APPRAISAL_DATE |  | DATE | fea.appraisal_date, lu.appraisal_date |  |
| APPRAISAL_FAIR_MARKET_VALUE |  | NUMBER(13,2) | fea.appraisal_fair_market_value, lu.appraisal_fair_market_value |  |
| ACQUIRED_FROM |  | VARCHAR2(20) | fea.acquired_from_cn, lu.acquired_from_cn |  |
| ESTIMATED_CURRENT_VALUE |  | NUMBER(13,2) | fea.current_value, lu.current_value |  |
| COST_IND_CODE |  | VARCHAR2(1) |  |  |
| FIELD_1 |  | VARCHAR2(4) |  | 1 record with data |
| FIELD_2 |  | VARCHAR2(8) |  | 1 record with data |
| FIELD_3 |  | VARCHAR2(16) |  | no data |
| NOTES |  | VARCHAR2(512) | fea.remarks, lu.remarks |  |
| building |  |  | ii_features fea, ii_buildings bld, ii_rps_value_streams vs |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | fea.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | fea.agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | fea.cn, bld.fea_cn |  |
| GROSS_SQ_FT_BLDG | NOT NULL | NUMBER(10) | fea.gross_sqft |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| SQ_FT_NET_OCCUPIABLE |  | NUMBER(10) |  |  |
| CONDITION_ADEQUACY_CODE |  | VARCHAR2(2) |  | from mt_code_2 |
| BUILDING_YEAR_BUILT |  | NUMBER(4) | fea.year_constructed, vs.start_date |  |
| BUILDING_LIFE_EXPECTANCY |  | NUMBER(3) | vs.life |  |
| SEISMIC_SAFETY_CODE |  | VARCHAR2(2) | ii_bldg_siesmic.siesmic_evaluation |  |
| NUMBER_OF_ELEVATORS |  | NUMBER(3) |  |  |
| NUMBER_OF_FLOORS |  | NUMBER(3) |  |  |
| NUMBER_OF_FLOORS_OCCUPIED |  | NUMBER(3) |  |  |
| SUPERSTRUCTURE_TYPE_CODE |  | VARCHAR2(2) |  | no data |
| WALL_CONSTRUCTION_TYPE_CODE |  | VARCHAR2(2) | ii_bldg_walls.wall_material |  |
| ROOF_CONSTRUCTION_TYPE_CODE |  | VARCHAR2(2) | ii_bldg_roof.type_of_roof |  |
| COOLING_SYSTEM_TYPE_CODE |  | VARCHAR2(2) |  | no data |
| HEATING_SYSTEM_TYPE_CODE |  | VARCHAR2(2) |  | no data |
| FIRE_PROTECTION_TYPE_CODE |  | VARCHAR2(2) |  | no data |
| ESTIMATED_REPLACEMENT_COST |  | NUMBER(12,2) |  |  |
| SECURITY_LEVEL |  | NUMBER(1) |  | no data |
| NOTES |  | VARCHAR2(512) |  |  |
| housing |  |  | ii_features fea |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | cn |  |
| HOUSING_ID | NOT NULL | VARCHAR2(5) | id |  |
| DATE_REC_ADDED | NOT NULL | DATE | created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | modified_by |  |
| HOUSING_TYPE |  | VARCHAR2(2) |  | no data |
| HOUSING_STATUS |  | VARCHAR2(1) |  |  |
| HOUSING_CURRENTLY_ASSIGNED |  | NUMBER(4) |  |  |
| HOUSING_LIVING_UNITS |  | NUMBER(3) |  |  |
| HOUSING_CAPACITY |  | NUMBER(4) |  |  |
| HOUSING_NUM_OF_BEDROOMS |  | NUMBER(3) |  |  |
| CONDITION_OF_QUARTERS_EXT |  | NUMBER(1) |  | no data |
| CONDITION_OF_QUARTERS_INT |  | NUMBER(1) |  | no data |
| RATE_OF_QUARTERS |  | NUMBER(8,2) |  | no data |
| RATE_FREQUENCY |  | VARCHAR2(1) |  | no data |
| HOUSING_COST_CENTER_CODE |  | VARCHAR2(5) |  | no data |
| HOUSING_FACILITY_TYPE |  | VARCHAR2(5) |  | no data |
| HOUSING_FACILITY_CONTRACTION |  | VARCHAR2(5) |  | no data |
| HOUSING_HISTORICAL_IND |  | VARCHAR2(1) |  |  |
| AT_ID_CODE |  | VARCHAR2(5) |  | no data |
| CO_LOCATED_FACILITY |  | VARCHAR2(30) |  | no data |
| HOUSING_UNIT_OFF_ON_AIRPORT |  | VARCHAR2(1) |  |  |
| HOUSING_UNIT_ORG_CODE |  | VARCHAR2(6) |  | no data |
| HOUSING_UNIT_ORG_DESC |  | VARCHAR2(30) |  | no data |
| GSA_CONTROL_NUMBER |  | VARCHAR2(5) |  | no data |
| HOUSING_USAGE_CODE |  | VARCHAR2(5) |  | no data |
| DUP_COUNT_CODE |  | VARCHAR2(3) |  | no data |
| FACILITY_CONG_DISTRICT |  | VARCHAR2(2) |  |  |
| FIELD_1 |  | VARCHAR2(4) |  | no data |
| FIELD_2 |  | VARCHAR2(8) |  | no data |
| FIELD_3 |  | VARCHAR2(16) |  | no data |
| NOTES |  | VARCHAR2(512) | fea.remarks |  |
| land |  |  | land_units |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | cn |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| ACREAGE_RURAL |  | NUMBER(14,4) | rural_acres |  |
| ACREAGE_URBAN |  | NUMBER(14,4) | urban_acres |  |
| NATIONAL_ENVIRONMENTAL_PROTECT |  | VARCHAR2(1) |  |  |
| PRINCIPAL_MERIDIAN_NUMBER |  | NUMBER(2) |  |  |
| COUNTY_PLAT_BOOK |  | VARCHAR2(10) |  |  |
| TOWNSHIP_NUMBERS |  | VARCHAR2(5) |  |  |
| COUNTY_PLAT_PAGE |  | NUMBER(5) |  |  |
| RANGE_NUMBERS |  | VARCHAR2(5) |  |  |
| LEGISLATIVE_JURISDICTION_CODE |  | VARCHAR2(2) |  | no data |
| ENDANGERED_SPECIES |  | VARCHAR2(1) |  | no data |
| WET_LAND |  | VARCHAR2(1) |  | no data |
| NOTES |  | VARCHAR2(512) | remarks |  |
| land_rights |  |  | land_units | only 2 records |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | cn |  |
| RIGHTS_ENCUM_CODE | NOT NULL | VARCHAR2(5) |  |  |
| DATE_REC_ADDED | NOT NULL | DATE | created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | modified_by |  |
| ACQUIRED_OR_NOT |  | VARCHAR2(1) |  |  |
| RIGHTS_ENCUM_ACRES |  | NUMBER(11,1) |  |  |
| RIGHTS_ENCUM_PCT |  | NUMBER(5,2) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| structure |  |  | ii_features, obj_name <> 'BUILDING', ii_rpa_value_streams vs |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | agency_code |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | cn |  |
| DATE_REC_ADDED | NOT NULL | DATE | created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | modified_by |  |
| STRUCTURE_YEAR_BUILT |  | NUMBER(4) | year_constructed |  |
| STRUCTURE_LIFE_EXPECTANCY |  | NUMBER(3) | vs.life |  |
| STRUCTURE_UNITS |  | NUMBER(12,1) |  |  |
| STRUCTURE_UNIT_TYPE |  | VARCHAR2(5) |  |  |
| LAST_INSPECT_DATE |  | DATE | date_last_inspected |  |
| NOTES |  | VARCHAR2(512) |  |  |
| lease_detail |  |  | accplishment_instruments ai, ii_leases ls, ii_contacts co |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | ai.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | ai.agency_code |  |
| SITE_SEQ_NO | NOT NULL | NUMBER | ls.gsa_installation_site_cn |  |
| LEASE_CONTRACT_NUMBER | NOT NULL | VARCHAR2(27) | ai.id with site_seq_no and mod_no |  |
| MOD_NO | NOT NULL | VARCHAR2(2) |  | amendment_no from ii_acc_ins_amendments? |
| AGENCY_LESSEE_INDICATOR | NOT NULL | VARCHAR2(1) |  |  |
| DATE_REC_ADDED | NOT NULL | DATE | ai.created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | ai.modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | ai.modified_by |  |
| LEASE_PROJECT_NUMBER |  | VARCHAR2(10) |  |  |
| LEASE_NAME |  | VARCHAR2(30) | ai.name |  |
| LEASE_TYPE_CODE |  | VARCHAR2(2) | ls.lease_type |  |
| INITIAL_LEASE_DATE |  | DATE |  |  |
| LEASE_EFFECTIVE_DATE |  | DATE | ls.effective_date |  |
| LEASE_EXPIRATION_DATE |  | DATE | ai.exp_expiration_date |  |
| LEASE_TERMINATION_DATE |  | DATE |  | no data |
| LEASE_TERMINATION_DAYS_NOTICE |  | NUMBER(3) | ls.termination_notice_days |  |
| LEASE_DELEGATION_CODE |  | VARCHAR2(2) |  |  |
| FTE_TOTAL |  | NUMBER(3) |  | compute from line items |
| LEASE_SUPPLEMENTAL_DATE |  | DATE |  |  |
| LEASE_PAYMENT_CURRENT |  | NUMBER(10,2) | ls.montly_rental_amount |  |
| LEASE_SPACE_SQ_FT_CURRENT |  | NUMBER(12,2) |  |  |
| LEASE_RATE_PER_SQFT_CURRENT |  | NUMBER(5,2) |  |  |
| LEASE_SPACE_ACRES_CURRENT |  | NUMBER(14,4) |  |  |
| LEASE_RATE_PER_ACRES_CURRENT |  | NUMBER(6,2) |  | no data |
| LEASE_PAYMENT_NEXT |  | NUMBER(10,2) |  |  |
| LEASE_SPACE_SQ_FT_NEXT |  | NUMBER(12,2) |  |  |
| LEASE_RATE_PER_SQFT_NEXT |  | NUMBER(5,2) |  |  |
| LEASE_SPACE_ACRES_NEXT |  | NUMBER(14,4) |  | no data |
| LEASE_RATE_PER_ACRES_NEXT |  | NUMBER(6,2) |  | no data |
| MO_TO_MO_YR_TO_YR |  | VARCHAR2(1) |  |  |
| FULLY_SERVICED |  | VARCHAR2(1) | ls.service_code |  |
| LUMP_SUM_PYMT |  | NUMBER(7) |  | no data |
| LEASE_RENEWAL_OPTION_YEARS |  | NUMBER(2) |  |  |
| LEASE_RENEWAL_DAYS_NOTICE |  | NUMBER(3) |  |  |
| RENEWAL_YEARS_PER_OPTION |  | NUMBER(2) | ls.option_period |  |
| RENEWAL_OPTIONS |  | NUMBER(2) | ls.number_of_options |  |
| EXPENSES_UTILITIES |  | NUMBER(7) |  | no data |
| EXPENSES_TAXES |  | NUMBER(7) |  | no data |
| EXPENSES_SERVICES |  | NUMBER(7) |  | no data |
| EXPENSES_OTHER |  | NUMBER(7) |  | no data |
| ESCALATION_FACTOR |  | NUMBER(4,3) | ls.escalator |  |
| APPROPRIATION_CODE |  | VARCHAR2(13) |  | no data |
| LESSOR_CONTACT_POINT |  | VARCHAR2(30) |  |  |
| LESSOR_CONTACT_TITLE |  | VARCHAR2(30) |  |  |
| LESSOR_NAME |  | VARCHAR2(30) | create contact record and link to this lease | generated lessor if for ii_contacts |
| LESSOR_TAX_ID_NUMBER |  | NUMBER(9) |  |  |
| LESSOR_PHONE |  | VARCHAR2(12) | create contact record and link to this lease |  |
| LESSOR_PHONE_EXTENSION |  | NUMBER(4) | create contact record and link to this lease |  |
| LESSOR_FAX |  | VARCHAR2(12) | create contact record and link to this lease |  |
| LESSOR_EMAIL |  | VARCHAR2(30) | create contact record and link to this lease |  |
| LESSOR_ADDRESS_1 |  | VARCHAR2(30) | create contact record and link to this lease |  |
| LESSOR_ADDRESS_2 |  | VARCHAR2(30) | create contact record and link to this lease |  |
| LESSOR_CITY |  | VARCHAR2(23) | create contact record and link to this lease |  |
| LESSOR_STATE |  | VARCHAR2(2) | create contact record and link to this lease |  |
| LESSOR_ZIP_CODE |  | VARCHAR2(10) | create contact record and link to this lease |  |
| LESSEE_CONTACT_POINT |  | VARCHAR2(30) |  |  |
| LESSEE_CONTACT_TITLE |  | VARCHAR2(30) |  | no data |
| LESSEE_NAME |  | VARCHAR2(30) |  | no data |
| LESSEE_TAX_ID_NUMBER |  | NUMBER(9) |  | no data |
| LESSEE_PHONE |  | VARCHAR2(12) |  |  |
| LESSEE_PHONE_EXTENSION |  | NUMBER(4) |  | no data |
| LESSEE_FAX |  | VARCHAR2(12) |  | no data |
| LESSEE_EMAIL |  | VARCHAR2(30) |  | no data |
| LESSEE_ADDRESS_1 |  | VARCHAR2(30) |  | no data |
| LESSEE_ADDRESS_2 |  | VARCHAR2(30) |  | no data |
| LESSEE_CITY |  | VARCHAR2(23) |  | no data |
| LESSEE_STATE |  | VARCHAR2(2) |  | no data |
| LESSEE_ZIP_CODE |  | VARCHAR2(10) |  | no data |
| NO_GARAGE_SPACES_CURRENT |  | NUMBER(4) |  | no data |
| GARAGE_DOLLARS_CURRENT |  | NUMBER(7) |  | no data |
| NO_GARAGE_SPACES_NEXT |  | NUMBER(4) |  | no data |
| GARAGE_DOLLARS_NEXT |  | NUMBER(7) |  | no data |
| NO_SURFACE_SPACES_CURRENT |  | NUMBER(4) |  | no data |
| SURFACE_DOLLARS_CURRENT |  | NUMBER(7) |  | no data |
| NO_SURFACE_SPACES_NEXT |  | NUMBER(4) |  | no data |
| SURFACE_DOLLARS_NEXT |  | NUMBER(7) |  | no data |
| EXPENSES_BASE_RENT |  | NUMBER(10,2) |  |  |
| FIELD_1 |  | VARCHAR2(4) |  |  |
| FIELD_2 |  | VARCHAR2(8) |  | no data |
| FIELD_3 |  | VARCHAR2(16) |  | no data |
| NOTES |  | VARCHAR2(512) |  | no data |
| lease_parameters |  |  | ii_lease_line_items lli | no new data, this table is used to assign multiple properties to a lease or multiple leases to a property, in this data lease to property is one-to-one |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) | ai.agency_code |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) | ai.agency_code |  |
| SITE_SEQ_NO | NOT NULL | NUMBER | ls.gsa_installation_site_cn |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | lli.fea_cn, lli.lu_cn |  |
| LEASE_CONTRACT_NUMBER | NOT NULL | VARCHAR2(27) | ai.id |  |
| MOD_NO | NOT NULL | VARCHAR2(2) |  | amendment_no from ii_acc_ins_amendments? |
| DATE_REC_ADDED | NOT NULL | DATE | ai.created_date |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE | ai.modified_date |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) | ai.modified_by |  |
| REMARK |  | VARCHAR2(2) |  | no data |
| e_lease_parameters |  |  |  | no new data, leases with errors? |
| AGENCY_CODE |  | VARCHAR2(2) | ai.agency_code |  |
| BUREAU_CODE |  | VARCHAR2(2) | ai.agency_code |  |
| INSTALLATION_NUMBER |  | VARCHAR2(5) | lu.id from lu.parent_cn for ls.gsa_installation_site_cn |  |
| SITE_NUMBER |  | VARCHAR2(2) | lu.id from ls.gsa_installation_site_cn |  |
| PROPERTY_ID |  | VARCHAR2(10) | fea.id or lu.id from lli.fea_cn or lli.lu_cn |  |
| SITE_SEQ_NO |  | VARCHAR2(8) | lu cn from ls.gsa_installation_site_cn |  |
| PROP_SEQ_NO |  | VARCHAR2(8) | lli.fea_cn, lli.lu_cn |  |
| LEASE_CONTRACT_NUMBER |  | VARCHAR2(27) | ai.id with site_seq_no and mod_no |  |
| MOD_NO |  | VARCHAR2(2) |  |  |
| DATE_REC_ADDED |  | VARCHAR2(8) | ai.created_date |  |
| DATE_REC_LAST_CHG |  | VARCHAR2(8) | ai.modified_date |  |
| LAST_OPERATOR_ID |  | VARCHAR2(30) | ai.modified_by |  |
| MESSAGE |  | VARCHAR2(100) |  |  |
| disposal |  |  |  |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) |  |  |
| PROP_SEQ_NO | NOT NULL | NUMBER |  |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| EXCESS_IND_CODE |  | VARCHAR2(1) |  |  |
| DISPOSAL_REASON_CODE |  | VARCHAR2(2) |  |  |
| EXCESS_DATE |  | DATE |  |  |
| DISPOSAL_DATE |  | DATE |  |  |
| DISPOSAL_METHOD_CODE |  | VARCHAR2(2) |  |  |
| DISPOSAL_AUTHORITY_CODE |  | VARCHAR2(2) |  |  |
| DISPOSAL_AMOUNT |  | NUMBER(11) |  |  |
| DISPOSAL_COST |  | NUMBER(12,2) |  |  |
| TRANSFER_TO |  | VARCHAR2(20) |  |  |
| DISPOSAL_PROCEEDS_CODE |  | VARCHAR2(2) |  |  |
| DISPOSAL_STATUS_CODE |  | VARCHAR2(2) |  | no data |
| ESTIMATED_EXCESS_DATE |  | DATE |  |  |
| ESTIMATED_VALUE |  | NUMBER(11) |  |  |
| EXCESS_SQFT |  | NUMBER(10) |  |  |
| EXCESS_ACRES |  | NUMBER(14,4) |  |  |
| REPORTED_TO_GSA_DATE |  | DATE |  | no data |
| GSA_RESPONSE_DATE |  | DATE |  | no data |
| GSA_ACCEPT_FLAG |  | VARCHAR2(1) |  |  |
| ACCEPTED_BY_HUD |  | VARCHAR2(1) |  |  |
| FIELD_1 |  | VARCHAR2(4) |  | no data |
| FIELD_2 |  | VARCHAR2(8) |  | no data |
| FIELD_3 |  | VARCHAR2(16) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| expense |  |  | ii_rpa_value_streams vs, ii_rpa_subledgers sub |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) |  |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | sub.fea_cn, sub.lu_cn |  |
| EXPENSE_DATE | NOT NULL | DATE | vs.start_date |  |
| EXPENSE_CODE | NOT NULL | VARCHAR2(6) | vs.gl_account |  |
| ORG_CODE | NOT NULL | VARCHAR2(5) |  |  |
| EXPENSE_DOLLAR_AMOUNT | NOT NULL | NUMBER(13,2) | vs.amount |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| OBJECT_CLASS |  | VARCHAR2(4) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| handicap_code |  |  | ii_features |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) |  |  |
| PROP_SEQ_NO | NOT NULL | NUMBER |  |  |
| HANDICAP_CODE | NOT NULL | VARCHAR2(2) | accessibility_compliance |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| hazard_code |  |  | ii_bldg_hazards |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) |  |  |
| PROP_SEQ_NO | NOT NULL | NUMBER | fea_cn |  |
| HAZARD_CODE | NOT NULL | VARCHAR2(2) | type_of_hazard |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| security_code |  |  | ii_bldg_security |  |
| AGENCY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| BUREAU_CODE | NOT NULL | VARCHAR2(2) |  |  |
| PROP_SEQ_NO | NOT NULL | NUMBER |  |  |
| SECURITY_CODE | NOT NULL | VARCHAR2(2) |  |  |
| DATE_REC_ADDED | NOT NULL | DATE |  |  |
| DATE_REC_LAST_CHG | NOT NULL | DATE |  |  |
| LAST_OPERATOR_ID | NOT NULL | VARCHAR2(30) |  |  |
| NOTES |  | VARCHAR2(512) |  |  |
| user_info |  |  | ii_rpa_user_access rpau, ii_contacts co, ii_phone_numbers pn |  |
| USER_ID | NOT NULL | VARCHAR2(30) | co.id |  |
| USER_TYPE | NOT NULL | VARCHAR2(1) | co.obj_name |  |
| USER_NAME |  | VARCHAR2(40) | rpau.user_name |  |
| USER_PHONE |  | VARCHAR2(12) | pn.international_code¦¦pn.area_code¦¦pn.phone_number where phone_number_type = 'BUSINESS' |  |
| USER_PHONE_EXTENSION |  | NUMBER(4) | pn.extension |  |
| USER_EMAIL |  | VARCHAR2(30) |  |  |
| USER_FAX |  | VARCHAR2(12) | pn.international_code¦¦pn.area_code¦¦pn.phone_number where phone_number_type = 'FAX' |  |
| AGENCY_ACCESS | NOT NULL | VARCHAR2(2) | rpau.agency_code |  |
| BUREAU_ACCESS | NOT NULL | VARCHAR2(2) | rpau.agency_code |  |
| SYSTEM_ADMIN_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| INVENTORY_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| LEASE_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| RENT_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| WORKSPACE_PLANNING_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| INCOME_EXPENSE_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| SUMMARY_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| BUDGET_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| AUTOCAD_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |
| PROJ_TRACK_MODULE | NOT NULL | VARCHAR2(1) | done by role |  |

Appendix I
Accounting Template

Appendix J
Unique Asset Identifier (UAI) Format

This appendix contains the format for the Unique Asset Identifier (UAI).

1.0	Agency Specific Formats

ARS:     	Agency     Proj Grp     Admin Org      Property ID

(2)			(2)			(up to 7)		(10)

FS:        	Agency     Proj Grp     Admin Org           CPN

(2)			(2)				  (6)		(5)

APHIS:  	Agency    Proj Grp      Admin Org          Asset ID

(2)			(2)			(up to 7)		(up to 10)

NRCS:  	Agency    Proj Grp      Admin Org          Asset ID

(2)			(2)			(up to 7)		(up to 10)

|  | Agency | Project Group | Location ID | Asset ID | UAI Parts | UAI Total |
| --- | --- | --- | --- | --- | --- | --- |
| ARS | (2) | (2) | Default Admin Org (7) | “Prop ID” (10) | 2+2+7+10 | 22 |
| FS | (2) | (2) | Default Admin Org (6) | ”CPN” (5) | 2+2+6+5 | 16 |
| APHIS | (2) | (2) | Default Admin Org (7) | ”Asset ID” (10) | 2+2+4+10 | 19 |
| NRCS | (2) | (2) | Default Admin Org (7) | ”Asset ID” (10) | 2+2+7+10 | 22 |
| DA |  |  |  |  |  |  |

2.0	CPAIS Screen Formats and Syntax

3.0	Generic UAI

Agency     Project Group     Location ID     Asset ID       [5 characters held in reserve for “SeqNo.”]

(2)                   (2)                    (7)                 (10)

Appendix K
Data Validation Reports

This appendix contains the following sample CPAIS Reports for use in validating the data conversion:

Reports for the validation of property data

- Installation Sites and Addresses

- Inventory–Government Owned and Leased

- Lease Basics

- Lease Details

- GSA Assignment Details

Reports for the validation of accounting data

- Subledger Summary

- Value Stream

- Miscellaneous year end reconciliation ( see attachment: reconclt samples.xls)

A.1. Installation Sites and Addresses

Agency: <All> ¦ GSA Region: <All> ¦ Admin Org: <All> ¦ State: <All> ¦ Address Type: L

| Installation # | Site ID | Name | Geo Locator | Geo Location | Address | County/Country |
| --- | --- | --- | --- | --- | --- | --- |
| 01000 | 00 | R1, NORTHERN REGION | 300830063 | MISSOULA, MISSOULA, MONTANA | 200 East Broadway., MISSOULA, MT, 59801 | MISSOULA |
|  | 01 | FORT LOLO SITE | 300830063 | MISSOULA, MISSOULA, MONTANA | 8 COTTONWDAD DRIVE, MISSOULA, MT, 59801 | MISSOULA |
|  | 02 | AFD SITE | 300830063 | MISSOULA, MISSOULA, MONTANA | 3467 WILLOW ROAD, MISSOULA, MT, 59801 | MISSOULA |
|  | 03 | BROADWAY SITE | 300830063 | MISSOULA, MISSOULA, MONTANA | 1000 Broadway, MISSOULA, MT, 59801 | MISSOULA |
| 01500 | 00 | BUTTE SITE | 300180001 | BUTTE, BEAVERHEAD, MONTANA | Butterfly street, BUTTE, MT, 59001 | BEAVERHEAD |
| 01606 | 00 | LBJ JCCC | 371710113 | FRANKLIN, MACON, NORTH CAROLINA | Route 1, Box 447, FRANKLIN, NC, 28734 | MACON |
| 01608 | 00 | SCHENCK JCCC | 373655175 | PISGAH FOREST, TRANSYLVANIA, NORTH CAROLINA | P.O. Box 98, PISGAH FOREST, NC, 28768 | TRANSYLVANIA |
| 02000 | 00 | R2, ROCKY MOUNTAIN REGION | 08 | LAKEWDAD, JEFFERSON, COLORADO | 740 Simms Street, LAKEWDAD, CO, 80225 | JEFFERSON |
| 03000 | 00 | R3, SOUTHWESTERN REGION | 350030001 | ALBUQUERQUE, BERNALILLO, NEW MEXICO | 333 Broadway SE, ALBUQUERQUE, NM, 87102 | BERNALILLO |
| 04000 | 00 | R4, INTERMOUNTAIN REGION | 49 | OGDEN, WEBER, UTAH | 324 25th street, OGDEN, UT, 84401 | WEBER |
| 07322 | 00 | MAIN LOCATION, BRDAKSVILLE, FL | 120390053 | BRDAKSVILLE, HERNANDO, FLORIDA | US 41, County Road 581, Brooksville, FL, 33512 | HERNANDO |
| 07323 | 00 | MAIN LOCATION, DUBOIS, IDAHO | 160430033 | DUBOIS, CLARK, IDAHO | US Sheep Experiment Station, Dubois, ID, 83423 | CLARK |
|  | 01 | HUMPHREY RANGE | 160430033 | DUBOIS, CLARK, IDAHO | US Sheep Experiment Station, Dubois, ID, 83423 | CLARK |
|  | 02 | HENNINGER RANGE | 160430033 | DUBOIS, CLARK, IDAHO | US Sheep Experiment Station, Dubois, ID, 83423 | CLARK |
|  | 03 | SUMMER RANGE | 160430033 | DUBOIS, CLARK, IDAHO | US Sheep Experiment Station, Dubois, ID, 83423 | CLARK |
|  | 04 | MUD LAKE FEEDLOT | 160430033 | DUBOIS, CLARK, IDAHO | US Sheep Experiment Station, Dubois, ID, 83423 | CLARK |
|  | 05 | LEASED LAND-RADAR HILL .1 | 160430033 | DUBOIS, CLARK, IDAHO | US SHEEP EXPERIMENT STATION, Dubois, ID, 83423 | CLARK |
|  | 07 | GENETIC RESEARCH CENTER | 999999999 |  |  | NOT IN LIST |
|  | 08 | LAKE RED BLUFF RECREATION AREA | 999999999 |  |  | NOT IN LIST |
|  | 09 | ELK CREEK BLUFF | 999999999 |  |  | NOT IN LIST |
|  | 51 | MENDOCINO SO & S/W | 064230021 | WILLOWS, GLENN, CALIFORNIA | 825 N. Humboldt Avenue, WILLOWS, CA, 95988 | GLENN |
|  | 52 | GRINDSTONE RD | 060840103 | CORNING, TEHAMA, CALIFORNIA | 22000 Corning Road, CORNING, CA, 96021 | TEHAMA |
|  | 53 | PROGENY FENCE | 060840103 | CORNING, TEHAMA, CALIFORNIA | Not Applicable, CORNING, CA, 96021 | TEHAMA |
| 07638 | 00 | MODOC NATIONAL FOREST | 060050049 | ALTURAS, MODOC, CALIFORNIA | ALTURAS, CA, 96101 | MODOC |
|  | 04 | SO FORK EQUIP SHOP | 060050049 | ALTURAS, MODOC, CALIFORNIA | ALTURAS, CA, 96101 | MODOC |
|  | 07 | DEVILS GARDEN RD | 060050049 | ALTURAS, MODOC, CALIFORNIA | ALTURAS, CA, 96101 | MODOC |
|  | 08 | BIG VALLEY RD | 999999999 |  |  | NOT IN LIST |
|  | 09 | CEDARVILLE COMPOUND | 060050049 | ALTURAS, MODOC, CALIFORNIA | ALTURAS, CA, 96101 | MODOC |
|  | 10 | DANHAUSER HOUSE | 060050049 | ALTURAS, MODOC, CALIFORNIA | ALTURAS, CA, 96101 | MODOC |
|  | 11 | WARM SPRINGS | 999999999 |  |  | NOT IN LIST |
|  | 51 | MODOC SO | 060050049 | ALTURAS, MODOC, CALIFORNIA | 800 W. 12th Street, ALTURAS, CA, 96101 | MODOC |
|  | 52 | WARNER MTN RD | 060615049 | CEDARVILLE, MODOC, CALIFORNIA | Main & Washington, CEDARVILLE, CA, 96104 | MODOC |
|  | 53 | DOUBLEHEAD RD | 063930093 | TULELAKE, SISKIYOU, CALIFORNIA | Hwy 139 & Main Street, TULELAKE, CA, 96134 | SISKIYOU |

A.2. Inventory - Government Owned and Leased

Installation No: 07516 ¦ Installation Name: BIGHORN NATIONAL FOREST

| Site No | Property ID | Property Name | Property Type | Property Use | Status | Govt Own Leas | Bldg Year Constructed | Building Gross Sqft | Total Acres | Strc Year Constructed | Struc Units | Struc Unit Type | Acquisition Date | Acquisition Cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 00 | 1 | SUPERVISOR’S OFFICE | B |  | EXISTING - OPERATIONAL | G | 10/01/2000 | 11,198 |  |  |  |  |  |  |
| 00 | 103019 | COW CAMP |  |  | EXISTING - OPERATIONAL | G | 09/01/1956 |  |  |  |  |  |  |  |
| 00 | 107015 | FRENCH CRK COW CAMP |  |  | EXISTING - OPERATIONAL | G | 09/01/1945 |  |  |  |  |  |  |  |
| 00 | 107016 | ROCK CREEK COW CAMP |  |  | EXISTING - OPERATIONAL | G | 09/01/1940 |  |  |  |  |  |  |  |
| 00 | 108008 | SOURDOUGH COW CAMP |  |  | EXISTING - OPERATIONAL | G | 09/01/1952 |  |  |  |  |  |  |  |
| 00 | 1111 | BUFFALO LEASED OFFICE |  |  | EXISTING - OPERATIONAL | G | 01/01/1997 | 4,368 |  |  |  |  |  |  |
| 00 | 1112 | BUFFALO LEASED WAREHOUSE #1 |  |  | EXISTING - OPERATIONAL | G | 06/01/1997 | 4,287 |  |  |  |  |  |  |
|  | Count: 7 |  |  |  |  |  |  | Sum: 19,853 | Sum: |  | Sum: |  |  | Sum: |

A.3. Lease Basics

Agency: 11 ¦ Managing Org: 01 ¦ Status Code: A

| Lease # | Name | Effective Date | Expiration Date | Annual Rental Amount | Number Of Options | Option Period Years | Option Notice Days | Option Notice Date | Termination Notice Days | Escalator | Capital Lease | Total Sqft | Total Acres | Lessor | Phone Number | Address | LCO | LCO Phone Number | LCOR | Lcor Phone Number |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5-REVIEW | REVIEW | 09/30/2004 | 12/31/2025 | $1.00 | 5 | 3 | 90 | 10/02/2025 | 120 | N | N | 10,000 | 35 | AHM PROPERTIES, LTD | (865)637-3770X28 | 3658 WOODLAND DRIVE, KNOXVILLE, TN, 37919 |  |  |  |  |
| 57-0343-0-0019 | BOZEMAN SO LAB | 03/01/2000 | 07/31/2002 | $4,800.00 | 0 | 0 | 30 | 07/01/2002 | 30 | N | N | 355 | 0 | City of Bozeman | (406)582-2308 | P. O. Box 1230, Bozeman, MT, 59771 |  |  |  |  |
| 57-0343-0-0020 | AFD SMOKEJUMPER SITE | 08/16/2000 | 08/15/2005 | $1.00 | 1 | 5 | 30 | 07/16/2005 | 30 | N | N | 0 | 1,280 | Circle H. Development Co. | (406)549-0434 | c/o Jay C. Raser, 2435 Mullan Road, Missoula, MT, 59802 |  |  |  |  |
| 57-0343-0-LE02 | JUDITH RD | 01/01/2000 | 12/31/2004 | $14,500.00 | 1 | 5 | 30 | 12/01/2004 | 30 | N | N | 3,976 | 0 | Pat Kirby |  |  |  |  |  |  |
| 57-0343-0-LE03 | MUSSELSHELL RD | 10/01/2000 | 09/30/2010 | $75,109.50 | 2 | 5 | 180 | 04/03/2010 | 180 | N | N | 31,341 | 0 | Ronald Fischer |  |  |  |  |  |  |
| 57-0343-0-NE094 | CLEARWATER RD | 11/14/1990 | 11/13/2005 | $82,844.64 | 1 | 5 | 365 | 11/13/2004 | 60 | Y | N | 6,496 | 0 | Blewett, Blewett, & Profitt | (208)983-2933 | P. O. Box 356, Grangeville, ID, 83530 |  |  |  |  |
| 57-0343-0-NE17 | RED RIVER PASTURE | 05/02/2000 | 11/30/2001 | $4,410.00 | 0 | 1 | 0 | 11/30/2001 | 60 | N | N | 0 | 115 | Edith Mullins | (208)842-2455 |  |  |  |  |  |
| 57-0343-1-BE127 | B-D SUPERVISORS OFFICE | 01/01/1992 | 12/30/2006 | $324,676.32 | 1 | 5 | 60 | 10/31/2006 | 180 | N | N | 52,607 | 0 | Mountain States Leasing/Dillon |  |  |  |  |  |  |
| 57-0343-1-BI120 | BITTERROOT SO | 09/13/1991 | 09/12/2006 | $324,451.58 | 1 | 5 | 30 | 08/13/2006 | 60 | Y | N | 40,903 | 0 | Mildenberger Enterprises | (406)363-4100 | P. O. Box 633, Hamilton, MT, 59840 |  |  |  |  |
| 57-0343-1-CL02 | CLEARWATER RADIO SITE | 10/01/2000 | 09/30/2005 | $50.00 | 3 | 5 | 30 | 08/31/2005 | 90 | N | N | 0 | 0 | City of Pierce | (208)464-2222 | PO Box 356, Pierce, ID, 83456 |  |  |  |  |
| 57-0343-1-CU143 | GRAND RIVER RD | 04/01/1991 | 03/31/2002 | $16,245.36 | 1 | 5 | 60 | 01/30/2002 | 90 | Y | N | 5,592 | 0 | Donald Even | (605)374-3771 | 501 2nd Street West, Lemmon, SD, 57638 |  |  |  |  |
| 57-0343-1-HE03 | HELENA SO ANNEX | 05/01/2001 | 04/30/2003 | $7,135.80 | 4 | 1 | 30 | 03/31/2003 | 30 | N | N | 1,010 | 0 | Helena Regional Airport Authority | (406)442-2821 | Helena Regional Airport, 2850 Skyway Drive, Helena, MT, 59602 |  |  |  |  |
| 57-0343-1-HE165 | HELENA SO | 05/01/1992 | 04/30/2007 | $184,552.97 | 1 | 5 | 30 | 03/31/2007 | 60 | Y | N | 12,931 | 0 | Helena Regional Airport Authority | (406)442-2821 | Helena Regional Airport, 2850 Skyway Drive, Helena, MT, 59602 |  |  |  |  |
| 57-0343-1-LE22 | L&C COMMUNICATION SITE | 10/01/2001 | 09/30/2002 | $100.00 | 3 | 1 | 30 | 08/31/2002 | 30 | N | N | 8 | 0 | Marlow TV Association |  |  |  |  |  |  |

A.4. Lease Details

Agency: 11 ¦ Managing Org: 01 ¦ Status Code: A

| Lease # | Name | Lease Originator | Effective Date | Expiration Date | Annual Rental Amount | Property Type | Site ID | Property Name | Area Of Space | UOM | Usage | Price Per Uom | Land Unit 2250a |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 57-0343-0-0019 | BOZEMAN SO LAB |  | 03/01/2000 | 07/31/2002 | $4,800.00 | BUILDING | L115 | GALLATIN NF LAB | 355 | SF | OTHER-BUILDING | $11.67 | N |
| 57-0343-0-0020 | AFD SMOKEJUMPER SITE |  | 08/16/2000 | 08/15/2005 | $1.00 | PARKING_LOT | L004 | AFD SMOKEJUMPER SITE | 1,280 | A | OTHER-BUILDING |  | N |
| 57-0343-0-LE02 | JUDITH RD |  | 01/01/2000 | 12/31/2004 | $14,500.00 | BUILDING | L154 | JUDITH RD OFFICE | 3,018 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | MISC_STORAGE | L155` | JUDITH RD WAREHOUSE | 955 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | PARKING_LOT | L155A | JUDITH RD PARKING SPACES | 3 | SF | OTHER-BUILDING |  | N |
| 57-0343-0-LE03 | MUSSELSHELL RD |  | 10/01/2000 | 09/30/2010 | $75,109.50 | BUILDING | L151 | MUSSELSHELL RD OFFICE | 5,351 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | MISC_STORAGE | L156 | MUSSELSHELL RD STORAGE | 5,525 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | MISC_STORAGE | L151A | MUSSELSHELL RD BASEMENT STORAGE | 1,110 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | PARKING_LOT | L156B | MUSSELSHELL PARKING SPACES | 55 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | WAREYARD | L156A | MUSSELLSHELL WAREYARD | 19,300 | SF | OTHER-BUILDING |  | N |
| 57-0343-0-NE094 | CLEARWATER RD |  | 11/14/1990 | 11/13/2005 | $82,844.64 | BUILDING | L173 | CLEARWATER RD OFFICE | 6,496 | SF | OFFICE BUILDING LOCATIONS-BUILDING |  | N |
| 57-0343-0-NE17 | RED RIVER PASTURE |  | 05/02/2000 | 11/30/2001 | $4,410.00 | LEASED LAND | L175 | RED RIVER RD PASTURE | 115 | A | GRAZING-LAND |  | N |
| 57-0343-1-BE127 | B-D SUPERVISORS OFFICE |  | 01/01/1992 | 12/30/2006 | $324,676.32 | BUILDING | L026 | BEAVERHEAD NF SUPERV. OFFICE | 22,289 | SF | OFFICE BUILDING LOCATIONS-BUILDING |  | N |
|  |  |  |  |  |  | BUILDING | L027 | BEAVERHEAD NF WAREHOUSE | 9,318 | SF | STORAGE-BUILDING |  | N |
|  |  |  |  |  |  | PARKING_LOT | L027C | PARKING SPACES | 0 | SF | OTHER-BUILDING | $0.00 | N |
|  |  |  |  |  |  | WAREYARD | L027A | WAREYARD | 21,000 | SF | OTHER-BUILDING | $0.98 | N |
| 57-0343-1-BI120 | BITTERRDAT SO |  | 09/13/1991 | 09/12/2006 | $324,451.58 | BUILDING | L031 | BITTERRDAT SUPERVISOR’S OFFICE | 16,993 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | MISC_STORAGE | L032 | SHOP/WAREHOUSE/STORAGE | 4,910 | SF | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | PARKING_LOT | L032B | PARKING SPACES |  |  | OTHER-BUILDING |  | N |
|  |  |  |  |  |  | WAREYARD | L032A | WAREYARD | 19,000 | SF | OTHER-BUILDING |  | N |

A.5. GSA Assignment Details

Agency Code: 00 ¦ Managing Org:

| CBR # | Effective Date | Expiration Date | Annual Rental Amount | Building ID | Building Name | Charge Type | Units | UOM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CA0062441 |  | 12/12/2003 | $28,260 | CA7079 | 5TH&”G” STREET | GSA Fee | 910 |  |
|  |  |  |  |  |  | Operating Costs | 671 |  |
|  |  |  |  |  |  | Pro Rata Joint Use Charges - Building Amenities | 239 | SF |
|  |  |  |  |  |  | Security services - Basic Charges | 910 | SF |
|  |  |  |  |  |  | Security services - Building Specific Amortized Captial | 910 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 671 | SF |
| DC0018427 |  | 12/12/2003 | $218,664 | DC0274 | PRKG LOT 12TH ST S | Parking - Surface (Number of spaces) | 113 | SP |
| DC0018507 |  | 12/12/2003 | $745,764 | DC0361 | 501 SCHDAL ST S.W | GSA Fee | 21,877 |  |
|  |  |  |  |  |  | Operating Costs | 21,877 |  |
|  |  |  |  |  |  | Security services - Basic Charges | 21,877 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 21,877 | SF |
| DC0018617 |  | 12/12/2003 | $1,164,132 | DC0399 | 2101 L ST N W | GSA Fee | 40,688 |  |
|  |  |  |  |  |  | Operating Costs | 40,688 |  |
|  |  |  |  |  |  | Parking - Structured (Number of spaces) | 6 | SP |
|  |  |  |  |  |  | Security services - Basic Charges | 40,688 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 40,688 | SF |
| DC0018706 |  | 12/12/2003 | $4,207,920 | DC0501 | SIDNEY YATES (AUDITORS) | Operating Costs | 152,329 |  |
|  |  |  |  |  |  | Parking - Surface (Number of spaces) | 16 | SP |
|  |  |  |  |  |  | Security services - Basic Charges | 152,329 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 152,329 | SF |
| DC0052208 |  | 12/12/2003 | $4,952,592 | DC0506 | 1800 M ST NW | GSA Fee | 192,050 |  |
|  |  |  |  |  |  | Operating Costs | 192,050 |  |
|  |  |  |  |  |  | Security services - Basic Charges | 192,050 | SF |
|  |  |  |  |  |  | Security services - Building Specific | 192,050 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 192,050 | SF |
| DC0052256 |  | 12/12/2003 | $1,093,044 | DC0343 | 370 L’ENFANT PROMENADE | GSA Fee | 27,629 |  |
|  |  |  |  |  |  | Operating Costs | 27,629 |  |
|  |  |  |  |  |  | Real Estate Taxes | 0 |  |
|  |  |  |  |  |  | Security services - Basic Charges | 27,629 | SF |
|  |  |  |  |  |  | Security services - Building Specific | 27,629 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 27,629 | SF |
| DC0052425 |  | 12/12/2003 | $3,369,804 | DC1128 | REPORTERS | GSA Fee | 124,850 |  |
|  |  |  |  |  |  | Operating Costs | 124,850 |  |
|  |  |  |  |  |  | Real Estate Taxes | 0 |  |
|  |  |  |  |  |  | Security services - Basic Charges | 124,850 | SF |
|  |  |  |  |  |  | Security services - Building Specific | 124,850 | SF |
|  |  |  |  |  |  | Shell Rental Rate - General | 124,850 | SF |

B.1 Subledger Summary

B.2 Value Streams

Appendix L
Conversion Certification Form

This appendix contains the sample form for certifying the source data file to be used for conversion into CPAIS.

# Footnotes

Modified from U.S. Department of Agriculture, Corporate Property Automated Information System to Corporate Financial System (CPAIS - FFIS Interface) Detailed Design, August 29, 2003, Version 1.0.