## UMC Only
Updated: | 2006-05-16
NOTE: | Revised per new UMC definition (only include "easily removed items")
Building No. | Issue Title | Champion | Responsible Department | Available Cost Information (x1000) | Estimate Quality | Proposed Funding Source | UMC
462 | Hot Shop Cleanout | T. Lambertson/ G. Olsen | SC | 240 | C | AA4D0009 | yes
555 | Contaminated Fume Hoods | D. Cabelli/ S. Howell | CO |  | --- | AA4D0011 | no | D&D
801 | D&F-Waste Storage Tank Disposal | D. Rocco/J. Bullis | MO | 1000 | A-B | AA1D0112 | yes
801 | Removal of Ducts to Stack | J. Bullis/S. Ferrone | MO |  | D | AA4D0007 | no | D&D
801 | Contaminated Fume Hoods, Blowers, and Ducts | J. Bullis/ G. Flett | MO | 60 | C | AA1D0102 | yes
801 | Abandoned Hot Cells | J. Bullis/ G. Flett | MO | 300 | C | AA1D0103 | yes
801 | Abandoned Acid Off-Gas System | J. Bullis/ G. Flett | MO |  | C | AA1D0104 | no | D&D
801 | Metallurgy Evaluation Labs (MEL) | R. Doty | EENS | 100 | --- | AA4D0036 | yes | Contents only
802 | Evaporator System | D. Rocco | EWMSD |  | C | AA4D0037 | no | D&D
811 | Aboveground Tank Removal | M. Clancy | EWMSD |  | C | AA2D0055 | no | D&D
815 | Non-acid off-gas line | J. Boccio/ R. Doty | EENS |  | C | I94D0019 | no | D&D
830 | Canals and Hot Cells | P. Kalb | EENS | 200 | D | AA4D0008 | yes | Contents only
900 | Disposal/Recycling of Suspect Scrap Metal | D. Dale/ G. Olsen | PR | 70 | C | AA4D0038 | yes
901 | Dynamitron/Cyclotron | R. Doty/D. Schlyer | EENS | 200 | --- | AA4D0012 | yes | contents only
902 | Cosmotron Tanks | T. Dilgen | AM | --- | --- | AA4D0040 | no
912 | C-AD Lead Storage Yards | E. Lessard/ D. Paquette | AD | --- | --- | AA4D0014 | yes
801 and 811 | Removal of A&B waste lines | J. Remien | EWMSD | 1500 | C | AA3D0046 | yes
815 and 830 | Remove Non-Acid Off-gas Ductwork | G. Flett | EP | --- | --- | AA4D0042 | yes
Total |  |  |  | 3670
DECONTAMINATION & DECOMMISSIONING
490 | Internal & External cleanup | C. Harris | MO | --- | --- | AA4D0023 | yes
491 | Decontamination & Decommissioning (D&D) | M. Bebon/ R. Rooks | DO |  | C | AA4D0019 | no | D&D
801 | Internal & External cleanup | J. Bullis/S. Ferrone | MO | 0 | D | AA4D0006 | yes | D&D
830 | Internal & External cleanup | P. Kalb | EENS | 0 | D | AA4D0020 | yes | D&D
900 | Collider-Accelerator Department Facilities Excess Materials | J. Scott | AD | 19500 | D | --- | yes
Total |  |  |  | 19500
EXCESS NUCLEAR & NON NUCLEAR MATERIALS
900 | Depleted Uranium/metal 18,120 kg (includes AGS C-3 line beam stop) | G. Shepherd/ K. Dahms | ESH&Q | 500 | D | --- | yes
| Deuterium/Heavy water 762.6 kg D20 (only degraded water) | K. Dahms | SE | 100 | D | --- | yes
| Strategic lithium (6Li)/LiF (1.34 kg) | K. Dahms | SE | 25 | D | --- | yes
| Highly enriched uranium/Other forms 114 Gm | G. Shepherd/ K. Dahms | ESH&Q | 50 | D | AA4D0046 (See note below) | yes
| Lead/Brick, sheet, pigs, misc. 50,000 kg | G. Todzia | EWMSD | 100 | D |  | yes
| Low enriched uranium/N/A 11.70 kg (mostly JANUS fission converter plates) | G. Shepherd/ K. Dahms | ESH&Q | 100 | D |  | yes
| Normal enriched uranium/N/A (334.8 kg) | K.Dahms | SE | 25 | D |  | yes
| Sitewide Materials (7,500 tons) | D. Rocco | EWMSD | 8000 | D |  | yes
| Sealed Sources (14,000 Curies) | D. Rocco | ESH&Q | 5000 | D |  | yes
| Plutonium (125 grams) | G. Shepherd/ K. Dahms | ESH&Q | 500 | D |  | yes
| Am-241 (31 grams) | G. Shepherd/ K. Dahms | ESH&Q | 1000 | D |  | yes
| Cf-252 (100 ugrams) | G. Shepherd/ K. Dahms | ESH&Q | 100 | D |  | yes
| TRU (160 grams) | G. Shepherd/ K. Dahms | ESH&Q | 4000 | D |  | yes
Total |  |  |  | 19500
Liability Total |  |  |  | 42670
From Additional List |  |  |  | 789
Grand Total |  |  |  | 43459
Say |  |  |  | 44000 | Original number was 76,000,000

## Projects-Programs-D&D
Updated: | 2006-05-09
NOTE: | Please confirm with Jason Remien (x3477) that this table is the most recent version
Building No. | Issue Title | Champion | Responsible Department | Available Cost Information | Estimate Quality | Proposed Funding Source | UMC
900 | Characterization of Radiological Contaminated Soils along Brookhaven Avenue (East of the NEXRAD Weather Station) | R. Lee | EWMSD | $40K | C | AA4D0087 | no
49 | Lead in soil beneath water tank (ST0049) | W. Chaloupka/ J. Remien | EP | $36K | C | AA4D0013 | no
428 | Incinerator ash deposits | J. DiNicola/ G. Olsen | EP | $60K | C | AA4D0010
462 | Hot Shop Cleanout | T. Lambertson/ G. Olsen | SC | $240K | C | AA4D0009 | yes
463 | Greenhouse soils | R. Sautkulis/ S. Ferrone | BO | $50K | D | AA1D0097 | no
490 | Disposition of sources associated with the Whole Body Irradiation Facility | W. Gunther | MO | $200K | C | AA2D0069
555 | Contaminated Fume Hoods | D. Cabelli/ S. Howell | CO | --- | --- | AA4D0011 | yes
610 | Lead in Soil – Storm Water Outfall 010 | R. Lee | EWMSD | $716K | A-B | AA3D0026 | no
801 | D&F-Waste Storage Tank Disposal | D. Rocco/J. Bullis | MO | $1M | A-B | AA1D0112 | yes
801 | Removal of Ducts to Stack | J. Bullis/S. Ferrone | MO | $5M | D | AA4D0007 | yes
801 | Contaminated Fume Hoods, Blowers, and Ducts | J. Bullis/ G. Flett | MO | $60K | C | AA1D0102 | yes
801 | Abandoned Hot Cells | J. Bullis/ G. Flett | MO | $300K | C | AA1D0103 | yes
801 | Abandoned Acid Off-Gas System | J. Bullis/ G. Flett | MO | $45K | C | AA1D0104 | yes
801 | Metallurgy Evaluation Labs (MEL) | R. Doty | EENS | --- | --- | AA4D0036 | yes
802 | Evaporator System | D. Rocco | EWMSD | $140K | C | AA4D0037 | yes
811 | Residual Contaminated Soils | M. Clancy | EWMSD | $250K | C | AA3D0045 | no
811 | Aboveground Tank Removal | M. Clancy | EWMSD | $500K | C | AA2D0055 | yes
815 | Non-acid off-gas line | J. Boccio/ R. Doty | EENS | $200K | C | I94D0019 | yes
830 | Canals and Hot Cells | P. Kalb | EENS | $1M | D | AA4D0008 | yes
848 | Lead contaminated soils at shotgun range (TR0848) | C. Carter/ D. Paquette | SS | --- | --- | AA4D0015 | no
900 | Disposal/Recycling of Suspect Scrap Metal | D. Dale/ G. Olsen | PR | $70K | C | AA4D0038 | yes
900 | "Open" Facility Review Project Issues | J. Remien | Issue Specific | --- | --- | --- | no
900 | "Transferred" Facility Review Project Issues | J. Remien | Issue Specific | --- | --- | --- | no
900 | Evaluate Hg Contamination in Bldg. Waste Piping | R. Scheidet/ R. Lee | EP | $300K | C | AA0D0078 | no
900 | SCDHS Experimental Facility (ALDO) | J. Remien/ E. Governale (SCDHS) | EWMSD | $15K | D | AA4D0039 | no
901 | PCB regulator | D. Schlyer/ A. Harris | CO | --- | --- | AA4D0016 | no
901 | Dynamitron/Cyclotron | R. Doty/D. Schlyer | EENS | $7.6M | --- | AA4D0012 | yes
902 | Cosmotron Tanks | T. Dilgen | AM | --- | --- | AA4D0040 | yes
912 | C-AD Lead Storage Yards | E. Lessard/ D. Paquette | AD | --- | --- | AA4D0014 | yes
930 | Replacement of PCB capacitors | V. Lo Destro | AD | $507K | C | AA1D0080 | no
1005 | Activated Soil Pile | J. Scott | AD | --- | --- | AA4D0041 | no
650 and 650A | Decontamination & Decommissioning (D&D) | T. Sperry | EWMSD | $6.2M | A-B | AA4D0018 | no | Some equipment is included but not the D&D
801 and 811 | Removal of A&B waste lines | J. Remien | EWMSD | $1.5M | C | AA3D0046 | yes
815 and 830 | Remove Non-Acid Off-gas Ductwork | G. Flett | EP | --- | --- | AA4D0042 | yes
DECONTAMINATION & DECOMMISSIONING
197 | Mercury removal | G. Flett/ J. Remien | EP | $150K | D | AA4D0017
423 | Floor drains/Contaminated soils | H. Hauptman | EP | --- | --- | AA4D0043
463 | Hydraulic Fluid Leak | J. Mills/ R. Sautkulis | EP | --- | --- | AA4D0044
490 | Internal & External cleanup | C. Harris | MO | --- | --- | AA4D0023 | yes
491 | Decontamination & Decommissioning (D&D) | M. Bebon/ R. Rooks | DO | $17.8M | C | AA4D0019 | yes
555 | Source vault removal and drywell | S. Howell | CO | $75K | D | AA4D0021
610 | Removal of old fuel supply lines | W. Chaloupka | EP | $1M | D | AA4D0025
801 | Internal & External cleanup | J. Bullis/S. Ferrone | MO | $4M | D | AA4D0006 | yes
830 | Internal & External cleanup | P. Kalb | EENS | $1M | D | AA4D0020 | yes
900 | Collider-Accelerator Department Facilities Excess Materials | J. Scott | AD | $19.5M | D | --- | yes
903 | Wood floor impregnated with oil & creosote | T. Dilgen | AM | --- | --- | AA4D0045
EXCESS NUCLEAR & NON NUCLEAR MATERIALS
900 | Depleted Uranium/metal 18,120 kg (includes AGS C-3 line beam stop) | G. Shepherd/ K. Dahms | ESH&Q | $500K | D | --- | yes
| Deuterium/Heavy water 762.6 kg D20 (only degraded water) | K. Dahms | SE | $100K | D | --- | yes
| Strategic lithium (6Li)/LiF (1.34 kg) | K. Dahms | SE | $25K | D | --- | yes
| Highly enriched uranium/Other forms 114 Gm | G. Shepherd/ K. Dahms | ESH&Q | $50K | D | AA4D0046 (See note below) | yes
| Lead/Brick, sheet, pigs, misc. 50,000 kg | G. Todzia | EWMSD | $100K | D |  | yes
| Low enriched uranium/N/A 11.70 kg (mostly JANUS fission converter plates) | G. Shepherd/ K. Dahms | ESH&Q | $100K | D |  | yes
| Normal enriched uranium/N/A (334.8 kg) | K.Dahms | SE | $25K | D |  | yes
| Sitewide Materials (7,500 tons) | D. Rocco | EWMSD | $8.0M | D |  | yes
| Sealed Sources (14,000 Curies) | D. Rocco | ESH&Q | $5.0M | D |  | yes
| Plutonium (125 grams) | G. Shepherd/ K. Dahms | ESH&Q | $500K | D |  | yes
| Am-241 (31 grams) | G. Shepherd/ K. Dahms | ESH&Q | $1.0M | D |  | yes
| Cf-252 (100 ugrams) | G. Shepherd/ K. Dahms | ESH&Q | $100K | D |  | yes
| TRU (160 grams) | G. Shepherd/ K. Dahms | ESH&Q | $4.0M | D |  | yes
Note: | ADS # AA4D0046 (Excess Nuclear Material Management Disposition Plan) is currently funded for $1M. This funding will be used to dispose of some sources and other high-activity material listed above but will not cover everything. Part of the scope for this ADS includes the preparation of a detailed cost estimate supporting an ADS to dispose of all the remaining more challenging items which have open paths to disposal, and a second Management and Disposition Plan detailing the course of action required to go forward on the remaining items. EWMSD personnel will manage this list (i.e., exploring and identifying viable paths to disposal for the items in the list, as well as updating the listing of excess radioactive inventory annually via a data call to the Laboratory) under Performance Measure 3.4.2 (Nuclear and Radiological Facilities and Operation).