Statement of Work

for

Meeting of the NCI’s Integrative Cancer Biology Program

Nashville, TN

April 30 – May 2, 2006

Background

The Division of Cancer Biology, NCI has planned a 2.5 day workshop to be held during the period of April 30 to May 2, 2006.  The meeting will take place in Nashville, TN at a hotel preferably located near the campus of Vanderbilt University.  We anticipate 15 invited speakers (domestic) and 105 meeting participants.  The speakers will be reimbursed for their hotel accommodations, air fare, per diem and ground transportation as per Federal Travel Regulations (FTRs).  The participants will pay for their hotel and travel expenses (no reimbursements).

STATEMENT OF WORK

PRE-MEETING:

Hotel

- Arrange for a hotel meeting site in Nashville, TN.  The preferred location for a hotel is one that is reasonably close to the Vanderbilt University campus.   Negotiate sleeping and meeting room rates.  Pay hotel deposits.

- Make arrangements for approximately 80 sleeping rooms for travelers for 2 nights, or up to 3 nights for 1 foreign traveler.

- Arrange for a large meeting room sufficient to accommodate 120 participants; seating should be a U-shaped table (for 40 attendees), perimeter seating (for 80 attendees) with a podium and projection screen facing the participants.

- Arrange for 2 Breakout rooms, for one day’s use, each for a 30-40 person capacity.

- Arrange for a room to accommodate a poster session for approximately 25 posters and computerized demonstration stations (approximately 12).  The poster session will require 13 stand-alone, double-sided poster boards to be placed in the room; the demonstration sessions will require a table for each of the 12 stations.

- Arrange and provide light refreshments during registration for 120 attendees.

- Arrange and provide an evening reception (heavy nibbles, cash bar) for 120 attendees.

- Arrange and provide 2 continental breakfasts and 1 working lunch for 120 attendees.

Reduce speaker per diem as required.

- Arrange and provide 1 morning and 2 afternoon breaks for 120 attendees.

- Coffee/tea/soft drinks to be available throughout the 2.5 days.

Symposium site

- Coordinate with the local hosts, Drs. Vito Quaranta and Lourdes Estrada, the selection of a suitable auditorium at Vanderbilt University to accommodate 150 attendees at  a half day Symposium.  If Vanderbilt University does not have an auditorium available, secure a ballroom at the meeting hotel to accommodate the Symposium.  Arrange for theatre seating for 150 attendees with a podium,  projection screen and table suitable for a panel discussion facing the audience.

- If the Symposium is held on the Vanderbilt University campus, secure a caterer to provide a break/snack (coffee/tea/soft drinks/nibbles) for 150 attendees.

- If the Symposium is held at the meeting hotel, arrange with the hotel to provide a break/snack (coffee/tea/soft drinks/nibbles) for 150 attendees.

Logistics

- Solicit travel information from speakers.

- Develop detailed travel itineraries for speakers.

- Provide speakers with prepaid tickets, by courier or postal services, in advance of travel, if possible.

- Make direct contact with speakers to ensure that they understand all travel arrangements and the extent of reimbursement.

- Provide easy access to registration (e.g., online website, email or fax); registration should be available at least six weeks prior to the meeting.

- Coordinate all pre-meeting mailings (email and/or postal service) and provide logistical and informational support for the meeting participants.

- Prepare pre-meeting and meeting packages for participants, to include an agenda, participant list, and other materials as defined by NCI/NIH staff; send to participants (email and/or postal service) and provide during the meeting (see below)

- Mail meeting notices and updates to participants (both email and/or postal service)

- Prepare name tags, name tents and meeting folders including agenda, participant list, and other duplicated materials as defined by NCI/NIH staff – to be prepared two weeks prior to meeting.

- Prepare any necessary paperwork related to the meeting as stipulated by NCI/NIH staff.

MEETING:

- Provide microphones for every two participants seated at the U-shaped table.

- Provide a lavaliere microphone for podium presentations .

- Provide 3-4 stand-alone microphones for participants seated in the perimeter areas.

- Provide all necessary audio-visual (AV) equipment for the large meeting room (LCD projector, laptop computer, overhead projector); provide flip charts with easels and markers in each of the 2 Breakout rooms.

- Provide an Internet connection in the general meeting room and multiple Internet connections in the poster/demonstration room.

- Provide all necessary audio-visual (AV) equipment for the Symposium (LCD projector, laptop computer), if located at the meeting hotel.

- Provide 2 stand-alone microphones for easy audience accessibility for the Symposium, if located at the meeting hotel.

- Determine and pay costs for a knowledgeable audio-visual (AV) technician to be available during the 2.5 day meeting to set up and run PowerPoint presentations using an LCD projector and laptop (PC- and MAC-compatible) computer system.

- Provide approximately 13 stand-alone, double-sided poster boards to be used during the 2.5 day meeting;  provide push pins to secure the posters.

- Determine and pay costs for appropriate support services during the 2.5 day meeting, including 1 person at the registration desk to assist participants and register attendees.

POST-MEETING:

- Reimburse speakers for ground transportation and other travel-related expenses as permitted under Government FTRs and Government policies.

- Provide post-meeting services to include contacting all speakers to ensure that all travel and per diem costs have been submitted and reimbursed; these services should extend for 3 months after the conclusion of the meeting.

- Provide meeting materials packets or information (via e-mail and/or mail) to those meeting participants who requested it but were unable to attend the meeting.

Deliverables

Logistical information that is prepared and mailed/emailed to the participants.

Participant name tags, name tents, meeting folders, etc., to be prepared 2 weeks prior to the meeting.

Participant packages, final participant list, agenda, etc., to be prepared 1 week prior to the meeting.

Professional Service Contract (PSC) equivalents to be provided to the participants at the end of the meeting.