| Step | Plan | Actual |  |
| --- | --- | --- | --- |
| Feb. 21 | Install capillary, leak check, heaters, OSP B blankets | Capillary circuit leak checked ISP continuity done ISP final prep done | 0 |
| Feb. 22 | Finish ISP prep, continuity ISP, Attach ISPs | ISP prep finished ISPs attached | 0 |
| Feb. 23 | Route fibers, start ENV routing | Fibers routed, ENV routing just started | 0 |
| Feb. 24 | Slack | No work | 0 |
| Feb. 25 | Slack | No work | 0 |
| Feb. 26 | Finish ENV routing, put upright | ENV routing continues. Other prep done | 0.5 |
| Feb. 27 | Install top optoboards, start testing | ENV routing continues | 1 |
| Feb. 28 | Finish opto testing, start mech work on opto | ENV completed and checked. Put upright. Started install and test of top optoboards, ½ done –one board | 1 |
| Mar. 1 | Finish mech work opto, attach and route heater cables. Start exhaust attach | Opto testing completed. | 1.5 |
| Mar. 2 | Finish exhaust attach and leak check. Dress heater cables | Top heaters attached, IR, blankets started.. Heater cables routed but not connected | 2 |
| Mar. 3 | Slack |  |  |
| Mar. 4 | Slack |  |  |
| Mar. 5 | Continuty. Can start |  |  |
| Mar. 6 | Can finish. Continuity |  |  |
| Mar. 7 | Repair. Continuity(if needed) |  |  |
| Mar. 8 | Final prep and box for SR1 |  |  |