Maine Department of Environmental Protection

Implementation of a Voluntary Auto Body/Repair Environmental Results Program

Quality Assurance Project Plan

Maine Department of Environmental Protection

Office of Innovation and Assistance

17 State House Station

Augusta, Maine 04333-0017

Sara M. Lippert

Phone: (207) 287-4432

Fax: (207) 287-2814

Email: sara.m.lippert@maine.gov

# A	PROJECT MANAGEMENT

## A1.	Approval Sheet

____________________________________________	_______________________

Sara Lippert							Date

Maine DEP

Environmental Specialist II

____________________________________________	_______________________

Ron Dyer							Date

Maine DEP

Director, Office of Innovation and Assistance

____________________________________________	_______________________

Julie Churchill							Date

Maine DEP

Assistant Director, Office of Innovation and Assistance

_____________________________________________ 	________________________

Steve DiMattei						Date

US EPA

QA Chemist

_____________________________________________	________________________

George Frantz							Date

US EPA

EPA-NE Project Officer

## A2.	Table of Contents

A	PROJECT MANAGEMENT	1

A1.	Approval Sheet	1

A2.	Table of Contents	2

A3.	Distribution List	4

A4.	Project/Task Organization	4

A5.	Problem Definition/Background	6

Rationale for initiating the project	6

Objectives of the project	6

Regulatory information, applicable criteria and action limits	6

A6.	Project/Task Description	6

Project overview.	6

Project summary and work schedule.	7

Geographic focus	9

Resource and time constraints	9

A7.	Quality Objectives and Criteria	9

Detailed performance measures	9

Quality objectives	11

A8.	Special Training/Certification	11

A9.	Documents and Records	12

Report format/information	12

Document/record control	12

Other records/documents	12

Storage of project information	12

Backup of electronic files	13

B	DATA GENERATION AND ACQUISITION	13

B1.	Sampling Process Design (Experimental Design)	13

B2.	Sampling Methods	13

Preparation of data collection instruments	14

B3.	Sample Handling and Custody	14

Data entry QA procedures	14

B4.	Analytical Methods	14

B5.	Quality Control	15

Crosschecking data	15

Data anomalies	15

Quality control statistics	15

B6.	Instrument/Equipment Testing, Inspection and Maintenance	15

B7.	Instrument/Equipment Calibration and Frequency	15

B8.	Inspection/Acceptance for Supplies and Consumables	15

B9.	Non-Direct Measurements (I.e., Secondary Data)	15

Key resources/support facilities needed	16

Determining limits to validity and operating conditions	16

B10.	Data Management	16

C	ASSESSMENT/OVERSIGHT	17

C1.	Assessment and Response Actions	17

C2.	Reports to Management	17

D	DATA REVIEW AND EVALUATION	18

D1.	Data Review, Verification and Validation	18

D2.	Verification and Validation Methods	18

D3.	Evaluating Data in Terms of User Needs	18

Mathematical and statistical formulae	20

Approach to managing unusable data	23

## A3.	Distribution List

Each person listed on the approval sheet and each person listed under Project/Task Organization will receive a copy of this Quality Assurance Project Plan (QAPP).  Individuals taking part in the project may request additional copies of the QAPP from personnel listed under Section A4.

This document has been prepared according to the United States Environmental Protection Agency publication EPA Requirements for Quality Assurance Project Plans dated March 2001 (QA/R-5).

## A4.	Project/Task Organization

Personnel involved in project implementation are listed in Table 1, and shown as an organization chart in Figure 1.

| Table 1: Project Implementation Personnel |
| --- |
| Individual | Role in Project | Organizational Affiliation |
| Sara Lippert | ERP Project Manager | Maine DEP |
| Ron Dyer Julie Churchill | ERP Management Support | Maine DEP |
| Michael Crow Richard Krop | Contractor | The Cadmus Group, Inc. |
| Ed Cousins Peter Carleton Louis Fontaine | Bureau of Air Quality Representative | Maine DEP |
| Scott Whittier Mike Hudson | Bureau of Remediation and Waste Management Representative | Maine DEP |
| Erich Kluck Sterling Pierce | Bureau of Land and Water Quality Representative | Maine DEP |

The Maine DEP ERP Project Manager will be responsible for the following activities:

- Identify facility universe

- Create sampling approach for Pollution Prevention (P2) audits

- Construct sampling strategy/schedule for P2 audits

- Develop web page for DEP web site

- Develop workbook and checklists

- Conduct P2 audits

- QA management

- Conduct outreach with regulated industry and internal/external stakeholders

- Maintain official, approved QAPP

- Data entry

- Database management

- Issue quarterly and annual reports to U.S. EPA

The Maine DEP ERP Management Support will be responsible for the following activities:

- Project oversight

- Assist in coordination of interdepartmental meetings

- Coordinate with senior management within each bureau

- Policy review

The Cadmus Group, Inc. will be responsible for the following activities:

- Help develop statistical methodology and Environmental Business Practice Indicators (EBPIs)

- Help develop sampling options

- Develop statistical methodology

The Maine DEP Bureau Representatives will be responsible for the following activities:

- Help develop EBPIs

- Help develop workbook, self-certification checklist, P2 audit checklist

- Conduct outreach at ERP workshops

The participating facilities will be responsible for submitting self-certification materials and, if applicable, return-to-compliance forms.

Figure 1:  Project Organizational Chart

## A5.	Problem Definition/Background

### Rationale for initiating the project

Maine contains over 4,000 registered motor vehicle auto body and auto repair shops in accordance with 1997 U.S. Economic Census (www.census.gov).  This is a significant amount of facilities and many are located in our densely populated areas that are classified in accordance with air quality non-attainment areas.  This project is a voluntary innovative permitting system based on the Environmental Results Program (ERP) model for a currently non-permitted sector.

### Objectives of the project

The main goals of this project is to promote pollution prevention concepts, increase public and industry awareness of environmental health concerns particularly in environmental justice, and measure increased environmental compliance. Because there are a significant amount of auto body businesses in Maine, it is anticipated a large impact will be made on the aggregate reductions in hazardous waste and air emissions. The focus area of our outreach will be the most populated areas in Maine (southern coastal), which also includes air quality non-attainment areas. The aggregate reduction impact in the Southern Maine region will not only improve the environment but also reduce exposures to the mass public to air toxins from both point source and fugitive emissions.

The measures we will be using to evaluate the project will include:

- Quantity of Air pollution reduced or mitigated including VOCs and HAPS through proper use of paints and cleaners. Changes in practices to high efficiency/transfer paint techniques and use of alternative cleaners.

- Rate of compliance with key Hazardous Waste regulations through manifest tracking and compliance checks.

- Quantity of water pollution reduced or mitigated- this will include compliance with the underground injection control program, wastewater discharge licenses issued and possibly secondary data from the program.

- Compliance rate will be assessed through initial and final compliance site assessments.

- Reduction in risk to the community focused in environmental justice neighborhoods within the Southern Maine regional air non-attainment region.

- Work with RCRA compliance staff on streamlining two existing hazardous waste policies/licenses (abbreviated license and rag/wipes)

### Regulatory information, applicable criteria and action limits

- Compliance with state and federal air regulations

- Compliance with state and federal hazardous waste regulations

- Compliance with state and federal water regulations

## A6.	Project/Task Description

### Project overview.

This project will allow Maine DEP to explore whether an approach modeled upon the Environmental Results Program (ERP) can help achieve these goals, while improving regulatory cost-effectiveness.   The ERP is an innovative approach to solving high-priority environmental problems in industry sectors largely comprised of small businesses.   The ERP concept combines technical assistance, self-certification, audits, and statistically based performance measurement in order to reduce environmental impacts of business.

The promise of ERP is that it will cost-effectively reduce environmental impacts of small businesses that may present a substantial cumulative environmental risk.  Businesses targeted so far by ERP include gas stations, auto salvage yards, auto body and mechanical repair shops, dry cleaners, and printers.  ERP can help environmental agencies identify previously unknown facilities, measure performance, increase regulatory efficiency, and help improve overall environmental performance.  ERP is in part designed to help facilities that want to comply but do not understand their requirements, and evidence suggests that ERP can motivate firms to comprehensively review their environmental performance and take needed action to come into compliance and adopt best practices.

### Project summary and work schedule.

This project's major tasks and timeline are outlined in the table below.

| Table 2: Schedule of major project tasks |
| --- |
| Task Name | Task Description | Start Date | End Date |
| Receive funding | Receive EPA grant funding for project | October 2004 | October 2004 |
| Hire staff | Hire staff for project | October 2004 | October 2004 |
| Train staff | Multi-media training for staff | October 2004 | October 2005 |
| Timeline development | Develop a Gantt chart detailing flow of work and timelines | October 2004 | October 2004 |
| Outreach | Coordinate and implement a multi-state workshop for the compliance staff and states awarded State Innovation Grants | October 2004 | December 2004 |
| Facility identification | Determine the exact characteristics of facilities to be included in this project, and compile a list of facilities from reliable sources. | October 2004 | December 2004 |
| Outreach | Convene internal stakeholders (DEP bureaus) | October 2004 | August 2005 |
| Outreach | Convene external stakeholders (Compliance Advisory Panel, Auto Associations) | October 2004 | August 2005 |
| Develop incentives | Develop incentives to attract volunteers into the ERP | October 2004 | August 2005 |
| Statistical methodology | Develop 10-20 Environmental Business Practice Indicators (EBPIs) in coordination with key DEP compliance representatives. Development of a statistical methodology to drive performance measurement and analytical tasks. | October 2004 | July 2005 |
| P2 audit checklist | Develop P2 audit checklist | October 2004 | April 2005 |
| Self-certification checklist | Develop multi-media compliance checklist for self-certification | October 2004 | May 2005 |
| Database development | Develop an ERP database to house indicator data | March 2005 | August 2005 |
| QAPP finalization & approval | Finalize QAPP based upon results of the measures identification, statistical methodology, and data management tasks. Primary data collection will not occur before relevant parts of the QAPP are finalized and approved by EPA. | February 2005 | August 2005 |
| Review existing compliance records | Review existing compliance records within the department to avoid audits at facilities when feasible with recent or ongoing compliance issues | October 2004 | Ongoing throughout project |
| Sampling approach | Design sampling approach such that we can determine if there are any statistically significant changes in environmental compliance | January 2005 | May 2005 |
| Test audit | Run a test audit to assure that audit checklist questions are appropriate | July 2005 | August 2005 |
| Workbook | Develop and complete a draft compliance workbook | October 2004 | August 2005 |
| Workshops | Conduct two workshops in the Southern Maine Regional Area to educate facilities regarding ERP workbooks/self-certification checklists | November 2005 | January 2005 |
| RCRA policy issues | Identify and assist in developing suggestions and streamlines on HW RCRA policy issues developed and drafted: 1. Wipes/rags treatment options & 2. Licensing technology | August 2004 | November 2005 |
| Baseline audits (establishing a performance measures baseline) | Audits at facilities to establish a baseline for performance measures. Facilities selected at random from the entire targeted population, based upon sample design from statistical methodology. | August 2005 | October 2005 |
| Baseline analysis | Analysis of audit data to establish a baseline for the project's performance measures. | November 2005 | December 2005 |
| Self-certification | Implementation of a voluntary facility self-certification approach. Self-certification refers to the submission of a legally binding record of a facility’s compliance and beyond-compliance practices. | November 2005 | January 2005 |
| Analysis of self-certification results | Analysis of self-certification data, with primary purpose of identifying opportunities for selective follow-up (next step). | February 2005 | March 2005 |
| Beyond compliance contracts | Initiate contracts to facilities that are high performers interested in beyond compliance education, through soliciting volunteers at ERP workshops and certification reviews | March 2006 | September 2006 |
| Selective follow-up | Selective follow-up with self-certifying facilities, based upon analysis of self-certification data. Selective follow-up may include phone calls, audits and enforcement. Selective follow-up is not typically based upon a random sample. | March 2005 | May 2006 |
| Post-certification audits | Follow up random post-certification audits | March 2005 | June 2006 |
| Data analysis | Tabulate scores for EBPIs and total compliance per facility (aggregate EBPIs), industry (aggregate EBPIs) | July 2006 | August2006 |
| Data analysis | Tabulate accuracy analysis scores for self certification vs. audits | July 2006 | August 2006 |
| STEP-UP sign up | Auto body & repair facilities begin the sign up process with the STEP-UP Program | September 2006 | October 2006 |
| Track RCRA policy issues | Track streamlines on HW RCRA policy issues developed and assist the department in carrying the policies forward | August 2004 | October 2006 |
| Case study | Develop and complete case study of ERP project (final report) | August 2006 | October 2006 |
| Reporting to EPA | Reporting shall include quarterly, annual and final reports. | October 2004 | October 2006 |

### Geographic focus

The focus of the project will be the Southern Maine air quality non-attainment areas in York, Cumberland and Sagadahoc counties.  This includes the cites/towns of: Alfred, Arundel, Berwick, Biddeford, Buxton, Eliot, Hollis, Kennebunk, Kennebunkport, Kittery, North Berwick, Old Orchard Beach, Saco, Sanford, York, Brunswick, Cape Elizabeth, Casco, Cumberland, Falmouth, Freeport, Gorham, Gray, New Gloucester, North Yarmouth, Portland, Scarborough, South Portland, Standish, Westbrook, Windham, Yarmouth, Bath, Bowdoinham, Richmond, Topsham, West Bath, and Woolwich.

### Resource and time constraints

The budget for the ERP project is $152,000 federal funding and $47,000 state funding.  This will be a two year project that will run October 2004 to October 2006.

## A7.	Quality Objectives and Criteria

### Detailed performance measures

This project is primarily interested in the following list of likely performance measures.  Note that one of the tasks of this project involves revisiting and reaffirming/revising these draft performance measures.

Regulatory Indicators:

- Does any airborne dust from sanding leave the business premises? (i.e. open windows, open doors, unfiltered exhaust vents)

- Does the shop carry out coating processes in a spray booth to contain paint emissions and over spray?

- Does painting and/or painting take place in areas outside of a spray booth?

- Do any airborne emissions from painting/coating leave the business premises? (i.e. open windows, open doors, unfiltered exhaust vents)

- Are solvents, contaminated rags or other VOC- and HAP-containing materials stored in closed containers when not in use?

- Does the shop generate any of the following wastes?  [Check all that apply.  For checked items, indicate how you dispose of the wastes.]

Waste: gasoline, brake fluid, lead acid batteries, paint, paint thinner, oil, parts cleaning solvents, batteries, fluorescent lamps, mercury switches, cathode ray tubes

- What is the greatest monthly amount of hazardous waste generated by the facility in the last 12 months?

- Does the shop properly label containers of hazardous waste (including waste paint, waste paint thinner and waste parts cleaning solvents)?  [Labels must indicate the contents of the container, must say "hazardous waste," must list the date of each deposit into the container and the date the container becomes full.]

- Does the shop containerize the wastes (like rags and other absorbent material) generated from cleanups of spills and dispose of it as hazardous waste?

- Have you ever filled out or signed a hazardous waste manifest?

- Does the shop ever add hazardous wastes such as waste gasoline, solvents or paint thinners into the waste oil?

- Have inactive floor drains been properly sealed/closed?

- Does the shop have any active floor drains?

- Does the shop conduct vehicle maintenance and repair in areas (bays) with unsealed floor drains?

- Are active and inactive floor drains registered with the MEDEP?

- Does the shop discharge wastewater (other than sanitary wastewater) to bathroom/kitchen sinks, toilets, showers, shop wash basins, emergency showers, eyewash stations, or other non-industrial wastewater outlets?

- If shops washes vehicles outside, where does the wash water discharge to? (ditch, stream, wetland, vegetated buffer, storm drain, other) [Check all that apply.]

Beyond Compliance Indicators:

- Does the shop train all employees in the proper use and handling of paints and coatings according to the manufacturers’ recommendations to minimize air emissions?

- Does the shop utilize enclosed spray gun cleaning, VOC recycling systems or other spray gun cleaning methods to reduce or eliminate VOC emissions?

- Does the shop employ a training program in the proper use and handling of solvents and waste products to minimize air emissions?

- Does the shop burn waste oil in a waste oil furnace?

### Quality objectives

Quality objectives for these performance measures will be developed as part of the Measures Identification and Statistical Methodology tasks.

This determination will take into account both the best practices for similar projects and the resources available for this project.  In part, the ERP Management Support will rely upon EPA's Generic Guide to Statistical Aspects of Developing an Environmental Results Program (2003) for advice in making decisions related to the optimizing the following aspects of data quality for this project:

- Precision

- Bias

- Representativeness

- Completeness

- Comparability

- Sensitivity (if applicable)

## A8.	Special Training/Certification

The Maine DEP will develop and deliver mandatory and voluntary training sessions to key parties to ensure quality data collection, to the extent practicable.

Mandatory intensive in-person training sessions will be delivered to the following individuals to ensure quality data collection:

- inspectors who will be collecting baseline and post-certification data

- data-entry personnel who will be processing data from audits and self-certification responses

- QA/QC personnel (if any additional training is needed to familiarize them with the project)

- Individuals who will be compiling the database containing the universe of facilities

Each session will cover proper data collection and QA procedures.  Training will be augmented by debriefing personnel shortly after their tasks have begun, to correct and clarify appropriate practices.

Voluntary intensive in-person training sessions will be offered to the self-certifying facilities.  Facilities will also be provided with clear written instructions on how to prepare and submit data, and they will be able to call a phone number to ask anonymous questions if they wish.

The ERP Management Support is responsible for ensuring that all personnel involved with data generation (including state personnel, contractors, and partners) have the necessary QA training to successfully complete their tasks and functions.  The ERP Management Support will document attendance at all training sessions.  Attendance records for voluntary trainings may not include names, given privacy/confidentiality concerns.

The ERP Management Support is also responsible for ensuring the self-certification materials sent to facilities clearly document how facilities should properly prepare and submit their data.

## A9.	Documents and Records

### Report format/information

The format for all data reporting packages will be consistent with the requirements and procedures used for data validation and data assessment described in this QAPP.

### Document/record control

The recording media for the project will be both paper and electronic.  The project will implement proper document control procedures for both, consistent with Maine DEP's Quality Management Plan.  For instance, hand-recorded data records will be taken with indelible ink, and changes to such data records will be made by drawing a single line through the error with an initial by the responsible person.  The ERP Project Manager will have ultimate responsibility for any and all changes to records and documents. Similar controls will be put in place for electronic records.

The Maine DEP ERP Project Manager shall retain all updated versions of the QAPP and be responsible for distribution of the current version of the QAPP.  The Maine DEP ERP Project Manager and the Maine DEP ERP Management Support will approve annual updates.  ERP Management Support shall retain copies of all management reports, memoranda, and all correspondence between the Maine DEP and all project personnel identified in A4.

### Other records/documents

Other records and documents that will be produced in conjunction with this project include:

- Audit checklists and reports

- Self-certification forms

- Return-to-compliance forms

- Non-applicability forms

- Enforcement documentation

- Facility outreach materials, including workbook, fact sheets, brochures, etc.

- Amended QAPP

- Readiness reviews (see below)

- Data handling reports

- Quarterly and annual progress reports to EPA

- Project final report (to include discussion of QA issues encountered, and how they were resolved)

### Storage of project information

The electronic information will be saved to a network server that is backed up daily.  All paper copies will be filed in a secure file cabinet in the Office of Innovation and Assistance until 3 years after the grant close date.

### Backup of electronic files

The information will be collected and organized in a dedicated secure database, which will be backed up daily.

# B	DATA GENERATION AND ACQUISITION

## B1.	Sampling Process Design (Experimental Design)

A key task in this project will be to develop a sound statistical methodology for collecting and analyzing facility data, in order to draw inferences related to the selected performance measures.  The major quality objective will be to collect representative data that truly reflect the conditions of the universe of facilities that this ERP focuses upon. Facility data is of two types:  (1) audit data, which will be collected by trained Maine DEP inspectors from randomly sampled facilities, and (2) self-certification data, which will be collected from facilities through a mail survey process.

To meet the precision targets of the survey, the sample for each round of inspections will include between 50 and 75 shops.  A simple random sample of shops will be selected.  Each shop will be assigned a unique random number.  Research Randomizer (http://www.randomizer.org/form.htm) will then be used to select random numbers from 1 through 159 (the amount of shops in the target universe).  The numbers from Research Randomizer will be compared to the random numbers assigned to the shops, and those will be the shops that will be audited.

## B2.	Sampling Methods

As described above, the primary data collected and used by this ERP will come from a survey data collection process.  The Maine DEP will conduct simple random Pollution Prevention (P2) audits of facilities in the universe for both the baseline and post certification audits.

Based on budgetary and other constraints, the DEP will be able to collect data from 50 to 75 shops.  The margin of error in estimating the percent of the eligible shops that use a specific environmental business practice at the 95 percent confidence level depends on the number of eligible shops in the sample.  The following table gives the largest possible error for several different sample sizes assuming that all shops in the sample are eligible (that is, the practice being measured applies to all shops in the sample).

| Sample Size | Margin of Error at 95% level will be less than or equal to: |
| --- | --- |
| 50 | 11.2% |
| 59 | 10.0% |
| 75 | 8.2% |

DEP also wishes to compare results between the two rounds of inspections.  If 50 shops are inspected in each round, and the business practice in question is relevant for all 50 shops, there is at least an 80 percent probability of detecting a real difference of 27 percent (at a 95 percent confidence level).  If 75 shops are included in each sample, there is at least an 80 percent probability of detecting a real difference of 22 percent (at a 95 percent confidence level).  Smaller observed differences can also indicate a real genuine change, but with less than 80 percent probability (The probability of detecting a real difference is often referred to as "power."  In this case, the recommended power for the test is 80 percent).

Please note that, as a general rule, if the number of eligible facilities for a given question is smaller than the sample size, then the effective sample size is lowered.  Consequently, the margin of error and confidence interval for that question will be larger than if the question applied to all facilities.  The size of the difference between the two rounds of inspections that indicates a real difference also will be larger.  Also, as the observed proportion moves away from 50%, the margin of error or confidence interval associated with that proportion will get smaller.

### Preparation of data collection instruments

All data collection instruments will be subject to multiple rounds of review by relevant internal and external stakeholders to help assure the collection of high-quality and representative data.  Data collection instruments will be prepared in accordance with the guidance on data collection instruments provided in EPA's Generic Guide to Statistical Aspects of Developing an Environmental Results Program (2003). Specifically, preparation will follow the checklist for data collection instruments provided in an appendix of that guide.

## B3.	Sample Handling and Custody

Upon completion of paper checklists, inspectors will sign the checklists. Inspectors will enter data from paper checklists into the electronic database.  Facilities will mail signed forms into Maine DEP, where data-entry staff will input data into the electronic database.

Chain of custody is not relevant to this project.

### Data entry QA procedures

Procedures for entering hand-written data into the database will follow standard quality assurance procedures (e.g., 100% verification using independent double key entry), consistent with Maine DEP's Quality Management Plan.  Detailed quality assurance procedures for data entry and acceptance will be prepared during the development and implementation of a data management strategy.

## B4.	Analytical Methods

This project will follow well-recognized statistical analytical methods for survey samples.   No physical tests or chemical analyses are anticipated for this project.

## B5.	Quality Control

This project will undertake the following specific steps to measure/estimate the effect of data errors, consistent with Maine DEP's Quality Management Plan.

### Crosschecking data

Completed questionnaires will be subjected to 100 percent editing review in preparation for data entry.  Every response field will be examined to check skip patterns, clarify handwriting, and identify any potential problems.  Each form will be entered with 100 percent verification; in other words, using independent double-key entry.  Primary data collection forms will be designed in such a way to allow internal crosschecking of data by comparing answers of different questions to each other, and such crosschecking will be automatic for electronically entered data. Further, post-certification audits will offer the opportunity to compare audit results with self-certification results, if the facilities sampled have submitted self-certification forms.

### Data anomalies

Procedures for handling data anomalies (such as outliers and missing data) will be handled based on guidance prepared in the project-specific statistical methodology.

### Quality control statistics

After the data are entered, several automated checks can be conducted.  Questions that required continuous variables should be checked to ensure that the answers are within acceptable ranges.  Consistency among answers also can be checked; e.g., if an affirmative response to one question precludes an affirmative response to another question, the automated checks can confirm the answers are consistent.

The quality control statistics to be used in this project are described in more detail in section D3.

## B6.	Instrument/Equipment Testing, Inspection and Maintenance

This section is not relevant to this project.  The project will not involve such scientific instruments and equipment.

## B7.	Instrument/Equipment Calibration and Frequency

This section is not relevant to this project.  The project will not involve such scientific instruments and equipment.

## B8.	Inspection/Acceptance for Supplies and Consumables

This section is not relevant to this project.  The project will not involve such supplies and consumables.

## B9.	Non-Direct Measurements (I.e., Secondary Data)

This project will rely upon secondary data to identify the facilities in the target population.

| Table 3: Non-Direct Measurements (I.e., Secondary Data) |
| --- |
| Data Sources | Intended Use | Rationale for Use | Acceptance Criteria |
| Maine DEP database of facilities | Identifying the target population, for the sample | Commonly accepted source of facility list | All records will be accepted unless sample response indicates facility should not be part of target population. Maine DEP will crosscheck any facility that self-identifies as non-applicable to this project. |

### Key resources/support facilities needed

Maine DEP will require access to the data sources mentioned above, and this information will be managed within the database created/utilized for the overall project.  Maine DEP does not anticipate any obstacles to this approach.

### Determining limits to validity and operating conditions

Database containing the list of targeted facilities will be designed such that the original source for all facility data is marked, and procedures will be in place such that only the ERP Project Manager can officially remove a facility entry from the target population.  In such cases, facility entry will not be deleted from the database but will be marked as non-applicable, and corrective data will be provided in fields parallel to the original data.

## B10.	Data Management

As part of this project, Maine DEP and The Cadmus Group, Inc. will develop a data management strategy, and amend the QAPP based upon the strategy.  The ERP Management Support is responsible for ensuring that that strategy is developed and that the QAPP is amended to reflect that strategy. The strategy will be consistent with the existing Maine DEP's Quality Management Plan.  Once amended, this QAPP section on data management will provide information on the following issues:

- Data management scheme, from field to final use and storage

- Standard recordkeeping and tracking practices, and document control system (citing relevant agency documentation)

- Data handling equipment/procedures that will be used to process, compile, analyze, and transmit data reliably and accurately

- Individuals responsible for elements of the data management scheme

- Process for data archival and retrieval

# C	ASSESSMENT/OVERSIGHT

## C1.	Assessment and Response Actions

The ERP Project Manager will conduct a Readiness Review immediately prior to the five major data collection tasks:  identifying targeted facilities, baseline audits, self-certification, targeted follow-up and post-certification audits.  The ERP Project Manager will report findings to the ERP Management Support, who will take corrective action (if any is necessary) before the data collection task begins.  Further, the ERP Management Support and ERP Project Manager will thoroughly debrief project implementation staff a short time after beginning their respective implementation tasks, to identify emerging/unanticipated problems and take corrective action, if necessary.

## C2.	Reports to Management

Three kinds of reports will be prepared: readiness reviews (described above), regular quarterly and annual progress reports, and project final report.  Progress reports will note the status of project activities and identify whether any QA problems were encountered (and, if so, how they were handled).  Project final report will analyze and interpret data, present observations, draw conclusions, identify data gaps, and describe any limitations in the way the data should be used.

Project QA Status Reports

| Type of Report | Frequency | Preparer | Recipients |
| --- | --- | --- | --- |
| Amended QAPP | Once, before primary data collection begins | Maine DEP ERP Project Manager | All recipients of original QAPP |
| Readiness Review | Before each major data collection task | Maine DEP ERP Project Manager | Maine DEP ERP Management Support |
| Progress Report | Quarterly | Maine DEP ERP Project Manager | U.S. EPA Project Officer (Copying US EPA OPEI) |
| Progress Report | Annually | Maine DEP ERP Project Manager | U.S. EPA Project Officer (Copying US EPA OPEI), stakeholders |
| Final Project Report | Once | Maine DEP ERP Project Manager | U.S. EPA Project Officer (Copying US EPA OPEI), stakeholders |

# D	DATA REVIEW AND EVALUATION

## D1.	Data Review, Verification and Validation

This QAPP shall govern the operation of the project at all times.  Each responsible party listed in Section A4 shall adhere to the procedural requirements of the QAPP and ensure that subordinate personnel do likewise.

This QAPP shall be reviewed at least annually to ensure that the project will achieve all intended purposes.  All the responsible persons listed in Section A4 shall participate in the review of the QAPP.  The ERP Management Support and ERP Project Manager are responsible for determining that data are of adequate quality to support this project.  The project will be modified as directed by the ERP Management Support.  The ERP Management Support shall be responsible for the implementation of changes to the project and shall document the effective date of all changes made.

It is expected that from time to time ongoing and perhaps unexpected changes will need to be made to the project.  The ERP Management Support shall authorize all changes or deviations in the operation of the project.  Any significant changes will be noted in the next report to EPA, and shall be considered an amendment to the QAPP.  All verification and validation methods will be noted in the analysis provided in the final project report.

## D2.	Verification and Validation Methods

To confirm that QA/QC steps have been handled in accordance with the QAPP, a readiness review will be conducted before key data collection/analysis steps, and data handling reports will be prepared after each step.  These reviews and reports will be consistent with Maine DEP's Quality Management Plan.  Standard statistical tests (described below in Section D3) will be used to determine the extent to which inferences can be drawn from the sample data.

## D3.	Evaluating Data in Terms of User Needs

This section was developed consistent DEP's Quality Management Plan and EPA's Generic Guide to Statistical Aspects of Developing an Environmental Results Program (2003).

Analysis of the Sample Data

The P2 audit checklist requires three types of responses.

1.  Dichotomous or yes/no responses.  The inspector indicates whether the shop uses the practice in question or not.  For example, the questionnaire asks under the air section “Does the shop carry out coating processes in a spray booth to contain paint emissions and over-spray?”

The majority of questions on the P2 audit checklist are yes/no questions.  These data can be used to estimate the proportion of facilities that use a particular practice in a single round of inspections or differences in proportions between the two rounds.

2.  Categorical response in which the inspector checks all that apply.  For example, the questionnaire asks “Does the shop use any painting and coating application techniques that minimize paint and coating use?  [Check all that apply.]”  The possible techniques include HVLP Spray Gun, Electrostatic Spray Gun, Laser Touch, and Other.

Each categorical response must be converted into a series of yes/no responses that represent all the possible ways the question can be answered.  If the inspector can check up to four responses, for example, there are 16 possible ways the question can be answered.  Continuing with the example of painting and coating techniques, the possible answers are:

1.	None

2.	HVLP Spray Gun Only

3.	Electrostatic Spray Gun Only

4.	Laser Touch Only

5.	Other Only

6.	HVLP Spray Gun and Electrostatic Spray Gun only

7.	HVLP Spray Gun and Laser Touch only

8.	HVLP Spray Gun and Other only

9.	Electrostatic Spray Gun and Laser Touch only

10.	Electrostatic Spray Gun and Other only

11.	Laser Touch and Other only

12.	HVLP Spray Gun, Electrostatic Spray Gun, and Laser Touch only

13.	HVLP Spray Gun, Laser Touch, and Other only

14.	HVLP Spray Gun, Electrostatic Spray Gun and Other only

15.	Electrostatic Spray Gun, Laser Touch, and Other only

16.	HVLP Spray Gun, Electrostatic Spray Gun, Laser Touch, and Other

Each of these 16 combinations becomes a yes/no variable (i.e., the facility either uses the combination or does not.)

Another approach for summarizing these categorical responses is to indicate the number of different practices used by each facility.  Continuing with the painting and coating example, the response to the question can be used to create other yes/no variables, such as:

1.	The facility uses none of the practices

2.	The facility uses exactly one of the practices

3.	The facility uses exactly two of the practices

4.	The facility uses exactly three of the practices

5.	The facility uses all four of the practices

6. 	The facility uses at least one of the practices

7. 	The facility uses two or more of the practices

8. 	The facility uses three or more of the practices

3.  Continuous variables.  For example, under general hazardous waste, the questionnaire asks “What is the greatest monthly amount of hazardous waste generated by the facility in the last 12 months?”

Using mean and standard deviation, the ResultsAnalyzer.XLS spreadsheet will calculate the 95 percent confidence interval for the mean for continuous data from a single sample.  It also will conduct hypotheses tests for differences in means between samples.

Proportions will be used to characterize the responses to the first two types of questions.  Means will be used to characterize the third type of data.  Associated 95 percent confidence intervals can be estimated for each.  The Cadmus Group, Inc. has provided Maine DEP with an Excel spreadsheet (ResultsAnalyzer.XLS) that will calculate the estimated proportion and 95 percent confidence intervals for the first two types of data.  Given a mean and standard deviation, it will calculate the 95 percent confidence interval for means as well.

### Mathematical and statistical formulae

Confidence Intervals for a Proportion from a Single Sample

The score interval for a proportion is given by:

(3)

Where:

p is the proportion of eligible facilities in the sample that use a specific practice.

Z is the standard normal deviate corresponding to the allowable probability that the confidence interval will not include the true proportion.

n is the number of eligible facilities in the sample to which the practice applies.

N is the number of facilities in the region of the state.

Confidence Intervals for a Mean

The confidence interval for a sample mean is given by:

(4)

Where:

is the sample mean among eligible facilities that use a specific practice.

t is the value of the t-distribution with n-1 degrees of freedom corresponding to the allowable probability that the confidence interval will not include the true proportion.

s is the standard deviation from the sample.

Hypothesis test for comparison of proportions from two samples

The test statistic is equal to:

(5)

Where:

is the difference in proportions between the two samples, p1-p2.

n1 is the size of the first sample.

n2 is the size of the second sample.

p is the average proportion of the two samples that use the practice in question,
(n1p1 + n2p2)/(n1 + n2).

The null hypothesis is that the proportions of eligible facilities in the population that use the practice in the two time periods are essentially the same.  The alternative hypothesis is that the proportion is greater in the second time period than in the first (i.e., it is a one-sided test).  The critical value is the value of a standard normal distribution corresponding to the allowable probability that the null hypothesis is rejected when it is true.

Hypothesis test for comparison of means from two samples

The test statistic is equal to:

(6)

Where:

is the difference in means between the two samples, p1-p2.

s1 is the standard deviation from the first sample.

s2 is the standard deviation from the second sample.

The null hypothesis is that the means in the two time periods are essentially the same.  The alternative hypothesis is that the mean is greater in the second time period than in the first (i.e., it is a one-sided test).  The critical value is the value of a t-distribution corresponding to the allowable probability that the null hypothesis is rejected when it is true.

Continuous Variables

The sample mean is the total quantity divided by the number of eligible facilities:

(1)

Where is the sample mean for the continuous variable x, xi is the observed quantity of x for shop i, and n is the number of facilities for which the practice is relevant.  The standard deviation is a measure of the variability in the data and is given by:

(2)

Excel or a statistics package may be used for these calculations.  The Excel function average() computes the average value of the range of cells listed in the parentheses.  The Excel function stdev() will calculate the standard deviation of the range of cells listed in the parentheses.

Sample Size Calculations

The formula for the sample size required to estimate a proportion with specified precision target for a single sample from an infinite population is:

(7)

Where:

p is the proportion.

is the half-width of the confidence interval.

Z is the standard normal deviate corresponding to the allowable probability that the confidence interval will not include the true proportion.

Corrected for a finite population, the required sample size is given by:

(8)

N is the size of the population.  The formula for the sample size required to test for a difference in proportions between two samples is:

(9)

Where:

Z1-α is the standard normal deviate corresponding to the allowable probability that the null hypothesis of the test will be rejected when it is true.

Z1-β is the standard normal deviate corresponding to the allowable probability that the null hypothesis of the test will be accepted when it is false.

r is the ratio of the size of the second sample to the size of the first sample.

is the minimum detectable difference between the proportions in the two samples.

Equation 8 assumes the underlying data are continuous.  To account for the fact that the data are not continuous, apply the following continuity adjustment:

(10)

### Approach to managing unusable data

Maine DEP's data collection approach is expected to minimize the incidence of unusable data with regard to facility audits.  The facility audits will be conducted by a trained Maine DEP professional knowledgeable about the intent of the questions.  This should minimize item non-response, a primary potential source of unusable data.  In the event that facilities do not have information on hand during the audit visit, DEP will follow-up with the facility at a later date to collect information.  Unusable data due to illegibility will also be minimized because the DEP auditor will be involved in inputting the audit data into an electronic format.  In some instances, unusable data may occur if a facility refuses to provide information to help answer a question.

In the event of unusable data for a particular facility on a particular question, the record will be flagged to indicate non-response (and differentiated from records for which a particular question was not relevant).  Further, the reason for non-response will be noted for later analysis if necessary.  Finally, the record will be dropped from the analysis of that question: i.e., the sample size for that question will be reduced.  Doing so will make it more difficult to hit precision targets for a particular question.

In the event that the amount of unusable data for a particular question is larger than 5%, DEP will report the percentage, along with conclusions regarding whether the incidence of unusable data creates a biased data set and therefore reduces data representativeness.   For example, the data could be considered biased if unusable data were substantially more likely to come from noncompliant facilities than from compliant facilities.

# Footnotes

Includes data from self-certification forms, return-to-compliance forms, and non-applicability forms.

# Text boxes

Contractor

Ron Dyer

ERP Management Support

Bureau of Remediation and Waste Management Representatives

Bureau of Land & Water Representatives

Bureau of Air Quality Representatives

Sara Lippert

ERP Project Manager

Julie Churchill

ERP Management Support