PROPOSED

## SSG-WI 2015 Case Preparation Process and Schedule

A.  2015 Cases to be created by SSG-WI

The following 2015 cases will be created by SSG-WI

- “Do Nothing” case

  - Loads - will be extrapolated to 2015 levels

  - No resources or transmission addition beyond 2008 case

  - Determine L&R by area, production costs by area, and congestion and congestion costs by area and location

- “Planned Resource Scenario” case

- Resource additions (2008 to 2015) – Add resources identified in utility IRPs, NWPCC 5th Power Plan and other formal resource plans.  Add renewables as necessary to meet RPSs.

- Perform L&R, set a target planning margin, and fill gaps with thermal units/RPS as needed

- Loads – same as “Do Nothing” case

- Transmission – Add transmission to integrate IRP resources and other transmission outlined in IRPs

- Run case, determine congestion and congestion costs by area/location

f.    Iterate to determine optimal regional transmission for the West that relieves congestion and integrates the resources in the “Planned Resource Scenario” case.

- Determine capital investment for incremental resources and transmission

- Determine annual fixed costs (real levelized)

- Run load, gas price and hydro sensitivities

- This case will be made available to others as a starting point for developing other resource and transmission scenarios

# B.   Process to develop SSG-WI 2015 Cases

1.   “Do Nothing” case – Load Forecasting Subgroup will develop 2015 load forecast.  Modeling Team will then run the “Do Nothing” case..

2.   “Planned Resource Scenario” case –

- Develop “strawman” matrix with required detail, for proposed resource additions (2009 to 2015). Generation SubGroup (GSG) will establish target planning margin for each area, and resolve discrepancies in the interpretation/application of RPS.  Those identified below should complete the matrix and submit to the GSG for review, reconciliation, and iteration. Only after all detail is obtained to fill the straw matrix will the matrix be provided to Modeling Team.

    - CEC, CAISO, and CA IOUs: CA resource additions

    - WIEB/LBL – IRP data from LBL for Avista, PSE, PGE, NWE, Sierra/NP, Xcel  (Note:  WIEB/LBL currently do not have the detail required to populate the matrix.  Coordination with the utilities and SPGs will be required)

    - WIEB – PNM filing with PRC

    - BPA/NWPCC – NW Publics & NWPCC 5th Power Plan. (Note:  BPA/Council currently do not have the detail required to populate the matrix.  Coordination with utilities and NTAC will be required)

    - PAC – PAC IRP

    - NREL/Modeling Team – Add renewables to meet RPS standards

b   GSG determines L&R by area.  SPG’s and State/Province’s review “strawman” matrix, make revisions and complete the details missing in the matrix and submit comments to GSG.  Submit to Modeling Team when details are complete.

- Modeling Team enters into model, and GSG, Modeling Team and Transmission SG iterate to determine transmission requirements for resources

- Prepare scenario material for review by SPGs and States/Provinces – Modeling Team

f.   Refer discrepancies to TSG for resolution

g..   If responses not received on time, go with “strawman”

C.   SCHEDULE

| Due Date | Activity | Lead |
| --- | --- | --- |
| July 19 | Convey proposed methodology to the TSG and PWG and ask for comment by July 26. Set up Conference Call with all involved individuals. | Dean Perry |
| July 29 | NM PRC/WIEB, CEC, BPA, etc. submit data to GSG. (See 2a above) NREL delivers to GSG renewable additions to meet RPSs. | See 2a above for names |
| August 12 | GSG performs L&R analysis, assembles “strawman” "Planned Resource" scenario including known modeling details and documentation and sends to SWAT, NTAC, RMATS, STEP WIEB and GSG. WIEB sends scenario data to states/provinces. (see 2a above) | Mary Johannis (GSG) |
| August 26 | SPGs and States review “Planned Resource” scenario. Complete all details needed for modeling. Comments and suggested changes sent to GSG. ALL MISSING RESOURCE DETAIL in the matrix should be completed as part of the submittal. (see 2b above) | Chris Reese, Rob Kondziolka, Ray Brush, STEP rep, WIEB (states/provinces) |
| September 9 | GSG reviews data submittals, assures all modeling details are included, resolves issues and forwards to Modeling Team (see 2b above) | Mary Johannis (GSG) |
| September 16 | Modeling Team enters data into model and runs initial congestion studies and presents results to Transmission Subgroup and GSGs. (see 2c above) | Mike DeWolf (ModelingTeam) |
| September 16 | Transmission Subgroup identifies transmission requirements to address congestion. Iterative process with Modeling Team and GSG. (Transmission Subgroup Meeting) | Trans Subgroup Chair |
| September 28 | Modeling Team reruns studies to optimize regional transmission to relieve congestion, determines costs, runs sensitivities and presents results to TSG. TSG Meeting to approve “Planned Resource” scenario. | Mike DeWolf (Modeling Team) |

# Comments

For  this “do nothing” case, we see no need to add resources to bring each area into L/R balance.  The model will identify areas if generation cannot meet load or (more likely) where production costs go up because of transmission constraints