Quarterly Report

Date of Report: August 1, 2006

Contract Number:  DTPH56-06-T-0004

Prepared for: DOT

Project Title: Plastic Pipe failure, Risk, and Threat Analysis

Prepared by:  Gas Technology Institute

For quarterly period ending:  June 30, 2006

SCH Date	   CMPL Date

Task # 1:  Project Advisory Group 		 04/30/2006      07/19/2006  *MS

- Technical Status

The work in Task 1 was to Form a Project Advisory Group (PAG) for Participation and Guidance on the project. GTI has completed the establishment of the PAG; the PAG includes members of APGA, APGA RF, and NGA as well as members from three gas distribution companies.

The GTI team has also begun working on Task 2. Task 2 involves conducting a Literary Search to Identify Risks and Threats to Plastic Gas Pipes by Soliciting Information From Gas Distribution Companies and Others. GTI has been reviewing available publications including DOT OPS Distribution Incident Data, Pipeline Accident Briefs, AGA publications and conference proceedings, as well as plastic pipe service manuals and integrity management manuals.  Additionally, GTI conducted a review of GTI’s 30-year database on plastic pipe field failures, causes, and risks.

Task 3 involves conducting surveys and questionnaires of AGA, APGA, NGA, PPDC, etc. to Solicit Information on Plastic Gas Pipe Field Failure Analysis and to develop a Database.  GTI has begun developing a series of questions for the survey. A couple of example questions are shown in the table below.  GTI team has also started preparing travel plans and contacting gas distribution companies to visit a number of gas companies to discuss the survey and to solicit plastic pipe failure information.

| 16 | How many In-service plastic pipe field failures have occurred in the last: |  |
| --- | --- | --- |
|  | year? |  |
|  | 5 years? |  |
|  | 10 years? |  |
| 17b | Have you had any failures caused by: |  |
|  | Rock Impingement? |  |
|  | How many? |  |
|  | Pipe Size? |  |
|  | Pipe Material? |  |
|  | Time in Service (in years)? |  |
|  | Year of Installation? |  |

Task 4 is Address and Assess Threats Associated with Brittle-Like Failures over Time in Plastic Pipes and in Fusion Joints Susceptible to Premature SCG Failures. 	GTI began soliciting from gas companies, pipe test samples of a few older lots of plastic gas materials that may be susceptible to premature brittle-like cracking. GTI has already received a few pipe samples of these materials; several of these received pipe samples have been cut into test specimens and prepared for accelerated long-term stress-rupture laboratory tests.

- Business Status

GTI held a teleconference attended by more than eight gas distribution companies to present the project objectives, tasks and approach and to discuss qualitative and quantitative risk assessment (RA) techniques to be implemented in soliciting a database and for establishing a relative risk indicator. GTI has also held several discussions with a few gas distribution companies directed at soliciting plastic gas pipes that failed in field service for the purpose of conducting a root-cause failure analysis.

- Schedule

Task 1 was to be completed by the end of April. It was not completed until mid-July as we waited for confirmation from several organizations.

- Payable Milestones

The submission of this quarterly report is the first payable milestone.

Results and Conclusions:

The review of the GRI database showed that in the last 15 to 20 years, GTI/GRI conducted several surveys of the gas distribution industry to determine the types, causes and approximate frequency of PE pipe field failures other than those due to excavation damage. During this time period, GTI/GRI also held several meetings with gas industry advisors with a wide geographical representation to solicit qualitative information and input on plastic pipe field failures. These early surveys and meetings provided important information on the types and the frequency of many types of plastic pipe field failures. On the basis of GTI/GRI surveys and meetings, conducted through about 1998, it was found that:

- The largest number of plastic pipe failures occurred and initiated at defects in saddle- and socket-fusion joints and grew in a Slow Crack Growth  (SCG) mode resulting in a leak.

- The second highest group of plastic pipe failures were at socket- and butt-fusion joints; however, these were due primarily to poor workmanship that resulted in a cold bond, lack of bond penetration, or other similar factors.

- The third largest group of plastic pipe failures were due to squeeze-off, impinging rocks, or pipe bending; these initiated and grew in a SCG mode.

Issues, Problems or Challenges:

There is a possibility that the GTI team will experience some delays while soliciting information from gas companies. GTI travel will be scheduled around gas company availability. Since multiple trips are planned with time between trips being necessary for compiling a database, there exists the possibility of scheduling conflicts.

Plans for Future Activity:

GTI plans to host a “Kick-off” meeting with PAG members and also travel to gas companies to gather information on plastic pipe failures.  Over the next quarter, GTI will continue working on the survey and literature search and on conducting laboratory tests on older plastic gas pipe failures and materials susceptible to brittle failures.

Public Page:

The Plastic Pipe Failure, Risk, and Thread Analysis project is currently underway at Gas Technology Institute. The project seeks to identify failure risks and threats to plastic gas pipes, perform root-cause analysis to identify which types of defects lead to failure, and prioritize the risks and threats. GTI identified seven tasks needed to accomplish these objectives.

Task 1 called for the formation of a Project Advisory Group (PAG). This task has been completed and marks the first accomplished milestone. The PAG includes members of a few gas industry associations as well as members from gas distribution companies. These individuals will participate and provide guidance.

GTI has also worked on tasks 2, 3, and 4, which are all related to information gathering. Task 2 entails a literary search. GTI has collected a large number of publications and is currently reviewing them and compiling the information.  A 30-year GTI/GRI database was reviewed. The results of this review showed the largest number of plastic pipe failures resulted from saddle- and socket-fusion joints followed by socket- and butt-fusion joints. Squeeze-off, impinging rocks, and pipe bending also resulted in plastic pipe failures.

Task 3 work requires solicitation of plastic pipe failure information from gas associations and distribution companies. GTI has been developing a survey for this purpose as well as forming travel plans to visit various organizations to obtain data.

The work GTI has performed on Task 4 has been accomplished through the use of GTI’s plastic pipe analyses laboratory. GTI has accepted a few pipe samples that are now prepared for accelerated long-term stress-rupture laboratory tests.

The information gathered thus far will be compiled into a database which will later be used to formulate equations and indexing techniques to calculate relative failure risk for plastic pipe segments.

Dr. Michael Mamoun

mike.mamoun@gastechnology.org

847.768.0953