## Vision: Safe Homes, Strong Families, Supportive Communities…No Alaskan Left Out in the Cold

| PRIORITY ONE: PROMOTE LOCALLY DELIVERED FAMILY CENTERED SERVICES |
| --- |
| Strategy(-ies) | Action(s) | Manager¹ | Implementer² | Expected Outcomes | Benchmarks/ Milestones | Completion Date (Estimated) |
| Strategy 1.1 Increase service accessibility and affordability of strength based wrap-around services across Alaska “One form, one time, one person” | Action 1.1.1 Assess tools and commonality among elements of tools: intake; self sufficiency matrix; evaluation criteria; integrate data reports/systems | Homelessness Ends in Alaska Advisory Team (HEAAT) members | To be determined after we conduct initial assessment. | Results of our assessment of tools will determine what we can and can’t do with common tools. Review of tools from other states. | By mid-August, hold first meeting to discuss common elements and determine next steps. By mid-October determine common elements. Meet with IT to investigate strategy for common tools. Technical assistance on Self Sufficiency Matrix tool from Charlene Moran Flaherty (AZ) obtained. | Mid October 2005 meeting December, 2005 as initial completion date. |
|  | Action 1.1.2 Share integration project results and lessons learned from the Mat-Su Fairbanks TANF project; Family to Family program; Family Promise of Mat Su and Kenai program; 477 Natives program; Neighborhood Housing in Mountain View; RuralCAP; Homeward / Community Bound; and other programs | Kitty Farnham Bill Hogan | Kitty Farnham Bill Hogan | Identify promising practices for potential replication | Review preliminary findings at September meeting | December 2005 |
|  | Action 1.1.3 Promote Asset Building (IDA), expand the Your Earnings Saved (YES) program, and leverage TANF Diversion funds to promote housing retention. | Jim Gurke Kitty Farnham | HEATT members | Include Council on Domestic Violence in discussions of initial TANF pilot. Tap into the Interfaith Hospitality Network, Alaska Mental Health Trust, school boards, and DEED homeless coordinators as contacts for cross training. | Identify existing training opportunities. Define cross training opportunities. Initial meeting in June 2005 to define YES expansion options and costs. | December 31, 2005 |
|  | Action 1.1.4 Assess the opportunities and gaps in health care access for homeless individuals, including behavioral health, primary care, and dental care. | Pat Carr | Pat Carr Bill Hogan Jerry Fuller | Identified needs and opportunities | At October 1, 2005 meeting review summary of opportunities and gaps for health care coverage through the community health centers. | October 1, 2005 |
|  | Action 1.1.5 Develop a plan of action for strengthening efforts to increase access to health care for homeless individuals | Pat Carr Jerry Fuller | HEATT members | Improved health care access for homeless individuals. | Draft action plan by February 1, 2006 | By March, 2006 HEATT meeting |
| Strategy 1.2 Transition planning for people leaving institutions (Key Themes: “Address where the cliffs occur”. “ Release no one to Homelessness”) | Action 1.2.1 Research best practices and tools for future action for transition planning for interim housing and release from Corrections, including childcare and resources for parents. | Jim Gurke | Jim Gurke | Findings reported by our September 2005 HEATT meeting, | Technical assistance on the Massachusetts program obtained. | December, 2005 |
| Strategy 1.3 Housing retention strategies | Action 1.3.1 Evaluate “Unit abandonment” causes | Jim Gurke | Jim Gurke | Interim report at Report at September 2005 meeting. Analyze significance and determine whether to do exit interviews in the future. | Final report with summary of data on unit abandonment including cross reference to other systems where people may be receiving services. | September, 2005 |
|  | Action 1.3.2 Develop an inventory of resources to promote housing retention | Sondra Meredith (re school liaison) Bill Hogan | Sondra Meredith Bill Hogan | Reports at September meeting. | DEED will assess knowledge of school liaisons’ knowledge of services to increase housing retention. List of DBH grantees and providers will be made available. | Final report by December, 2005 |
|  | Action 1.3.3 Expand and standardize tenant training and education through: Cooperative Extension Service; Beyond Shelter; St. Vincent DePaul; school districts | Kris Duncan Sondra Meredith HEATT members | Kris Duncan Sondra Meredith HEATT members | Report of various education programs provided by Kris at HEATT’s. Recommend best practices for strengthening tenant housing skills. Apply for HUD ROSS grant. | Assess various tenant education programs. Sondra will forward information on life skills curriculum focused on tenant/housing skills. Explore developing and disseminating a standardized tenant education program. | December, 2005 |
| Progress to Date | Barriers and/or Situational Changes | Immediate Next Steps (including potential technical assistance needs) |
| HEATT meeting held on 6/6/05 to refine action steps. | Travel and vacation schedule create difficulty with meeting planning. | Set up standing monthly meetings. Technical assistance on Self Sufficiency Matrix tool from Charlene Moran Flaherty (AZ) obtained. |

¹  The Manager is the individual responsible for coordinating each action.

²   The Implementer is the individual (or entity) responsible for carrying out each action.

| PRIORITY TWO: INCREASE COLLABORATION AND COODINATION WITH PARTNERS TO END HOMELESSNESS |
| --- |
| Strategy(-ies) | Action(s) | Manager | Implementer | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 2.1 Promote Ownership of the Plan | Action 2.1.1 Identify and inventory existing partners, stakeholders, linkages. | Kris Duncan | Kris Duncan | Draft list of inventory | By September 2005 develop a list of stakeholder groups. Assess investment of funding. Review Continuum of Care inventory in federal application | By September HEATT meeting. |
|  | Action 2.1.2 Engage and leverage business, employer and foundation partners, e.g. Fannie Mae, Freddie Mac, Rasmuson Foundation | Kris Duncan | Kris Duncan | Invite new partners to work with the HEATT members. | By October 2005 | Ongoing |
|  | Action 2.1.3 Promote regional partnership development | Bill Hogan, Kitty Farnham | Bill Hogan Kitty Farnham | Identify DHSS regions relevant to homelessness plan. By September 2005 develop a list of stakeholder groups. | At the September HEATT meeting, create a list of regional stakeholders to invite to participate. | September, 2005 |
|  | Action 2.1.4 Develop marketing strategies | HEATT members | HEATT members | Hold an in-state Policy Academy to assess and plan for data / tool solutions based on information from Georgia. | TA from Georgia and the Policy Academy. | July, 2006 |
| Strategy 2.2 Maintain focus on state and federal policies impacting services in Alaska | Action 2.2.1 Conduct further analysis of Harvard Study impacts on Alaska and respond by June 13, 2005. | Jim Gurke | Jim Gurke with input from Indian Housing Authorities | Alaska would receive an exemption or waiver | Further analysis and comment on the Harvard Study impact to Alaska provided before June 13, 2005. | June 13, 2005 |
|  | Action 2.2.2 Identify policy issues (boulders and barriers) that work against service integration to end homelessness. | HEATT members | HEATT members | Create policy “SWAT” team to work on barriers. HUD will use relevant Alaska data on Per Unit Month | Dialogue with Congressional Delegation Dialogue with Federal agencies and staff | January, 2006 November , 2005. Ongoing. |
| Progress to Date | Barriers and/or Situational Changes | Immediate Next Steps (including potential technical assistance needs) |
| Action 2.2.1 completed: Jim Gurke contacted various representatives and provided comments on Harvard study to assess applicability to Alaska. HEAAT meeting held June 6, 2005. |  | Request TA from Georgia team and Policy Academy |

| PRIORITY THREE: INCREASE SAFE AND AFFORDABLE HOUSING STOCK |
| --- |
| Strategy(-ies) | Action(s) | Manager | Implementer | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 3.1 Promote local incentives for development of affordable housing | Action 3.1.1 Partner with Native organizations | Kris Duncan Bill Hogan | HEATT members | Additional housing in Anchorage; e.g. Linkage with Cook Inlet Housing Authority to sponsor 20 Oxford Homes. | List of partner organizations Obtain information and technical assistance from Hawaii regarding strategies to engage business and builder stakeholders. | October, 2005 October, 2005. |
|  | Action 3.1.2 Compile and assess community housing inventory | Denny DeWitt Kris Duncan | Denny DeWitt Kris Duncan | Inventory list of community housing completed | Secure information from DCED and Alaska Municipal League on local land acquisition strategies. | November 2005 |
|  | Action 3.1.3 Identify potential local land acquisition opportunities | HEATT members | HEATT members | Promote local land acquisition for use for affordable housing. | Completed inventory of local land acquisition opportunities | December, 2005 |
| Strategy 3.2 Promote the creation of a housing trust fund | Action 3.2.1 Endorse and implement Interagency Council on Homelessness proposal | Kris Duncan Karleen Jackson | Interagency Council on Homelessness | Integration of plans | Draft plan forwarded to Governor’s Interagency Council on Homelessness by May 5, 2005. | Ongoing |
|  | Action 3.2.2 Advise the managers of the Trust on strategies to end homelessness | Jeff Jessee Dr. Doolittle | Jeff Jessee Dr. Doolittle | Integration of plans | HEATT plan forwarded to Trust by June, 2006 | Ongoing |
| Progress to Date | Barriers and/or Situational Changes | Immediate Next Steps (including potential technical assistance needs) |
| HEATT plans forwarded to Interagency Council on Homelessness and Alaska Mental Health Trust Authority |  | Obtain technical assistance from Hawaii regarding strategies to engage business and builder stakeholders. |

| PRIORITY FOUR: INTEGRATE HOMELESS PLANNING EFFORTS ACROSS ALASKA |
| --- |
| Strategy(-ies) | Action(s) | Manager | Implementer | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 4.1 Develop recommendations to Governor’s Interagency Council on Homelessness | Action 4.1.1 Incorporate Interagency Council on Homelessness and HEAAT recommendations into related plans. | Pat Carr | HEATT members | Integration of planning efforts | Presentation of draft plans. | Ongoing |
|  | Action 4.1.2 Incorporate final Interagency Council on Homelessness plan into Policy Academy plan | Pat Carr | HEATT members | Integration of planning efforts | Presentation of draft plans. | Ongoing |
|  | Action 4.1.3 Identify related planning efforts & liaisons to HEAAT | Pat Carr | HEATT members | Integration of planning efforts | Presentation of draft plans. | Ongoing |
|  | Action 4.1.4 Incorporate HEAAT recommendations into related plans | Pat Carr | HEATT members | Integration of planning efforts | Presentation of draft plans. | Ongoing |
| Progress to Date | Barriers and/or Situational Changes | Immediate Next Steps (including potential technical assistance needs) |
| Provided comments on Interagency Council draft plan in May, 2005. | Planning is an ongoing process. |  |