## Project Descriptions
FY 2008 FLEET PROJECT DESCRIPTIONS
2006-10-02
|  | Ship Time | Line | New | PPBES Program | Project
VESSELS & Timeline | Project(s) |  | Office | Strategic Goal | Manager | Description
RAINIER
October to December | 1. Coastal Survey (Washington Coast or Kenai Peninsula) | 57 | NOS | Commerce & Transportation | Rich Edwing/MTS | 1. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
April to June | 2. Coastal Survey (Keku & Chatam Straights) | 59 | NOS | Commerce & Transportation | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
June to September | 3. Coastal Survey (Alaska Peninsula & Kodiak) | 71 | NOS | Commerce & Transportation | Rich Edwing/MTS | 2. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
September | 4. Benthic Habitat Characterization - MBNMS | 20 | NOS | Ecosystems | Doug Brown/CMRP | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
| Total Project DAS | 207 |  |  |  | 3. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
| Total OD | 230 |  |  |  | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
4. Continued Seafloor Mapping effort and to Study the Impact of Bottom Trawling. Contact: CS = Bill
Douros, N/ORM6x22, (831) 647-4201
FAIRWEATHER
October to November | 1. Coastal Survey (Prince William Sound) | 33 | NOS | Commerce & Transportation | Rich Edwing/MTS | 1. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
March to April, September | 2. Coastal Survey (SE Alaska) | 67 | NOS | Commerce & Transportation | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
April to July | 3. Coastal Survey (SW Alaska) | 87 | NOS | Commerce & Transportation | Rich Edwing/MTS | 2. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
July & August | 4. Habitat Research | 20 | NMFS/NOS | Ecosystems/C&T | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
| Total Project DAS | 207 |  |  |  | 3. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
| Total OD | 230 |  |  |  | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
4. Fish Sonar Test and Characterize and Map Benthic Fish Habitat. Contact: LCDR Doug Baird or
Bob McConnaughey, F/AKC2, (206) 526-4150
MILLER FREEMAN
October & April to May | 1. PaCOOS | 40 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Conduct Ocean Observing System Studies Along the U.S. West Coast. Contact: CS = Bill Peterson
January to February & March | 2. Winter Killer Whale Studies | 36 | NMFS | Ecosystems | Steve Murawski/EOP | F/NWC32, (541) 867-0201
February | 3. Pollock Survey/Calibration | 20 | NMFS | Ecosystems | Steve Murawski/EOP | 2. Conduct studies of Killer Whales Along the U.S. West Coast to Better Understand Their Distribution
February to March | 4. Pollock Survey/Calibration | 11 | NMFS | Ecosystems | Steve Murawski/EOP | and Habitats. Contact: CS = Brad Hanson, F/NWC, (206) 860-3220
April | 5. Fisheries-Oceanography (FOCI) | 14 | NMFS/OAR | Ecosystems | Steve Murawski/EOP | 3. Conduct Stock Assessment Survey Around the Shumagin/Sanak Is. Contact: CS = Chris Wilson,
May | 6. Fisheries-Oceanography (FOCI) | 12 | NMFS/OAR | Ecosystems | Steve Murawski/EOP | F/AKC1 (206) 526-6435
June to July | 7. Salmon Survival | 32 | NMFS | Ecosystems | Steve Murawski/EOP | 4. Conduct Stock Assessment Survey Around Shelikof Strait Contact: CS = Chris Wilson, F/AKC1,
July to September | 8. Pollock Survey/Calibration | 61 | NMFS | Ecosystems | Steve Murawski/EOP | (206) 526-6435
September | 9. Fisheries-Oceanography (FOCI) | 19 | NMFS/OAR | Ecosystems | Steve Murawski/EOP | 5. Mooring Operations, Collect CTD and ADCP Data. Contact: CS = Phyllis Stabeno, R/PMEL, (206)
| Total Project DAS | 245 |  |  |  | 526-6453
| Total OD | 270 |  |  |  | 6. Conduct Stock Assessment Survey in Western Gulf of Alaska and Shelikof Straits. Contact: CS =
Janet Duffy-Anderson
7. Conduct Survey of Salmon Stocks Along the U.S. West Coast. Contact: CS = Richard Brodeur
(541) 867-0109
8. Conduct Pollock Stock Assessment Survey in Eastern Bering Sea and Shelikof Straits. Contact:
Chris Wilson, F/AKC1, (206) 526-6435
6. Conduct Juvenile Flatfish in Eastern Bering Sea. Contact: CS = Janet Duffy-Anderson
OSCAR DYSON
Fall | 1. Acoustic Research | 14 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Survey-Related Research will be Conducted to Evaluate and Improve Current Methodologies Which are
February & March | 2. Pollock Survey | 25 | NMFS | Ecosystems | Steve Murawski/EOP | Used to Routinely Monitor Walleye Pollock and Other Semi-Pelagic Species. Contact: Chris Wilson,
Winter | 3. FIT/Pollock Research | 24 | NMFS | Ecosystems | Steve Murawski/EOP | F/AKC1, (206) 526-6435
April | 4. Ice Seal Ecology | 30 | NMFS | Ecosystems | Steve Murawski/EOP | 2. Acoustic-Trawl Survey to Determine the Distribution and Abundance of the Pre-Spawning
May to July | 5. Pollock Survey | 61 | NMFS | Ecosystems | Steve Murawski/EOP | Walleye Pollock in Bering Sea and Gulf of Alaska, as well as the Pelagic Component of Walleye
July to August | 6. Northern Pollock Survey | 32 | NMFS | Ecosystems | Steve Murawski/EOP | Pollock and Large Marine Mammals in the Eastern Bering Sea. Contact: CS = Chris Wilson, F/AKC1,
August to September | 7. Bering-Aleutian Salmon International survey (BASIS) | 44 | NMFS | Ecosystems | Steve Murawski/EOP | (206) 526-6435
| Total Project DAS | 230 |  |  |  | 3. Acoustic-trawl survey methods used to determine whether commercial pollock fishing causes localized
| Total OD | 250 |  |  |  | depletion and/or disruption of endangered Stellar sea lion prey fields. Contact: Elizabeth Longerwell (206) 526-4231
4. Evaluate the Distribution, Abundance and Ecology of Ice Seals with a Focus on Ribbon Seals in the
Bering Sea Marginal Ice Zone. Contact: CS = John L. Bengtson, F/AKC3 (206) 526-4015
5. Acoustic-Trawl Survey to Determine the Distribution and Abundance of the Pre-Spawning
Walleye Pollock in Bering Sea and Gulf of Alaska, as well as the Pelagic Component of Walleye
Pollock and Large Marine Mammals in the Eastern Bering Sea. Contact: CS = Chris Wilson, F/AKC1,
(206) 526-6435
6. Acoustic-Trawl Survey to Determine the Distribution and Abundance of the Pre-Spawning
Walleye Pollock in Bering Sea and Gulf of Alaska, as well as the Pelagic Component of Walleye
Pollock and Large Marine Mammals in the Eastern Bering Sea. Contact: CS = Chris Wilson, F/AKC1,
(206) 526-6435
7. International cooperative research on salmon ecology in the Bering Sea. Contact: CS = Ed Farley
F/AKC4 (907) 789-6085
KA'IMIMOANA
Oct to Dec & Feb to Sep | 1. Recover and Deploy Tropical-Atmosphere Ocean | 231 | NWS | Climate | Tom Karl/COA | 1. Recovery and Deployment of TAO/ATLAS Moorings. Contact: CS = Michael McPhaden
| (TAO) Array |  |  |  |  | PMEL (206) 526-6783
Spring or Summer | 2. Exchange Tsunami/DART Buoy @ 125W | 2 | NWS | Weather & Water | David Green/TSU | 2. Recover and Deploy DART Mooring at Station 46406. Contact: CS = Shannon McArthur (228) 688-
| Total Project DAS | 233 |  |  |  | 2830
| Total OD | 260
MCARTHUR II
October to December | 1. US Pacific West Coast Cetacean Assessment & PaCOOS | 60 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Estimate the Abundance of Whales, Dolphins and Porpoises in the Waters of the U.S. EEZ
March | 2. Ecosystem Assessment Surveys | 21 | NOS | Ecosystems | Doug Brown/CMRP | Contact: CS = Jay Barlow/SWFSC (858) 546-7178
April | 3. Larval Transport | 14 | NOS | Ecosystems | Doug Brown/CMRP | 2. Baseline Monitoring for Plankton, Fish Larvae, Birds, Mammals and Human Activites.
April | 4. South Slough National Estuarine Research Reserve | 12 | NOS | Ecosystems | Doug Brown/CMRP | Contact: CS = Jan Roletto (415) 561-6622
May | 5. NCCOS-OCNMS Deep Corals/Sponges | 15 | NOS | Ecosystems | Leon Cammen/ERP | 3. Describe Northern California Coastal Circulation. Contact: CS = Dan Howard, N/ORM6x24, (415)
May to June | 6. Marine Mammal, Seabird and Habitat Surveys | 25 | NOS | Ecosystems | Doug Brown/CMRP | 663-0314
June to September | 7. Large Whale Assessment | 70 | NMFS | Ecosystems | Steve Murawski/EOP | 4. Physical and Biotic Linkages Between the Nearshore Pacific Ocean and the Estuarine Waters off the
| Total Project DAS | 217 |  |  |  | Southern Oregon Coast. Contact: CS = Steve Rumrill/University of Oregon (541) 888-5558, ext. 302
| Total OD | 250 |  |  |  | 5. Joint Study of Critical Offshore Habitats (Occupied by Unique Coral/Sponge Assemblages) and
Their Susceptibility to Fishing/Harvest Impacts within OCNMS. Contact: CS = Jeff Hyland N/SCI4
(843) 762-8652
6. Sighting Surveys of Marine Mammals and Seabirds and Sonar Surveys for Habitat Mapping.
Contacts: CS = Ed Bowlby/OCNMS (360) 457-6622, ext. 17 & Carol Bernthal, N/ORM6x26, (360) 457-6622
ext. 11
7. In support of ESA status reviews, recovery plans, and down-listing-a line-transect and passive acoustic
survey to estimate the status of endangered fin whales in the North Pacific. Contact: TBD
HI'IALAKAI
October | 1. Main Hawiian Islands Coral Reef Ecosystem Mapping | 30 | NOS | Ecosystems | David Kennedy/COR | 1. Multibeam Data Collection and Optical Groundtruthing. Contact: CS = Russell Brainard - F/PIC (808)
January to April | 2. American Samoa Coral Reef Monitoring & Assess (RAMP) | 73 | NOS | Ecosystems | David Kennedy/COR | 592-7011
January | 3. American Samoa Outreach and Education | 5 | NOS | Ecosystems | Doug Brown/CMRP | 2. Benthic Habitat Mapping and Long-Term Biological and Oceanographic Monitoring of the Coral
April | 4. Exchange Tsunami/DART Buoy near Kona Coast | 2 | NWS | Weather & Water | David Green/TSU | Reef Ecosystems of American Samoa. Contact: CS = Russell Brainard-F/PIC (808) 592-7011
May | 5. MHI Education and Outreach | 5 | NOS | Ecosystems | Doug Brown/CMRP | 3. Teach Students Basic Oceanographic Techniques as Intro to Marine Science Careers; Introduce Local
May to June | 6. NWHI Coral Reef Ecosystem Mapping | 34 | NOS | Ecosystems | David Kennedy/COR | Leaders to NOAA Science Objectives. Contact: CS = Nancy Daschbach, N/ORM6x25, (684) 633-7354
June to July | 7. NWHI Coral Reef Biology | 23 | NOS | Ecosystems | David Kennedy/COR | 4. Recover and Deploy DART Mooring Near Kona Coast. Contact: CS = Shannon McArthur (228) 688-
July | 8. NWHI Education and Outreach Expedition | 14 | NOS | Ecosystems | David Kennedy/COR | 2830
July to August | 9. MHI Coral Reef Assessment and Monitoring | 26 | NOS | Ecosystems | David Kennedy/COR | 5. Provide Opportunities for Students and Educators in Hawaii to Learn About NOAA. Contact: CS =
September | 10. NWHI Maritime Heritage Survey | 28 | NOS | Ecosystems | David Kennedy/COR | Patty Miller (808) 879-2818
| Total Project DAS | 240 |  |  |  | 6. Multibean Data Collection and Optical Groundtruthing in NWHI Coral Reef Ecosystem. Contact: CS =
| Total OD | 250 |  |  |  | Russell Brainard - F/PIC (808) 592-7011
7. Conduct Diver Surveys in the NWHI Coral Reefs. Contact: CS = Randall Kosaki (808) 933-8183
8. Experiential Learning for Teachers & Students in the NWHI. Contact: CS = Andy Collins (808) 397-2660
9. Conduct Oceanographic and Biological Monitoring: Diver Surveys. Contact: CS = Russell Brainard
F/PIC (808) 592-7011
10. Conduct Maritime Heritage Survey and Assessment of Known and Unlocated Sites for Management
and Resource Preservation Purposes. CS = Hans Van Tilburg (808) 397-2404 ext. 264
OSCAR ELTON SETTE
October to November | 1. Marine Debris Maintenance | 34 | NOS | Ecosystems | David Kennedy/COR | 1. To conduct marine debris mitigation activities on coral reef ecosystems of the NWHI. Contact: Russell
November to December | 2. Monk Seal Foraging Studies | 22 | NMAO | Ecosystems | Steve Murawski/EOP | Brainard (808) 592-7011
December & March | 3. Transits to and from West Coast Shipyards | 20 | NMAO | Ecosystems | Steve Murawski/EOP | 2. Conduct Studies to Monitor Marine Mammal and Fish Interactions. Contact: CS = Jason Baker
March | 4. FBSAD Longline | 17 | NMFS | Ecosystems | Steve Murawski/EOP | (808) 983-5711
April to May | 5. Highly Migratory Species Oceanography | 29 | NMFS | Ecosystems | Steve Murawski/EOP | 3. Shipyard Transits
May & August | 6. Monk Seal PSD Camps | 40 | NMFS | Ecosystems | Steve Murawski/EOP | 4
June | 7. FBSAD Lobster Assessment | 28 | NMFS | Ecosystems | Steve Murawski/EOP
July to August | 8. PSD Cetacean/EOD Deep Coral | 26 | NMFS/NOS | Ecosystems | Steve Murawski/EOP | 5. Conduct Surveys of the Physical Environment and Associated Biology of Critical Habitat Identified
August to September | 9. CRED RAMP | 22 | NOS | Ecosystems | David Kennedy/COR | with HMS. Contact: CS = Jeffery Polovina (808) 983-5390
| Total Project DAS | 238 |  |  |  | 6. Establish Field stations for population studies and monitoring of monk seals in the MHI & NWHI. Contact:
| Total OD | 250 |  |  |  | Jason Baker (808) 983-5711
7. Conduct Lobster Assessment Studies in NWHI. Contact: CS = Gerard DiNardo (808) 983-5397
8
9
DAVID STARR JORDAN
October to December | 1. ETP Dolphin Assessment | 60 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Assess the Status of Dolphin Stocks that have Taken as Incidental Catch in the Yellowfin Tuna Purse-
March to April | 2. Pelagic Species Assessment | 50 | NMFS | Ecosystems | Steve Murawski/EOP | seine Fishery in the ETP. Contact: CS = Lisa T. Balance (858)546-7173
May to June | 3. Juvenile Rockfish Survey | 45 | NMFS | Ecosystems | Steve Murawski/EOP | 2. West coast Synoptic Sardine Survey in support of FMPs and MSFCMA. CONTACT: CS = Roger Hewitt
June | 4. Juvenile Salmon | 10 | NMFS | Ecosystems | Steve Murawski/EOP | (858) 546-5602
July | 5. White Abalone Survey | 19 | NMFS | Ecosystems | Steve Murawski/EOP | 3. Determine Distribution and Abundance of Pelagic Juvenile, Young-of-the-Year, Rockfish Between
August to September | 6. Cowcod/Sardine/Rockfish | 55 | NMFS | Ecosystems | Steve Murawski/EOP | San Diego and Delgada, CA. Contacts: CS = Steve Ralston-F/SWC5 (831) 420-3949
| Total Project DAS | 239 |  |  |  | 4. Anadramous species assessment survey in support of Salmon FMP, MSFCMA and ESA. Contact: CS =
| Total OD | 250 |  |  |  | Bruce MacFarlane (831) 420-3900
5. During Daylight Hours Operate ROV to Survey White Abalone. Night Time Hours will be Spent
Surveying Habitat with Multi-Beam Sonar. Contact: Roger Hewitt F/SWC1 (858) 546-5602
6. Sardine and Rockfish Survey and Cowcod Assessment Off the Coast of Central California. Contact:
CS = Roger Hewitt, F/SWC1 (858) 546-5602
FSV4
August to September | 1. Transit and Shakedown Cruises | 30 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Delivered to NOAA Late in FY06 and will Conduct Sea Trials/Shakedown Cruises. Contact: Chuck
| Total Project DAS | 30 |  |  |  | Byrne, F/NEC (508) 495-2224
| Total OD | 30
JOHN N. COBB
Fall & Winter | 1. Small Cetacean Surveys & Shipyard Transits | 27 | NMFS/NMAO | Ecosystems | Steve Murawski/EOP | 1. Collect Data on the Abundance, Distribution and Stock Structure of Small Cetaceans. Contact: CS =
Spring, Summer,Fall | 2. Killer Whale and Humpback Whale Survey- | 25 | NMFS | Ecosystems | Steve Murawski/EOP | Marilyn Dahlheim-F/AKC3 (206) 526-4020
Spring, Summer, Fall | 3. Harbor Seal Assessments/Counts- | 34 | NMFS | Ecosystems | Steve Murawski/EOP | 2. Collect Data on the Abundance, Distribution and Stock Structure of Cetaceans, Particularly
Summer | 4. Juvenile Sablefish Studies- | 15 | NMFS | Ecosystems | Steve Murawski/EOP | Killer Whales and Humpback in SE Alaska. Contact: CS = Marilyn Dahlheim-F/AKC3 (206) 526-4020
Summer | 5. Studies of Alaskan Corals & Sponges- | 10 | NMFS | Ecosystems | Steve Murawski/EOP | 3. Surveys to Photograph and Census Harbor Seals. Contact: CS = Dave Withrow-F/AKC3 (206)
Summer | 6. Nearshore Groundfish Habitat- | 10 | NMFS | Ecosystems | Steve Murawski/EOP | 526-4019
Summer | 7. Juvenile Salmon | 40 | NMFS | Ecosystems | Steve Murawski/EOP | 4. Tag and Release Juvenile Sablefish to Determine Migration Patterns and Age When Sable-
| Total Project DAS | 161 |  |  |  | fish Recruit to the Commercial Fishery. Contact: CS = Tom Rutecki-F/AKC4 (907) 789-6001
| Total OD | 200 |  |  |  | 5. Studies to Monitor Growth, Recruitment, Predation and Oceanographic Conditions at
Selected Study Sites in SE Alaska Where Corals and Sponges are Abundant. Contact: CS = Robert
Stone-F/AKC4 (907) 789-6031
6. Determine Linkages Between Habitat and Groundfish Assemblages in Nearshore Waters of SE
Alaska. Contact: CS = Scott Johnson-F/AKC4 (907) 789-6063
7. Maintain Time Series of Biophysical Data Related to the Seasonal Distribution of Juvenile
Pacific Salmon as They Migrate Through a Major Coastal Corridor in the Northern Region of SE
Alaska. Contact: CS = Joe Orsi-F/AKC4 (907) 789-6034
RONALD H. BROWN
October | 1. Stratus Ocean Reference Station | 25 | OAR | Climate | Tom Karl/COA | 1. Recover and Deploy Long-Term Surface Flux Reference Site Mooring. Contact: CS = Robert
October to December | 2. Recover & Deploy Tropical-Atmosphere Ocean (TAO) Array | 46 | NWS | Climate | Tom Karl/COA | Weller/WHOI (508) 289-2508
March to April | 3. NEAQS-IPY 2008 & Radiative Forcing & Trop Ozone | 46 | OAR | Climate/Weather & Water | Albritton/CF-Meagher/AQ | 2. Recovery and Deployment of TAO Moorings. Contact: CS = Michael McPhaden/PMEL (206)
May to June | 4. NTAS/Move | 50 | OAR | Climate | Tom Karl/COA | 526-6783
June to July | 5. Western Boundary Time Series | 20 | OAR | Climate | Tom Karl/COA | 3. The NOAA Climate Forcing and Air Quality Programs will Conduct a Combined Air Quality
July to September | 6. African Monsoon Multidisciplinary Analysis (AMMA) | 60 | OAR | Climate | Tom Karl/COA | and Climate Research Study to Better Characterize Marine/Continental Chemical and Meteor-
ological Processes to Assess Their Impact on Air Quality in New England and Radiative Forcing of
| Total Project DAS | 247 |  |  |  | Climate. Contact: CS = Tim Bates NOAA/PMEL (206) 526-6248
| Total OD | 275 |  |  |  | 4. Maintain Surface Mooring at 15N 51W for Air Sea Flux Measurements in Support of OGP Climate
Observations and CTD/Water Samples. Contacts: CS = Al Plueddemann/WHOI (508) 289-2789 and
Mike Johnson, R/OGP, (301) 427-2330
5. Continue the Physical and Chemical Properties of the Florida Current and Deep Western
Boundary Current. Contact: CS = Molly Baringer R/AOML (305)-361-4345
6. Improve Understanding of the West African Monsoon and its Influence both on the Regional
Environment and Atlantic Tropical Cyclone Development. Contact: CS = R.L. Molinari AOML
(305) 361-4344
OKEANOS EXPLORER
Oct to Dec & March to September | 1. Projects TBD | 215 | OAR/NOS | Ecosystems | Leon Cammen/ERP
| Total Project DAS | 215
| Total OD | 250
THOMAS JEFFERSON
October & November | 1. Coastal Survey (Long Island Sound) | 32 | NOS | Commerce & Transportation | Rich Edwing/MTS | 1. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
February to April | 2. Coastal Survey (Chesapeake Bay) | 32 | NOS | Commerce & Transportation | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
April to July | 3. Coastal Survey (Gulf of Mexico) | 70 | NOS | Commerce & Transportation | Rich Edwing/MTS | 2. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
July | 4. Multibeam Imaging of NW Gulf of Mexico | 10 | NOS | Ecosystems | Doug Brown/CMRP | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
July | 5. Integrated Coastal Ocean Mapping | 13 | NOS | Commerce & Transportation | Rich Edwing/MTS | 3. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
August to September | 6. Coastal Survey (New York Harbor) | 50 | NOS | Commerce & Transportation | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
| Total Project DAS | 207 |  |  |  | 4. Continuing Ongoing Effort to Map the Tropographic Features in the NW Gulf of Mexico
| Total OD | 235 |  |  |  | Contact: CS = G.P. Schmahl, N/ORM6x11, (979) 846-5942
5. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
6. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
OREGON II
October to November | 1. SEAMAP(SM) Fall Bottomfish Survey | 43 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Continuation of a 21 Year Data Base and is the Backbone of Fishery-Independent Assess-
January | 2. SM Stripped Bass Tagging | 25 | NMFS/NOS | Ecosystems | Steve Murawski/EOP | ment of Recruitment Strength for Many of These Species. Contact: CS = Butch Pellegrin SEC4
June to July | 3. SEAMAP(SM) Summer Bottomfish Survey | 38 | NMFS | Ecosystems | Steve Murawski/EOP | (228) 762-4591
July to August | 4. Coral/Oculina Habitat Ecosystem Assessment | 20 | NMFS | Ecosystems | David Kennedy/COR | 2. Assess the Striped Bass Stocks Under Striped Bass Management Plan. Contact: CS = Larry
| Total Project DAS | 126 |  |  |  | Settle-N/SCI3 (252) 728-8736
| Total OD | 130 |  |  |  | 3. Continuation of a 21 Year Data Base and is the Backbone of Fishery-Independent Assess-
ment of Recruitment Strength for Many of These Species. Contact: CS = Butch Pellegrin SEC4
(228) 762-4591
4. To monitor coral health and use of the closed and adjacent open areas by groupers. CS = Andrew
David (850) 234-6541
FSV3
October to November, June to July | 1. SEAMAP(SM) Fall/Summer Bottomfish Survey | 38 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Continuation of a 21 Year Data Base and is the Backbone of Fishery-Independent Assess-
January to April | 2. SM Reef Fish Survey Ecosystem Assessment | 107 | NMFS | Ecosystems | Steve Murawski/EOP | ment of Recruitment Strength for Many of These Species. Contact: CS = Butch Pellegrin SEC4
July to September | 3. Shark/Red Snapper Survey | 55 | NMFS | Ecosystems | Steve Murawski/EOP | (228) 762-4591
| Total Project DAS | 200 |  |  |  | 2. Assess Hard Bottom Habitat for the Development of Fishery-Independent Indices of Spawning Stocks
| Total OD | 207 |  |  |  | of Reef Fish in the Gulf of Mexico. Contact: CS = Chris Gledhill, F/SEC3, (228) 762-4591 ext. 284
3. Assess the Abundance and Distribution of Coastal Sharks, Red Snapper and Grouper Off the Gulf of
Mexico in Depths Down to ~375 meters. Contact: CS = Mark Grace, F/SEC4 (228) 762-4591, ext. 281
HENRY B. BIGELOW
October & September | 1. Autumn Bottom Trawl | 52 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Meet the Needs of Fishery Management Plans for Fish and Invertebrate Species. Contact: CS = Russell
November & May | 2. Bottom Trawl Calibration Experiment | 38 | NMFS | Ecosystems | Steve Murawski/EOP | Brown, F/NEC22, (508) 495-2213
November to December, August | 3. Benthic Habitat | 31 | NMFS | Ecosystems | Steve Murawski/EOP | 2. Gear Calibration. Contact: CS = Russel Brown, F/NEC22, (508) 495-2213
February | 4. Winter Bottom Trawl | 24 | NMFS | Ecosystems | Steve Murawski/EOP | 3. Conduct essential fish habitat studies from nid Atlantic Bight to Georges Banks. CS = Robert Reid
March to April | 5. Spring Bottom Trawl | 48 | NMFS | Ecosystems | Steve Murawski/EOP | F/NEC23, (732) 872-3000 ext. 3020
June to July | 6. Cetacean and Turtle Abundance | 60 | NMFS | Ecosystems | Steve Murawski/EOP | 4. Meet the Needs of Fishery Management Plans for Fish and Invertebrate Species. Contact: CS = Russell
| Total Project DAS | 253 |  |  |  | Brown, F/NEC22, (508) 495-2213
| Total OD | 365 |  |  |  | 5. Meet the Needs of Fishery Management Plans for Fish and Invertebrate Species. Contact: CS = Russell
Brown, F/NEC22, (508) 495-2213
6. Conduct Stock Assessment of Cetacean and Turtle Abundance from Cape Fear to Nove Scotia.
CS = Richard Merrick, F/NEC32, (508) 495-2291
DELAWARE II
October & September | 1. Herring Acoustic Calibration | 44 | NMFS | Ecosystems | Steve Murawski/EOP | 1. Meet the needs of pelagic fish and invertabrate Fishery Management Plans. Contact: CS = Russell
November, June to July, August | 2. Ecosystem Monitoring Survey | 57 | NMFS | Ecosystems | Steve Murawski/EOP | Brown, F/NEC22, (508) 495-2213
February | 3. LMRCSC/Educational COOP | 12 | NMFS | Ecosystems | Steve Murawski/EOP | 2. Monitor the biological and environmental components of NE U.S. coastal ecosystems
March | 4. Stillwagen Bank NMS | 12 | NMFS | Ecosystems | Steve Murawski/EOP | and document seasonal conditions in the physical and biological environment which supports
March to April | 5. Right Whale Biology | 30 | NMFS | Ecosystems | Steve Murawski/EOP | the growth and survival of fish and invertebrate stocks. Contact: CS = David Mountain (508) 495-2271
April | 6. Survey Gear Trials | 12 | NMFS | Ecosystems | Steve Murawski/EOP | 3. Educational COOP Program for Minority Students. Contact: CS = Eric B. May
April | 7. GoMOOS/Deepwater Biodiversity Studies | 18 | NMFS | Ecosystems | Steve Murawski/EOP | 4. Conduct Essential Fish Habitat Survey in Massachusetts Bay. CS = Ben Cowle-Haskell
May to June | 8. Large Whale Feeding | 25 | NMFS | Ecosystems | Steve Murawski/EOP | 5. Conduct Stock Assessment of Large Whales from Georges Bank to Gulf of Maine. CS = Richard
July to August | 9. Cetacean Biology | 26 | NMFS | Ecosystems | Steve Murawski/EOP | Merrick, F/NEC32, (508) 495-2291
| Total Project DAS | 236 |  |  |  | 6. Gear Improvemnt. Contact: CS = Russell Brown, F/NEC22, (508) 495-2213
| Total OD | 240 |  |  |  | 7. Recover ans Deploy a Current Meter Mooring in NE Channel and Measure Water Column Properties
in the Vicinity of the Mooring - Biodiversity is Conducted to Support Fishery Management Plans for Fish
and Invertebrate Species. Contacts: CS = David Mountain (508) 495-2271 and Michael Vecchion, F/NEC5,
(202) 357-4990
8. Conduct Stock Assessment of Large Whales from Georges Bank to Gulf of Maine. CS = Richard
Merrick, F/NEC32, (508) 495-2291
9. Conduct Stock Assessment Survey from Cape Hatteras to Nova Scotia. CS = Richard Merrick
F/NEC32, (508) 495-2291
GORDON GUNTER
October to November & Winter | 1. Deep Water Trawling & Shipyard Transits | 44 | NMFS/NMAO | Ecosystems | Steve Murawski/EOP | 1. Assess the Abundance and Distribution of the Pelagic and Bottomfish Stocks out to the
February to March | 2. Marine Protected Areas/Habitat Surveys | 20 | NMFS | Ecosystems | Steve Murawski/EOP | Edge of the Gulf of Mexico from Texas to Florida. Contact: CS = Walter Ingram-F/SEC4 (228)
March to May | 3. Pelagic Longline | 43 | NMFS | Ecosystems | Steve Murawski/EOP | 762-4591, ext 235
May to June | 4. Spring Ichthyoplankton Survey | 42 | NMFS | Ecosystems | Steve Murawski/EOP | 2. Conduct Essential Fish Habitat Surveys Along the South Atlantic Coast. CS = Andrew David
June to August | 5. Mammal Survey/Sperm Whale | 55 | NMFS | Ecosystems | Steve Murawski/EOP | (850) 234-6541
August to September | 6. SEAMAP Fall Ichthyoplankton Survey | 36 | NMFS | Ecosystems | Steve Murawski/EOP | 3. Assess the Abundance and Distribution of Pelagic Sharks, Tuna, Billfish and Swordfish in the Gulf of
| Total Project DAS | 240 |  |  |  | Mexico. Contact: CS = Mark Grace, F/SEC4, (228) 762-4591, ext. 281
| Total OD | 250 |  |  |  | 4. Collect Ichthyoplankton Samples with Plankton Gear for the Purpose of Estimating Abundance
and Defining the Distribution of Commercial and Recreational Important Species. Contact: CS =
Steve Turner, F/SEC2, (305) 361-4482 ext. 482
5. Conduct Stock Assessment of Marine Mammals/Sperm Whales in Gulf of Mexico. CS = Lance
Garrison, F/SEC2, (305) 361-4488 ext. 488
6. Collect Ichthyoplankton Samples with Plankton Gear for the Purpose of Estimating Abundance
and Defining the Distribution of Commercial and Recreational Important Species. Contact: CS =
Joanne Lyczkowski-F/SEC4 (228) 762-4591, ext 277
NANCY FOSTER
October & Winter | 1. CSC At Sea & Transects Program & Shipyard Transits | 12 | NOS/NMAO | Ecosystems | Doug Brown/CMRP | 1. Research-oriented day cruises for college students, high school students and K-12 teachers.
February | 2. Habitat Ecology for Ecosystem-Based Management | 12 | NOS | Ecosystems | Leon Cammen/ERP | Contact: CS = Leslie Sautter (843) 953-5586
February to March | 3. USVI Caribbean Benthic Habitat Mapping | 18 | NOS | Ecosystems | David Kennedy/COR | 2. On-Going Research for Habitat Mapping and Use of Seagrass and Coral, Including Injury Recovery.
March | 4. Habitat Mapping of Proposed MPA Sites | 18 | OAR | Ecosystems | Leon Cammen/ERP | Contact: CS = Jud Kenworthy-N/SCI3 (252) 728-8750
March to April | 5. Benthic Studies to Support Management Needs @ GRNMS | 10 | NOS | Ecosystems | Leon Cammen/ERP | 3. Multibeam Data Collection and Optical Groundtruthing. Contact: Mark Monaco, N/SCI1 (301) 713-
April | 6. Grey's Reef Comparison of Fisheries and Methodology | 11 | NOS | Ecosystems | Doug Brown/CMRP | 3028 ext. 160
April | 7. Grey's Reef Development Cruise | 11 | NOS | Ecosystems | Doug Brown/CMRP | 4. Mapping Seafloor Habitat in New Proposed MPA Sites. Contact: CS = Andrew Shepard (910) 962-
May | 8. Research and Monitoring at SBNMS | 28 | NOS | Ecosystems | Doug Brown/CMRP | 2446
June | 9. Ecosystem Impact of Climate Change on Invasive Species | 18 | NOS | Ecosystems | Leon Cammen/ERP | 5. Conduct Survey of Benthic Fauna and Ecological Condition at GRNMS. Contact: CS = Jeff Hyland
June | 10. Exploration of Invertebrate Species | 10 | NOS | Ecosystems | Doug Brown/CMRP | N/SCI4, (843) 762-8652
July | 11. Florida Straits | 18 | NOS | Ecosystems | Leon Cammen/ERP | 6. Cruise Support Comparison of Various Fisheries Assessment Techniques. Contact: CS = Greg
July | 12. Coral Condition Survey and Multibeam Mapping(FKNMS) | 13 | NOS | Ecosystems | Doug Brown/CMRP | McFall, N/ORM6x13, (912) 598-2416
August | 13. Biogeographic Analysis of Tortugas Ecological Reserve | 12 | NOS | Ecosystems | Leon Cammen/ERP | 7. Developmental Cruise and Diving Support to Accommodate Academic and Scientific Interest.
August | 14. Coral Disease Monitoring (FGBNMS) | 13 | NOS | Ecosystems | Doug Brown/CMRP | Contact: CS = Greg McFall, N/ORM6x13, (912) 598-2416
August | 15. Ocean Exploration Cruises | 24 | OAR | Ecosystems | Leon Cammen/ERP | 8. Research and monitoring programs that focus on maritime heritage resource inventory,
| Total Project DAS | 228 |  |  |  | landscape ecology of fishes, distribution of invertebrates relative to sediment type, foraging
| Total OD | 250 |  |  |  | ecology of baleen whales and impact of noise pollution on endangered whales. Contact: CS =
David Wiley/NORM6x15 (781) 545-8026, ext 211
9. Effects of Climate Change on Hard-Bottom Communities and Native Tropical Corals. Contact:
CS = Greg Piniak (252) 728-8732
10. Explore Complex and Unique Habitats in a Transet from the St. Helena Sound. Contact: CS =
Elizabeth Wenner (843) 953-9226
11. Evaluation of Benthetic Habitats. Contact: CS = Albrey Arrington (561) 741-0192
12. Assess Overall Distribution and Frequency of Coral Disease in the FKNMS. Contact: CS = Brian
Keller, N/ORM6x12, (305) 743-2437 ext. 25
13. On-Going Research Cruises to Determine Post-Implementation Effects of TER. Contact: CS =
Mark Fonseca, N/SCI3, (252) 728-8729
14. Monitor and Sample Coral Disease at FGBNMS. Contact: CS = G.P. Schmahl, N/ORM6x11, (979)
846-5942
15. Baseline characterizations of unknown or poorly known areas (sites TBD). Contact: Jeremy
Potter, R/OE, (301) 713-9444 ext. 136
RUDE/SWATH
October to November | 1. Coastal Survey (Chesapeake Bay) | 39 | NOS | Commerce & Transportation | Rich Edwing/MTS | 1. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
February to April | 2. Crossdeck to SWATH and Testing | 39 | NOS | Commerce & Transportation | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
May to August | 3. Coastal Survey (New England) | 100 | NOS | Commerce & Transportation | Rich Edwing/MTS | 2. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
May to July | 4. Coastal Survey (Long Island Sound) | 22 | NOS | Commerce & Transportation | Rich Edwing/MTS | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
| Total Project DAS | 200 |  |  |  | 3. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
| Total OD | 220 |  |  |  | graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
4. Hydrographic and Integrated Ocean Mapping Surveys. Critical and Priority Areas of "NOAA Hydro-
graphic Survey priorities. Contact: LCDR Doug Baird, N/CS31, (301) 713-2702 ext 112
COR = Coral, HAB = Habitat, CMPR = Coastal and Marine Resources, EOP = Ecosystem Observations, ERP = Ecosystem Research, COA = Climate Observations and Analysis, CLF = Climate Forcing, AQL = Air Quality, TSU = Tsunami, MTS = Marine Transportation Systems
DAS = Days At Sea, OD = Operating Days (Operating Days = DAS or day inport other than homeport), CS = Chief Scientist
| Estimated Total Days-At_Sea (DAS) | 4399
| Estimated Total Operating Days (OD) | 4892